## Summary
Metric | Value
Slack Status | Using slack column: Total Slack (normalized to days)
Negative Slack | 190
Excessive Slack (>200d) | 15172
Missing Predecessors | 0
Missing Successors | 0
Constraints (GAO-flag, non-ASAP) | 12561
Baseline Variance (Late > 20d) | 673
Low-Quality Name | 461

## Negative_Slack
UID | Task Name | Start | Finish | Duration | Total Slack | Predecessors | Successors | Percent Complete | __SlackDays | Severity
6847 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 58 | -13d | 524SS+19d | 527SS | 0.07 | -13 | Critical
6848 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 58 | -13d | 526SS | 529SS+22d | 0.07 | -13 | Critical
6850 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 | -1d | 527SS+22d | 530SS,532SS,4717SS | 0.5 | -1 | Critical
6851 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 | -1d | 529SS | 4717SS | 0 | -1 | Critical
6863 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | October 2, 2025 8:00 AM | December 24, 2025 5:00 PM | 58 | -13d | 547SS+19d | 551SS+22d,4716FS-12d | 0.12 | -13 | Critical
2674 | Resource Family Approval: Build | October 6, 2025 8:00 AM | December 26, 2025 5:00 PM | 57 | -32d |  |  | 0 | -32 | Critical
2675 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -32d |  |  | 0 | -32 | Critical
2676 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -32d | 998 | 1012SS,2316SS,1370SS,1019SS,1024SS+38d,1029SS,4639FS-19d | 0 | -32 | Critical
2683 | Milestone 27: Complaints (CARESV1-505) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -13d |  |  | 0 | -13 | Critical
2684 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -13d | 1011SS | 1020SS,2320SS,2324SS,4650SS+19d | 0 | -13 | Critical
2688 | Milestone 28: Legal Action (CARESV1-504) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d |  |  | 0 | -32 | Critical
2689 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1011SS+38d | 1025SS,4661FS-19d | 0 | -32 | Critical
2690 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1024SS | 1026SS,4661FS-19d | 0 | -32 | Critical
2691 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1025SS | 4661FS-19d | 0 | -32 | Critical
2701 | Resource Family: SIT | October 6, 2025 8:00 AM | December 26, 2025 5:00 PM | 57 | -13d |  |  | 0 | -13 | Critical
2702 | Milestone 26: Maintain Resource Family Home (CARESV1-508) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -13d |  |  | 0 | -13 | Critical
2703 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Application (CARESV1-56) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -13d | 1011SS | 1030SS,1037SS,1042SS+38d,4639FS-19d | 0 | -13 | Critical
1235 | Financial Management: Build | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM | 75 | -50d |  |  | 0 | -50 | Critical
1236 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d |  |  | 0 | -50 | Critical
1237 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1136FS+57d,1141 | 1145SS,1146SS,1147SS,1366SS | 0 | -50 | Critical
1238 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS | 1146SS | 0 | -50 | Critical
1239 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS,1145SS | 1147SS,4685FS-19d | 0 | -50 | Critical
1240 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS,1146SS | 1154SS,4685FS-19d | 0 | -50 | Critical
1241 | Milestone 24: Track Assistance Costs (CARESV1-506) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d |  | 523FF+6d | 0 | -16 | Critical
1242 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1140 | 1150SS,1151SS,4700FS-19d | 0 | -16 | Critical
1243 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1149SS | 1151SS,4700FS-19d | 0 | -16 | Critical
1244 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1149SS,1150SS | 1159SS,4700FS-19d | 0 | -16 | Critical
1245 | Financial Management: SIT | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM | 75 | -16d |  |  | 0 | -16 | Critical
1246 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d |  |  | 0 | -44 | Critical
1247 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1147SS | 1155SS,1156SS,1157SS,4689 | 0 | -44 | Critical
1248 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1154SS | 1156SS,4689 | 0 | -44 | Critical
1249 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1154SS,1155SS | 1157SS,4689 | 0 | -44 | Critical
1251 | Milestone 24: Track Assistance Costs (CARESV1-506) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d |  | 3002 | 0 | -16 | Critical
1252 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1151SS | 1160SS,1161SS,4700FS-19d | 0 | -16 | Critical
1253 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1159SS | 1161SS,4700FS-19d | 0 | -16 | Critical
1254 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -16d | 1159SS,1160SS | 1169,4699FF,4700FS-19d | 0 | -16 | Critical
4736 | Milestone 32: Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | -13d | 1278 | 1282SS,4728FS-19d | 0.93 | -13 | Critical
4750 | Milestone 32: SIT | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | -13d | 1280SS | 1284,4728FS-19d,4732 | 0.88 | -13 | Critical
4291 | Milestone (LIS/FAS data) 26.1 - Design | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 151 | -7d |  | 1427 | 0.86 | -7 | Critical
4292 | Milestone (LIS/FAS data) 26.1 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -7d | 1426 | 1428,4644 | 0 | -7 | Critical
4312 | H3 Re-work (Conduct Hardening) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | -17d | 345 | 2988,2991,2992,3001,3003,3004,3005 | 0.45 | -17 | Critical
11209 | EUST - 3R (Reports) | December 26, 2025 8:00 AM | June 2, 2026 5:00 PM | 108 | -17d |  |  | 0 | -17 | Critical
11210 | EUST - 3R Preparation | December 26, 2025 8:00 AM | February 24, 2026 5:00 PM | 40 | -17d |  |  | 0 | -17 | Critical
11211 | EUST 3R - Identification and validation of scenarios | December 26, 2025 8:00 AM | January 26, 2026 5:00 PM | 20 | -13d | 525FS-3d,548FS-3d | 1843,1848 | 0 | -13 | Critical
11212 | EUST 3R - Deployment to Staging | February 2, 2026 8:00 AM | February 13, 2026 5:00 PM | 10 | -17d | 525,548,1842,2985,2986,2987,2988,2989,2990,2991,2992,2993,2994,2995,2996,2997,2998,2999,3000,3001,3002,3003,3004,3005,3007,3008,3009,3010,3011,3012,3013,3014 | 1844,1845,1846,1847,1848 | 0 | -17 | Critical
11213 | EUST 3R - User setup and access validation | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 | -17d | 1843 | 1848 | 0 | -17 | Critical
11214 | EUST 3R - Pdl validation of scenarios in the environment | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 | -17d | 1843 | 1848 | 0 | -17 | Critical
11215 | EUST 3R - Conduct EUST Training | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 | -17d | 1843 | 1848 | 0 | -17 | Critical
11216 | EUST 3R - Confirm EUST Readiness | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 | -17d | 1843,1287 | 1848 | 0 | -17 | Critical
11217 | EUST 3R Go-No-Go | February 24, 2026 8:00 AM | February 24, 2026 5:00 PM | 1 | -17d | 1847,1843,1844,1845,1846,1842,2976,2977,2978,2979,2980,2981,2982 | 1850FS-1d | 0 | -17 | Critical
11218 | EUST - 3R Execution | February 24, 2026 8:00 AM | June 2, 2026 5:00 PM | 69 | -17d |  |  | 0 | -17 | Critical
11220 | EUST for Milestones 29, 30 | February 24, 2026 8:00 AM | April 6, 2026 5:00 PM | 29 | -17d | 528FS-1d,550FS-1d,1848FS-1d | 1851,4779 | 0 | -17 | Critical
11221 | EUST 3R - Triage/Prioritize Findings | April 7, 2026 8:00 AM | April 20, 2026 5:00 PM | 10 | -17d | 1850 | 1852 | 0 | -17 | Critical
11222 | EUST 3R - Build/SIT Findings | April 21, 2026 8:00 AM | May 18, 2026 5:00 PM | 20 | -17d | 1851 | 1853 | 0 | -17 | Critical
11223 | EUST 3R - QA Findings | May 19, 2026 8:00 AM | June 2, 2026 5:00 PM | 10 | -17d | 1852 | 1856FS-16d | 0 | -17 | Critical
2872 | EUST - 4 | May 1, 2026 5:00 PM | July 10, 2026 5:00 PM | 48 | -12d |  |  | 0 | -12 | Critical
2873 | Validation for All Milestones | May 11, 2026 8:00 AM | June 5, 2026 5:00 PM | 19 | -17d | 1853FS-16d | 1857SS,5611FF-5d,5612FF+8d,5613FF+10d | 0 | -17 | Critical
6983 | Security Controls and Capacity Management - Conduct Detailed Design | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 379 | -10d | 2407 | 2414SS,2415FS+19d | 0.96 | -10 | Critical
6930 | Perform Feature Expansion | December 1, 2025 8:00 AM | August 6, 2026 5:00 PM | 172 | -10d | 2414,2409FF,2408FS+19d,2405 | 5625 | 0 | -10 | Critical
6931 | Semantic Layer Data Model Development | May 1, 2023 8:00 AM | August 5, 2026 5:00 PM | 820 | -9d | 2399SS | 5625,2435SS | 0.75 | -9 | Critical
6932 | Org Enablement - Knowledge Transfer | October 1, 2024 8:00 AM | August 7, 2026 5:00 PM | 464 | -16d | 2412SS | 5625FS+5d | 0.56 | -16 | Critical
3982 | County Specific - Reports (CARESV1-14107) | June 10, 2024 8:00 AM | October 9, 2026 5:00 PM | 588 | -16d | 2435 | 5628 | 0.57 | -16 | Critical
3983 | Reporting & Analytics - Functional Reports (Operational) (CARESV1-14112) | June 30, 2023 8:00 AM | January 30, 2026 5:00 PM | 648 | -1d |  |  | 0.75 | -1 | Critical
3986 | CARESV1-18895 Reporting & Analytics: M6 (LOE) | January 2, 2025 8:00 AM | January 29, 2026 5:00 PM | 270 | -16d | 1475 | 1843 | 0.73 | -16 | Critical
3987 | CARESV1-21984 Reporting & Analytics: M6.1 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
3989 | CARESV1-18896 Reporting & Analytics: M8 (LOE) | January 2, 2025 8:00 AM | January 28, 2026 5:00 PM | 269 | -15d | 1475 | 1843 | 0.73 | -15 | Critical
3990 | CARESV1-18897 Reporting & Analytics: M9 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
3991 | CARESV1-20274 Reporting & Analytics: M10 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
3994 | CARESV1-20273 Reporting & Analytics: M14 (LOE) | January 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 250 | -14d | 496 | 1843 | 0.71 | -14 | Critical
4000 | CARESV1-21985 Reporting & Analytics: M21 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
4001 | CARESV1-31449 Reporting & Analytics: M23 (LOE) | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 | -16d | 1158 | 1843 | 0 | -16 | Critical
4002 | CARESV1-27765 Reporting & Analytics: M24 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
4003 | CARESV1-30207 Reporting & Analytics: M26 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
4004 | CARESV1-21986 Reporting & Analytics: M27 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 | -17d | 1479 | 1843 | 0 | -17 | Critical
8376 | Phase 2: Readiness and Cutover | October 6, 2025 8:00 AM | December 16, 2026 5:00 PM | 300 | -50d |  |  | 0.01 | -50 | Critical
8378 | CARES V1 Train the Trainer | August 7, 2026 8:00 AM | September 18, 2026 5:00 PM | 30 | -50d | 5617SS,3872 | 3874 | 0 | -50 | Critical
8379 | CARES V1 End-User Training | September 21, 2026 8:00 AM | December 16, 2026 5:00 PM | 60 | -50d | 3873 | 3886 | 0 | -50 | Critical
8380 | CARES V1 Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 29 | -38d | 5626SS | 3886 | 0 | -38 | Critical
8390 | CARES V1 Go-Live and Support | December 17, 2026 8:00 AM | January 15, 2027 5:00 PM | 20 | -50d | 3874,3875,5629,3885,3528,3381,3386,3429,3496,3518,3522,3544,3549,3552,3701,3870,3449,3498,3564,3881 | 3887,3889SS | 0 | -50 | Critical
8391 | SPR 6 - Complete the CWS-CARES V1 Implementation | January 15, 2027 5:00 PM | January 15, 2027 5:00 PM | 0 | -50d | 3886 | 3893 | 0 | -50 | Critical
10827 | Group 1 Resource Family Approval (Milestones 26/26.1, 27, 28) | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM | 423 | -32d |  |  | 0.35 | -32 | Critical
10852 | Milestone 26/26.1 - Maintain Resource Family Home | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM | 203 | -13d |  |  | 0.33 | -13 | Critical
10853 | BD 5 - MS 26/26.1: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4634,1008,1011FS-19d,1029FS-19d | 4640SS | 0 | -13 | Critical
10854 | BD 5 - MS 26/26.1: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4639SS | 4641FF | 0 | -13 | Critical
10855 | BD 5 - MS 26/26.1: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4640FF | 4642FS-5d,4644FS-5d | 0 | -13 | Critical
13890 | BD 5 - MS 26/26.1: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4641FS-5d,1427 | 4645FS+12d | 0 | -13 | Critical
10858 | BD 5 - MS 26/26.1: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4644FS+12d | 4646 | 0 | -13 | Critical
10859 | BD 5 - MS 26/26.1: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4645 | 4647 | 0 | -13 | Critical
10860 | BD 5 - MS 26/26.1: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4646 | 4648 | 0 | -13 | Critical
10861 | MS 26/26.1 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4647,4642,4643 | 4671,5611,5612,4806,4807 | 0 | -13 | Critical
10862 | Milestone 27 - Complaints | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM | 203 | -13d |  |  | 0.33 | -13 | Critical
10867 | BD 5 - MS 27: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 1008,1019SS+19d,1020SS | 4651SS | 0 | -13 | Critical
10868 | BD 5 - MS 27: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4650SS | 4652SS | 0 | -13 | Critical
10869 | BD 5 - MS 27: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4651SS | 4653FS-5d,4655FS-5d | 0 | -13 | Critical
13889 | BD 5 - MS 27: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4652FS-5d | 4656FS+12d | 0 | -13 | Critical
10872 | BD 5 - MS 27: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4655FS+12d | 4657 | 0 | -13 | Critical
10873 | BD 5 - MS 27: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4656 | 4658 | 0 | -13 | Critical
10874 | BD 5 - MS 27: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4657 | 4659 | 0 | -13 | Critical
10875 | MS 27 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4658,4653,4654 | 4671,5611,5612,4808,4809 | 0 | -13 | Critical
10876 | Milestone 28 - Legal Action | June 2, 2025 8:00 AM | April 20, 2026 5:00 PM | 222 | -32d |  |  | 0.31 | -32 | Critical
10881 | BD 5 - MS 28: - Discovery and Develop Training Curriculum (Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 1024FS-19d,1025FS-19d,1026FS-19d | 4662SS | 0 | -32 | Critical
10882 | BD 5 - MS 28: - Review Training Curriculum with VPODs(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 4661SS | 4663SS | 0 | -32 | Critical
10883 | BD 5 - MS 28: - Incorporate VPODs Feedback(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 4662SS | 4664FS-5d,4666FS-5d | 0 | -32 | Critical
13888 | BD 5 - MS 28: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 5 | -32d | 4663FS-5d | 4667FS+12d | 0 | -32 | Critical
10886 | BD 5 - MS 28: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 2, 2026 8:00 AM | March 13, 2026 5:00 PM | 29 | -32d | 4666FS+12d | 4668 | 0 | -32 | Critical
10887 | BD 5 - MS 28: - Review Training Content with VPOD & TAW (Build Drop Update) | March 16, 2026 8:00 AM | March 27, 2026 5:00 PM | 10 | -32d | 4667 | 4669 | 0 | -32 | Critical
10888 | BD 5 - MS 28: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 30, 2026 8:00 AM | April 13, 2026 5:00 PM | 10 | -32d | 4668 | 4670 | 0 | -32 | Critical
10889 | MS 28 - Finalize Training Content | April 14, 2026 8:00 AM | April 20, 2026 5:00 PM | 5 | -32d | 4669,4664,4665 | 4671,5611,5612,4810,4811 | 0 | -32 | Critical
10912 | Milestone 23/23.1/23.2 - Track Administrative Costs | April 1, 2025 8:00 AM | May 14, 2026 5:00 PM | 283 | -50d |  |  | 0.51 | -50 | Critical
13885 | BD 5 - MS 23/23.1/23.2: - Discovery and Develop Training Curriculum (Build Drop Update) | December 26, 2025 8:00 AM | February 9, 2026 5:00 PM | 30 | -50d | 1146FS-19d,1147FS-19d | 4686SS | 0 | -50 | Critical
13887 | BD 5 - MS 23/23.1/23.2: - Review Training Curriculum with VPODs(Build Drop Update) | December 26, 2025 8:00 AM | February 9, 2026 5:00 PM | 30 | -50d | 4685SS | 4687SS | 0 | -50 | Critical
13886 | BD 5 - MS 23/23.1/23.2: - Incorporate VPODs Feedback(Build Drop Update) | December 26, 2025 8:00 AM | February 2, 2026 5:00 PM | 25 | -50d | 4686SS | 4688 | 0 | -50 | Critical
13884 | BD 5 - MS 17: Finalize Training Curriculum (Build Drop Update) | February 3, 2026 8:00 AM | February 9, 2026 5:00 PM | 5 | -50d | 4687 | 4689SS | 0 | -50 | Critical
13883 | BD 5 - MS 23/23.1/23.2: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | February 3, 2026 8:00 AM | February 9, 2026 5:00 PM | 5 | -50d | 4688SS,1154,1155,1156 | 4690FS+12d,4898 | 0 | -50 | Critical
10918 | BD 5- MS 23/23.1/23.2: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 27, 2026 8:00 AM | April 9, 2026 5:00 PM | 29 | -50d | 1167SS-36d,1249SS-36d,4689FS+12d | 4691 | 0 | -50 | Critical
10919 | BD 5 - MS 23/23.1/23.2: - Review Training Content with VPOD & TAW (Build Drop Update) | April 10, 2026 8:00 AM | April 23, 2026 5:00 PM | 10 | -50d | 4690 | 4692 | 0 | -50 | Critical
10920 | BD 5 - MS 23/23.1/23.2: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | April 24, 2026 8:00 AM | May 7, 2026 5:00 PM | 10 | -50d | 4691 | 4693 | 0 | -50 | Critical
10921 | MS 23/23.1 - Finalize Training Content | May 8, 2026 8:00 AM | May 14, 2026 5:00 PM | 5 | -50d | 4692,4683,4684 | 4709,5611,5612,4802,4803 | 0 | -50 | Critical
10922 | Milestone 24 - Track Assistance Costs | March 24, 2025 8:00 AM | March 23, 2026 5:00 PM | 251 | -13d |  |  | 0.53 | -13 | Critical
13880 | BD 5 - MS 24: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 1149FS-19d,1150FS-19d,1151FS-19d,1159FS-19d,1160FS-19d,1161FS-19d | 4701SS | 0 | -13 | Critical
13882 | BD 5 - MS 24: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4700SS | 4702SS | 0 | -13 | Critical
13881 | BD 5 - MS 24: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4701SS | 4703FS-5d | 0 | -13 | Critical
13879 | BD 5 - MS 24: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4702FS-5d | 4704SS | 0 | -13 | Critical
13878 | BD 5 - MS 24: - Develop Training Content - Quick Guides, Knoweldge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4703SS | 4705FS+12d | 0 | -13 | Critical
10932 | BD 5 - MS 24: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 1171SS-36d,4704FS+12d | 4706 | 0 | -13 | Critical
10933 | BD 5 - MS 24: - Review Training Content with VPOD& TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4705 | 4707 | 0 | -13 | Critical
10934 | BD 5 - MS 24: - Incorporate Feedback from VPOD& TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4706 | 4708 | 0 | -13 | Critical
10935 | MS 24 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4707,4698,4699 | 4709,5611,5612,4804,4805 | 0 | -13 | Critical
10939 | Group 1 Reports (Milestones 29, 30) | October 31, 2025 8:00 AM | March 23, 2026 5:00 PM | 96 | -13d |  |  | 0 | -13 | Critical
13877 | BD 5 - MS 29,30- Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | January 12, 2026 5:00 PM | 23 | -13d | 549FS-12d | 4717 | 0 | -13 | Critical
10954 | BD 5 - MS 29,30- Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 13, 2026 8:00 AM | February 13, 2026 5:00 PM | 23 | -13d | 529SS,530SS,551SS,4716 | 4718 | 0 | -13 | Critical
10955 | BD 5 - MS 29,30 - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4717 | 4719 | 0 | -13 | Critical
10956 | BD 5 - MS 29,30 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4718 | 4720 | 0 | -13 | Critical
10957 | MS 29, 30 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4719,4715 | 4721,5611,5612,4909 | 0 | -13 | Critical
10961 | Group 1 Admin Console (Milestones 32 - Miscellaneous) | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM | 301 | -13d |  |  | 0.21 | -13 | Critical
10971 | BD 5 - MS 32 - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4724,1278,1280FS-19d,1282FS-19d | 4729SS | 0 | -13 | Critical
10972 | BD 5 - MS 32 - Review Training Curriculum with VPODs (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4728SS | 4730SS | 0 | -13 | Critical
10973 | BD 5 - MS 32 - Incorporate VPODs Feedback (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4729SS | 4731FS-5d | 0 | -13 | Critical
10974 | MS 32 - Finalize Training Curriculum | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4730FS-5d | 4736,4732SS | 0 | -13 | Critical
13876 | BD 5 - MS 32 - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Updates) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4731SS,1282 | 4733FS+12d | 0 | -13 | Critical
10976 | BD 5 - MS 32 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Updates) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4732FS+12d | 4734 | 0 | -13 | Critical
10977 | BD 5 - MS 32 - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4733 | 4735 | 0 | -13 | Critical
10978 | BE 5 - MS 32 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4734 | 4736 | 0 | -13 | Critical
10979 | MS 32 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4735,4727,4731 | 4737,5611,5612,4814,4815 | 0 | -13 | Critical
13611 | Develop and Launch 'CWS-CARES 101: Ongoing Case Work and Finish a Case' Video | September 16, 2025 8:00 AM | December 12, 2025 5:00 PM | 62 | -4d |  |  | 0.31 | -4 | Critical
13613 | DevelopCWS-CARES 101: Ongoing Case Work & Finish a Case video storyboard | October 10, 2025 8:00 AM | October 21, 2025 5:00 PM | 8 | -4d | 5314 | 5316 | 0.12 | -4 | Critical
13614 | Complete reviews of CWS-CARES 101: Ongoing Case Work & Finish a Case video storyboard, including ELT | October 22, 2025 8:00 AM | November 17, 2025 5:00 PM | 18 | -4d | 5315 | 5317 | 0 | -4 | Critical
13615 | Incorporate ELT feedback and develop CWS-CARES 101: Ongoing Case Work & Finish a Case Vyond video | November 18, 2025 8:00 AM | November 26, 2025 5:00 PM | 7 | -4d | 5316 | 5318FS+1d | 0 | -4 | Critical
13616 | Complete reviews of CWS-CARES 101: Ongoing Case Work & Finish a Case Vyond video and launch | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 10 | -4d | 5317FS+1d | 5320 | 0 | -4 | Critical
13617 | Develop and Launch 'CWS-CARES 101: Court Processing' Video | December 15, 2025 8:00 AM | March 16, 2026 5:00 PM | 62 | -4d |  |  | 0 | -4 | Critical
13618 | Develop CWS-CARES 101: Court Processing video script and complete validation | December 15, 2025 8:00 AM | January 15, 2026 5:00 PM | 22 | -4d | 5318 | 5321,5338SS+12d | 0 | -4 | Critical
10074 | Develop and Launch the 'Day in the Life' video | January 2, 2026 8:00 AM | April 24, 2026 5:00 PM | 78 | -4d |  |  | 0 | -4 | Critical
13640 | Develop 'Day in the Life' video script and complete validation | January 2, 2026 8:00 AM | January 27, 2026 5:00 PM | 17 | -4d | 5320SS+12d | 5339 | 0 | -4 | Critical
13641 | Develop 'Day in the Life' video storyboard | January 28, 2026 8:00 AM | February 6, 2026 5:00 PM | 8 | -4d | 5338 | 5340 | 0 | -4 | Critical
13642 | Complete reviews of 'Day in the Life' video storyboard, including ELT | February 9, 2026 8:00 AM | March 5, 2026 5:00 PM | 18 | -4d | 5339 | 5341 | 0 | -4 | Critical
13643 | Incorporate ELT feedback and develop draft 'Day in the Life' Vyond video | March 6, 2026 8:00 AM | March 16, 2026 5:00 PM | 7 | -4d | 5340 | 5342 | 0 | -4 | Critical
13644 | Complete reviews of 'Day in the Life' Vyond video and launch | March 17, 2026 8:00 AM | April 24, 2026 5:00 PM | 28 | -4d | 5341 | 5344,5361 | 0 | -4 | Critical
10075 | Develop and Complete Reviews of the 'Preparing for CARES Go-Live' video | April 27, 2026 8:00 AM | August 17, 2026 5:00 PM | 79 | -4d |  |  | 0 | -4 | Critical
13645 | Develop 'Preparing for CARES Go-Live' video script and complete validation | April 27, 2026 8:00 AM | May 21, 2026 5:00 PM | 19 | -4d | 5342 | 5346,5345 | 0 | -4 | Critical
13646 | Develop 'Preparing for CARES Go-Live' video storyboard | May 22, 2026 8:00 AM | June 2, 2026 5:00 PM | 7 | -4d | 5344 | 5346 | 0 | -4 | Critical
13647 | Complete reviews of 'Preparing for CARES Go-Live' video storyboard, including ELT | June 3, 2026 8:00 AM | June 29, 2026 5:00 PM | 19 | -4d | 5344,5345 | 5347 | 0 | -4 | Critical
13648 | Incorporate ELT feedback and develop draft 'Preparing for CARES Go-Live' Vyond video | June 30, 2026 8:00 AM | July 10, 2026 5:00 PM | 8 | -4d | 5346 | 5348 | 0 | -4 | Critical
13649 | Complete reviews of 'Preparing for CARES Go-Live' Vyond video and launch | July 13, 2026 8:00 AM | August 17, 2026 5:00 PM | 26 | -4d | 5347 | 5350SS,5361 | 0 | -4 | Critical
10076 | Develop and Launch the 'What Happens Next?' video | July 13, 2026 8:00 AM | November 2, 2026 5:00 PM | 80 | -4d |  |  | 0 | -4 | Critical
13650 | Develop 'What Happens Next?' video script and complete validation | July 13, 2026 8:00 AM | August 7, 2026 5:00 PM | 20 | -4d | 5348SS | 5351 | 0 | -4 | Critical
13651 | Develop 'What Happens Next?' video storyboard | August 10, 2026 8:00 AM | August 19, 2026 5:00 PM | 8 | -4d | 5350 | 5352,5356SS+6d | 0 | -4 | Critical
10077 | Develop and Launch the 'Resources Overview' video | August 18, 2026 8:00 AM | December 11, 2026 5:00 PM | 80 | -4d |  |  | 0 | -4 | Critical
13655 | Develop 'Resources Overview' video script and complete validation | August 18, 2026 8:00 AM | September 11, 2026 5:00 PM | 18 | -4d | 5351SS+6d | 5357 | 0 | -4 | Critical
13656 | Develop 'Resources Overview' video storyboard | September 14, 2026 8:00 AM | September 23, 2026 5:00 PM | 8 | -4d | 5356 | 5358 | 0 | -4 | Critical
13657 | Complete reviews of 'Resources Overview' video storyboard, including ELT | September 24, 2026 8:00 AM | October 19, 2026 5:00 PM | 18 | -4d | 5357 | 5359 | 0 | -4 | Critical
13658 | Incorporate ELT feedback and develop draft 'Resources Overview' Vyond video | October 20, 2026 8:00 AM | October 30, 2026 5:00 PM | 9 | -4d | 5358 | 5360 | 0 | -4 | Critical
13659 | Complete reviews of 'Resources Overview' Vyond video and launch | November 2, 2026 8:00 AM | December 11, 2026 5:00 PM | 27 | -4d | 5359 | 5361 | 0 | -4 | Critical
10078 | Video Series Program Completed | December 11, 2026 5:00 PM | December 11, 2026 5:00 PM | 0 | -4d | 5360,5354,5348,5342,5336 | 5629FS-43d | 0 | -4 | Critical
10982 | Content Integration - Pilot | May 1, 2026 8:00 AM | August 5, 2026 5:00 PM | 67 | -40d |  |  | 0 | -40 | Critical
10983 | Integrate Final Product Updates into Online Training Content | May 15, 2026 8:00 AM | July 16, 2026 5:00 PM | 43 | -50d | 1856FF-5d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5616 | 0 | -50 | Critical
10984 | Integrate Final Product Updates into ILT Content | May 15, 2026 8:00 AM | August 5, 2026 5:00 PM | 57 | -49d | 1856FF+8d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5617 | 0 | -49 | Critical
10987 | Training Delivery | July 17, 2026 8:00 AM | December 14, 2026 5:00 PM | 103 | -50d |  |  | 0 | -50 | Critical
10988 | Deliver Self Paced Online Training | July 17, 2026 8:00 AM | November 30, 2026 5:00 PM | 93 | -50d | 5611 | 5624SS+5d,5617SS+15d | 0 | -50 | Critical
10989 | Deliver TTT Training | August 7, 2026 8:00 AM | September 17, 2026 5:00 PM | 29 | -50d | 5616SS+15d,5612 | 5624,5618,3873SS | 0 | -50 | Critical
10990 | Deliver ILT | September 18, 2026 8:00 AM | December 14, 2026 5:00 PM | 59 | -32d | 5617,1904,1905,534,554,562 | 5620FF,5619FF | 0 | -32 | Critical
10991 | Deliver Refresher Training | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -32d | 5618FF | 5620FS-40d | 0 | -32 | Critical
10992 | Complete Final Sandbox Participation | October 15, 2026 8:00 AM | December 14, 2026 5:00 PM | 40 | -32d | 5618FF,5619FS-40d | 5630 | 0 | -32 | Critical
10993 | Pilot Execution | January 28, 2026 8:00 AM | December 14, 2026 5:00 PM | 221 | -48d |  |  | 0 | -48 | Critical
10995 | Conduct Pilot Users' Training | September 18, 2026 8:00 AM | October 15, 2026 5:00 PM | 20 | -49d | 5616SS+5d,5617 | 5626,5625SS+8d | 0 | -49 | Critical
10996 | Pilot Readiness Review and Go-No-Go Decision | September 30, 2026 8:00 AM | October 13, 2026 5:00 PM | 10 | -47d | 2415,2416,2417FS+5d,2438,2440,2442,5624SS+8d | 5626 | 0 | -47 | Critical
10997 | Conduct Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 29 | -49d | 5623,5625,5624 | 5627,5628,3875SS | 0 | -49 | Critical
10998 | Pilot Remediation | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -48d | 5626 | 5629 | 0 | -48 | Critical
10999 | Production Readiness Review and Go-No-Go Decision | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -49d | 5626,3049,2983,2152,1859 | 5629FS+1d,5630 | 0 | -49 | Critical
11000 | Production Execution | December 15, 2026 5:00 PM | December 15, 2026 5:00 PM | 0 | -49d | 5627,5628FS+1d,5611,5612,5613,5361FS-43d | 5630,3886 | 0 | -49 | Critical
6686 | Go-Live CWS-CARES V1 | October 26, 2026 5:00 PM | October 26, 2026 5:00 PM | 0 | -33d | 5629,5628,5620,2392,1855,4840,4841,4874,5306,5549,4883,4954,5372,5373,5026,5146,5215,5276,5330,5526,5539,5566,5642 | 5643FS+4d | 0 | -33 | Critical

## Excessive_Slack
UID | Task Name | Start | Finish | Duration | Total Slack | Predecessors | Successors | Percent Complete | __SlackDays | Severity
4935 | Completed/In-flight Milestones | April 26, 2022 8:00 AM | January 30, 2026 5:00 PM | 944 | 425d |  |  | 0.98 | 425 | Warning
11260 | Milestone 10: Case Closure (CARESV1-532) | February 27, 2023 8:00 AM | November 28, 2025 5:00 PM | 693 | 467d |  |  | 0.94 | 467 | Warning
11271 | M10: Build | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.91 | 505 | Warning
11290 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 378 | 2264SS,2529SS,381SS | 0.91 | 505 | Warning
11273 | M10: State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d |  |  | 0.82 | 467 | Warning
11296 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 383 | 2530SS,4512SS,389SS,387SS | 0.71 | 467 | Warning
11276 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 389SS | 391 | 0 | 467 | Warning
11277 | Milestone 10 (Case Closure) Jira # CARES V1-532 Complete | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 0 | 467d | 390 |  | 0 | 467 | Warning
6702 | Milestone 29: Federal Reports (CARESV1-503) | August 28, 2024 8:00 AM | January 30, 2026 5:00 PM | 357 | 425d |  |  | 0.4 | 425 | Warning
6843 | M29: Build | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 | 446d |  |  | 0.3 | 446 | Warning
6844 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 | 446d | 1433FF+21d,1148FF+6d | 524SS,4712SS+37d | 0.3 | 446 | Warning
6845 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 | 446d | 523SS | 526SS+19d,4712SS+37d | 0.3 | 446 | Warning
6711 | Milestone 30: State Reports (CARESV1-502) | September 17, 2024 8:00 AM | January 27, 2026 5:00 PM | 340 | 428d |  |  | 0.49 | 428 | Warning
6860 | M30: Build | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM | 77 | 449d |  |  | 0.34 | 449 | Warning
6861 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM | 77 | 449d | 545 | 549SS+19d | 0.34 | 449 | Warning
6720 | Milestone 31: Adhoc Reports (CARESV1-501) | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 | 467d |  |  | 0.62 | 467 | Warning
6882 | M31: Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 467d |  |  | 0.57 | 467 | Warning
7005 | CARESV1-34751 Technical Analytical Training (LOE) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 467d | 559SS | 561SS | 0.57 | 467 | Warning
2 | Process Areas | November 3, 2022 8:00 AM | May 1, 2026 5:00 PM | 873 | 362d |  |  | 0.87 | 362 | Warning
746 | Courts | May 22, 2023 8:00 AM | October 3, 2025 5:00 PM | 596 | 505d |  |  | 0.88 | 505 | Warning
760 | Courts: Holistic Design Milestones | May 22, 2023 8:00 AM | October 3, 2025 5:00 PM | 596 | 505d |  |  | 0.88 | 505 | Warning
864 | Courts: Build | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d |  |  | 0.89 | 544 | Warning
871 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d |  |  | 0.77 | 544 | Warning
873 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 867SS | 869SS,4567 | 0.83 | 544 | Warning
874 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 868SS | 882SS,4567 | 0.48 | 544 | Warning
880 | Milestone 18: Other Hearings (CARESV1-516) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d |  |  | 0.93 | 544 | Warning
881 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 852 | 877SS,2296SS,4597 | 0.88 | 544 | Warning
882 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 876SS | 878SS,4597 | 0.94 | 544 | Warning
883 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 877SS | 879FF,1480FF,891SS,4597 | 0.97 | 544 | Warning
884 | Courts Build Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 0 | 544d | 878FF | 4597 | 0.85 | 544 | Warning
4915 | Courts: SIT | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d |  |  | 0.82 | 544 | Warning
4929 | Milestone 18: Other Hearings (CARESV1-516) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d |  |  | 0.87 | 544 | Warning
4930 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 878SS | 892SS,4597,4601 | 0.88 | 544 | Warning
4931 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 891SS | 893SS,4597,4601 | 0.94 | 544 | Warning
4933 | Courts SIT Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 0 | 544d | 893FF | 2998,4597 | 0.85 | 544 | Warning
885 | Courts: State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.29 | 505 | Warning
892 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.18 | 505 | Warning
893 | M16: B1 09.11 Generate Notices (CARESV1-67) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 884 | 898SS,2564SS | 0.35 | 505 | Warning
896 | Milestone 17: Status Reviews (CARESV1-517) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.21 | 505 | Warning
897 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 889 | 902SS,2570SS | 0.42 | 505 | Warning
898 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 901SS | 903SS | 0.25 | 505 | Warning
901 | Milestone 18: Other Hearings (CARESV1-516) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.51 | 505 | Warning
902 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 893 | 907SS,2576SS | 0.65 | 505 | Warning
903 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 906SS | 908SS | 0.5 | 505 | Warning
905 | Courts: Joint Review | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.22 | 505 | Warning
923 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.07 | 505 | Warning
925 | M16: B1 09.11 Generate Notices (CARESV1-67) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 899SS | 912SS,2565SS | 0.2 | 505 | Warning
927 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 912SS | 914FF | 0.02 | 505 | Warning
10452 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 913FF |  | 0 | 505 | Warning
938 | Milestone 17: Status Reviews (CARESV1-517) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.09 | 505 | Warning
940 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 904SS | 917SS,2571SS | 0.15 | 505 | Warning
942 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 917SS | 919SS | 0.22 | 505 | Warning
943 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 918SS | 920FF | 0 | 505 | Warning
10453 | Milestone 17: Status Reviews (CARESV1-517) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 919FF |  | 0 | 505 | Warning
951 | Milestone 18: Other Hearings (CARESV1-516) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d |  |  | 0.55 | 505 | Warning
953 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 908SS | 923SS,2577SS | 0.65 | 505 | Warning
954 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 922SS | 924SS | 0.62 | 505 | Warning
955 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 923SS | 925FF | 0.37 | 505 | Warning
10454 | Milestone 18: Other Hearings (CARESV1-516) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 924FF |  | 0 | 505 | Warning
966 | Resource Family Approval | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | 430 | Warning
967 | Resource Family Approval: Holistic Design Milestones | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | 430 | Warning
968 | Group 1 Resource Family Approval (Milestones 26, 27, 28) | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | 430 | Warning
4195 | Resource Family Approval: Holistic Design Artifacts | July 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 167 | 636d |  |  | 0.99 | 636 | Warning
978 | Resource Family Approval - Design Cycle 2 | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 | 636d |  |  | 0.99 | 636 | Warning
981 | Resource Family Approval - Design Cycle 2 - Final Review and Design Baseline | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 34 | 636d | 941SS+5d | 992FF,1000FF | 0.97 | 636 | Warning
2677 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1011SS | 1013SS | 0 | 467 | Warning
2678 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1012SS | 1014SS | 0 | 467 | Warning
2679 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1013SS | 1015SS | 0 | 467 | Warning
2680 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1014SS | 1016SS | 0 | 467 | Warning
2681 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1015SS | 1017SS | 0 | 467 | Warning
2682 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1016SS |  | 0 | 467 | Warning
2686 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1020SS | 1022SS | 0 | 467 | Warning
2687 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1021SS |  | 0 | 467 | Warning
2719 | Resource Family Approval: State QA | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM | 37 | 430d |  |  | 0.18 | 430 | Warning
2720 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0.05 | 448 | Warning
2726 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1051SS | 1053SS | 0.33 | 448 | Warning
2692 | Milestone 27: Complaints (CARESV1-505) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0.56 | 448 | Warning
2693 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1047SS | 1056SS | 0.88 | 448 | Warning
2694 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1055SS | 1057SS | 0.89 | 448 | Warning
2695 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1056SS | 1058SS | 0.45 | 448 | Warning
2767 | Resource Family Approval: Joint Review | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM | 37 | 430d |  |  | 0 | 430 | Warning
2768 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0 | 448 | Warning
2770 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1053SS | 1066SS | 0 | 448 | Warning
2771 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1065SS | 1067SS | 0 | 448 | Warning
2772 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1066SS | 1068SS | 0 | 448 | Warning
2773 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1067SS | 1069SS | 0 | 448 | Warning
2774 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1068SS | 1070SS | 0 | 448 | Warning
2822 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1069SS | 1071SS | 0 | 448 | Warning
2775 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1070SS | 1072FF | 0 | 448 | Warning
10455 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1071FF |  | 0 | 448 | Warning
2783 | Milestone 27: Complaints (CARESV1-505) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0 | 448 | Warning
2785 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1058SS,989 | 1075SS | 0 | 448 | Warning
2786 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1074SS | 1076SS | 0 | 448 | Warning
2787 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1075SS | 1077SS | 0 | 448 | Warning
2788 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1076SS | 1078FF | 0 | 448 | Warning
10456 | Milestone 27: Complaints (CARESV1-505) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1077FF |  | 0 | 448 | Warning
2798 | Milestone 28: Legal Action (CARESV1-504) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d |  |  | 0 | 430 | Warning
2800 | M28: B1: RFA Legal actions (CARESV1-17) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1062SS | 1081SS | 0 | 430 | Warning
2801 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1080SS | 1082SS | 0 | 430 | Warning
2802 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1081SS | 1083FF | 0 | 430 | Warning
10457 | Milestone 28: Legal Action (CARESV1-504) Complete | January 23, 2026 5:00 PM | January 23, 2026 5:00 PM | 0 | 430d | 1082FF |  | 0 | 430 | Warning
1176 | Financial Management | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | 411 | Warning
1190 | Financial Management: Holistic Design Milestones | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | 411 | Warning
4899 | Group 1 Financial Management (Milestones 23/23.1, 24) | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | 411 | Warning
1255 | Financial Management: State QA | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0.14 | 411 | Warning
1256 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0.25 | 411 | Warning
1258 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1164SS | 1166SS | 0 | 411 | Warning
11532 | Financial Management: User Feedback (23/23.1, 24) | December 11, 2025 8:00 AM | December 26, 2025 5:00 PM | 11 | 448d |  |  | 0 | 448 | Warning
11533 | Financial Management - Conduct Hands-on keyboard User Feedback sessions | December 11, 2025 8:00 AM | December 26, 2025 5:00 PM | 11 | 448d | 1171FF | 1180FF | 0 | 448 | Warning
1265 | Financial Management: Joint Review | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0 | 411 | Warning
1266 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d |  |  | 0 | 411 | Warning
1268 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1167SS | 1177SS,1178SS,1179SS | 0 | 411 | Warning
1269 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS | 1178SS | 0 | 411 | Warning
1270 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS,1177SS | 1179SS | 0 | 411 | Warning
1271 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS,1178SS | 1180FF | 0 | 411 | Warning
10458 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) Complete | February 20, 2026 5:00 PM | February 20, 2026 5:00 PM | 0 | 411d | 1179FF,1173FF |  | 0 | 411 | Warning
1283 | Milestone 24: Track Assistance Costs (CARESV1-506) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0 | 448 | Warning
1285 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1171SS | 1183SS | 0 | 448 | Warning
1286 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1182SS | 1184SS | 0 | 448 | Warning
1287 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1183SS | 1185FF | 0 | 448 | Warning
10459 | Milestone 24: Track Assistance Costs (CARESV1-506) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1184FF |  | 0 | 448 | Warning
7532 | Eligibility | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | 429 | Warning
7533 | Eligibility: Holistic Design Milestones | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | 429 | Warning
7534 | Group 1 Eligibility (Milestone 21) | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | 429 | Warning
7587 | Eligibility: Build | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d |  |  | 0.38 | 467 | Warning
7588 | Milestone 21: Eligibility Programs (CARESV1-511) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d |  |  | 0.38 | 467 | Warning
7591 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1231SS,1233SS | 1235SS | 0.9 | 467 | Warning
7592 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1231SS,1234SS | 1238SS | 0 | 467 | Warning
7603 | Eligibility: SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d |  |  | 0.58 | 467 | Warning
7604 | Milestone 21: Eligibility Programs (CARESV1-511) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d |  |  | 0.58 | 467 | Warning
7607 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1239SS,1240SS | 128SS | 0.9 | 467 | Warning
7613 | Eligibility: State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0.8 | 448 | Warning
7614 | Milestone 21: Eligibility Programs (CARESV1-511) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d |  |  | 0.8 | 448 | Warning
7616 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1245SS |  | 0 | 448 | Warning
7623 | Eligibility: Joint Review | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d |  |  | 0 | 429 | Warning
7624 | Milestone 21: Eligibility Programs (CARESV1-511) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d |  |  | 0 | 429 | Warning
7638 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1249 |  | 0 | 429 | Warning
7625 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1249 | 1254SS,1255SS,1256SS | 0 | 429 | Warning
7626 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS | 1255SS | 0 | 429 | Warning
7627 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS,1254SS | 1256SS | 0 | 429 | Warning
7628 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS,1255SS | 1257FF | 0 | 429 | Warning
10460 | Milestone 21: Eligibility Programs (CARESV1-511) Complete | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 429d | 1256FF |  | 0 | 429 | Warning
6335 | Shared Services | November 3, 2022 8:00 AM | March 2, 2026 3:00 PM | 829.75 | 405.25d |  |  | 0.93 | 405.25 | Warning
6336 | Shared Services: Holistic Design Milestones | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM | 279 | 544d |  |  | 0.99 | 544 | Warning
6337 | Group 1 Shared Services | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM | 279 | 544d |  |  | 0.99 | 544 | Warning
6339 | Shared Services: Holistic Design Artifacts | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM | 279 | 544d |  |  | 0.99 | 544 | Warning
6344 | Shared Services - Design Cycle 2 | October 31, 2024 8:00 AM | August 8, 2025 5:00 PM | 192 | 544d |  |  | 0.98 | 544 | Warning
6345 | Shared Services - Design Cycle 2 - Prepare Walkthrough | October 31, 2024 8:00 AM | July 18, 2025 5:00 PM | 177 | 559d | 1295SS+63d | 1298SS+5d,1314SS | 0.98 | 559 | Warning
6346 | Shared Services - Design Cycle 2 - Conduct Design Walkthrough | November 7, 2024 8:00 AM | July 25, 2025 5:00 PM | 177 | 554d | 1297SS+5d | 1299SS+5d | 0.98 | 554 | Warning
6347 | Shared Services - Design Cycle 2 - Final Review and Design Baseline | November 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 182 | 544d | 1298SS+5d | 1314FF | 0.98 | 544 | Warning
11203 | Shared Services Milestones | August 14, 2023 8:00 AM | March 2, 2026 3:00 PM | 637.75 | 405.25d |  |  | 0.89 | 405.25 | Warning
11104 | Shared Services - Case Planning Framework (M7) | July 15, 2024 8:00 AM | October 3, 2025 5:00 PM | 309 | 505d |  |  | 0.97 | 505 | Warning
11204 | Shared Services - Case Planning Framework (M7) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 1320 |  | 0.77 | 505 | Warning
11107 | Shared Services - Content Management (M7) | July 15, 2024 8:00 AM | October 3, 2025 5:00 PM | 309 | 505d |  |  | 0.92 | 505 | Warning
11366 | Shared Services - Content Management (M7) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 1324 |  | 0.43 | 505 | Warning
11110 | Shared Services - Deletion (M11) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM | 277 | 467d |  |  | 0.81 | 467 | Warning
11112 | Shared Services - Deletion (M11) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 467d | 1327 | 1329 | 0.62 | 467 | Warning
11367 | Shared Services - Deletion (M11) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1328 |  | 0 | 467 | Warning
11113 | Shared Services - Duplicate Management (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM | 311 | 448d |  |  | 0.7 | 448 | Warning
11368 | Shared Services - Duplicate Management (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1047SS,1332FS-60d |  | 0.18 | 448 | Warning
11122 | Shared Services - Matching (M11) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM | 277 | 467d |  |  | 0.94 | 467 | Warning
11124 | Shared Services - Matching (M11) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 1339FS+49d | 1341 | 0.62 | 505 | Warning
11125 | Shared Services - MDM (Master Data Management) (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM | 311 | 448d |  |  | 0.82 | 448 | Warning
11127 | Shared Services - MDM (Master Data Management) (M26) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1343 | 1345FS-106d | 0 | 467 | Warning
11372 | Shared Services - MDM (Master Data Management) (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1047SS,1344FS-106d |  | 0 | 448 | Warning
11128 | Shared Services - Notifications (reminders, alerts) (M15) | August 14, 2023 8:00 AM | October 3, 2025 5:00 PM | 538 | 505d |  |  | 0.92 | 505 | Warning
11373 | Shared Services - Notifications (reminders, alerts) (M15) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 439SS,1348 |  | 0 | 505 | Warning
11131 | Shared Services - Person Profile (M13) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM | 277 | 467d |  |  | 0.97 | 467 | Warning
11374 | Shared Services - Person Profile (M13) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1352 |  | 0.85 | 467 | Warning
11134 | Shared Services - Product Metrics (M23) | December 4, 2024 8:00 AM | February 4, 2026 1:48 PM | 292.6 | 422.4d |  |  | 0.83 | 422.4 | Warning
11375 | Shared Services - Product Metrics (M23) - State QA | December 1, 2025 8:00 AM | February 4, 2026 1:48 PM | 19 | 422.4d | 1164SS,1356FS-127d |  | 0.6 | 422.4 | Warning
11143 | Shared Services - Search (M23) | December 4, 2024 8:00 AM | March 2, 2026 3:00 PM | 309.75 | 405.25d |  |  | 0.84 | 405.25 | Warning
11377 | Shared Services - Search (M23) - State QA | December 1, 2025 8:00 AM | March 2, 2026 3:00 PM | 19 | 405.25d | 1366 |  | 0.75 | 405.25 | Warning
11146 | Shared Services - Worker Mgmt./ Hierarchy (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM | 311 | 448d |  |  | 0.77 | 448 | Warning
11147 | Shared Services - Worker Mgmt./ Hierarchy (M26) - Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 254 | 448d | 934SS | 1370 | 0.94 | 448 | Warning
11148 | Shared Services - Worker Mgmt./ Hierarchy (M26) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 448d | 1011SS,1369 | 1371 | 0 | 448 | Warning
11378 | Shared Services - Worker Mgmt./ Hierarchy (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1370 |  | 0 | 448 | Warning
11149 | Shared Services - Workload View (M13) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM | 277 | 467d |  |  | 0.81 | 467 | Warning
11151 | Shared Services - Workload View (M13) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 467d | 709SS,1373 | 1375 | 0.62 | 467 | Warning
11379 | Shared Services - Workload View (M13) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 467d | 1374 |  | 0 | 467 | Warning
12681 | Shared Services Admin Services | November 3, 2022 8:00 AM | November 28, 2025 5:00 PM | 768 | 467d |  |  | 0.95 | 467 | Warning
12685 | RBAC Framework (SalesForce) | November 3, 2022 8:00 AM | November 28, 2025 5:00 PM | 768 | 467d |  |  | 0.93 | 467 | Warning
12684 | Shared Services - RBAC Framework (SalesForce) - Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 467d | 1379 |  | 0.31 | 467 | Warning
12677 | Shared Services - RBAC Framework (Tableau) - Build | April 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 151 | 485d |  |  | 0.9 | 485 | Warning
43871 | EUST 3 Build Drop Demos | May 30, 2025 8:00 AM | January 9, 2026 5:00 PM | 155 | 439d |  |  | 0.53 | 439 | Warning
43880 | BD 4 Demo | October 20, 2025 8:00 AM | November 14, 2025 5:00 PM | 19 | 439d |  |  | 0 | 439 | Warning
43881 | Conduct and Gather User Feedback | October 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 10 | 439d | 1397FS+20d | 1400SS | 0 | 439 | Warning
43868 | Capture and Document in JIRA | October 20, 2025 8:00 AM | November 14, 2025 5:00 PM | 19 | 439d | 1399SS | 1402FS+14d | 0 | 439 | Warning
43869 | BD 5 Demo | December 8, 2025 8:00 AM | January 9, 2026 5:00 PM | 23 | 439d |  |  | 0 | 439 | Warning
43870 | Conduct and Gather User Feedback | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 | 439d | 1400FS+14d | 1403SS | 0 | 439 | Warning
43865 | Capture and Document in JIRA | December 8, 2025 8:00 AM | January 9, 2026 5:00 PM | 23 | 439d | 1402SS |  | 0 | 439 | Warning
4273 | Interfaces | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM | 731 | 448d |  |  | 0.96 | 448 | Warning
4274 | Milestone FCED 20.1 (M19/20/21/13) (CARESV1-45363) | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM | 731 | 448d |  |  | 0.99 | 448 | Warning
11587 | Milestone FCED 20.1 (M19/20/21/13) (CARESV1-45363) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1410FF |  | 0 | 448 | Warning
4284 | Milestone CMA 7.1 (CARESV1-45369) | May 24, 2024 8:00 AM | October 3, 2025 5:00 PM | 343 | 505d |  |  | 0.87 | 505 | Warning
4288 | Milestone CMA 7.1 - QA and End-to-End Testing | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 1421 | 1423 | 0.04 | 505 | Warning
11589 | Milestone CMA 7.1 (CARESV1-45369) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 1422 |  | 0 | 505 | Warning
4289 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM | 366 | 448d |  |  | 0.73 | 448 | Warning
4293 | Milestone (LIS/FAS data) 26.1 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1427 | 1429FF | 0.08 | 448 | Warning
11590 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1428FF |  | 0 | 448 | Warning
4294 | Milestone CECRIS 23.2 (CARESV1-45376) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM | 366 | 448d |  |  | 0.79 | 448 | Warning
4297 | Milestone CECRIS 23.2 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 446d | 1432 | 1434,523FF+21d | 0 | 446 | Warning
4298 | Milestone CECRIS 23.2 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1433 | 1435 | 0 | 448 | Warning
11591 | Milestone CECRIS 23.2 (CARESV1-45376) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1434 |  | 0 | 448 | Warning
6814 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) | April 24, 2023 8:00 AM | October 3, 2025 5:00 PM | 616 | 505d |  |  | 0.97 | 505 | Warning
6470 | M10.1: State QA | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d |  |  | 0.96 | 505 | Warning
6472 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1463SS | 1465SS | 0.96 | 505 | Warning
6473 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1464SS | 1469FF | 0.92 | 505 | Warning
6477 | M10.1: Joint Review | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d |  |  | 0.84 | 505 | Warning
6479 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1467SS | 1469SS | 0.92 | 505 | Warning
6480 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1468SS,1465FF | 1470 | 0.59 | 505 | Warning
11592 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 1469 |  | 0 | 505 | Warning
4299 | Hardening | September 4, 2023 8:00 AM | December 1, 2025 5:00 PM | 562 | 466d |  |  | 0.75 | 466 | Warning
4311 | H3 (Hardening - 6.1, 7, 7.1, 9, 10, 10.1, 11, 13, 14, 16, 17, 18, 20.1, 21, 23, 23.1, 23.2, 24, 26, 26.1, 27, 28) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | 466d |  |  | 0.45 | 466 | Warning
5478 | H3 EUST Backlog (Resolve Prior EUST Findings) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | 466d | 707FF,735FF,717FF,745FF,713FF,741FF,878FF,893FF | 1481SS | 0.45 | 466 | Warning
11626 | H3 Re-skin of EUST-3 Milestones (1, 9, 10, 14, 21) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | 466d | 1480SS |  | 0.45 | 466 | Warning
2858 | EUST (Extended User Scenario Testing) / Validation Sprints in CARES V1 | February 1, 2024 8:00 AM | July 10, 2026 5:00 PM | 613 | 314d? |  |  | 0.45 | 314 | Warning
2864 | EUST - 3 | October 28, 2024 8:00 AM | May 19, 2026 5:00 PM | 389 | 350d? |  |  | 0.17 | 350 | Warning
43567 | EUST 3 - Preparation | October 28, 2024 8:00 AM | February 26, 2026 5:00 PM | 332 | 407d? |  |  | 0.29 | 407 | Warning
43568 | EUST 3 - Scenario Writing | May 19, 2025 8:00 AM | December 26, 2025 5:00 PM | 154 | 448d? |  |  | 0.6 | 448 | Warning
43578 | Build Drop 2 Scenario Writing | June 13, 2025 8:00 AM | August 15, 2025 5:00 PM | 45 | 539d |  |  | 0.99 | 539 | Warning
43588 | Review and Validate Key Actions/Steps | August 11, 2025 8:00 AM | August 15, 2025 5:00 PM | 5 | 539d |  | 1641FF | 0.9 | 539 | Warning
43589 | Submit Final Scenarios to Training Team | August 15, 2025 8:00 AM | August 15, 2025 5:00 PM | 1 | 539d | 1640FF | 1767 | 0.9 | 539 | Warning
43590 | Build Drop 3 Scenario Writing | July 7, 2025 8:00 AM | September 15, 2025 5:00 PM | 50 | 519d |  |  | 0.78 | 519 | Warning
43599 | Submit completed testing and key Actions and sed to User Feedback Team | September 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 1 | 521d | 1650 |  | 0.1 | 521 | Warning
43601 | Submit Final Scenarios to Training Team | September 15, 2025 8:00 AM | September 15, 2025 5:00 PM | 1 | 519d | 1652 | 1768 | 0.05 | 519 | Warning
43602 | Build Drop 4 Scenario Writing | August 18, 2025 8:00 AM | November 14, 2025 5:00 PM | 63 | 476d |  |  | 0.44 | 476 | Warning
43605 | PaaS application demo and walkthrough of developed funcationality | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 504d |  |  | 0 | 504 | Warning
43607 | Develop Scenario Narratives | October 3, 2025 8:00 AM | October 17, 2025 5:00 PM | 11 | 495d | 1656SS |  | 0.09 | 495 | Warning
43608 | Review Draft Scenario Narratives with Service Areas | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 480d | 1658 | 1661FF | 0 | 480 | Warning
43609 | Submit Scenario Narratives to Technical Testing Team | October 17, 2025 8:00 AM | October 17, 2025 5:00 PM | 1 | 480d | 1660FF | 1662 | 0 | 480 | Warning
43610 | Conduct Testing and Add Key Actions | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 15 | 480d | 1661 |  | 0 | 480 | Warning
43611 | Submit completed testing and key Actions and sed to User Feedback Team | November 7, 2025 8:00 AM | November 7, 2025 5:00 PM | 1 | 476d |  | 1664 | 0 | 476 | Warning
43612 | Review and Validate Key Actions/Steps | November 10, 2025 8:00 AM | November 14, 2025 5:00 PM | 4 | 476d | 1663 |  | 0 | 476 | Warning
43613 | Submit Final Scenarios to Training Team | November 14, 2025 8:00 AM | November 14, 2025 5:00 PM | 1 | 439d |  | 1769 | 0 | 439 | Warning
43614 | Build Drop 5 Scenario Writing | September 17, 2025 8:00 AM | January 14, 2026 5:00 PM | 82 | 436d |  |  | 0.13 | 436 | Warning
43615 | Conduct Initial Analysis of Planned Build Drop 5 | September 17, 2025 8:00 AM | November 28, 2025 5:00 PM | 51 | 466d |  | 1669 | 0.25 | 466 | Warning
43616 | Delivery of Build Drop Completed | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 1 | 426d |  | 1670 | 0 | 426 | Warning
43617 | PaaS application demo and walkthrough of developed funcationality | December 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 1 | 466d | 1667 |  | 0 | 466 | Warning
43618 | Conduct Funcational Analysis | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 426d | 1668 | 1672 | 0 | 426 | Warning
43619 | Develop Scenario Narratives | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 10 | 457d |  |  | 0 | 457 | Warning
43620 | Review Draft Scenario Narratives with Service Areas | December 8, 2025 8:00 AM | December 12, 2025 5:00 PM | 5 | 426d | 1670 | 1673FF | 0 | 426 | Warning
43621 | Submit Scenario Narratives to Technical Testing Team | December 12, 2025 8:00 AM | December 12, 2025 5:00 PM | 1 | 426d | 1672FF | 1674 | 0 | 426 | Warning
43622 | Conduct Testing and Add Key Actions | December 15, 2025 8:00 AM | January 6, 2026 5:00 PM | 15 | 426d | 1673 | 1675 | 0 | 426 | Warning
43623 | Submit completed testing and key Actions and sed to User Feedback Team | January 7, 2026 8:00 AM | January 7, 2026 5:00 PM | 1 | 426d | 1674 | 1676 | 0 | 426 | Warning
43624 | Review and Validate Key Actions/Steps | January 8, 2026 8:00 AM | January 13, 2026 5:00 PM | 4 | 426d | 1675 | 1677 | 0 | 426 | Warning
43625 | Submit Final Scenarios to Training Team | January 14, 2026 8:00 AM | January 14, 2026 5:00 PM | 1 | 426d | 1676 | 1770 | 0 | 426 | Warning
43828 | Usability Testing Feedback (Previously Milestone User Feedback) | July 11, 2025 8:00 AM | January 13, 2026 5:00 PM | 128 | 437d |  |  | 0.19 | 437 | Warning
43831 | Usability Testing (BD 1-3) | September 8, 2025 8:00 AM | December 3, 2025 5:00 PM | 61 | 464d |  |  | 0.26 | 464 | Warning
43835 | Load users to SharePoint feedback site as needed | October 7, 2025 8:00 AM | November 3, 2025 5:00 PM | 20 | 484d |  |  | 0 | 484 | Warning
43838 | Confirm Staging Environment Readiness | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 494d |  | 1689SS | 0 | 494 | Warning
43839 | Complete Build / SIT and data load in Staging | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 5 | 494d | 1688SS | 1690SS | 0 | 494 | Warning
43840 | Data loaded in staging (Day 0 data) | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 5 | 494d | 1689SS | 1692,1694 | 0 | 494 | Warning
43841 | PaaS User Access Testing to Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 490d |  |  | 0 | 490 | Warning
43842 | Complete State QA of code in Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 489d | 1690 | 1693 | 0 | 489 | Warning
43843 | Hold User Feedback Kickoff Meeting | October 27, 2025 8:00 AM | October 27, 2025 5:00 PM | 1 | 489d | 1692 |  | 0 | 489 | Warning
43844 | Schedule M-Th office hours for 2 weeks of testing | October 27, 2025 8:00 AM | October 27, 2025 5:00 PM | 1 | 489d | 1690 |  | 0 | 489 | Warning
43845 | Conduct User Feedback Testing | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM | 10 | 465d |  | 1696SS | 0 | 465 | Warning
43846 | Capture feedback in MS Teams and Document in JIRA | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM | 10 | 465d | 1695SS | 1697 | 0 | 465 | Warning
43847 | Report out on User Feedback | November 10, 2025 8:00 AM | November 20, 2025 5:00 PM | 8 | 465d | 1696 | 1698 | 0 | 465 | Warning
43848 | Present findings to ELT | November 24, 2025 8:00 AM | November 24, 2025 5:00 PM | 1 | 464d | 1697 | 1699FS+5d | 0 | 464 | Warning
43849 | Present findings to User Feedback participants | December 3, 2025 8:00 AM | December 3, 2025 5:00 PM | 1 | 464d | 1698FS+5d |  | 0 | 464 | Warning
43850 | Usability Testing (BD 4) | November 24, 2025 8:00 AM | January 13, 2026 5:00 PM | 34 | 437d |  |  | 0 | 437 | Warning
43851 | Confrim User Permission Sets Validated | November 24, 2025 8:00 AM | November 26, 2025 5:00 PM | 3 | 468d |  |  | 0 | 468 | Warning
43852 | Confirm Staging Environment Readiness | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | 462 | Warning
43853 | Complete Build / SIT and data load in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | 462 | Warning
43854 | Data loaded in staging (Day 0 data) | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | 462 | Warning
43855 | Complete State QA of code in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | 462 | Warning
43856 | Hold User Feedback Kickoff Meeting | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM | 1 | 461d |  |  | 0 | 461 | Warning
43857 | Schedule M-Th office hours for 2 weeks of testing | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM | 1 | 461d |  |  | 0 | 461 | Warning
43858 | Conduct User Feedback Testing | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 | 452d |  |  | 0 | 452 | Warning
43859 | Capture feedback in MS Teams and Document in JIRA | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 | 437d |  | 1710 | 0 | 437 | Warning
43860 | Report out on User Feedback | December 22, 2025 8:00 AM | January 2, 2026 5:00 PM | 8 | 437d | 1709 | 1711 | 0 | 437 | Warning
43861 | Present findings to ELT | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 437d | 1710 | 1712FS+5d | 0 | 437 | Warning
43862 | Present findings to User Feedback participants | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1 | 437d | 1711FS+5d |  | 0 | 437 | Warning
43647 | EUST 3 - User setup and access validation | November 7, 2024 8:00 AM | March 10, 2025 5:00 PM |  | 650d? |  |  | 0.09 | 650 | Warning
43651 | Send communication to all counties for participation in EUST 3 | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 504d | 1716 | 1718SS,1721SS,1722SS,1723SS | 0.5 | 504 | Warning
43652 | Schedule EUST overview/Q&A meeting for counties | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 504d | 1717SS |  | 0.5 | 504 | Warning
43653 | Hold EUST 3 overview meeting option 1 | November 6, 2025 8:00 AM | November 6, 2025 5:00 PM | 1 | 480d |  | 1720 | 0 | 480 | Warning
43654 | Hold EUST 3 overview meeting option 2 | November 7, 2025 8:00 AM | November 7, 2025 5:00 PM | 1 | 480d | 1719 |  | 0 | 480 | Warning
43655 | Document county participants in EUST 3 | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 454d | 1717SS | 1729FS-1d | 0 | 454 | Warning
43656 | Add new users to spreadsheet: Users by County | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 468d | 1717SS |  | 0 | 468 | Warning
43657 | Add county participants to Microsoft Teams Space for EUST 3 Feedback | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 468d | 1717SS |  | 0 | 468 | Warning
43658 | Communicate with County teams to test access to EUST 3 | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM | 5 | 425d |  | 1725SS | 0 | 425 | Warning
43659 | Confirm EUST 3 environment connectivity for all counties | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM | 5 | 425d | 1724SS | 1726FS-5d | 0 | 425 | Warning
43660 | Confirm EUST 3 county user access to the environment | February 10, 2026 8:00 AM | February 17, 2026 5:00 PM | 5 | 414d | 1725FS-5d,1754 |  | 0 | 414 | Warning
43661 | User Provisioning | October 13, 2025 8:00 AM | January 16, 2026 5:00 PM | 66 | 434d |  |  | 0 | 434 | Warning
43662 | Identify Office / Unit Structure Needs for EUST 3 | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 485d |  | 1761 | 0 | 485 | Warning
43663 | Provision users to EUST environment | November 26, 2025 8:00 AM | December 17, 2025 5:00 PM | 15 | 454d | 1721FS-1d |  | 0 | 454 | Warning
43664 | Produce Template for Office / Unit Structure | November 26, 2025 8:00 AM | November 26, 2025 5:00 PM | 1 | 434d |  | 1731 | 0 | 434 | Warning
43665 | Distribute the Template to Counties | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 1 | 434d | 1730 | 1732 | 0 | 434 | Warning
43666 | Counties to fill out Office / Unit Structure and Return | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 10 | 434d | 1731 | 1733 | 0 | 434 | Warning
43667 | Coordinate with OKTA to complete IP whitelisting for counties in EUST | December 15, 2025 8:00 AM | January 6, 2026 5:00 PM | 15 | 434d | 1732 | 1734SS | 0 | 434 | Warning
43668 | Confirm User Set up w/OKTA team | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 5 | 434d | 1733SS | 1735FS-1d | 0 | 434 | Warning
43669 | Assign Profile, Permissions and complete user set up/complete spreadsheet | December 19, 2025 8:00 AM | January 5, 2026 5:00 PM | 10 | 434d | 1734FS-1d | 1736FS-1d | 0 | 434 | Warning
43670 | Receive communication from OKTA team that user set up is complete and active | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 434d | 1735FS-1d | 1739,1737 | 0 | 434 | Warning
43671 | Upload Office / Unit Structure from templates | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d | 1736 | 1738SS-1d | 0 | 434 | Warning
43672 | Provision Users for EUST 3 (Okta Team) | January 9, 2026 8:00 AM | January 15, 2026 5:00 PM | 5 | 435d | 1737SS-1d |  | 0 | 435 | Warning
43673 | Communicate to end users and confirm access (CC SPOC) or if they need a PW reset | January 16, 2026 8:00 AM | January 16, 2026 5:00 PM | 1 | 434d | 1736 |  | 0 | 434 | Warning
43674 | EUST 3 Infrastructure / Environment Setup | October 28, 2024 8:00 AM | February 9, 2026 5:00 PM | 320 | 419d |  |  | 0.02 | 419 | Warning
43676 | Setup Okta Integration | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d | 1743SS | 1751SS | 0 | 443 | Warning
43677 | Mule API Updated Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 439d |  | 1742SS | 0 | 439 | Warning
43678 | DocuEdge Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 439d |  |  | 0 | 439 | Warning
43679 | DocuEdge Mule Endpoint Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 414d |  | 1746 | 0 | 414 | Warning
43680 | DocuEdge Configuration | January 7, 2026 8:00 AM | January 9, 2026 5:00 PM | 3 | 414d | 1745 | 1749 | 0 | 414 | Warning
43681 | AEM Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 442d |  |  | 0 | 442 | Warning
43682 | SOLR API Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 442d |  |  | 0 | 442 | Warning
43683 | Salesforce Integration | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 414d | 1746 | 1750 | 0 | 414 | Warning
43684 | Deploy code build (Initial) | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 414d | 1749 | 1752 | 0 | 414 | Warning
43685 | Snowflake Updated Deployment | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d | 1742SS |  | 0 | 443 | Warning
43686 | Syncing users in Okta | January 27, 2026 8:00 AM | February 2, 2026 5:00 PM | 5 | 414d | 1750 | 1753 | 0 | 414 | Warning
43687 | Validate Access for Testing Team | February 3, 2026 8:00 AM | February 4, 2026 5:00 PM | 2 | 414d | 1752 | 1754 | 0 | 414 | Warning
43688 | Smoke Test Initial Environment Build | February 5, 2026 8:00 AM | February 9, 2026 5:00 PM | 3 | 414d | 1753 | 1726 | 0 | 414 | Warning
43689 | Deployment to EUST 3 Environment | November 17, 2025 8:00 AM | January 26, 2026 5:00 PM | 47 | 429d |  |  | 0 | 429 | Warning
43690 | Final Code Deployment for EUST 3 Admin | January 6, 2026 8:00 AM | January 6, 2026 5:00 PM | 1 | 437d |  | 1758 | 0 | 437 | Warning
43691 | Final Code Depoloyment for EUST 3 | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 429d | 1759 |  | 0 | 429 | Warning
43692 | Smoke Test Environment | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 5 | 437d | 1756 |  | 0 | 437 | Warning
43693 | EUST 3 Data Readiness | November 17, 2025 8:00 AM | January 16, 2026 5:00 PM | 42 | 429d |  | 1757 | 0 | 429 | Warning
43694 | Identify Transactional Data Needs for EUST 3 (including volume) | November 17, 2025 8:00 AM | December 30, 2025 5:00 PM | 30 | 436d |  | 1761 | 0 | 436 | Warning
43695 | Confirm Data needs for EUST 3 Office / Unit and Transactional Data | December 31, 2025 8:00 AM | January 7, 2026 5:00 PM | 5 | 436d | 1728,1760 |  | 0 | 436 | Warning
43696 | Develop steps to manually create Transactional Data | December 8, 2025 8:00 AM | January 6, 2026 5:00 PM | 20 | 437d |  |  | 0 | 437 | Warning
43697 | Deploy EUST 3 Package and Day 0 Data | January 5, 2026 8:00 AM | January 16, 2026 5:00 PM | 10 | 429d |  |  | 0 | 429 | Warning
43698 | EUST 3 - Conduct User Training | July 14, 2025 8:00 AM | February 26, 2026 5:00 PM | 157 | 407d |  |  | 0.41 | 407 | Warning
43699 | Virtual Instructor-Led Training (1/12/26 - 2/20/26) | July 14, 2025 8:00 AM | January 29, 2026 5:00 PM | 138 | 426d |  |  | 0.55 | 426 | Warning
43703 | Develop Training Curriculum and Materials (Drop 4) | November 17, 2025 8:00 AM | December 8, 2025 5:00 PM | 15 | 439d | 1665 | 1771FF+7d | 0 | 439 | Warning
43704 | Develop Training Curriculum and Materials (Drop 5) | January 15, 2026 8:00 AM | January 29, 2026 5:00 PM | 10 | 426d | 1677 |  | 0 | 426 | Warning
43705 | Confirm Number of Admin Console Training Attendees (by Course) | December 17, 2025 8:00 AM | December 17, 2025 5:00 PM | 1 | 439d | 1769FF+7d | 1773FS+10d | 0 | 439 | Warning
43706 | Schedule Training Sessions | December 22, 2025 8:00 AM | December 22, 2025 5:00 PM | 1 | 451d |  |  | 0 | 451 | Warning
43707 | Finalize Training Materials | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 439d | 1771FS+10d |  | 0 | 439 | Warning
43708 | Load Quick Reference Guides and Knowledge Base Articles for Admin | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | 434 | Warning
43709 | Deliver training for EUST 3 Admin Console | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | 434 | Warning
43710 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | 434 | Warning
43711 | Load Quick Reference Guides and Knowledge Base Articles for EUST3 | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | 434 | Warning
43712 | Deliver training for EUST 3 | January 12, 2026 8:00 AM | January 30, 2026 5:00 PM | 14 | 425d |  |  | 0 | 425 | Warning
43713 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 30, 2026 5:00 PM | 14 | 425d |  |  | 0 | 425 | Warning
43714 | Load Quick Reference Guides and Knowledge Base Articles for Reporting Training | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 1 | 425d |  |  | 0 | 425 | Warning
43715 | Deliver training for EUST 3 Reporting Training | February 23, 2026 8:00 AM | February 26, 2026 5:00 PM | 4 | 407d |  |  | 0 | 407 | Warning
43716 | Support Office Hours / Delivery Make-Up Sessions (As needed) | February 23, 2026 8:00 AM | February 26, 2026 5:00 PM | 4 | 407d |  |  | 0 | 407 | Warning
43717 | EUST 3 - Deployment to CARES EUST V1 | January 6, 2026 8:00 AM | January 27, 2026 5:00 PM | 15 | 428d |  |  | 0 | 428 | Warning
43718 | Confirm readiness of environment | January 6, 2026 8:00 AM | January 12, 2026 5:00 PM | 5 | 428d |  | 1786,1787,1785,1788,1789,1790,1791 | 0 | 428 | Warning
43719 | Confirm interface integration connection | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43720 | Test interface integration with EUST environment - FCED/CalSAWS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43721 | Test interface integration with EUST environment - JNET/San Bern. | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43722 | Test interface integration with EUST environment - SDM/Evident Change | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43723 | Test interface integration with EUST environment - P-CIS/Opeeka | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43724 | Test interface integration with EUST environment - LIS/FAS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43725 | Test interface integration with EUST environment - CECRIS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | 428 | Warning
43726 | EUST 3 Go-No-Go | January 5, 2026 8:00 AM | February 9, 2026 5:00 PM | 25 | 419d |  |  | 0 | 419 | Warning
43727 | EUST 3 Admin Go-No-Go | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d |  |  | 0 | 443 | Warning
43728 | EUST 3 Go-No-Go (session 1) | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d |  |  | 0 | 443 | Warning
43729 | EUST 3 Final Go-No-Go | January 26, 2026 8:00 AM | January 26, 2026 5:00 PM | 1 | 429d |  |  | 0 | 429 | Warning
43730 | EUST 3 Reporting - Confirm EUST Readiness | February 9, 2026 8:00 AM | February 9, 2026 5:00 PM | 1 | 419d |  |  | 0 | 419 | Warning
43731 | Validation for all scenarios | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 1 | 425d |  |  | 0 | 425 | Warning
43733 | Facilitate EUST 3 Admin Kickoff | January 20, 2026 8:00 AM | January 20, 2026 5:00 PM | 1 | 433d |  |  | 0 | 433 | Warning
43734 | EUST 3 Admin Testing Start | January 20, 2026 8:00 AM | January 20, 2026 5:00 PM | 1 | 433d |  |  | 0 | 433 | Warning
43735 | Facilitate EUST 3 Kickoff | February 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 1 | 424d |  |  | 0 | 424 | Warning
43736 | EUST 3 Testing Start | February 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 1 | 424d |  |  | 0 | 424 | Warning
43737 | Facilitate EUST 3 Reporting Kickoff | February 23, 2026 8:00 AM | February 23, 2026 5:00 PM | 1 | 410d |  |  | 0 | 410 | Warning
43738 | EUST 3 Reporting Testing Start | February 23, 2026 8:00 AM | February 23, 2026 5:00 PM | 1 | 410d |  | 1815SS | 0 | 410 | Warning
43739 | EUST 3 Validation | January 16, 2026 8:00 AM | April 3, 2026 5:00 PM | 53 | 382d |  |  | 0 | 382 | Warning
43740 | EUST 3 Admin Console (Partial M32) | January 20, 2026 8:00 AM | January 30, 2026 5:00 PM | 9 | 382d |  | 1807 | 0 | 382 | Warning
43741 | Validation for Milestone 1, 2, 3 ,4, 5, 6, 8, 15, 15.1, 19, 20, 20.1 | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1806 | 1808SS,1809SS,1810SS,1811SS,1812SS,1813SS,1814SS | 0 | 382 | Warning
43742 | Test interface integration with EUST environment - FCED/CalSAWS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43743 | Test interface integration with EUST environment - JNET/San Bern. | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43744 | Test interface integration with EUST environment - SDM/Evident Change | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43745 | Test interface integration with EUST environment - P-CIS/Opeeka | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43746 | Test interface integration with EUST environment - LIS/FAS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43747 | Test interface integration with EUST environment - CECRIS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43748 | EUST for Milestones 6.1, 7, 7.1, 9, 10, 10.1, 11, 13, 14, 16, 17, 18, 20.1, 21, 23, 23.1, 23.2, 24, 26, 26.1, 27, 28, 29, 30, 32 | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | 382 | Warning
43749 | EUST 3 Reporting | February 23, 2026 8:00 AM | April 3, 2026 5:00 PM | 29 | 382d | 1804SS |  | 0 | 382 | Warning
43750 | EUST 3 Feedback | January 13, 2026 8:00 AM | April 3, 2026 5:00 PM | 56 | 382d |  |  | 0 | 382 | Warning
43751 | Prepare MS Teams feedback template for feedback in alignment with JIRA fields | January 13, 2026 8:00 AM | January 16, 2026 5:00 PM | 4 | 434d |  |  | 0 | 434 | Warning
43752 | Schedule EUST Office Hours | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1 | 437d |  |  | 0 | 437 | Warning
43753 | Conduct Office Hours | January 16, 2026 8:00 AM | April 3, 2026 5:00 PM | 53 | 382d |  |  | 0 | 382 | Warning
43754 | Schedule prioritization sessions to prioritize feedback | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1 | 437d |  |  | 0 | 437 | Warning
43755 | Upload the spreadsheet w/user feedback to JIRA | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d |  | 1822SS,1823SS,1824SS | 0 | 382 | Warning
43756 | Manage MS teams feedback | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d | 1821SS |  | 0 | 382 | Warning
43757 | EUST 3 - Build/SIT Findings | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d | 1821SS |  | 0 | 382 | Warning
43758 | EUST 3 - QA Findings | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d | 1821SS |  | 0 | 382 | Warning
43759 | EUST 3 - Triage/Prioritize Findings | February 23, 2026 8:00 AM | April 14, 2026 5:00 PM | 36 | 375d |  |  | 0 | 375 | Warning
43760 | Sentiment Survey | February 23, 2026 8:00 AM | April 14, 2026 5:00 PM | 36 | 375d |  |  | 0 | 375 | Warning
43761 | Coordinate with comms team to prepare mid-point sentiment survey | February 23, 2026 8:00 AM | February 27, 2026 5:00 PM | 5 | 406d |  |  | 0 | 406 | Warning
43762 | Send link to mid-point survey | March 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 1 | 396d |  | 1829SS | 0 | 396 | Warning
43763 | Consoladate mid-point sentiment survey | March 2, 2026 8:00 AM | March 13, 2026 5:00 PM | 10 | 396d | 1828SS |  | 0 | 396 | Warning
43764 | Coordinate with Communications team to prepare the Sentiment Survey for EUST | March 30, 2026 8:00 AM | April 6, 2026 5:00 PM | 5 | 376d |  | 1831SS | 0 | 376 | Warning
43765 | Send link to Sentiment Survey to EUST Participants | April 1, 2026 8:00 AM | April 1, 2026 5:00 PM | 1 | 375d | 1830SS | 1832SS | 0 | 375 | Warning
43766 | Consoladate sentiment survey results for close out presentation | April 1, 2026 8:00 AM | April 14, 2026 5:00 PM | 10 | 375d | 1831SS |  | 0 | 375 | Warning
43767 | EUST 3 - Closeout | April 13, 2026 8:00 AM | May 19, 2026 5:00 PM | 27 | 350d |  |  | 0 | 350 | Warning
43768 | Confirm exit criteria for EUST is met | April 13, 2026 8:00 AM | April 13, 2026 5:00 PM | 1 | 350d |  | 1835 | 0 | 350 | Warning
43769 | Prepare presentations to ELT | April 14, 2026 8:00 AM | April 24, 2026 5:00 PM | 9 | 350d | 1834 | 1838FS+15d,1836 | 0 | 350 | Warning
43770 | Present to ELT (DOF, BOD tentatively as well) | April 27, 2026 8:00 AM | April 27, 2026 5:00 PM | 1 | 365d | 1835 | 1837 | 0 | 365 | Warning
43771 | Schedule Presentation to the counties | April 28, 2026 8:00 AM | April 28, 2026 5:00 PM | 1 | 365d | 1836 |  | 0 | 365 | Warning
43772 | Present to the counties | May 18, 2026 8:00 AM | May 18, 2026 5:00 PM | 1 | 350d | 1835FS+15d | 1839 | 0 | 350 | Warning
43773 | Send EUST wrap-up email confirmation | May 19, 2026 8:00 AM | May 19, 2026 5:00 PM | 1 | 350d | 1838 |  | 0 | 350 | Warning
2875 | LOE Activities | April 1, 2021 8:00 AM | December 9, 2026 3:24 PM | 1427.8 | 210.2d |  |  | 0.82 | 210.2 | Warning
2876 | Forms - DocuEdge (CARESV1-4220) | June 1, 2022 8:00 AM | December 8, 2025 5:00 PM | 883 | 461d |  |  | 0.94 | 461 | Warning
2877 | Research & Proof of Concept | June 1, 2022 8:00 AM | November 14, 2025 5:00 PM | 868 | 476d | 12SS+25d | 1909 | 0.97 | 476 | Warning
2879 | DocuEdge - Product Development & Support | August 15, 2022 8:00 AM | December 8, 2025 5:00 PM | 831 | 461d |  |  | 0.94 | 461 | Warning
2928 | DocuEdge - Milestone 6.1 | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 | 467d |  |  | 0.81 | 467 | Warning
2929 | DocuEdge - Milestone 6.1 - CARESV1-313 ADM - CM - File Management and Metadata | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 | 467d | 308FS+102d,1958 | 1961SS | 0.8 | 467 | Warning
2930 | DocuEdge - Milestone 6.1 - CARESV1-315 ADM - CM - Redaction | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 | 467d | 308SS,1960SS | 1962SS | 0.8 | 467 | Warning
2931 | DocuEdge - Milestone 6.1 - CARESV1-317 ADM - CM - Versioning | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 | 467.5d | 308SS,1961SS | 1963SS | 0.81 | 467.5 | Warning
2932 | DocuEdge - Milestone 6.1 - CARESV1-319 ADM - CM - Retrieval | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 | 467.5d | 308SS,1962SS | 1964SS | 0.81 | 467.5 | Warning
2933 | DocuEdge - Milestone 6.1 - CARESV1-320 ADM - CM - Upload | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 | 467.5d | 308SS,1963SS | 1965SS | 0.81 | 467.5 | Warning
2934 | DocuEdge - Milestone 6.1 - CARESV1-322 ADM - CM - Storage | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 | 467.5d | 308SS,1964SS | 1966SS | 0.81 | 467.5 | Warning
2935 | DocuEdge - Milestone 6.1 - CARESV1-323 ADM - CM - Search | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 | 467.5d | 308SS,1965SS | 1968FS-335d | 0.81 | 467.5 | Warning
3056 | DocuEdge - Milestone 23 | March 11, 2025 8:00 AM | December 8, 2025 5:00 PM | 189 | 461d |  |  | 0.79 | 461 | Warning
3059 | DocuEdge - Milestone 23 - CARESV1-317 ADM - CM - Versioning | May 13, 2025 8:00 AM | December 4, 2025 5:00 PM | 143 | 463d | 2089FS-142d | 2091FS-1834d | 0.74 | 463 | Warning
3063 | DocuEdge - Milestone 23 - CARESV1-323 ADM - CM - Search | March 18, 2025 8:00 AM | December 8, 2025 5:00 PM | 184 | 461d | 2093FS-183d |  | 0.79 | 461 | Warning
3064 | DocuEdge - Milestone 24 | March 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 186 | 465d |  |  | 0.82 | 465 | Warning
3070 | DocuEdge - Milestone 24 - CARESV1-322 ADM - CM - Storage | September 16, 2025 8:00 AM | October 23, 2025 5:00 PM | 28 | 466d | 2100 | 2102 | 0.68 | 466 | Warning
3071 | DocuEdge - Milestone 24 - CARESV1-323 ADM - CM - Search | October 27, 2025 8:00 AM | December 2, 2025 5:00 PM | 25 | 465d | 2101 |  | 0 | 465 | Warning
3072 | DocuEdge - Milestone 26 | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 395 | 465d |  |  | 0.87 | 465 | Warning
3073 | DocuEdge - Milestone 26 - CARESV1-313 ADM - CM - File Management and Metadata | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 395 | 465d | 2048SS-20d | 2105SS | 0.91 | 465 | Warning
3077 | DocuEdge - Milestone 26 - CARESV1-320 ADM - CM - Upload | October 8, 2025 8:00 AM | November 12, 2025 5:00 PM | 25 | 478d | 2107 | 163,2109SS-45d | 0.12 | 478 | Warning
3078 | DocuEdge - Milestone 26 - CARESV1-322 ADM - CM - Storage | September 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 58 | 465d | 2108SS-45d | 2110FF | 0.4 | 465 | Warning
3079 | DocuEdge - Milestone 26 - CARESV1-323 ADM - CM - Search | August 12, 2025 8:00 AM | December 2, 2025 5:00 PM | 78 | 465d | 2109FF |  | 0.55 | 465 | Warning
3131 | Data Conversion LOE (CARESV1-13763) | June 20, 2022 8:00 AM | December 9, 2026 3:24 PM | 1120.8 | 210.2d |  |  | 0.9 | 210.2 | Warning
3132 | Non-Structured Data Conversion Activities (CARESV1-11551) | February 1, 2023 8:00 AM | June 26, 2026 5:00 PM | 854 | 272d |  |  | 0.93 | 272 | Warning
3169 | Micro Conversion scripts | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM | 472 | 444d |  |  | 0.94 | 444 | Warning
3174 | Micro Conversion scripts - Build scripts for DC Cycle6 Scope objects | September 29, 2025 8:00 AM | October 17, 2025 5:00 PM | 15 | 444d | 2185FS+85d | 2373FS-5d,2193SS+5d | 0.67 | 444 | Warning
3176 | Converted Data Load to Snowflake | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM | 472 | 444d |  |  | 0.94 | 444 | Warning
3182 | Converted Data Load to Snowflake - Build views for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 444d | 2186SS+5d | 2373FS-5d,2199SS | 0.5 | 444 | Warning
5569 | Trigger analysis for data conversion | May 6, 2024 8:00 AM | October 17, 2025 5:00 PM | 367 | 444d |  |  | 0.97 | 444 | Warning
5574 | Trigger analysis for data conversion - Analysis for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 444d | 2193SS | 2373FS-5d | 0.5 | 444 | Warning
3311 | Conversion Cycles | April 3, 2023 8:00 AM | December 9, 2026 3:24 PM | 925.8 | 210.2d |  |  | 0.67 | 210.2 | Warning
5630 | Cycle 6 ( Eligibility, Financial, RFA) | September 8, 2025 8:00 AM | January 9, 2026 5:00 PM | 86 | 439d |  |  | 0.14 | 439 | Warning
5631 | Conversion Cycle 6 - ETL | September 8, 2025 8:00 AM | October 17, 2025 5:00 PM | 30 | 439d | 2367 | 2370 | 0.83 | 439 | Warning
5632 | Conversion Cycle 6 - Link Documents | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 15 | 439d | 2369 | 2371FS-25d | 0 | 439 | Warning
5633 | Conversion Cycle 6 - Solr Load | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 439d | 2370FS-25d | 2372FS-10d | 0 | 439 | Warning
5634 | Conversion Cycle 6 - Snowflake Load | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 15 | 439d | 2371FS-10d | 2373FS-5d | 0 | 439 | Warning
5635 | Conversion Cycle 6 - Micro Conversion Execution | October 20, 2025 8:00 AM | December 23, 2025 5:00 PM | 45 | 439d | 2186FS-5d,2193FS-5d,2199FS-5d,2212FS-5d,2214FS-5d,2372FS-5d | 2374FS-55d | 0 | 439 | Warning
5636 | Conversion Cycle 6 - SIT | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 20 | 439d | 2373FS-55d | 2375 | 0 | 439 | Warning
5637 | Conversion Cycle 6 - QA | November 3, 2025 8:00 AM | December 2, 2025 5:00 PM | 20 | 439d | 2374 | 2376FS-2d | 0 | 439 | Warning
5638 | Conversion Cycle 6 - County Validation | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 439d | 2375FS-2d | 2377 | 0 | 439 | Warning
5639 | Conversion Cycle 6 - Review & Closure | December 29, 2025 8:00 AM | January 9, 2026 5:00 PM | 9 | 439d | 2376 |  | 0 | 439 | Warning
11580 | Final Conversion | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM | 43 | 210.2d |  |  | 0 | 210.2 | Warning
11581 | Final Structured Data Conversion | October 6, 2026 3:24 PM | November 3, 2026 3:24 PM | 20 | 210.2d | 2392FS-1d | 2395FS-13d | 0 | 210.2 | Warning
11582 | Final Conversion - Link Documents to Structured Data | October 15, 2026 3:24 PM | December 9, 2026 3:24 PM | 36 | 210.2d | 2394FS-13d | 2396FS-43d | 0 | 210.2 | Warning
11583 | Final Conversion - Run Micro Conversion (Structured Data and Documents) | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM | 43 | 210.2d | 2395FS-43d |  | 0 | 210.2 | Warning
6943 | County Transition | May 1, 2023 8:00 AM | November 24, 2026 5:00 PM | 897 | 219d |  |  | 0.46 | 219 | Warning
11547 | County - Forms | May 2, 2024 8:00 AM | May 26, 2026 5:00 PM | 518 | 346d |  |  | 0.27 | 346 | Warning
6989 | Forms Training | May 2, 2024 8:00 AM | March 2, 2026 5:00 PM | 459 | 405d |  |  | 0.2 | 405 | Warning
6991 | Forms Training - Instructor Led Trainings | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 | 467d | 557SS,2421FS-29d | 2423SS | 0 | 467 | Warning
6992 | Forms Training - Conduct Workshops | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 | 467d | 557SS,2422SS | 2424SS | 0 | 467 | Warning
6993 | Forms Training - Perform On Demand Trainings | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 | 467d | 557SS,2423SS | 2425SS-76d | 0 | 467 | Warning
6994 | Forms Training - Planned KT Session | August 11, 2025 8:00 AM | March 2, 2026 5:00 PM | 139 | 405d | 559SS,2424SS-76d | 2426FS-289d | 0 | 405 | Warning
11545 | Forms Training - Prioritize | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 170 | 374d | 2426 | 2428SS | 0.14 | 374 | Warning
11558 | Monitor Progress for Prioritized Forms | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 198 | 346d | 2427SS |  | 0.12 | 346 | Warning
11548 | County - External Systems | July 9, 2025 8:00 AM | November 24, 2026 5:00 PM | 348 | 219d |  |  | 0 | 219 | Warning
11549 | County - External Systems - Identify | July 9, 2025 8:00 AM | February 11, 2026 5:00 PM | 150 | 219d | 1049SS-100d | 2431 | 0 | 219 | Warning
11550 | County - External Systems - Prioritize | February 12, 2026 8:00 AM | October 14, 2026 5:00 PM | 170 | 219d | 2430 | 2432FS-170d | 0 | 219 | Warning
11559 | Monitor Progress for Prioritized External Systems | February 12, 2026 8:00 AM | November 24, 2026 5:00 PM | 198 | 219d | 2431FS-170d |  | 0 | 219 | Warning
11553 | County Analytics Transition | May 1, 2023 8:00 AM | May 26, 2026 5:00 PM | 770 | 346d |  |  | 0.7 | 346 | Warning
11554 | County Analytics Transition - Identify | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 | 346d | 2435FS+144d | 2444 | 0 | 346 | Warning
11555 | County Analytics Transition - Prioritize | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 170 | 346d | 2443 | 2445FS-170d | 0 | 346 | Warning
11560 | County Analytics Transition - Monitor Progress for Prioritized Reports | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 198 | 346d | 2444FS-170d |  | 0 | 346 | Warning
3369 | Forms - DocGen | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM | 905 | 445d |  |  | 0.87 | 445 | Warning
3399 | DocGen - Product Development & Support | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM | 905 | 445d |  |  | 0.85 | 445 | Warning
3428 | DocGen - Milestone 7 | September 11, 2023 8:00 AM | December 31, 2025 5:00 PM | 579 | 445d |  |  | 0.83 | 445 | Warning
3434 | DocGen - Milestone 7 - Joint Review | June 2, 2025 8:00 AM | December 31, 2025 1:29 PM | 103 | 445.44d | 766SS,2510FS-148d |  | 0.63 | 445.44 | Warning
3449 | DocGen - Milestone 10 | February 27, 2023 8:00 AM | December 30, 2025 5:00 PM | 714 | 446d |  |  | 0.6 | 446 | Warning
3455 | DocGen - Milestone 10 - Joint Review | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 59 | 446d | 389SS,2530FS-105d |  | 0.08 | 446 | Warning
3463 | DocGen - Milestone 11 | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM | 441 | 446d |  |  | 0.73 | 446 | Warning
3469 | DocGen - Milestone 11 - Joint Review | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 59 | 446d | 781SS,2536FS-105d |  | 0.08 | 446 | Warning
3470 | DocGen - Milestone 13 | February 12, 2024 8:00 AM | December 30, 2025 4:22 PM | 473.92 | 446.08d |  |  | 0.78 | 446.08 | Warning
3476 | DocGen - Milestone 13 - Joint Review | July 30, 2025 4:22 PM | December 30, 2025 4:22 PM | 105 | 446.08d | 2542FS-105d |  | 0.49 | 446.08 | Warning
3491 | DocGen - Milestone 16 | March 8, 2024 8:00 AM | December 30, 2025 8:38 AM | 455.08 | 446.92d |  |  | 0.83 | 446.92 | Warning
3497 | DocGen - Milestone 16 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 103 | 446.92d | 911SS,2564FS-148d |  | 0.64 | 446.92 | Warning
3498 | DocGen - Milestone 17 | April 26, 2024 8:00 AM | December 30, 2025 8:38 AM | 421.08 | 446.92d |  |  | 0.82 | 446.92 | Warning
3504 | DocGen - Milestone 17 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 103 | 446.92d | 916SS,2570FS-148d |  | 0.64 | 446.92 | Warning
3505 | DocGen - Milestone 18 | May 22, 2023 8:00 AM | December 30, 2025 8:38 AM | 654.08 | 446.92d |  |  | 0.87 | 446.92 | Warning
3511 | DocGen - Milestone 18 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 103 | 446.92d | 922SS,2576FS-148d |  | 0.64 | 446.92 | Warning
3526 | DocGen - Milestone 21 | June 19, 2024 8:00 AM | December 30, 2025 2:26 PM | 384.68 | 446.32d |  |  | 0.73 | 446.32 | Warning
3532 | DocGen - Milestone 21 - Joint Review | May 30, 2025 2:26 PM | December 30, 2025 2:26 PM | 147 | 446.32d | 2590FS-147d |  | 0.63 | 446.32 | Warning
3533 | DocGen - Milestone 23 | April 26, 2024 8:00 AM | December 30, 2025 5:00 PM | 422 | 446d |  |  | 0.7 | 446 | Warning
3539 | DocGen - Milestone 23 - Joint Review | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 | 446d | 2596FS-57d |  | 0.05 | 446 | Warning
3547 | DocGen - Milestone 26 | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM | 441 | 446d |  |  | 0.8 | 446 | Warning
3553 | DocGen - Milestone 26 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 | 446d | 2602FS-148d |  | 0.64 | 446 | Warning
3554 | DocGen - Milestone 27 | January 25, 2024 8:00 AM | December 30, 2025 5:00 PM | 486 | 446d |  |  | 0.81 | 446 | Warning
3560 | DocGen - Milestone 27 - Joint Review | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 | 446d | 2608FS-146d |  | 0.63 | 446 | Warning
3561 | DocGen - Milestone 28 | December 9, 2024 8:00 AM | December 30, 2025 5:00 PM | 266 | 446d |  |  | 0.73 | 446 | Warning
7443 | DocGen - Milestone 28 - QA | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 | 446d | 2614FS-146d |  | 0.63 | 446 | Warning
3619 | Testing - ADA (CARESV1-5420) | April 4, 2022 8:00 AM | January 30, 2026 5:00 PM | 960 | 425d |  |  | 0.34 | 425 | Warning
3621 | Perform ADA Validation (CARESV1-5421) | January 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 269 | 425d |  |  | 0.33 | 425 | Warning
3628 | M6.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3629 | M7: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3630 | M7.1 ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3632 | M9: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3633 | M10: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3634 | M10.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3635 | M11: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3636 | M13: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3637 | M14: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3640 | M16: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3641 | M17: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3642 | M18: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3644 | M21: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3646 | M20.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3647 | M23: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3648 | M23.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3649 | M23.2: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3650 | M24: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3651 | M26: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3652 | M26.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3653 | M27: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3654 | M28: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3655 | M29: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
5536 | M30: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
5537 | M31: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
5538 | M32: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | 425 | Warning
3656 | Testing - Automation (CARESV1-21622) | December 2, 2024 8:00 AM | January 30, 2026 5:00 PM | 292 | 425d |  |  | 0.47 | 425 | Warning
3657 | Create Automation Scripts | December 2, 2024 8:00 AM | December 23, 2025 5:00 PM | 267 | 450d |  |  | 0.51 | 450 | Warning
3664 | M6.1: Create Automation scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 425d | 2672 | 2688SS-10d,2710FS+6d,2711FS+6d,2712FS+6d,2714FS+6d,2715FS+6d,2716FS+6d,2717FS+6d,2718FS+6d,2719FS+6d,2721FS+6d,2722FS+6d,2723FS+6d,2725FS+6d,2727FS+6d,2728FS+6d,2729FS+6d,2730FS+6d,2731FS+6d,2732FS+6d,2733FS+6d,2734FS+6d,2735FS+6d,2736FS+6d,2737FS+6d,2... | 0 | 425 | Warning
3665 | M7: Create Automation scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 59 | 452d | 2668SS+8d | 2675SS-92d,2751SS-92d | 0.1 | 452 | Warning
3666 | M7.1 Create Automation scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d | 2677SS-20d,2679SS-20d,2682SS-20d,2753SS-20d,2755SS-20d,2758SS-20d | 0.83 | 485 | Warning
3668 | M9: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
3669 | M10: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d | 2680SS-23d,2681SS-23d,2756SS-23d,2757SS-23d | 0.23 | 450 | Warning
3670 | M10.1: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
3671 | M11: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | 450 | Warning
3672 | M13: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | 450 | Warning
3673 | M14: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
3676 | M16: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2683FS+154d | 2690SS+3d,2766SS+3d | 0.23 | 450 | Warning
3677 | M17: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
3678 | M18: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
3680 | M21: Create Automation scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 49 | 450d | 2673SS-10d |  | 0 | 450 | Warning
3682 | M20.1: Create Automation scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 68 | 450d | 2684SS+3d | 2691SS-7d,2692SS-7d,2693SS-7d,2699SS-7d,2700SS-7d,2701SS-7d,2767SS-7d,2768SS-7d,2769SS-7d,2775SS-7d,2776SS-7d,2777SS-7d | 0.19 | 450 | Warning
3683 | M23: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
3684 | M23.1: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
3685 | M23.2: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2694SS-33d,2695SS-33d,2696SS-33d,2697SS-33d,2698SS-33d,2770SS-33d,2771SS-33d,2772SS-33d,2773SS-33d,2774SS-33d | 0.27 | 450 | Warning
3686 | M24: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
3687 | M26: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
3688 | M26.1: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
3689 | M27: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
3690 | M28: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
3691 | M29: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
3692 | M30: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
3693 | M31: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2702SS-1d,2778SS-1d | 0.27 | 450 | Warning
3694 | M32: Create Automation scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | 467 | Warning
3704 | Execute Automation Scripts | January 31, 2025 8:00 AM | January 30, 2026 5:00 PM | 251 | 425d |  |  | 0.31 | 425 | Warning
3711 | M6.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3712 | M7: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3713 | M7.1 Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3715 | M9: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3716 | M10: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3717 | M10.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3718 | M11: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3719 | M13: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3720 | M14: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3723 | M16: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3724 | M17: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3725 | M18: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3727 | M21: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3729 | M20.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3730 | M23: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3731 | M23.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3732 | M23.2: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3733 | M24: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3734 | M26: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3735 | M26.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3736 | M27: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3737 | M28: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3738 | M29: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3739 | M30: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3740 | M31: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3741 | M32: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3777 | Testing - Performance (CARESV1-22880) | September 1, 2022 8:00 AM | January 30, 2026 5:00 PM | 854 | 425d |  |  | 0.49 | 425 | Warning
3779 | Create Performance Testing Scripts | December 2, 2024 8:00 AM | December 23, 2025 5:00 PM | 267 | 450d |  |  | 0.51 | 450 | Warning
5655 | M6.1: Create Performance Testing scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 450d | 2672 |  | 0 | 450 | Warning
5656 | M7: Create Performance Testing scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 59 | 452d | 2668SS+8d |  | 0.1 | 452 | Warning
5486 | M7.1 Create Performance Testing scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d |  | 0.83 | 485 | Warning
5488 | M9: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
5489 | M10: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
5490 | M10.1: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
5491 | M11: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | 450 | Warning
5492 | M13: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | 450 | Warning
5493 | M14: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | 450 | Warning
5496 | M16: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
5497 | M17: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
5498 | M18: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | 450 | Warning
5500 | M21: Create Performance Testing scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 49 | 450d | 2673SS-10d |  | 0 | 450 | Warning
5502 | M20.1: Create Performance Testing scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 68 | 450d | 2684SS+3d |  | 0.19 | 450 | Warning
5503 | M23: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
5504 | M23.1: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
3791 | M23.2: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
5509 | M24: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
5510 | M26: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
5511 | M26.1: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
5512 | M27: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
5513 | M28: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | 450 | Warning
5514 | M29: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
5657 | M30: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
5658 | M31: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | 450 | Warning
5515 | M32: Create Performance Testing scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | 467 | Warning
11631 | Execute Performance Testing Scripts | January 31, 2025 8:00 AM | January 30, 2026 5:00 PM | 251 | 425d |  |  | 0.31 | 425 | Warning
5522 | M6.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5523 | M7: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5524 | M7.1 Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5526 | M9: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5527 | M10: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5528 | M10.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5529 | M11: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5530 | M13: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
5531 | M14: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11632 | M16: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11633 | M17: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11634 | M18: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11636 | M21: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11638 | M20.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11639 | M23: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11640 | M23.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11641 | M23.2: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11642 | M24: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11643 | M26: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11644 | M26.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11645 | M27: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11646 | M28: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11647 | M29: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11648 | M30: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11649 | M31: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
11650 | M32: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | 425 | Warning
3814 | CCWIS | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1153 | 203d |  |  | 0.99 | 203 | Warning
3815 | CCWIS Self-Assessments (Checklist) (CARESV1-14449) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2825SS | 1855,2828SS | 0.99 | 203 | Warning
3816 | CARESV1-19070 CCWIS Self-Assessments (Checklist) - Implementation | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2827SS | 1855,2829SS | 0.99 | 203 | Warning
3817 | California CCWIS Monitoring Review (CARESV1-14450) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2828SS | 1855,2830SS | 0.99 | 203 | Warning
3818 | Governance (CARESV1-14456) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2829SS | 1855,2831SS | 0.99 | 203 | Warning
3819 | Expectation Management (CARESV1-14446) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2830SS | 1855,2832SS | 0.99 | 203 | Warning
3820 | Conflict Management (CARESV1-14447) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2831SS | 1855,2976SS | 0.99 | 203 | Warning
3821 | Security | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM | 921 | 423d |  |  | 0.98 | 423 | Warning
3828 | DevSecOps (CARESV1-14453) | April 8, 2024 8:00 AM | December 19, 2025 5:00 PM | 430 | 452d |  |  | 0.85 | 452 | Warning
13697 | Okta Migration | June 23, 2025 8:00 AM | December 19, 2025 5:00 PM | 126 | 452d |  |  | 0.66 | 452 | Warning
13703 | Okta Pre-prod Migration | September 15, 2025 8:00 AM | December 15, 2025 5:00 PM | 64 | 456d | 2909FS-10d | 2912SS | 0.31 | 456 | Warning
13696 | Okta API Security Migration | September 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 68 | 452d | 2911SS |  | 0.29 | 452 | Warning
3836 | External Systems (CARESV1-14108) | November 15, 2024 8:00 AM | October 30, 2026 5:00 PM | 491 | 235d |  |  | 0.3 | 235 | Warning
13177 | Template development | November 15, 2024 8:00 AM | June 27, 2025 5:00 PM | 153 | 573d |  |  | 0.94 | 573 | Warning
13189 | Data Template County feedback | June 13, 2025 8:00 AM | June 20, 2025 5:00 PM | 6 | 578d | 2925FS-1d |  | 0.95 | 578 | Warning
13193 | Data Template Revision 2 | June 23, 2025 8:00 AM | June 27, 2025 5:00 PM | 5 | 573d | 2929 |  | 0.5 | 573 | Warning
13201 | Conversion ETL Development and Test | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 | 445d |  |  | 0.19 | 445 | Warning
13202 | ETL code development and unit testing for Drop 1 | June 2, 2025 8:00 AM | October 17, 2025 5:00 PM | 98 | 495d |  |  | 0.24 | 495 | Warning
13203 | ETL code development and unit testing for Drop 2 | June 2, 2025 8:00 AM | November 21, 2025 5:00 PM | 122 | 471d |  |  | 0.2 | 471 | Warning
13204 | ETL code development and unit testing for Drop 3 | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 | 445d |  |  | 0.16 | 445 | Warning
13205 | Receive Data template for Dry Run 1 | June 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 108 | 485d |  |  | 0 | 485 | Warning
13206 | Dry run1 | November 3, 2025 8:00 AM | January 16, 2026 5:00 PM | 51 | 434d |  |  | 0 | 434 | Warning
13207 | Data Conversion & Issue remediation | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 434d |  | 2945 | 0 | 434 | Warning
13208 | Generate Conversion Report | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 10 | 434d | 2944 | 2946 | 0 | 434 | Warning
13161 | Data Validation Support | December 15, 2025 8:00 AM | December 26, 2025 5:00 PM | 9 | 434d | 2945 | 2947 | 0 | 434 | Warning
13162 | System Testing | December 29, 2025 8:00 AM | January 16, 2026 5:00 PM | 14 | 434d | 2946 |  | 0 | 434 | Warning
13163 | Receive Data template for Dry Run 2 | December 22, 2025 8:00 AM | January 16, 2026 5:00 PM | 18 | 434d |  |  | 0 | 434 | Warning
13164 | Dry run2 | January 20, 2026 8:00 AM | March 20, 2026 5:00 PM | 43 | 391d |  |  | 0 | 391 | Warning
13165 | Data Conversion & Issue remediation | January 20, 2026 8:00 AM | February 6, 2026 5:00 PM | 14 | 391d |  | 2951 | 0 | 391 | Warning
13166 | Generate Conversion Report | February 9, 2026 8:00 AM | February 20, 2026 5:00 PM | 9 | 391d | 2950 | 2952,2954 | 0 | 391 | Warning
13167 | Data Validation Support | February 23, 2026 8:00 AM | March 6, 2026 5:00 PM | 10 | 391d | 2951 | 2953 | 0 | 391 | Warning
13168 | System Testing | March 9, 2026 8:00 AM | March 20, 2026 5:00 PM | 10 | 391d | 2952 |  | 0 | 391 | Warning
13169 | Receive Data template for Dry Run 3 | February 23, 2026 8:00 AM | March 20, 2026 5:00 PM | 20 | 391d | 2951 |  | 0 | 391 | Warning
13170 | Dry run3 | March 23, 2026 8:00 AM | May 29, 2026 5:00 PM | 48 | 343d |  |  | 0 | 343 | Warning
13171 | Data Conversion & Issue remediation | March 23, 2026 8:00 AM | April 17, 2026 5:00 PM | 19 | 343d |  | 2957,2960 | 0 | 343 | Warning
13172 | Generate Conversion Report | April 20, 2026 8:00 AM | May 1, 2026 5:00 PM | 10 | 343d | 2956 | 2958 | 0 | 343 | Warning
13173 | Data Validation Support | May 4, 2026 8:00 AM | May 15, 2026 5:00 PM | 10 | 343d | 2957 | 2959 | 0 | 343 | Warning
13174 | System Testing | May 18, 2026 8:00 AM | May 29, 2026 5:00 PM | 9 | 343d | 2958 |  | 0 | 343 | Warning
13175 | Receive Data template for Dry Run 4 | April 20, 2026 8:00 AM | May 29, 2026 5:00 PM | 29 | 343d | 2956 |  | 0 | 343 | Warning
13176 | Dry run4 | June 1, 2026 8:00 AM | August 6, 2026 5:00 PM | 48 | 295d |  |  | 0 | 295 | Warning
13153 | Data Conversion & Issue remediation | June 1, 2026 8:00 AM | June 19, 2026 5:00 PM | 15 | 295d |  | 2963 | 0 | 295 | Warning
13154 | Generate Conversion Report | June 22, 2026 8:00 AM | July 2, 2026 5:00 PM | 9 | 295d | 2962 | 2964 | 0 | 295 | Warning
13155 | Data Validation Support | July 6, 2026 8:00 AM | July 24, 2026 5:00 PM | 15 | 295d | 2963 | 2965 | 0 | 295 | Warning
13156 | System Testing | July 27, 2026 8:00 AM | August 6, 2026 5:00 PM | 9 | 295d | 2964 |  | 0 | 295 | Warning
13157 | Integrated Testing | February 6, 2026 8:00 AM | August 6, 2026 5:00 PM | 126 | 295d |  |  | 0 | 295 | Warning
13158 | Data load support | February 6, 2026 8:00 AM | July 31, 2026 5:00 PM | 122 | 295d |  | 2968SS+5d | 0 | 295 | Warning
13159 | Testing Support | February 13, 2026 8:00 AM | August 6, 2026 5:00 PM | 121 | 295d | 2967SS+5d |  | 0 | 295 | Warning
13160 | Production data load | August 3, 2026 8:00 AM | October 30, 2026 5:00 PM | 64 | 235d |  |  | 0 | 235 | Warning
13149 | Pre-Production activities and CutOver Support, Receive Data Templates for Prod load | August 3, 2026 8:00 AM | August 14, 2026 5:00 PM | 10 | 235d |  | 2971 | 0 | 235 | Warning
13150 | Production data load | August 17, 2026 8:00 AM | August 28, 2026 5:00 PM | 10 | 235d | 2970 | 2972 | 0 | 235 | Warning
13151 | Pilot - Go live | August 31, 2026 8:00 AM | August 31, 2026 5:00 PM | 1 | 235d | 2971 | 2973 | 0 | 235 | Warning
13152 | Hyper Care | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d | 2972 |  | 0 | 235 | Warning
13228 | Consolidated Self Assessments (C-SA) | January 2, 2025 8:00 AM | December 15, 2026 5:00 PM | 490 | 206d |  |  | 0.35 | 206 | Warning
13229 | C-SA ACF Reporting 2025 | January 2, 2025 8:00 AM | December 15, 2025 5:00 PM | 240 | 456d |  |  | 0.75 | 456 | Warning
13275 | Q4 C-SA ACF Reporting 2025 | October 14, 2025 8:00 AM | December 15, 2025 5:00 PM | 43 | 456d |  |  | 0 | 456 | Warning
13276 | Initiate Q4 ACF reporting of C-SA with all resources | October 14, 2025 8:00 AM | October 14, 2025 5:00 PM | 1 | 456d |  | 3091 | 0 | 456 | Warning
13277 | Create Q4 C-SA draft & share SharePoint location with all resources | October 15, 2025 8:00 AM | October 15, 2025 5:00 PM | 1 | 456d | 3090 | 3092 | 0 | 456 | Warning
13278 | 1st review of Q4 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | October 16, 2025 8:00 AM | October 21, 2025 5:00 PM | 4 | 456d | 3091 | 3093 | 0 | 456 | Warning
13279 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 1 | 456d | 3092 | 3094 | 0 | 456 | Warning
13280 | 1st review of Q4 C-SA by Service Managers (SMs) to review, edit & comment | October 23, 2025 8:00 AM | October 28, 2025 5:00 PM | 4 | 456d | 3093 | 3095 | 0 | 456 | Warning
13281 | Conduct Checkpoint w/ SMs for Q4 C-SA status | October 29, 2025 8:00 AM | October 29, 2025 5:00 PM | 1 | 456d | 3094 | 3096 | 0 | 456 | Warning
13282 | 2nd review of Q4 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | October 30, 2025 8:00 AM | November 4, 2025 5:00 PM | 4 | 456d | 3095 | 3097 | 0 | 456 | Warning
13283 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 5, 2025 8:00 AM | November 5, 2025 5:00 PM | 1 | 456d | 3096 | 3098 | 0 | 456 | Warning
13284 | 1st pre-liminary review & feedback of Q4 C-SA by Product & Technology Leadership | November 6, 2025 8:00 AM | November 12, 2025 5:00 PM | 4 | 456d | 3097 | 3099 | 0 | 456 | Warning
13285 | 2nd & final review & approval of Q4 C-SA by Service Managers (SMs) | November 13, 2025 8:00 AM | November 18, 2025 5:00 PM | 4 | 456d | 3098 | 3100 | 0 | 456 | Warning
13286 | Conduct Checkpoint w/ Product & Technology Leadership | November 19, 2025 8:00 AM | November 19, 2025 5:00 PM | 1 | 456d | 3099 | 3101 | 0 | 456 | Warning
13287 | 3rd & final review & approval of Q4 C-SA by PaaS, PVS, & CDI teams | November 20, 2025 8:00 AM | November 25, 2025 5:00 PM | 4 | 456d | 3100 | 3102 | 0 | 456 | Warning
13288 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 26, 2025 8:00 AM | November 26, 2025 5:00 PM | 1 | 456d | 3101 | 3103 | 0 | 456 | Warning
13289 | 2nd & final review & approval of Q4 C-SA by Product & Technology Leadership | November 28, 2025 8:00 AM | December 3, 2025 5:00 PM | 4 | 456d | 3102 | 3104 | 0 | 456 | Warning
13290 | Conduct final status checkpoint w/ Product & Technology Leadership for Q4 C-SA | December 4, 2025 8:00 AM | December 4, 2025 5:00 PM | 1 | 456d | 3103 | 3105 | 0 | 456 | Warning
13291 | Conduct final readiness check of Q4 C-SA to request ELT Approval | December 5, 2025 8:00 AM | December 8, 2025 5:00 PM | 2 | 456d | 3104 | 3106 | 0 | 456 | Warning
13292 | Request review & approval from ELT of Q4 C-SA | December 9, 2025 8:00 AM | December 12, 2025 5:00 PM | 4 | 456d | 3105 | 3107FS-1d | 0 | 456 | Warning
13293 | Submit ELT approved Q4 C-SA to PMO Filing | December 12, 2025 8:00 AM | December 12, 2025 5:00 PM | 1 | 456d | 3106FS-1d | 3108 | 0 | 456 | Warning
13294 | Closeout Q4 C-SA process | December 15, 2025 8:00 AM | December 15, 2025 5:00 PM | 1 | 456d | 3107 |  | 0 | 456 | Warning
13248 | C-SA ACF Reporting 2026 | January 5, 2026 8:00 AM | December 15, 2026 5:00 PM | 238 | 206d |  |  | 0 | 206 | Warning
13249 | Q1 C-SA ACF Reporting 2026 | January 5, 2026 8:00 AM | April 17, 2026 5:00 PM | 72 | 206d |  |  | 0 | 206 | Warning
13250 | Initiate Q1 ACF reporting of C-SA with all resources | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 206d |  | 3112 | 0 | 206 | Warning
13251 | Create Q1 C-SA draft & share SharePoint location with all resources | January 6, 2026 8:00 AM | January 20, 2026 5:00 PM | 10 | 206d | 3111 | 3113 | 0 | 206 | Warning
13252 | 1st review of Q1 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | January 21, 2026 8:00 AM | January 29, 2026 5:00 PM | 7 | 206d | 3112 | 3114 | 0 | 206 | Warning
13253 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q1 C-SA status | January 30, 2026 8:00 AM | February 10, 2026 5:00 PM | 8 | 206d | 3113 | 3115 | 0 | 206 | Warning
13254 | 1st review of Q1 C-SA by Service Managers (SMs) to review, edit & comment | February 11, 2026 8:00 AM | February 18, 2026 5:00 PM | 5 | 206d | 3114 | 3116 | 0 | 206 | Warning
13255 | Conduct Checkpoint w/ SMs for Q1 C-SA status | February 19, 2026 8:00 AM | February 19, 2026 5:00 PM | 1 | 206d | 3115 | 3117 | 0 | 206 | Warning
13256 | 2nd review of Q1 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | February 20, 2026 8:00 AM | February 26, 2026 5:00 PM | 5 | 206d | 3116 | 3118 | 0 | 206 | Warning
13257 | Conduct checkpoint w/ Leads from PaaS, PVS,& CDI for Q1 C-SA status | February 27, 2026 8:00 AM | March 5, 2026 5:00 PM | 5 | 206d | 3117 | 3119 | 0 | 206 | Warning
13258 | 1st pre-liminary review & feedback of Q1 C-SA by Product & Technology Leadership | March 6, 2026 8:00 AM | March 6, 2026 5:00 PM | 1 | 206d | 3118 | 3120 | 0 | 206 | Warning
13259 | 2nd& final review & approval of Q1 C-SA by Service Managers (SMs) | March 9, 2026 8:00 AM | March 13, 2026 5:00 PM | 5 | 206d | 3119 | 3121 | 0 | 206 | Warning
13260 | Conduct Checkpoint w/ Product& Technology Leadership | March 16, 2026 8:00 AM | March 16, 2026 5:00 PM | 1 | 206d | 3120 | 3122 | 0 | 206 | Warning
13261 | 3rd & final review & approval of Q1 C-SA by PaaS, PVS, & CDI teams | March 17, 2026 8:00 AM | March 25, 2026 5:00 PM | 7 | 206d | 3121 | 3123 | 0 | 206 | Warning
13262 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q1 C-SA status | March 26, 2026 8:00 AM | March 26, 2026 5:00 PM | 1 | 206d | 3122 | 3124 | 0 | 206 | Warning
13263 | 2nd& final review & approval of Q1 C-SA by Product & Technology Leadership | March 27, 2026 8:00 AM | April 3, 2026 5:00 PM | 5 | 206d | 3123 | 3125 | 0 | 206 | Warning
13264 | Conduct final status checkpoint w/ Product & Technology Leadership for Q1 C-SA | April 6, 2026 8:00 AM | April 7, 2026 5:00 PM | 2 | 206d | 3124 | 3126 | 0 | 206 | Warning
13265 | Conduct final readiness check of Q1 C-SA to request ELT Approval | April 8, 2026 8:00 AM | April 8, 2026 5:00 PM | 1 | 206d | 3125 | 3127 | 0 | 206 | Warning
13230 | Request review & approval from ELT of Q1 C-SA | April 9, 2026 8:00 AM | April 15, 2026 5:00 PM | 5 | 206d | 3126 | 3128 | 0 | 206 | Warning
13231 | Submit ELT approved Q1 C-SA to ACF | April 16, 2026 8:00 AM | April 16, 2026 5:00 PM | 1 | 206d | 3127 | 3129 | 0 | 206 | Warning
13232 | Closeout Q1 C-SA process | April 17, 2026 8:00 AM | April 17, 2026 5:00 PM | 1 | 206d | 3128 | 3131 | 0 | 206 | Warning
13233 | Q2 C-SA ACF Reporting 2026 | April 20, 2026 8:00 AM | June 16, 2026 5:00 PM | 41 | 206d |  |  | 0 | 206 | Warning
13562 | Initiate Q2 ACF reporting of C-SA with all resources | April 20, 2026 8:00 AM | April 20, 2026 5:00 PM | 1 | 206d | 3129 | 3132 | 0 | 206 | Warning
13563 | Create Q2 C-SA draft & share SharePoint location with all resources | April 21, 2026 8:00 AM | April 23, 2026 5:00 PM | 3 | 206d | 3131 | 3133 | 0 | 206 | Warning
13564 | 1st review of Q2 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | April 24, 2026 8:00 AM | April 29, 2026 5:00 PM | 4 | 206d | 3132 | 3134 | 0 | 206 | Warning
13565 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q2 C-SA status | April 30, 2026 8:00 AM | May 1, 2026 5:00 PM | 2 | 206d | 3133 | 3135 | 0 | 206 | Warning
13566 | 1st review of Q2 C-SA by Service Managers (SMs) to review, edit & comment | May 4, 2026 8:00 AM | May 6, 2026 5:00 PM | 3 | 206d | 3134 | 3136 | 0 | 206 | Warning
13567 | Conduct Checkpoint w/ SMs for Q2 C-SA status | May 7, 2026 8:00 AM | May 7, 2026 5:00 PM | 1 | 206d | 3135 | 3137 | 0 | 206 | Warning
13568 | 2nd review of Q2 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | May 8, 2026 8:00 AM | May 12, 2026 5:00 PM | 3 | 206d | 3136 | 3138 | 0 | 206 | Warning
13569 | Conduct checkpoint w/ Leads from PaaS, PVS,& CDI for Q2 C-SA status | May 13, 2026 8:00 AM | May 18, 2026 5:00 PM | 4 | 206d | 3137 | 3139 | 0 | 206 | Warning
13585 | 1st pre-liminary review & feedback of Q2 C-SA by Product & Technology Leadership | May 19, 2026 8:00 AM | May 19, 2026 5:00 PM | 1 | 206d | 3138 | 3140 | 0 | 206 | Warning
13586 | 2nd& final review & approval of Q2 C-SA by Service Managers (SMs) | May 20, 2026 8:00 AM | May 22, 2026 5:00 PM | 3 | 206d | 3139 | 3141 | 0 | 206 | Warning
13587 | Conduct Checkpoint w/ Product& Technology Leadership | May 26, 2026 8:00 AM | May 26, 2026 5:00 PM | 1 | 206d | 3140 | 3142 | 0 | 206 | Warning
13588 | 3rd & final review & approval of Q2 C-SA by PaaS, PVS, & CDI teams | May 27, 2026 8:00 AM | May 29, 2026 5:00 PM | 3 | 206d | 3141 | 3143 | 0 | 206 | Warning
13589 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q2 C-SA status | June 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 1 | 206d | 3142 | 3144 | 0 | 206 | Warning
13590 | 2nd& final review & approval of Q2 C-SA by Product & Technology Leadership | June 2, 2026 8:00 AM | June 5, 2026 5:00 PM | 4 | 206d | 3143 | 3145 | 0 | 206 | Warning
13591 | Conduct final status checkpoint w/ Product & Technology Leadership for Q2 C-SA | June 8, 2026 8:00 AM | June 8, 2026 5:00 PM | 1 | 206d | 3144 | 3146 | 0 | 206 | Warning
13592 | Conduct final readiness check of Q2 C-SA to request ELT Approval | June 9, 2026 8:00 AM | June 9, 2026 5:00 PM | 1 | 206d | 3145 | 3147 | 0 | 206 | Warning
13593 | Request review & approval from ELT of Q2 C-SA | June 10, 2026 8:00 AM | June 15, 2026 5:00 PM | 4 | 206d | 3146 | 3148FS-1d | 0 | 206 | Warning
13594 | Submit ELT approved Q2 C-SA to PMO Filing | June 15, 2026 8:00 AM | June 15, 2026 5:00 PM | 1 | 206d | 3147FS-1d | 3149 | 0 | 206 | Warning
13595 | Closeout Q2 C-SA process | June 16, 2026 8:00 AM | June 16, 2026 5:00 PM | 1 | 206d | 3148 | 3151FS+18d | 0 | 206 | Warning
13596 | Q3 C-SA ACF Reporting 2026 | July 14, 2026 8:00 AM | September 15, 2026 5:00 PM | 45 | 206d |  |  | 0 | 206 | Warning
13597 | Initiate Q3 ACF reporting of C-SA with all resources | July 14, 2026 8:00 AM | July 14, 2026 5:00 PM | 1 | 206d | 3149FS+18d | 3152 | 0 | 206 | Warning
13598 | Create Q3 C-SA draft & share SharePoint location with all resources | July 15, 2026 8:00 AM | July 17, 2026 5:00 PM | 3 | 206d | 3151 | 3153 | 0 | 206 | Warning
13599 | 1st review of Q3 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | July 20, 2026 8:00 AM | July 23, 2026 5:00 PM | 4 | 206d | 3152 | 3154 | 0 | 206 | Warning
13600 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | July 24, 2026 8:00 AM | July 27, 2026 5:00 PM | 2 | 206d | 3153 | 3155 | 0 | 206 | Warning
13601 | 1st review of Q3 C-SA by Service Managers (SMs) to review, edit & comment | July 28, 2026 8:00 AM | July 31, 2026 5:00 PM | 4 | 206d | 3154 | 3156 | 0 | 206 | Warning
13602 | Conduct Checkpoint w/ SMs for Q3 C-SA status | August 3, 2026 8:00 AM | August 3, 2026 5:00 PM | 1 | 206d | 3155 | 3157 | 0 | 206 | Warning
13603 | 2nd review of Q3 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | August 4, 2026 8:00 AM | August 7, 2026 5:00 PM | 4 | 206d | 3156 | 3158 | 0 | 206 | Warning
13570 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 10, 2026 8:00 AM | August 13, 2026 5:00 PM | 4 | 206d | 3157 | 3159 | 0 | 206 | Warning
13571 | 1st pre-liminary review & feedback of Q3 C-SA by Product & Technology Leadership | August 14, 2026 8:00 AM | August 14, 2026 5:00 PM | 1 | 206d | 3158 | 3160 | 0 | 206 | Warning
13572 | 2nd & final review & approval of Q3 C-SA by Service Managers (SMs) | August 17, 2026 8:00 AM | August 19, 2026 5:00 PM | 3 | 206d | 3159 | 3161 | 0 | 206 | Warning
13573 | Conduct Checkpoint w/ Product & Technology Leadership | August 20, 2026 8:00 AM | August 20, 2026 5:00 PM | 1 | 206d | 3160 | 3162 | 0 | 206 | Warning
13574 | 3rd & final review & approval of Q3 C-SA by PaaS, PVS, & CDI teams | August 21, 2026 8:00 AM | August 26, 2026 5:00 PM | 4 | 206d | 3161 | 3163 | 0 | 206 | Warning
13575 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 27, 2026 8:00 AM | August 27, 2026 5:00 PM | 1 | 206d | 3162 | 3164 | 0 | 206 | Warning
13576 | 2nd & final review & approval of Q3 C-SA by Product & Technology Leadership | August 28, 2026 8:00 AM | September 2, 2026 5:00 PM | 4 | 206d | 3163 | 3165 | 0 | 206 | Warning
13577 | Conduct final status checkpoint w/ Product & Technology Leadership for Q3 C-SA | September 3, 2026 8:00 AM | September 3, 2026 5:00 PM | 1 | 206d | 3164 | 3166 | 0 | 206 | Warning
13578 | Conduct final readiness check of Q3 C-SA to request ELT Approval | September 4, 2026 8:00 AM | September 4, 2026 5:00 PM | 1 | 206d | 3165 | 3167 | 0 | 206 | Warning
13579 | Request review & approval from ELT of Q3 C-SA | September 8, 2026 8:00 AM | September 14, 2026 5:00 PM | 5 | 206d | 3166 | 3168FS-1d | 0 | 206 | Warning
13580 | Submit ELT approved Q3 C-SA to PMO Filing | September 14, 2026 8:00 AM | September 14, 2026 5:00 PM | 1 | 206d | 3167FS-1d | 3169 | 0 | 206 | Warning
13581 | Closeout Q3 C-SA process | September 15, 2026 8:00 AM | September 15, 2026 5:00 PM | 1 | 206d | 3168 | 3171FS+20d | 0 | 206 | Warning
13582 | Q4 C-SA ACF Reporting 2026 | October 14, 2026 8:00 AM | December 15, 2026 5:00 PM | 42 | 206d |  |  | 0 | 206 | Warning
13583 | Initiate Q4 ACF reporting of C-SA with all resources | October 14, 2026 8:00 AM | October 14, 2026 5:00 PM | 1 | 206d | 3169FS+20d | 3172 | 0 | 206 | Warning
13584 | Create Q4 C-SA draft & share SharePoint location with all resources | October 15, 2026 8:00 AM | October 19, 2026 5:00 PM | 3 | 206d | 3171 | 3173 | 0 | 206 | Warning
13234 | 1st review of Q4 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | October 20, 2026 8:00 AM | October 23, 2026 5:00 PM | 4 | 206d | 3172 | 3174 | 0 | 206 | Warning
13235 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | October 26, 2026 8:00 AM | October 27, 2026 5:00 PM | 2 | 206d | 3173 | 3175 | 0 | 206 | Warning
13236 | 1st review of Q4 C-SA by Service Managers (SMs) to review, edit & comment | October 28, 2026 8:00 AM | November 2, 2026 5:00 PM | 4 | 206d | 3174 | 3176 | 0 | 206 | Warning
13237 | Conduct Checkpoint w/ SMs for Q4 C-SA status | November 3, 2026 8:00 AM | November 3, 2026 5:00 PM | 1 | 206d | 3175 | 3177 | 0 | 206 | Warning
13238 | 2nd review of Q4 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | November 4, 2026 8:00 AM | November 6, 2026 5:00 PM | 3 | 206d | 3176 | 3178 | 0 | 206 | Warning
13239 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 9, 2026 8:00 AM | November 12, 2026 5:00 PM | 3 | 206d | 3177 | 3179 | 0 | 206 | Warning
13240 | 1st pre-liminary review & feedback of Q4 C-SA by Product & Technology Leadership | November 13, 2026 8:00 AM | November 13, 2026 5:00 PM | 1 | 206d | 3178 | 3180 | 0 | 206 | Warning
13241 | 2nd & final review & approval of Q4 C-SA by Service Managers (SMs) | November 16, 2026 8:00 AM | November 18, 2026 5:00 PM | 3 | 206d | 3179 | 3181 | 0 | 206 | Warning
13242 | Conduct Checkpoint w/ Product & Technology Leadership | November 19, 2026 8:00 AM | November 19, 2026 5:00 PM | 1 | 206d | 3180 | 3182 | 0 | 206 | Warning
13243 | 3rd & final review & approval of Q4 C-SA by PaaS, PVS, & CDI teams | November 20, 2026 8:00 AM | November 25, 2026 5:00 PM | 4 | 206d | 3181 | 3183 | 0 | 206 | Warning
13220 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 30, 2026 8:00 AM | November 30, 2026 5:00 PM | 1 | 206d | 3182 | 3184 | 0 | 206 | Warning
13221 | 2nd & final review & approval of Q4 C-SA by Product & Technology Leadership | December 1, 2026 8:00 AM | December 4, 2026 5:00 PM | 4 | 206d | 3183 | 3185 | 0 | 206 | Warning
13222 | Conduct final status checkpoint w/ Product & Technology Leadership for Q4 C-SA | December 7, 2026 8:00 AM | December 7, 2026 5:00 PM | 1 | 206d | 3184 | 3186 | 0 | 206 | Warning
13223 | Conduct final readiness check of Q4 C-SA to request ELT Approval | December 8, 2026 8:00 AM | December 8, 2026 5:00 PM | 1 | 206d | 3185 | 3187 | 0 | 206 | Warning
13224 | Request review & approval from ELT of Q4 C-SA | December 9, 2026 8:00 AM | December 14, 2026 5:00 PM | 4 | 206d | 3186 | 3188FS-1d | 0 | 206 | Warning
13225 | Submit ELT approved Q4 C-SA to PMO Filing | December 14, 2026 8:00 AM | December 14, 2026 5:00 PM | 1 | 206d | 3187FS-1d | 3189 | 0 | 206 | Warning
13226 | Closeout Q4 C-SA process | December 15, 2026 8:00 AM | December 15, 2026 5:00 PM | 1 | 206d | 3188 |  | 0 | 206 | Warning
12557 | Develop Pilot Plan - Version 3 | July 1, 2025 8:00 AM | November 24, 2025 5:00 PM | 102 | 215d |  |  | 0.62 | 215 | Warning
11656 | Review Pilot Plan Version 3 with BOD | September 29, 2025 8:00 AM | October 31, 2025 5:00 PM | 25 | 215d | 3446FS+4d | 3448 | 0.2 | 215 | Warning
11783 | Incorporate Feedback from BOD for Pilot Plan Version 3 | November 3, 2025 8:00 AM | November 17, 2025 5:00 PM | 10 | 215d | 3447 | 3449 | 0 | 215 | Warning
11655 | Final Pilot Plan Version 3 Approved | November 18, 2025 8:00 AM | November 24, 2025 5:00 PM | 5 | 215d | 3448 | 3886 | 0 | 215 | Warning
12044 | Generate September 2025 Org Readiness Report | October 1, 2025 8:00 AM | October 21, 2025 5:00 PM | 15 | 205d |  |  | 0.53 | 205 | Warning
12046 | Review September Org Readiness Report with State Implementation Lead | October 8, 2025 8:00 AM | October 14, 2025 5:00 PM | 5 | 205d | 3845,3847 | 3849 | 0.6 | 205 | Warning
12047 | Review September Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | October 15, 2025 8:00 AM | October 21, 2025 5:00 PM | 5 | 205d | 3848 | 3852 | 0 | 205 | Warning
13712 | Sandbox Activities | May 1, 2025 8:00 AM | August 14, 2026 5:00 PM | 325 | 289d |  |  | 0.38 | 289 | Warning
43983 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part IV | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 344d | 3898 | 3900 | 0 | 344 | Warning
43984 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part V | September 2, 2025 8:00 AM | October 1, 2025 5:00 PM | 22 | 344d | 3899 | 3901SS | 0 | 344 | Warning
43985 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part I | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 344d | 3900SS | 3902 | 0 | 344 | Warning
43986 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part II | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 344d | 3901 | 3903FS-1d | 0 | 344 | Warning
43987 | Launch Sandbox for Cohort 2 Users (EUST 2 code) | October 31, 2025 8:00 AM | October 31, 2025 5:00 PM | 1 | 344d | 3902FS-1d | 3904 | 0 | 344 | Warning
43988 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part III | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 344d | 3903 | 3905 | 0 | 344 | Warning
43989 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part I | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 344d | 3904 | 3906 | 0 | 344 | Warning
43990 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part II | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 344d | 3905 | 3907FS-1d | 0 | 344 | Warning
43991 | Launch Sandbox for Cohort 3 Users (EUST 2 code) | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 1 | 344d | 3906FS-1d | 3908 | 0 | 344 | Warning
43992 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part III | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 344d | 3907 | 3909SS | 0 | 344 | Warning
43993 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part I | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 344d | 3908SS | 3910 | 0 | 344 | Warning
43994 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part II | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 21 | 344d | 3909 | 3911 | 0 | 344 | Warning
43971 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part III | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 344d | 3910 | 3912FS-1d | 0 | 344 | Warning
43972 | Launch Sandbox for Cohort 4 Users (EUST 3 code) | April 30, 2026 8:00 AM | April 30, 2026 5:00 PM | 1 | 344d | 3911FS-1d | 3913 | 0 | 344 | Warning
43973 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part IV | May 1, 2026 8:00 AM | May 28, 2026 5:00 PM | 19 | 344d | 3912 |  | 0 | 344 | Warning
13720 | Cohort 1 Group 1 | May 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 128 | 486d |  |  | 0.89 | 486 | Warning
13721 | Prepare and Support Sandbox for Cohort 1 Group 1 Users (EUST 2 code) | May 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 128 | 486d |  | 3895SS | 0.89 | 486 | Warning
13714 | Cohort 1 Group 3 | August 21, 2025 8:00 AM | October 30, 2025 5:00 PM | 50 | 486d |  |  | 0.69 | 486 | Warning
13717 | Complete follow up with Counties on responses and object IDs | September 22, 2025 8:00 AM | October 10, 2025 5:00 PM | 15 | 500d | 3932 |  | 0.9 | 500 | Warning
13737 | Review/finalize Sandbox User Orientation for Cohort 1 Group 3 and conduct Dry Run | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 486d | 3935 | 3938 | 0 | 486 | Warning
13738 | Create transactional sample data for expected data volume of Cohort 1 Group 3 users | October 6, 2025 8:00 AM | October 22, 2025 5:00 PM | 13 | 492d | 3934 |  | 0 | 492 | Warning
13744 | Conduct Sandbox Orientation with Cohort 1 Group 3 | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 2 | 486d | 3936 | 3939,3940 | 0 | 486 | Warning
13745 | Activate Cohort 1 Group 3 Users | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 1 | 486d | 3938 | 3941 | 0 | 486 | Warning
13746 | Conduct User Access Support Office Hours for Cohort 1 Group 3 | October 22, 2025 8:00 AM | October 27, 2025 5:00 PM | 4 | 489d | 3938 |  | 0 | 489 | Warning
13747 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | October 23, 2025 8:00 AM | October 27, 2025 5:00 PM | 3 | 486d | 3939 | 3942FS-1d | 0 | 486 | Warning
13748 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | October 27, 2025 8:00 AM | October 28, 2025 5:00 PM | 2 | 486d | 3941FS-1d | 3943FS-1d | 0 | 486 | Warning
13749 | Conduct Sandbox Training Webinars for Cohort 1 Group 3 | October 28, 2025 8:00 AM | October 30, 2025 5:00 PM | 3 | 486d | 3942FS-1d |  | 0 | 486 | Warning
43893 | Update FAQ Prior to Cohort 2 Activities | September 15, 2025 8:00 AM | October 17, 2025 5:00 PM | 25 | 495d |  |  | 0.81 | 495 | Warning
43890 | Complete ADA review of updated Sandbox FAQ | October 13, 2025 8:00 AM | October 15, 2025 5:00 PM | 3 | 495d | 3949 | 3951 | 0 | 495 | Warning
43889 | Publish updated Sandbox FAQ to the Implementation Portal | October 16, 2025 8:00 AM | October 17, 2025 5:00 PM | 2 | 495d | 3950 |  | 0 | 495 | Warning
13742 | Cohort 2 | September 15, 2025 8:00 AM | October 30, 2025 5:00 PM | 34 | 486d |  |  | 0.4 | 486 | Warning
13756 | Review/finalize Sandbox User Orientation for Cohort 2 and conduct Dry Run | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 437d | 3955 | 3958 | 0 | 437 | Warning
13757 | Create transactional sample data for expected data volume of Cohort 2 users | October 13, 2025 8:00 AM | October 22, 2025 5:00 PM | 8 | 492d | 3955,3954 |  | 0 | 492 | Warning
13758 | Conduct Sandbox Orientation with Cohort 2 | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 2 | 437d | 3956 | 3959,3960 | 0 | 437 | Warning
13759 | Activate Cohort 2 Users | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 1 | 437d | 3958 | 3961,3962 | 0 | 437 | Warning
13760 | Conduct User Access Support Office Hours for Cohort 2 | October 22, 2025 8:00 AM | October 27, 2025 5:00 PM | 4 | 489d | 3958 |  | 0 | 489 | Warning
13761 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | October 23, 2025 8:00 AM | October 27, 2025 5:00 PM | 3 | 489d | 3959 |  | 0 | 489 | Warning
13718 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | October 23, 2025 8:00 AM | October 28, 2025 5:00 PM | 4 | 437d | 3959 | 3963FS-1d | 0 | 437 | Warning
13719 | Conduct Sandbox Training Webinars for Cohort 2 | October 28, 2025 8:00 AM | October 30, 2025 5:00 PM | 3 | 437d | 3962FS-1d | 3965FS+6d | 0 | 437 | Warning
43899 | Conduct Retrospective for Cohort 2 | November 10, 2025 8:00 AM | December 5, 2025 5:00 PM | 18 | 437d |  |  | 0 | 437 | Warning
43900 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | November 10, 2025 8:00 AM | November 19, 2025 5:00 PM | 7 | 437d | 3963FS+6d | 3966 | 0 | 437 | Warning
43898 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | November 20, 2025 8:00 AM | December 5, 2025 5:00 PM | 11 | 437d | 3965 | 3971FS-5d | 0 | 437 | Warning
43917 | Update FAQ Prior to Cohort 3 Activities | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | 437d |  |  | 0 | 437 | Warning
43918 | Update Sandbox FAQ document ahead of Cohort 3 | December 1, 2025 8:00 AM | December 8, 2025 5:00 PM | 6 | 437d | 3966FS-5d | 3972 | 0 | 437 | Warning
43919 | Review updated Sandbox FAQ with all impacted teams involved with Sandbox activities, followed by a final review with Implementation Leadership | December 9, 2025 8:00 AM | December 16, 2025 5:00 PM | 6 | 437d | 3971 | 3973 | 0 | 437 | Warning
43920 | Incorporate Sandbox FAQ updates | December 17, 2025 8:00 AM | December 18, 2025 5:00 PM | 2 | 437d | 3972 | 3974 | 0 | 437 | Warning
43921 | Conduct ELT review of Sandbox FAQ updates | December 19, 2025 8:00 AM | January 2, 2026 5:00 PM | 9 | 437d | 3973 | 3975 | 0 | 437 | Warning
43922 | Incorporate ELT feedback for Sandbox FAQ updates | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 437d | 3974 | 3976 | 0 | 437 | Warning
43923 | Complete ADA review of updated Sandbox FAQ | January 7, 2026 8:00 AM | January 9, 2026 5:00 PM | 3 | 437d | 3975 | 3977 | 0 | 437 | Warning
43924 | Publish updated Sandbox FAQ to the Implementation Portal | January 12, 2026 8:00 AM | January 13, 2026 5:00 PM | 2 | 437d | 3976 |  | 0 | 437 | Warning
43925 | Cohort 3 | November 17, 2025 8:00 AM | January 22, 2026 5:00 PM | 45 | 372d |  |  | 0 | 372 | Warning
43926 | Draft, review, and distribute email communications to Cohort 3 Organizations to determine Cohort 3 Sandbox Users | November 17, 2025 8:00 AM | November 21, 2025 5:00 PM | 5 | 372d |  | 3980 | 0 | 372 | Warning
43927 | Complete follow up with Counties on responses and object IDs | November 24, 2025 8:00 AM | December 19, 2025 5:00 PM | 19 | 372d | 3979 | 3981SS | 0 | 372 | Warning
43928 | Confirm Cohort 3 Users | November 24, 2025 8:00 AM | December 12, 2025 5:00 PM | 14 | 372d | 3980SS | 3982 | 0 | 372 | Warning
43929 | Send email communication with registration links for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 5 | 372d | 3981 | 3983FS+8d | 0 | 372 | Warning
43930 | Review/finalize Sandbox User Orientation for Cohort 3 and conduct Dry Run | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 372d | 3982FS+8d | 3984SS | 0 | 372 | Warning
43931 | Create Jira ticket to request setup of Cohort 3 users | January 5, 2026 8:00 AM | January 12, 2026 5:00 PM | 6 | 372d | 3983SS | 3985SS | 0 | 372 | Warning
43932 | Create transactional sample data for expected data volume of Cohort 3 users | January 5, 2026 8:00 AM | January 14, 2026 5:00 PM | 8 | 372d | 3984SS | 3986FS-3d | 0 | 372 | Warning
43933 | Conduct Sandbox Orientation with Cohort 3 | January 12, 2026 8:00 AM | January 13, 2026 5:00 PM | 2 | 372d | 3985FS-3d | 3987 | 0 | 372 | Warning
43934 | Activate Cohort 3 Users | January 14, 2026 8:00 AM | January 14, 2026 5:00 PM | 1 | 372d | 3986 | 3988FS-1d | 0 | 372 | Warning
43935 | Conduct User Access Support Office Hours for Cohort 3 | January 14, 2026 8:00 AM | January 20, 2026 5:00 PM | 4 | 372d | 3987FS-1d | 3989FS-2d | 0 | 372 | Warning
43936 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | January 16, 2026 8:00 AM | January 20, 2026 5:00 PM | 2 | 372d | 3988FS-2d | 3990FS-1d | 0 | 372 | Warning
43937 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | January 20, 2026 8:00 AM | January 21, 2026 5:00 PM | 2 | 372d | 3989FS-1d | 3991FS-1d | 0 | 372 | Warning
43938 | Conduct Sandbox Training Webinars for Cohort 3 | January 21, 2026 8:00 AM | January 22, 2026 5:00 PM | 2 | 372d | 3990FS-1d | 3993FS+11d | 0 | 372 | Warning
43939 | Conduct Retrospective for Cohort 3 | February 9, 2026 8:00 AM | March 6, 2026 5:00 PM | 19 | 372d |  |  | 0 | 372 | Warning
43940 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | February 9, 2026 8:00 AM | February 19, 2026 5:00 PM | 8 | 372d | 3991FS+11d | 3994 | 0 | 372 | Warning
43941 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | February 20, 2026 8:00 AM | March 6, 2026 5:00 PM | 11 | 372d | 3993 | 3996FS+5d | 0 | 372 | Warning
43942 | Update FAQ Prior to Cohort 4 Activities | March 16, 2026 8:00 AM | April 17, 2026 5:00 PM | 24 | 372d |  |  | 0 | 372 | Warning
43943 | Update Sandbox FAQ document ahead of Cohort 4 | March 16, 2026 8:00 AM | March 20, 2026 5:00 PM | 5 | 372d | 3994FS+5d | 3997 | 0 | 372 | Warning
43944 | Review updated Sandbox FAQ with all impacted teams involved with Sandbox activities, followed by a final review with Implementation Leadership | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 5 | 372d | 3996 | 3998 | 0 | 372 | Warning
43945 | Incorporate Sandbox FAQ updates | March 30, 2026 8:00 AM | April 1, 2026 5:00 PM | 2 | 372d | 3997 | 3999FS-1d | 0 | 372 | Warning
43946 | Conduct ELT review of Sandbox FAQ updates | April 1, 2026 8:00 AM | April 9, 2026 5:00 PM | 7 | 372d | 3998FS-1d | 4000 | 0 | 372 | Warning
43947 | Incorporate ELT feedback for Sandbox FAQ updates | April 10, 2026 8:00 AM | April 10, 2026 5:00 PM | 1 | 372d | 3999 | 4001 | 0 | 372 | Warning
43909 | Complete ADA review of updated Sandbox FAQ | April 13, 2026 8:00 AM | April 15, 2026 5:00 PM | 3 | 372d | 4000 | 4002 | 0 | 372 | Warning
43910 | Publish updated Sandbox FAQ to the Implementation Portal | April 16, 2026 8:00 AM | April 17, 2026 5:00 PM | 2 | 372d | 4001 |  | 0 | 372 | Warning
43911 | Cohort 4 | February 17, 2026 8:00 AM | April 30, 2026 5:00 PM | 52 | 289d |  |  | 0 | 289 | Warning
43912 | Draft, review, and distribute email communications to Cohort 4 Organizations to determine Cohort 4 Sandbox Users | February 17, 2026 8:00 AM | February 25, 2026 5:00 PM | 7 | 289d |  | 4005 | 0 | 289 | Warning
43913 | Complete follow up with Counties on responses and object IDs. | February 26, 2026 8:00 AM | March 26, 2026 5:00 PM | 21 | 289d | 4004 | 4006SS | 0 | 289 | Warning
43914 | Confirm Cohort 4 Users | February 26, 2026 8:00 AM | March 19, 2026 5:00 PM | 16 | 289d | 4005SS | 4007SS+2d | 0 | 289 | Warning
43915 | Draft, review, and distribute email communications to Cohort 1-3 Organizations to provide advanced note about EUST 3 code in the V1 Readiness Environment | March 2, 2026 8:00 AM | March 11, 2026 5:00 PM | 8 | 289d | 4006SS+2d | 4008FS+7d | 0 | 289 | Warning
43948 | Send email communication with registration links for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 5 | 289d | 4007FS+7d | 4009FS+9d,4012SS | 0 | 289 | Warning
43949 | Review/finalize Sandbox User Orientation for Cohort 4 and conduct Dry Run | April 13, 2026 8:00 AM | April 17, 2026 5:00 PM | 5 | 289d | 4008FS+9d | 4010SS | 0 | 289 | Warning
43950 | Create Jira ticket to request setup of Cohort 4 users | April 13, 2026 8:00 AM | April 20, 2026 5:00 PM | 6 | 289d | 4009SS | 4011SS | 0 | 289 | Warning
43916 | Create transactional sample data for expected data volume of Cohort 4 users | April 13, 2026 8:00 AM | April 22, 2026 5:00 PM | 8 | 289d | 4010SS | 4013SS+1d | 0 | 289 | Warning
43905 | Draft, review, and distribute email communications to all Sandbox users about the upcoming code drop | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 5 | 386d | 4008SS |  | 0 | 386 | Warning
43906 | Load EUST 3 code into the V1 Readiness Environment and confirm any critical fixes from EUST 3 are deployed | April 14, 2026 8:00 AM | April 17, 2026 5:00 PM | 4 | 289d | 4011SS+1d | 4014 | 0 | 289 | Warning
43907 | Conduct Sandbox Orientation with Cohort 4 | April 20, 2026 8:00 AM | April 21, 2026 5:00 PM | 2 | 289d | 4013 | 4015 | 0 | 289 | Warning
43951 | Activate Cohort 4 Users | April 22, 2026 8:00 AM | April 22, 2026 5:00 PM | 1 | 289d | 4014 | 4016FS-1d | 0 | 289 | Warning
43952 | Conduct User Access Support Office Hours for Cohort 4 | April 22, 2026 8:00 AM | April 27, 2026 5:00 PM | 4 | 289d | 4015FS-1d | 4017FS-2d | 0 | 289 | Warning
43956 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | April 24, 2026 8:00 AM | April 27, 2026 5:00 PM | 2 | 289d | 4016FS-2d | 4018FS-1d | 0 | 289 | Warning
43957 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | April 27, 2026 8:00 AM | April 28, 2026 5:00 PM | 2 | 289d | 4017FS-1d | 4019FS-1d | 0 | 289 | Warning
43958 | Conduct Sandbox Training Webinars for Cohort 4 | April 28, 2026 8:00 AM | April 30, 2026 5:00 PM | 3 | 289d | 4018FS-1d | 4021FS+6d | 0 | 289 | Warning
43959 | Conduct Retrospective for Cohort 4 | May 11, 2026 8:00 AM | August 14, 2026 5:00 PM | 68 | 289d |  |  | 0 | 289 | Warning
43953 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | May 11, 2026 8:00 AM | May 20, 2026 5:00 PM | 8 | 289d | 4019FS+6d | 4022 | 0 | 289 | Warning
43954 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | May 21, 2026 8:00 AM | June 5, 2026 5:00 PM | 11 | 289d | 4021 | 4023FS+29d | 0 | 289 | Warning
43955 | Draft, review, and distribute email communications to all Sandbox users about the upcoming code drop | July 20, 2026 8:00 AM | July 24, 2026 5:00 PM | 5 | 289d | 4022FS+29d | 4024FS+10d | 0 | 289 | Warning
43908 | Load the latest code into the V1 Readiness Environment, following completion of Process Simulation activities | August 10, 2026 8:00 AM | August 14, 2026 5:00 PM | 5 | 289d | 4023FS+10d |  | 0 | 289 | Warning
8398 | Training | July 25, 2022 8:00 AM | September 30, 2026 5:00 PM | 1050 | 257d |  |  | 0.79 | 257 | Warning
13667 | Develop, Review, and Finalize Implementation Organizations Training Plan | July 1, 2025 8:00 AM | February 27, 2026 5:00 PM | 166 | 406d |  |  | 0.56 | 406 | Warning
13670 | Conduct Implementation Organizations Training Plan meetings – Part III | September 22, 2025 8:00 AM | October 31, 2025 5:00 PM | 30 | 406d | 4275 | 4280 | 0.5 | 406 | Warning
13673 | Draft Implementation Organizations Training Plans – Part III | September 22, 2025 8:00 AM | October 31, 2025 5:00 PM | 30 | 406d | 4278 | 4280 | 0.5 | 406 | Warning
13674 | Draft Implementation Organizations Training Plans – Part IV | November 3, 2025 8:00 AM | December 12, 2025 5:00 PM | 28 | 406d | 4276,4279 | 4281 | 0 | 406 | Warning
13675 | Complete Draft Implementation Organizations Training Plans | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 5 | 406d | 4280 | 4282FS+8d | 0 | 406 | Warning
13676 | Review Implementation Organizations Training Plans | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | 406d | 4281FS+8d | 4283SS+19d | 0 | 406 | Warning
13677 | Finalize Implementation Organizations Training Plans | February 2, 2026 8:00 AM | February 26, 2026 5:00 PM | 18 | 406d | 4282SS+19d | 4284 | 0 | 406 | Warning
13678 | Complete Implementation Organizations Training Plans | February 27, 2026 8:00 AM | February 27, 2026 5:00 PM | 1 | 406d | 4283 |  | 0 | 406 | Warning
8587 | Development Training Materials | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM | 842 | 334d |  |  | 0.78 | 334 | Warning
8588 | Participate in Inception Meetings | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM | 842 | 334d |  |  | 0.78 | 334 | Warning
8617 | Develop CARES Global Programs | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM | 669 | 396d |  |  | 0.8 | 396 | Warning
11499 | CARES Basics | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM | 669 | 396d | 4303FS+9d,4294,4296,4300 | 4306SS | 0.84 | 396 | Warning
11500 | CARES Navigation | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM | 669 | 376d | 4305SS | 4925 | 0.84 | 376 | Warning
11507 | Approval/Audit History | January 29, 2024 8:00 AM | March 13, 2026 5:00 PM | 534 | 376d | 4309SS+9d | 4925 | 0.81 | 376 | Warning
11506 | Person(s) | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4307 | 4312SS | 0.78 | 396 | Warning
11505 | Contact Log and Tribal Inquiries | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4311SS | 4313SS | 0.78 | 396 | Warning
11503 | Task | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4312SS | 4314SS | 0.78 | 396 | Warning
11502 | Documents | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4313SS | 4315SS | 0.78 | 396 | Warning
11501 | Case Management Engagement: Family Transfer Request | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 376d | 4314SS | 4925 | 0.78 | 376 | Warning
13060 | Supervisor Assign Secondary | January 24, 2025 8:00 AM | March 13, 2026 5:00 PM | 285 | 376d | 4308SS+6d | 4925 | 0.64 | 376 | Warning
13061 | Addresses - Holistic | December 17, 2024 8:00 AM | March 13, 2026 5:00 PM | 310 | 376d | 4309 | 4925 | 0.66 | 376 | Warning
10500 | Process Areas | May 28, 2024 8:00 AM | May 14, 2026 5:00 PM | 494 | 353d |  |  | 0.73 | 353 | Warning
10501 | Case Management | May 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 418 | 429d |  |  | 0.85 | 429 | Warning
10606 | Group 2 On-Going Case Work (Milestones 6.1, 7) | June 17, 2024 8:00 AM | January 26, 2026 5:00 PM | 404 | 429d |  |  | 0.82 | 429 | Warning
11094 | Milestone 6.1 - Prevention Services | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 | 467d |  |  | 0.88 | 467 | Warning
11099 | MS 6.1 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 128 | 467d | 4451SS+1d |  | 0.74 | 467 | Warning
10625 | Milestone 07/7.1 - Case Plan | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.76 | 429 | Warning
13930 | BD 3 - MS 7/7.1 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d | 702,703,704,705,706,707,730,731,732,733,734,735 | 4471SS | 0.75 | 485 | Warning
13932 | BD 3 - MS 7/7.1 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d | 4470SS | 4472SS | 0.75 | 485 | Warning
13931 | BD - 3 MS 7/7.1: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 52 | 485d | 4472FS-52d | 4474SS+4d | 0.71 | 485 | Warning
10635 | Milestone 09 - Case Management - Engagement and Services | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.82 | 429 | Warning
13926 | BD 3 - MS 9 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d | 339FS+402d,340FS+402d,341FS+402d,342FS+402d,343FS+402d,345FS+402d,346FS+402d,347FS+402d,348FS+402d,349FS+402d | 4486SS | 0.75 | 485 | Warning
13927 | BD 3 - MS 9 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d | 4485SS | 4487SS | 0.75 | 485 | Warning
13925 | BD 3 - MS 9: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 52 | 485d | 4487FS-52d | 4489SS+4d | 0.71 | 485 | Warning
13924 | BD 3 - MS 9 - Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | August 26, 2025 8:00 AM | October 31, 2025 5:00 PM | 48 | 466d | 4488SS+4d | 4893 | 0.69 | 466 | Warning
10649 | Group 3 Finish a Case (Milestones 10, 11, 13) | August 12, 2024 8:00 AM | January 26, 2026 5:00 PM | 365 | 410d |  |  | 0.78 | 410 | Warning
10674 | Milestone 10 - Case Closure | June 3, 2025 8:00 AM | December 15, 2025 5:00 PM | 136 | 437d |  |  | 0.75 | 437 | Warning
13923 | BD 4 -MS 10 - Develop Training Content - Knowledge Base Articles, Quick Guides (Build Drop Update) | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 471d | 4509,632 | 4893 | 0 | 471 | Warning
10684 | Milestone 11 - Aftercare and Re-entry | June 3, 2025 8:00 AM | December 15, 2025 5:00 PM | 136 | 437d |  |  | 0.75 | 437 | Warning
13922 | BD 4 - MS 11: Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 471d | 4520,597,598,599 | 4893 | 0 | 471 | Warning
10698 | Milestone 13 - Adoption | June 3, 2025 8:00 AM | January 26, 2026 5:00 PM | 163 | 410d |  |  | 0.71 | 410 | Warning
13917 | BD 4 -MS 13 - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | November 10, 2025 8:00 AM | November 17, 2025 5:00 PM | 5 | 456d | 4531FS+15d,590,591,592,593,594,595 | 4893 | 0 | 456 | Warning
10712 | Case Management Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4374,4389,4401,4414,4425,4436,4443,4478,4493,4499,4515,4526,4537,5382,5388,5394,5400,5406,5419,5425,5433,5440,5448,5413,4379,4463 | 4925 | 0 | 409 | Warning
10713 | Courts | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | 429 | Warning
10715 | Group 1 Courts Processing (Milestones 14, 16, 17, 18) | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | 429 | Warning
10741 | Courts Processing: Training | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | 429 | Warning
10746 | Milestone 14 - Warrants | April 1, 2025 8:00 AM | November 14, 2025 5:00 PM | 160 | 476d |  |  | 0.94 | 476 | Warning
10751 | MS 14 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 19, 2025 8:00 AM | November 14, 2025 5:00 PM | 126 | 476d | 409FS+289d |  | 0.81 | 476 | Warning
10770 | Milestone 17 - Status Review | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.77 | 429 | Warning
13905 | BD 3 - MS 17: - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 54 | 490d | 871,872,873,874,886,887,888,889 | 4583SS | 0.81 | 490 | Warning
13906 | BD 3 - MS 17: - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 54 | 490d | 4582SS | 4584SS | 0.81 | 490 | Warning
13904 | BD 3 - MS 17: - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 54 | 490d | 4583SS | 4585SS+7d | 0.81 | 490 | Warning
13903 | BD 3 - MS 17: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 47 | 490d | 4584SS+7d | 4586SS+4d | 0.79 | 490 | Warning
10784 | Milestone 18 - Other Hearing | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 | 467d |  |  | 0.86 | 467 | Warning
10793 | MS 18 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 | 467d | 893SS-20d |  | 0.74 | 467 | Warning
10798 | Courts Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4560,4575,4590,4605 | 4925 | 0 | 409 | Warning
10799 | Eligibility | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | 409 | Warning
10801 | Group 1 Eligibility (Milestones 21) | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | 409 | Warning
10809 | Eligibility: Training | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | 409 | Warning
10824 | Eligibility Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4629 | 4925 | 0 | 409 | Warning
10825 | Resource Family Approval | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM | 423 | 351d |  |  | 0.35 | 351 | Warning
10890 | Resource Family Approval Process Area Completed | April 20, 2026 5:00 PM | April 20, 2026 5:00 PM | 0 | 351d | 4648,4659,4670 | 4925 | 0 | 351 | Warning
10891 | Financial Management | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM | 364 | 334d |  |  | 0.55 | 334 | Warning
10893 | Group 1 Financial Management (Milestones 23/23.1, 24) | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM | 364 | 334d |  |  | 0.55 | 334 | Warning
10936 | Financial Management Process Area Completed | May 14, 2026 5:00 PM | May 14, 2026 5:00 PM | 0 | 334d | 4693,4708 | 4925FS-1d | 0 | 334 | Warning
10958 | Reports Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 0 | 370d | 4720 | 4925,4812,4813 | 0 | 370 | Warning
10959 | Admin Console | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM | 301 | 370d |  |  | 0.21 | 370 | Warning
10980 | Admin Console Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 0 | 370d | 4736 | 4925 | 0 | 370 | Warning
10981 | Information Sessions Completed for All Process Areas | August 15, 2025 5:00 PM | August 15, 2025 5:00 PM | 0 | 519d | 5444FS+9mo,5479FS+9mo,5487FS+9mo,5493FS+9mo,5499FS+9mo,5507FS+9mo,5513FS+9mo,5521FS+6mo,5410FS+9mo | 4925 | 0 | 519 | Warning
9646 | Develop Hardening Modules for MS 3,4,5 | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM | 548 | 334d |  |  | 0.64 | 334 | Warning
9662 | Hardening M5 Investigations-Determination | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM | 548 | 334d |  |  | 0.26 | 334 | Warning
13819 | Develop Hardening Modules for All Milestones | April 6, 2026 5:00 PM | June 11, 2026 5:00 PM | 47 | 334d |  |  | 0 | 334 | Warning
13820 | Hardening Work Starts | April 6, 2026 5:00 PM | April 6, 2026 5:00 PM | 0 | 335d | 1850 | 4780,4781,4782,4783,4784,4785,4786,4787,4788,4789,4790,4791,4792,4793,4794,4795,4796,4797,4798,4799,4800,4801,4802,4803,4804,4805,4806,4807,4808,4809,4810,4811,4812,4813,4814,4815 | 0 | 335 | Warning
13835 | MS 6.1 - Prevention Services - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4463 |  | 0 | 362 | Warning
13836 | MS 6.1 - Prevention Services - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4463 |  | 0 | 362 | Warning
13854 | MS 7/7.1 - Case Plan - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4478 |  | 0 | 362 | Warning
13855 | MS 7/7.1 - Case Plan - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4478 |  | 0 | 362 | Warning
13856 | MS 9 - Case Management - Engagement and Services - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4493 |  | 0 | 362 | Warning
13857 | MS 9 - Case Management - Engagement and Services - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4493 |  | 0 | 362 | Warning
13858 | MS 10/10.1 - Case Closure - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4515 |  | 0 | 362 | Warning
13859 | MS 10/10.1 - Case Closure - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4515 |  | 0 | 362 | Warning
13860 | MS 11 - After Care and Re-entry - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4526 |  | 0 | 362 | Warning
13861 | MS 11 - After Care and Re-entry - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4526 |  | 0 | 362 | Warning
13862 | MS 13 - Adoptions - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4537 |  | 0 | 362 | Warning
13863 | MS 13 - Adoptions - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4537 |  | 0 | 362 | Warning
13864 | MS 14 - Warrants - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4560 |  | 0 | 362 | Warning
13865 | MS 14 - Warrants - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4560 |  | 0 | 362 | Warning
13866 | MS 16 - Jurisdiction and Disposition Hearing - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4575 |  | 0 | 362 | Warning
13867 | MS 16 - Jurisdiction and Disposition Hearing - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4575 |  | 0 | 362 | Warning
13868 | MS 17 - Status Reviews - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4590 |  | 0 | 362 | Warning
13869 | MS 17 - Status Reviews - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4590 |  | 0 | 362 | Warning
13870 | MS 18 - Other Hearing - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4605 |  | 0 | 362 | Warning
13871 | MS 18 - Other Hearing - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4605 |  | 0 | 362 | Warning
13872 | MS 21 - Eligibility Program - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4629 |  | 0 | 362 | Warning
13873 | MS 21 - Eligibility Program - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4629 |  | 0 | 362 | Warning
13874 | MS 23/23.1/23.2 - Track Administrative Costs - Hardening - Update Quick Guides, Knowledge Base Articles | May 15, 2026 8:00 AM | June 11, 2026 5:00 PM | 19 | 334d | 4779,4693 |  | 0 | 334 | Warning
13875 | MS 23/23.1/23.2 - Track Administrative Costs - Hardening - Update On-Demand Programs and Lessons | May 15, 2026 8:00 AM | June 11, 2026 5:00 PM | 19 | 334d | 4779,4693 |  | 0 | 334 | Warning
13837 | MS 24 - Track Assistance Costs - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4708 |  | 0 | 362 | Warning
13838 | MS 24 - Track Assistance Costs - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4708 |  | 0 | 362 | Warning
13839 | MS 26/26.1 - Maintain Resource Family Home - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4648 |  | 0 | 362 | Warning
13840 | MS 26/26.1 - Maintain Resource Family Home - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4648 |  | 0 | 362 | Warning
13841 | MS 27 - Complaints - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4659 |  | 0 | 362 | Warning
13842 | MS 27 - Complaints - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4659 |  | 0 | 362 | Warning
13843 | MS 28 - Legal Action - Hardening - Update Quick Guides, Knowledge Base Articles | April 21, 2026 8:00 AM | May 15, 2026 5:00 PM | 19 | 352d | 4779,4670 |  | 0 | 352 | Warning
13844 | MS 28 - Legal Action - Hardening - Update On-Demand Programs and Lessons | April 21, 2026 8:00 AM | May 15, 2026 5:00 PM | 19 | 352d | 4779,4670 |  | 0 | 352 | Warning
13845 | MS 29/30 - Reports - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4721 |  | 0 | 362 | Warning
13846 | MS 29/30 - Reports - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4721 |  | 0 | 362 | Warning
13847 | MS 32 - Admin Console - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 362d | 4779,4736 |  | 0 | 362 | Warning
13848 | MS 32 - Admin Console - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 19 | 335d | 4779,4736 | 4816 | 0 | 335 | Warning
13849 | Hardening Work Completed | May 4, 2026 8:00 AM | May 4, 2026 5:00 PM | 1 | 335d | 4815 | 4914,4918 | 0 | 335 | Warning
9669 | Develop Strategy (Approach and Roadmap) for Developing and Delivering ILT | August 14, 2023 8:00 AM | February 27, 2026 5:00 PM | 637 | 386d |  |  | 0.9 | 386 | Warning
9686 | Develop ILT Training Materials | May 13, 2024 8:00 AM | February 27, 2026 5:00 PM | 451 | 386d |  |  | 0.71 | 386 | Warning
9689 | Develop ILT Training Materials - Cycle 3 | September 11, 2025 8:00 AM | November 21, 2025 5:00 PM | 51 | 386d | 4850 | 4852 | 0.43 | 386 | Warning
9690 | Develop ILT Training Materials - Cycle 4 | November 24, 2025 8:00 AM | February 27, 2026 5:00 PM | 65 | 386d | 4851 | 4925 | 0 | 386 | Warning
13049 | Develop the TTT Materials | October 6, 2025 8:00 AM | June 10, 2026 5:00 PM | 170 | 335d |  |  | 0 | 335 | Warning
13050 | Identify TTT Materials Needed | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 15 | 425d | 4883 | 4887 | 0 | 425 | Warning
13051 | Develop the TTT Materials | October 27, 2025 8:00 AM | November 17, 2025 5:00 PM | 15 | 425d | 4886 | 4888 | 0 | 425 | Warning
13052 | Review the TTT Materials | November 18, 2025 8:00 AM | December 9, 2025 5:00 PM | 15 | 425d | 4887 | 4889 | 0 | 425 | Warning
13053 | Incorporate Feedback and Finalize the TTT Materials | December 10, 2025 8:00 AM | December 31, 2025 5:00 PM | 15 | 425d | 4888 | 4925 | 0 | 425 | Warning
13771 | Publish Training Materials | November 3, 2025 8:00 AM | June 10, 2026 5:00 PM | 150 | 335d |  |  | 0 | 335 | Warning
13779 | Set 1 Drops 1-4 QG and KBAs and 36 On-Demand Programs | November 3, 2025 8:00 AM | December 15, 2025 5:00 PM | 29 | 456d |  |  | 0 | 456 | Warning
13780 | Configure Enablement for Staging Evnironment | November 3, 2025 8:00 AM | November 14, 2025 5:00 PM | 9 | 457d |  | 4893 | 0 | 457 | Warning
13781 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to Staging for User Feedback | November 18, 2025 8:00 AM | November 18, 2025 5:00 PM | 1 | 456d | 4892,4474,4489,4511,4521,4532,4571,4586,4625,4463,4560,4605 | 4894 | 0 | 456 | Warning
13782 | Link Materials for Staging Environment | November 19, 2025 8:00 AM | November 25, 2025 5:00 PM | 5 | 456d | 4893 | 4895 | 0 | 456 | Warning
13783 | Test On-Demand Training Programs | November 26, 2025 8:00 AM | December 8, 2025 5:00 PM | 8 | 456d | 4894 | 4896 | 0 | 456 | Warning
13784 | Enable User Access and Assign On-Demand Programs | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | 456d | 4895 |  | 0 | 456 | Warning
13785 | Set 2 Drops 1-5 QG and KBAs and 61 On-Demand Programs | February 10, 2026 8:00 AM | March 30, 2026 5:00 PM | 34 | 385d |  |  | 0 | 385 | Warning
13786 | Configure Enablement for EUST 3 Evnironment | February 10, 2026 8:00 AM | February 13, 2026 5:00 PM | 4 | 385d | 4689 | 4899 | 0 | 385 | Warning
13787 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | February 17, 2026 8:00 AM | February 17, 2026 5:00 PM | 1 | 385d | 4898,4515,4526,4575 | 4900 | 0 | 385 | Warning
13788 | Link Materials for EUST 3 Environment | February 18, 2026 8:00 AM | February 24, 2026 5:00 PM | 5 | 385d | 4899 | 4901 | 0 | 385 | Warning
13789 | Test On-Demand Training Programs | February 25, 2026 8:00 AM | March 3, 2026 5:00 PM | 5 | 385d | 4900 | 4902 | 0 | 385 | Warning
13790 | Enable User Access and Assign On-Demand Programs | March 4, 2026 8:00 AM | March 30, 2026 5:00 PM | 19 | 385d | 4901 |  | 0 | 385 | Warning
13791 | Set 3 Updates to QGs and KBAs and 81 On-Demand Programs | January 27, 2026 8:00 AM | March 2, 2026 5:00 PM | 24 | 405d |  |  | 0 | 405 | Warning
13792 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | January 27, 2026 8:00 AM | January 27, 2026 5:00 PM | 1 | 405d | 4478,4537,4493,4590,4629 | 4905 | 0 | 405 | Warning
13793 | Link Materials for EUST 3 Envt | January 28, 2026 8:00 AM | February 3, 2026 5:00 PM | 5 | 405d | 4904 | 4906 | 0 | 405 | Warning
13772 | Test On-Demand Training Programs | February 4, 2026 8:00 AM | February 17, 2026 5:00 PM | 9 | 405d | 4905 | 4907 | 0 | 405 | Warning
13773 | Enable User Access and On-Demand Programs | February 18, 2026 8:00 AM | March 2, 2026 5:00 PM | 9 | 405d | 4906 |  | 0 | 405 | Warning
13774 | Set 4 Updates to QGs and KBAs and 104 On-Demand Programs | March 24, 2026 8:00 AM | April 6, 2026 5:00 PM | 9 | 381d |  |  | 0 | 381 | Warning
13775 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | March 24, 2026 8:00 AM | March 24, 2026 5:00 PM | 1 | 381d | 4720 | 4910 | 0 | 381 | Warning
13776 | Link Materials for EUST 3 Envt | March 25, 2026 8:00 AM | March 30, 2026 5:00 PM | 4 | 381d | 4909 | 4911 | 0 | 381 | Warning
13777 | Test On-Demand Training Programs | April 1, 2026 8:00 AM | April 2, 2026 5:00 PM | 2 | 381d | 4910 | 4912 | 0 | 381 | Warning
13799 | Enable User Access and On-Demand Programs | April 3, 2026 8:00 AM | April 6, 2026 5:00 PM | 2 | 381d | 4911 |  | 0 | 381 | Warning
13800 | Set 5 All Training Materials (After Hardening Updates Complete) | May 5, 2026 8:00 AM | June 10, 2026 5:00 PM | 26 | 335d |  |  | 0 | 335 | Warning
13801 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to Sandbox Envt | May 5, 2026 8:00 AM | May 5, 2026 5:00 PM | 1 | 335d | 4816 | 4915 | 0 | 335 | Warning
13802 | Link Materials for Sandbox Envt | May 6, 2026 8:00 AM | May 12, 2026 5:00 PM | 5 | 335d | 4914 | 4916 | 0 | 335 | Warning
13778 | Test On-Demand Training Programs for Sandbox Envt | May 13, 2026 8:00 AM | May 27, 2026 5:00 PM | 10 | 335d | 4915 | 4917 | 0 | 335 | Warning
13767 | Enable User Access and On-Demand Programs for Sandbox Envt | May 28, 2026 8:00 AM | June 10, 2026 5:00 PM | 10 | 335d | 4916 |  | 0 | 335 | Warning
13768 | Configure Enablement for Production Environment | May 5, 2026 8:00 AM | May 11, 2026 5:00 PM | 5 | 349d | 4816 | 4919 | 0 | 349 | Warning
13769 | Publish Completed Training Quick Guides and Knowledge Base Articles to Prodcution Envt | May 12, 2026 8:00 AM | May 12, 2026 5:00 PM | 1 | 349d | 4918 | 4920 | 0 | 349 | Warning
13794 | Link Materials for Production Envt | May 13, 2026 8:00 AM | May 20, 2026 5:00 PM | 6 | 349d | 4919 |  | 0 | 349 | Warning
12586 | Update CWS CARES Glossary | February 3, 2025 8:00 AM | June 11, 2026 5:00 PM | 341 | 334d |  |  | 0.26 | 334 | Warning
9701 | Update CWS CARES Glossary with Terms from Milestone 6.1,7,9,10,11,13,14,16,17,18 | November 17, 2025 8:00 AM | December 19, 2025 5:00 PM | 24 | 386d | 4922FS+175d | 4924FS+22d | 0 | 386 | Warning
9702 | Updae CWS CARES Glossary with Terms from all Milestones | January 26, 2026 8:00 AM | February 27, 2026 5:00 PM | 24 | 386d | 4923FS+22d | 4925 | 0 | 386 | Warning
9703 | Develop after-training evaluations | May 14, 2026 8:00 AM | June 11, 2026 5:00 PM | 20 | 334d | 4924,4104,4187,4247,4306,4310,4315,4341,4357,4365,4538,4545,4606,4630,4637,4671,4678,4709FS-1d,4721,4737,4738,4770,4922,4116,4127,4139,4150,4448,4754,4767,4777,4316,4317,4272,4852,4889 |  | 0 | 334 | Warning
9720 | Organizational Change Management (OCM) | August 15, 2022 8:00 AM | December 11, 2026 5:00 PM | 1084 | 208d |  |  | 0.82 | 208 | Warning
9870 | Execute OCM plan- Deliverable Tasks 5.2 - 5.3, 5.7-5.8 | September 1, 2022 8:00 AM | December 11, 2026 5:00 PM | 1071 | 208d |  |  | 0.79 | 208 | Warning
9958 | Define Phase | December 7, 2022 8:00 AM | October 23, 2026 5:00 PM | 974 | 239d |  |  | 0.76 | 239 | Warning
9997 | OCM Advisory Workgroup Engagement | November 1, 2023 8:00 AM | October 23, 2026 5:00 PM | 747 | 239d |  |  | 0.64 | 239 | Warning
12214 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 24 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 239d | 5244 | 5246 | 0.35 | 239 | Warning
12215 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 25 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 239d | 5245 | 5247 | 0 | 239 | Warning
12216 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 26 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 239d | 5246 | 5248 | 0 | 239 | Warning
12217 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 27 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 239d | 5247 | 5249 | 0 | 239 | Warning
12218 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 28 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 239d | 5248 | 5250 | 0 | 239 | Warning
12219 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 29 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 21 | 239d | 5249 | 5251 | 0 | 239 | Warning
12220 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 30 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 239d | 5250 | 5252 | 0 | 239 | Warning
12221 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 31 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 239d | 5251 | 5253 | 0 | 239 | Warning
12222 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 32 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 239d | 5252 | 5254 | 0 | 239 | Warning
12223 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 33 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 239d | 5253 | 5255 | 0 | 239 | Warning
12224 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 34 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 239d | 5254 | 5256 | 0 | 239 | Warning
12225 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 35 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 239d | 5255 | 5257 | 0 | 239 | Warning
12226 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 36 | October 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17 | 239d | 5256 | 5621 | 0 | 239 | Warning
10015 | Develop Phase | February 27, 2023 8:00 AM | December 11, 2026 5:00 PM | 952 | 208d |  |  | 0.78 | 208 | Warning
10016 | Create Sandbox Strategy | October 3, 2023 8:00 AM | February 21, 2025 5:00 PM | 347 | 422d |  |  | 0.99 | 422 | Warning
13055 | Finalize the Updates for the Sandbox Strategy | February 18, 2025 8:00 AM | February 21, 2025 5:00 PM | 4 | 422d | 5275FS-1d | 5630 | 0.5 | 422 | Warning
10045 | Video Series Program | August 28, 2023 8:00 AM | December 11, 2026 5:00 PM | 825 | 208d |  |  | 0.48 | 208 | Warning
10066 | OCM Video Series Development and Delivery | December 18, 2023 8:00 AM | December 11, 2026 5:00 PM | 749 | 208d |  |  | 0.45 | 208 | Warning
11670 | Develop and Launch Change Impact Video Series - 'CWS-CARES 101 Videos' | March 3, 2025 8:00 AM | June 8, 2026 5:00 PM | 319 | 337d |  |  | 0.43 | 337 | Warning
13629 | Develop and Launch 'CWS-CARES 101: Placement and Eligibility' Video | June 24, 2025 8:00 AM | September 15, 2025 5:00 PM | 58 | 519d |  |  | 0.66 | 519 | Warning
13632 | Complete reviews of CWS-CARES 101: Placement & Eligibility video storyboard, including ELT | July 30, 2025 8:00 AM | August 22, 2025 5:00 PM | 18 | 519d | 5309 | 5311 | 0.75 | 519 | Warning
13633 | Incorporate ELT feedback and develop draft CWS-CARES 101: Placement & Eligibility Vyond video | August 25, 2025 8:00 AM | September 2, 2025 5:00 PM | 6 | 519d | 5310 | 5312 | 0 | 519 | Warning
13634 | Complete reviews of CWS-CARES 101: Placement & Eligibility Vyond video and launch | September 3, 2025 8:00 AM | September 15, 2025 5:00 PM | 9 | 519d | 5311 | 5314 | 0 | 519 | Warning
10073 | Develop and Launch the 'How to Promote System Adoption' video | June 24, 2025 8:00 AM | September 18, 2025 5:00 PM | 61 | 304d |  |  | 0.69 | 304 | Warning
13637 | Complete reviews of 'How to Promote System Adoption' video storyboard, including ELT | July 31, 2025 8:00 AM | August 25, 2025 5:00 PM | 18 | 304d | 5333 | 5335 | 0.9 | 304 | Warning
13638 | Incorporate ELT feedback and develop draft 'How to Promote System Adoption' Vyond video | August 26, 2025 8:00 AM | September 5, 2025 5:00 PM | 8 | 304d | 5334 | 5336 | 0 | 304 | Warning
13639 | Complete reviews of 'How to Promote System Adoption' Vyond video and launch | September 8, 2025 8:00 AM | September 18, 2025 5:00 PM | 9 | 304d | 5335 | 5361 | 0 | 304 | Warning
10120 | Deliver Phase | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM | 920 | 239d |  |  | 0.7 | 239 | Warning
10131 | Information Sessions | January 18, 2024 8:00 AM | February 27, 2026 5:00 PM | 531 | 405d |  |  | 0.7 | 405 | Warning
13690 | Deliver Process Information Session: Probation - Part 2 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 424d | 5560FS+41d | 5564 | 0 | 424 | Warning
12671 | Deliver Process Information Session 4: Court Processing Regional Sessions - Part 2 | December 15, 2025 8:00 AM | January 12, 2026 5:00 PM | 19 | 438d | 5562 |  | 0 | 438 | Warning
13691 | Deliver Process Information Session: CDSS | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 424d | 5561 | 5621 | 0 | 424 | Warning
10162 | Communications | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM | 920 | 239d |  |  | 0.69 | 239 | Warning
10163 | Draft and distribute monthly communications products | July 3, 2023 8:00 AM | October 23, 2026 5:00 PM | 832 | 239d |  |  | 0.69 | 239 | Warning
12242 | Draft and distribute monthly communications products 28 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 239d | 5595 | 5597 | 0.35 | 239 | Warning
12243 | Draft and distribute monthly communications products 29 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 239d | 5596 | 5598 | 0 | 239 | Warning
12244 | Draft and distribute monthly communications products 30 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 239d | 5597 | 5599 | 0 | 239 | Warning
12245 | Draft and distribute monthly communications products 31 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 239d | 5598 | 5600 | 0 | 239 | Warning
12246 | Draft and distribute monthly communications products 32 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 239d | 5599 | 5601 | 0 | 239 | Warning
12247 | Draft and distribute monthly communications products 33 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 21 | 239d | 5600 | 5602 | 0 | 239 | Warning
12248 | Draft and distribute monthly communications products 34 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 239d | 5601 | 5603 | 0 | 239 | Warning
12249 | Draft and distribute monthly communications products 35 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 239d | 5602 | 5604 | 0 | 239 | Warning
12250 | Draft and distribute monthly communications products 36 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 239d | 5603 | 5605 | 0 | 239 | Warning
12251 | Draft and distribute monthly communications products 37 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 239d | 5604 | 5606 | 0 | 239 | Warning
12252 | Draft and distribute monthly communications products 38 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 239d | 5605 | 5607 | 0 | 239 | Warning
12253 | Draft and distribute monthly communications products 39 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 239d | 5606 | 5608 | 0 | 239 | Warning
12254 | Draft and distribute monthly communications products 40 | October 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17 | 239d | 5607 | 5621 | 0 | 239 | Warning
10288 | Go-Live | October 26, 2026 8:00 AM | October 26, 2026 5:00 PM | 1 | 239d | 5010,5055,5057,5097,5155,5220,5233,5274,5609,5557,5257,5608,5564 |  | 0 | 239 | Warning
23994 | Alameda CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
23995 | Alameda CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
24017 | Alameda CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
24018 | Alameda CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24019 | Alameda CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24020 | Alameda CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24021 | Alameda CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24022 | Alameda CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24023 | Alameda CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24024 | Alameda CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24025 | Alameda CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24026 | Alameda CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24027 | Alameda CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24028 | Alameda CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24029 | Alameda CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24036 | Alameda CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
24037 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 5688SS | 0 | 414 | Warning
24038 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 5687SS |  | 0 | 414 | Warning
24039 | Alameda CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 5690SS | 0 | 362 | Warning
24040 | Alameda CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 5689SS |  | 0 | 362 | Warning
24041 | Alameda CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24042 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 5693SS | 0 | 352 | Warning
24043 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 5692SS |  | 0 | 352 | Warning
24044 | Alameda CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24045 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 5696SS | 0 | 288 | Warning
24046 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 5695SS |  | 0 | 288 | Warning
24047 | Alameda CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24048 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 5699SS | 0 | 268 | Warning
24049 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 5698SS |  | 0 | 268 | Warning
24050 | Alameda CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24051 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 5702SS | 0 | 246 | Warning
24052 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 5701SS |  | 0 | 246 | Warning
24053 | Alameda CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24054 | Alameda CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.32 | 234 | Warning
24057 | Alameda CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 5706 |  | 0.2 | 234 | Warning
24061 | Alameda CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24064 | Alameda CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 5713 |  | 0.2 | 466 | Warning
24065 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24067 | Alameda CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 5716 | 5718 | 0.2 | 405 | Warning
24068 | Alameda CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 5717 |  | 0 | 405 | Warning
24069 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24070 | Alameda CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 5721 | 0.2 | 405 | Warning
24071 | Alameda CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 5720 | 5722 | 0 | 405 | Warning
24072 | Alameda CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 5721 |  | 0 | 405 | Warning
24073 | Alameda CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24074 | Alameda CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 5725 | 0 | 362 | Warning
24075 | Alameda CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 5724 | 5726 | 0 | 362 | Warning
24076 | Alameda CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 5725 |  | 0 | 362 | Warning
24077 | Alameda CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24078 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24079 | Alameda CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.39 | 298 | Warning
24080 | Alameda CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.67 | 357 | Warning
24081 | Alameda CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 5732SS | 0.8 | 405 | Warning
24082 | Alameda CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 5731SS | 5733 | 0.6 | 357 | Warning
24083 | Alameda CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 5732 |  | 0 | 357 | Warning
24088 | Alameda CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
24090 | Alameda CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 5739 |  | 0.2 | 485 | Warning
24091 | Alameda CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
24093 | Alameda CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 5742SS | 5744,5747,5745SF+30d | 0.2 | 298 | Warning
24094 | Alameda CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 5743 |  | 0 | 298 | Warning
24095 | Alameda CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5743SF+30d |  | 0 | 298 | Warning
24096 | Alameda CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24097 | Alameda CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 5743 |  | 0 | 345 | Warning
24098 | Alameda CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.65 | 445 | Warning
24100 | Alameda CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 5749SS | 5751SS | 0.6 | 485 | Warning
24101 | Alameda CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 5750SS |  | 0.4 | 445 | Warning
24106 | Alameda CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.67 | 508 | Warning
24108 | Alameda CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 5757 |  | 0.2 | 508 | Warning
24109 | Alameda CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
24111 | Alameda CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 5760SS | 5765,5762 | 0.2 | 298 | Warning
24112 | Alameda CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 5761 |  | 0 | 298 | Warning
24113 | Alameda CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
24114 | Alameda CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24115 | Alameda CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 5761 |  | 0 | 345 | Warning
24116 | Alameda CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24117 | Alameda CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24118 | Alameda CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24119 | Alameda CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24120 | Alameda CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24121 | Alameda CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24122 | Alameda CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24123 | Alameda CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24124 | Alameda CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24125 | Alameda CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24126 | Alameda CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24127 | Alameda CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24128 | Alameda CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24131 | Alameda CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
24132 | Alameda CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24133 | Alameda CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24134 | Alameda CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24135 | Alameda CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5794 | 0 | 234 | Warning
24136 | Alameda CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5795 | 0 | 234 | Warning
24138 | Alameda CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24139 | Alameda CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5800SF+30d |  | 0 | 309 | Warning
24140 | Alameda CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5801SF+30d |  | 0 | 309 | Warning
24141 | Alameda CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5802SF+30d |  | 0 | 309 | Warning
24142 | Alameda CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5803SF+30d |  | 0 | 309 | Warning
24143 | Alameda CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5804SF+30d |  | 0 | 309 | Warning
24144 | Alameda CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 5785 |  | 0 | 234 | Warning
24145 | Alameda CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 5786 |  | 0 | 234 | Warning
24146 | Alameda CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24147 | Alameda CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 5806FS+12d | 0 | 240 | Warning
24148 | Alameda CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
24149 | Alameda CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 5806SF+60d | 0 | 250 | Warning
24150 | Alameda CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5789SF+30d | 0 | 240 | Warning
24151 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5790SF+30d | 0 | 240 | Warning
24152 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5791SF+30d | 0 | 240 | Warning
24153 | Alameda CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5792SF+30d | 0 | 240 | Warning
24154 | Alameda CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5793SF+30d | 0 | 240 | Warning
24155 | Alameda CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
24156 | Alameda CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 5797FS+12d,5799SF+60d |  | 0 | 240 | Warning
24159 | Alpine CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
24164 | Alpine CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
24165 | Alpine CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
24166 | Alpine CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
24167 | Alpine CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
24169 | Alpine CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.4 | 235 | Warning
24170 | Alpine CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
24193 | Alpine CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24194 | Alpine CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24195 | Alpine CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24196 | Alpine CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24197 | Alpine CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24198 | Alpine CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24199 | Alpine CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24200 | Alpine CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24201 | Alpine CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24202 | Alpine CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24203 | Alpine CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24204 | Alpine CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24211 | Alpine CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
24212 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 5863SS | 0 | 414 | Warning
24213 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 5862SS |  | 0 | 414 | Warning
24214 | Alpine CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 5865SS | 0 | 362 | Warning
24215 | Alpine CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 5864SS |  | 0 | 362 | Warning
24216 | Alpine CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24217 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 5868SS | 0 | 352 | Warning
24218 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 5867SS |  | 0 | 352 | Warning
24219 | Alpine CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24220 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 5871SS | 0 | 288 | Warning
24221 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 5870SS |  | 0 | 288 | Warning
24222 | Alpine CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24223 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 5874SS | 0 | 268 | Warning
24224 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 5873SS |  | 0 | 268 | Warning
24225 | Alpine CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24226 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 5877SS | 0 | 246 | Warning
24227 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 5876SS |  | 0 | 246 | Warning
24228 | Alpine CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24229 | Alpine CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.34 | 234 | Warning
24232 | Alpine CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 5881 |  | 0.2 | 234 | Warning
24236 | Alpine CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24239 | Alpine CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 5888 |  | 0.4 | 466 | Warning
24240 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24242 | Alpine CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 5891 | 5893 | 0.4 | 405 | Warning
24243 | Alpine CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 5892 |  | 0 | 405 | Warning
24244 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24245 | Alpine CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 5896 | 0.6 | 405 | Warning
24246 | Alpine CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 5895 | 5897 | 0 | 405 | Warning
24247 | Alpine CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 5896 |  | 0 | 405 | Warning
24248 | Alpine CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24249 | Alpine CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 5900 | 0 | 362 | Warning
24250 | Alpine CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 5899 | 5901 | 0 | 362 | Warning
24251 | Alpine CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 5900 |  | 0 | 362 | Warning
24252 | Alpine CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24253 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24254 | Alpine CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.47 | 298 | Warning
24255 | Alpine CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
24258 | Alpine CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 5907 |  | 0 | 357 | Warning
24263 | Alpine CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
24265 | Alpine CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 5914 |  | 0 | 485 | Warning
24266 | Alpine CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
24268 | Alpine CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 5917SS | 5919,5922,5920SF+30d | 0.2 | 298 | Warning
24269 | Alpine CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 5918 |  | 0 | 298 | Warning
24270 | Alpine CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5918SF+30d |  | 0 | 298 | Warning
24271 | Alpine CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24272 | Alpine CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 5918 |  | 0 | 345 | Warning
24273 | Alpine CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.71 | 445 | Warning
24274 | Alpine CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 5925SS | 0.95 | 485 | Warning
24275 | Alpine CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 5924SS | 5926SS | 0.6 | 485 | Warning
24276 | Alpine CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 5925SS |  | 0.6 | 445 | Warning
24284 | Alpine CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.27 | 298 | Warning
24286 | Alpine CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 5935SS | 5940,5937 | 0.4 | 298 | Warning
24287 | Alpine CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 5936 |  | 0 | 298 | Warning
24288 | Alpine CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
24289 | Alpine CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24290 | Alpine CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 5936 |  | 0 | 345 | Warning
24291 | Alpine CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24292 | Alpine CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24293 | Alpine CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24294 | Alpine CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24295 | Alpine CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24296 | Alpine CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24297 | Alpine CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24298 | Alpine CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24299 | Alpine CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24300 | Alpine CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24301 | Alpine CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24302 | Alpine CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24303 | Alpine CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24306 | Alpine CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
24307 | Alpine CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24308 | Alpine CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24309 | Alpine CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24310 | Alpine CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5969 | 0 | 234 | Warning
24311 | Alpine CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5970 | 0 | 234 | Warning
24313 | Alpine CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24314 | Alpine CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5975SF+30d |  | 0 | 309 | Warning
24315 | Alpine CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5976SF+30d |  | 0 | 309 | Warning
24316 | Alpine CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5977SF+30d |  | 0 | 309 | Warning
24317 | Alpine CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5978SF+30d |  | 0 | 309 | Warning
24318 | Alpine CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5979SF+30d |  | 0 | 309 | Warning
24319 | Alpine CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 5960 |  | 0 | 234 | Warning
24320 | Alpine CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 5961 |  | 0 | 234 | Warning
24321 | Alpine CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24322 | Alpine CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 5981FS+12d | 0 | 240 | Warning
24323 | Alpine CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
24324 | Alpine CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 5981SF+60d | 0 | 250 | Warning
24325 | Alpine CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5964SF+30d | 0 | 240 | Warning
24326 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5965SF+30d | 0 | 240 | Warning
24327 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5966SF+30d | 0 | 240 | Warning
24328 | Alpine CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5967SF+30d | 0 | 240 | Warning
24329 | Alpine CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5968SF+30d | 0 | 240 | Warning
24330 | Alpine CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
24331 | Alpine CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 5972FS+12d,5974SF+60d |  | 0 | 240 | Warning
24334 | Amador CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
24339 | Amador CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
24340 | Amador CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
24341 | Amador CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
24342 | Amador CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
24344 | Amador CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
24345 | Amador CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
24368 | Amador CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24369 | Amador CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24370 | Amador CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24371 | Amador CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24372 | Amador CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24373 | Amador CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24374 | Amador CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24375 | Amador CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24376 | Amador CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24377 | Amador CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24378 | Amador CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24379 | Amador CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24386 | Amador CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
24387 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6038SS | 0 | 414 | Warning
24388 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6037SS |  | 0 | 414 | Warning
24389 | Amador CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6040SS | 0 | 362 | Warning
24390 | Amador CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6039SS |  | 0 | 362 | Warning
24391 | Amador CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24392 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6043SS | 0 | 352 | Warning
24393 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6042SS |  | 0 | 352 | Warning
24394 | Amador CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24395 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6046SS | 0 | 288 | Warning
24396 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6045SS |  | 0 | 288 | Warning
24397 | Amador CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24398 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6049SS | 0 | 268 | Warning
24399 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6048SS |  | 0 | 268 | Warning
24400 | Amador CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24401 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6052SS | 0 | 246 | Warning
24402 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6051SS |  | 0 | 246 | Warning
24403 | Amador CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24404 | Amador CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.34 | 234 | Warning
24407 | Amador CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6056 |  | 0.2 | 234 | Warning
24411 | Amador CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24414 | Amador CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 6063 |  | 0.4 | 466 | Warning
24415 | Amador CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24418 | Amador CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6067 |  | 0 | 405 | Warning
24419 | Amador CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24420 | Amador CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6071 | 0 | 405 | Warning
24421 | Amador CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6070 | 6072 | 0 | 405 | Warning
24422 | Amador CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6071 |  | 0 | 405 | Warning
24423 | Amador CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24424 | Amador CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6075 | 0 | 362 | Warning
24425 | Amador CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6074 | 6076 | 0 | 362 | Warning
24426 | Amador CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6075 |  | 0 | 362 | Warning
24427 | Amador CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24428 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24429 | Amador CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.35 | 298 | Warning
24430 | Amador CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
24431 | Amador CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 6082SS | 0.6 | 405 | Warning
24432 | Amador CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 6081SS | 6083 | 0.6 | 357 | Warning
24433 | Amador CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 6082 |  | 0 | 357 | Warning
24438 | Amador CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
24440 | Amador CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 6089 |  | 0 | 485 | Warning
24441 | Amador CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
24443 | Amador CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 6092SS | 6094,6097,6095SF+30d | 0.2 | 298 | Warning
24444 | Amador CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6093 |  | 0 | 298 | Warning
24445 | Amador CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6093SF+30d |  | 0 | 298 | Warning
24446 | Amador CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24447 | Amador CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6093 |  | 0 | 345 | Warning
24448 | Amador CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.54 | 445 | Warning
24449 | Amador CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 6100SS | 0.4 | 485 | Warning
24450 | Amador CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 6099SS | 6101SS | 0.6 | 485 | Warning
24451 | Amador CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 6100SS |  | 0.6 | 445 | Warning
24459 | Amador CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
24461 | Amador CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 6110SS | 6115,6112 | 0.2 | 298 | Warning
24462 | Amador CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6111 |  | 0 | 298 | Warning
24463 | Amador CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
24464 | Amador CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24465 | Amador CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6111 |  | 0 | 345 | Warning
24466 | Amador CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24467 | Amador CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24468 | Amador CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24469 | Amador CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24470 | Amador CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24471 | Amador CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24472 | Amador CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24473 | Amador CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24474 | Amador CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24475 | Amador CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24476 | Amador CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24477 | Amador CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24478 | Amador CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24481 | Amador CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
24482 | Amador CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24483 | Amador CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24484 | Amador CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24485 | Amador CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6144 | 0 | 234 | Warning
24486 | Amador CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6145 | 0 | 234 | Warning
24488 | Amador CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24489 | Amador CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6150SF+30d |  | 0 | 309 | Warning
24490 | Amador CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6151SF+30d |  | 0 | 309 | Warning
24491 | Amador CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6152SF+30d |  | 0 | 309 | Warning
24492 | Amador CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6153SF+30d |  | 0 | 309 | Warning
24493 | Amador CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6154SF+30d |  | 0 | 309 | Warning
24494 | Amador CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6135 |  | 0 | 234 | Warning
24495 | Amador CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6136 |  | 0 | 234 | Warning
24496 | Amador CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24497 | Amador CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6156FS+12d | 0 | 240 | Warning
24498 | Amador CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
24499 | Amador CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6156SF+60d | 0 | 250 | Warning
24500 | Amador CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6139SF+30d | 0 | 240 | Warning
24501 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6140SF+30d | 0 | 240 | Warning
24502 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6141SF+30d | 0 | 240 | Warning
24503 | Amador CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6142SF+30d | 0 | 240 | Warning
24504 | Amador CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6143SF+30d | 0 | 240 | Warning
24505 | Amador CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
24506 | Amador CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6147FS+12d,6149SF+60d |  | 0 | 240 | Warning
24509 | Colusa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
24514 | Colusa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
24515 | Colusa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
24516 | Colusa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
24517 | Colusa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
24519 | Colusa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
24520 | Colusa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
24542 | Colusa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
24543 | Colusa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24544 | Colusa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24545 | Colusa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24546 | Colusa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24547 | Colusa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24548 | Colusa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24549 | Colusa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24550 | Colusa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24551 | Colusa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24552 | Colusa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24553 | Colusa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24554 | Colusa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24561 | Colusa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
24562 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6213SS | 0 | 414 | Warning
24563 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6212SS |  | 0 | 414 | Warning
24564 | Colusa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6215SS | 0 | 362 | Warning
24565 | Colusa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6214SS |  | 0 | 362 | Warning
24566 | Colusa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24567 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6218SS | 0 | 352 | Warning
24568 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6217SS |  | 0 | 352 | Warning
24569 | Colusa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24570 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6221SS | 0 | 288 | Warning
24571 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6220SS |  | 0 | 288 | Warning
24572 | Colusa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24573 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6224SS | 0 | 268 | Warning
24574 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6223SS |  | 0 | 268 | Warning
24575 | Colusa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24576 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6227SS | 0 | 246 | Warning
24577 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6226SS |  | 0 | 246 | Warning
24578 | Colusa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24579 | Colusa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.52 | 234 | Warning
24582 | Colusa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6231 |  | 0.6 | 234 | Warning
24586 | Colusa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24590 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24592 | Colusa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 6241 | 6243 | 0 | 405 | Warning
24593 | Colusa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6242 |  | 0 | 405 | Warning
24594 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24596 | Colusa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6245 | 6247 | 0 | 405 | Warning
24597 | Colusa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6246 |  | 0 | 405 | Warning
24598 | Colusa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24599 | Colusa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6250 | 0 | 362 | Warning
24600 | Colusa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6249 | 6251 | 0 | 362 | Warning
24601 | Colusa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6250 |  | 0 | 362 | Warning
24602 | Colusa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24603 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24604 | Colusa CW-Technical | January 1, 2025 8:00 AM | July 10, 2026 5:00 PM | 382 | 314d |  |  | 0.31 | 314 | Warning
24619 | Colusa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24620 | Colusa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24621 | Colusa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24622 | Colusa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24623 | Colusa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24624 | Colusa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24625 | Colusa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24626 | Colusa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24627 | Colusa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24628 | Colusa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24629 | Colusa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24630 | Colusa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24631 | Colusa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24634 | Colusa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
24635 | Colusa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24636 | Colusa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24637 | Colusa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24638 | Colusa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6297 | 0 | 234 | Warning
24639 | Colusa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6298 | 0 | 234 | Warning
24641 | Colusa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24642 | Colusa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6303SF+30d |  | 0 | 309 | Warning
24643 | Colusa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6304SF+30d |  | 0 | 309 | Warning
24644 | Colusa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6305SF+30d |  | 0 | 309 | Warning
24645 | Colusa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6306SF+30d |  | 0 | 309 | Warning
24646 | Colusa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6307SF+30d |  | 0 | 309 | Warning
24647 | Colusa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6288 |  | 0 | 234 | Warning
24648 | Colusa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6289 |  | 0 | 234 | Warning
24649 | Colusa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24650 | Colusa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6309FS+12d | 0 | 240 | Warning
24651 | Colusa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
24652 | Colusa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6309SF+60d | 0 | 250 | Warning
24653 | Colusa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6292SF+30d | 0 | 240 | Warning
24654 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6293SF+30d | 0 | 240 | Warning
24655 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6294SF+30d | 0 | 240 | Warning
24656 | Colusa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6295SF+30d | 0 | 240 | Warning
24657 | Colusa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6296SF+30d | 0 | 240 | Warning
24658 | Colusa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
24659 | Colusa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6300FS+12d,6302SF+60d |  | 0 | 240 | Warning
24662 | Contra Costa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
24667 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
24668 | Contra Costa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
24669 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
24670 | Contra Costa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
24672 | Contra Costa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
24673 | Contra Costa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
24695 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
24696 | Contra Costa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24697 | Contra Costa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24698 | Contra Costa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24699 | Contra Costa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24700 | Contra Costa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24701 | Contra Costa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24702 | Contra Costa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24703 | Contra Costa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24704 | Contra Costa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24705 | Contra Costa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24706 | Contra Costa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24707 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24714 | Contra Costa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
24715 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6366SS | 0 | 414 | Warning
24716 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6365SS |  | 0 | 414 | Warning
24717 | Contra Costa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6368SS | 0 | 362 | Warning
24718 | Contra Costa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6367SS |  | 0 | 362 | Warning
24719 | Contra Costa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24720 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6371SS | 0 | 352 | Warning
24721 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6370SS |  | 0 | 352 | Warning
24722 | Contra Costa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24723 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6374SS | 0 | 288 | Warning
24724 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6373SS |  | 0 | 288 | Warning
24725 | Contra Costa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24726 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6377SS | 0 | 268 | Warning
24727 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6376SS |  | 0 | 268 | Warning
24728 | Contra Costa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24729 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6380SS | 0 | 246 | Warning
24730 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6379SS |  | 0 | 246 | Warning
24731 | Contra Costa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24732 | Contra Costa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.47 | 234 | Warning
24735 | Contra Costa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6384 |  | 0.6 | 234 | Warning
24739 | Contra Costa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24742 | Contra Costa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 6391 |  | 0.2 | 466 | Warning
24743 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24745 | Contra Costa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 6394 | 6396 | 0 | 405 | Warning
24746 | Contra Costa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6395 |  | 0 | 405 | Warning
24747 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24748 | Contra Costa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6399 | 0.2 | 405 | Warning
24749 | Contra Costa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6398 | 6400 | 0 | 405 | Warning
24750 | Contra Costa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6399 |  | 0 | 405 | Warning
24751 | Contra Costa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24752 | Contra Costa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6403 | 0 | 362 | Warning
24753 | Contra Costa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6402 | 6404 | 0 | 362 | Warning
24754 | Contra Costa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6403 |  | 0 | 362 | Warning
24755 | Contra Costa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24756 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24757 | Contra Costa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.45 | 298 | Warning
24758 | Contra Costa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.89 | 357 | Warning
24761 | Contra Costa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 6410 |  | 0.6 | 357 | Warning
24769 | Contra Costa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
24771 | Contra Costa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 6420SS | 6422,6425,6423SF+30d | 0.2 | 298 | Warning
24772 | Contra Costa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6421 |  | 0 | 298 | Warning
24773 | Contra Costa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6421SF+30d |  | 0 | 298 | Warning
24774 | Contra Costa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24775 | Contra Costa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6421 |  | 0 | 345 | Warning
24776 | Contra Costa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
24779 | Contra Costa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 6428SS |  | 0.2 | 445 | Warning
24787 | Contra Costa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
24789 | Contra Costa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 6438SS | 6443,6440 | 0.2 | 298 | Warning
24790 | Contra Costa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6439 |  | 0 | 298 | Warning
24791 | Contra Costa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
24792 | Contra Costa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24793 | Contra Costa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6439 |  | 0 | 345 | Warning
24794 | Contra Costa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24795 | Contra Costa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24796 | Contra Costa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24797 | Contra Costa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24798 | Contra Costa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24799 | Contra Costa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24800 | Contra Costa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24801 | Contra Costa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24802 | Contra Costa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24803 | Contra Costa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24804 | Contra Costa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24805 | Contra Costa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24806 | Contra Costa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24809 | Contra Costa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | 384 | Warning
24810 | Contra Costa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24811 | Contra Costa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24812 | Contra Costa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24813 | Contra Costa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6472 | 0 | 234 | Warning
24814 | Contra Costa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6473 | 0 | 234 | Warning
24816 | Contra Costa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24817 | Contra Costa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6478SF+30d |  | 0 | 309 | Warning
24818 | Contra Costa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6479SF+30d |  | 0 | 309 | Warning
24819 | Contra Costa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6480SF+30d |  | 0 | 309 | Warning
24820 | Contra Costa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6481SF+30d |  | 0 | 309 | Warning
24821 | Contra Costa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6482SF+30d |  | 0 | 309 | Warning
24822 | Contra Costa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6463 |  | 0 | 234 | Warning
24823 | Contra Costa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6464 |  | 0 | 234 | Warning
24824 | Contra Costa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24825 | Contra Costa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6484FS+12d | 0 | 240 | Warning
24826 | Contra Costa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
24827 | Contra Costa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6484SF+60d | 0 | 250 | Warning
24828 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6467SF+30d | 0 | 240 | Warning
24829 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6468SF+30d | 0 | 240 | Warning
24830 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6469SF+30d | 0 | 240 | Warning
24831 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6470SF+30d | 0 | 240 | Warning
24832 | Contra Costa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6471SF+30d | 0 | 240 | Warning
24833 | Contra Costa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
24834 | Contra Costa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6475FS+12d,6477SF+60d |  | 0 | 240 | Warning
24837 | Del Norte CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
24842 | Del Norte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
24843 | Del Norte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
24844 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
24845 | Del Norte CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
24847 | Del Norte CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.43 | 235 | Warning
24848 | Del Norte CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
24871 | Del Norte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
24872 | Del Norte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
24873 | Del Norte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
24874 | Del Norte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
24875 | Del Norte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
24876 | Del Norte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
24877 | Del Norte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
24878 | Del Norte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24879 | Del Norte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
24880 | Del Norte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
24881 | Del Norte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24882 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
24889 | Del Norte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | 445 | Warning
24890 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6541SS | 0 | 414 | Warning
24891 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6540SS |  | 0 | 414 | Warning
24892 | Del Norte CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6543SS | 0 | 362 | Warning
24893 | Del Norte CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6542SS |  | 0 | 362 | Warning
24894 | Del Norte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
24895 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6546SS | 0 | 352 | Warning
24896 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6545SS |  | 0 | 352 | Warning
24897 | Del Norte CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
24898 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6549SS | 0 | 288 | Warning
24899 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6548SS |  | 0 | 288 | Warning
24900 | Del Norte CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
24901 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6552SS | 0 | 268 | Warning
24902 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6551SS |  | 0 | 268 | Warning
24903 | Del Norte CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
24904 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6555SS | 0 | 246 | Warning
24905 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6554SS |  | 0 | 246 | Warning
24906 | Del Norte CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
24907 | Del Norte CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.34 | 234 | Warning
24910 | Del Norte CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6559 |  | 0.2 | 234 | Warning
24914 | Del Norte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24917 | Del Norte CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 6566 |  | 0.2 | 466 | Warning
24918 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24920 | Del Norte CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 6569 | 6571 | 0 | 405 | Warning
24921 | Del Norte CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6570 |  | 0 | 405 | Warning
24922 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24924 | Del Norte CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6573 | 6575 | 0 | 405 | Warning
24925 | Del Norte CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6574 |  | 0 | 405 | Warning
24926 | Del Norte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
24927 | Del Norte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6578 | 0 | 362 | Warning
24928 | Del Norte CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6577 | 6579 | 0 | 362 | Warning
24929 | Del Norte CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6578 |  | 0 | 362 | Warning
24930 | Del Norte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
24931 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
24932 | Del Norte CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.2 | 298 | Warning
24933 | Del Norte CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0 | 357 | Warning
24934 | Del Norte CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d |  | 6585SS | 0 | 357 | Warning
24935 | Del Norte CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 6584SS | 6586 | 0 | 357 | Warning
24936 | Del Norte CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 6585 |  | 0 | 357 | Warning
24943 | Del Norte CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
24945 | Del Norte CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 6594SS | 6596,6599,6597SF+30d | 0 | 298 | Warning
24946 | Del Norte CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6595 |  | 0 | 298 | Warning
24947 | Del Norte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6595SF+30d |  | 0 | 298 | Warning
24948 | Del Norte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24949 | Del Norte CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6595 |  | 0 | 345 | Warning
24950 | Del Norte CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
24953 | Del Norte CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 6602SS |  | 0 | 445 | Warning
24961 | Del Norte CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
24963 | Del Norte CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 6612SS | 6617,6614 | 0 | 298 | Warning
24964 | Del Norte CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6613 |  | 0 | 298 | Warning
24965 | Del Norte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
24966 | Del Norte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
24967 | Del Norte CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6613 |  | 0 | 345 | Warning
24968 | Del Norte CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
24969 | Del Norte CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24970 | Del Norte CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24971 | Del Norte CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24972 | Del Norte CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24973 | Del Norte CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24974 | Del Norte CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24975 | Del Norte CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24976 | Del Norte CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24977 | Del Norte CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24978 | Del Norte CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24979 | Del Norte CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
24980 | Del Norte CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
24983 | Del Norte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
24984 | Del Norte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
24985 | Del Norte CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
24986 | Del Norte CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
24987 | Del Norte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6646 | 0 | 234 | Warning
24988 | Del Norte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6647 | 0 | 234 | Warning
24990 | Del Norte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
24991 | Del Norte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6652SF+30d |  | 0 | 309 | Warning
24992 | Del Norte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6653SF+30d |  | 0 | 309 | Warning
24993 | Del Norte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6654SF+30d |  | 0 | 309 | Warning
24994 | Del Norte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6655SF+30d |  | 0 | 309 | Warning
24995 | Del Norte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6656SF+30d |  | 0 | 309 | Warning
24996 | Del Norte CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6637 |  | 0 | 234 | Warning
24997 | Del Norte CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6638 |  | 0 | 234 | Warning
24998 | Del Norte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
24999 | Del Norte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6658FS+12d | 0 | 240 | Warning
25000 | Del Norte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25001 | Del Norte CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6658SF+60d | 0 | 250 | Warning
25002 | Del Norte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6641SF+30d | 0 | 240 | Warning
25003 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6642SF+30d | 0 | 240 | Warning
25004 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6643SF+30d | 0 | 240 | Warning
25005 | Del Norte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6644SF+30d | 0 | 240 | Warning
25006 | Del Norte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6645SF+30d | 0 | 240 | Warning
25007 | Del Norte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25008 | Del Norte CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6649FS+12d,6651SF+60d |  | 0 | 240 | Warning
25011 | El Dorado CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25016 | El Dorado CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25017 | El Dorado CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25018 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25019 | El Dorado CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25021 | El Dorado CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
25022 | El Dorado CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25044 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25045 | El Dorado CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25046 | El Dorado CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25047 | El Dorado CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25048 | El Dorado CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25049 | El Dorado CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25050 | El Dorado CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25051 | El Dorado CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25052 | El Dorado CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25053 | El Dorado CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25054 | El Dorado CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25055 | El Dorado CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25056 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25063 | El Dorado CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
25064 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6715SS | 0 | 414 | Warning
25065 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6714SS |  | 0 | 414 | Warning
25066 | El Dorado CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6717SS | 0 | 362 | Warning
25067 | El Dorado CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6716SS |  | 0 | 362 | Warning
25068 | El Dorado CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25069 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6720SS | 0 | 352 | Warning
25070 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6719SS |  | 0 | 352 | Warning
25071 | El Dorado CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25072 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6723SS | 0 | 288 | Warning
25073 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6722SS |  | 0 | 288 | Warning
25074 | El Dorado CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25075 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6726SS | 0 | 268 | Warning
25076 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6725SS |  | 0 | 268 | Warning
25077 | El Dorado CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25078 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6729SS | 0 | 246 | Warning
25079 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6728SS |  | 0 | 246 | Warning
25080 | El Dorado CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25081 | El Dorado CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.33 | 234 | Warning
25084 | El Dorado CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6733 |  | 0.2 | 234 | Warning
25088 | El Dorado CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25091 | El Dorado CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 6740 |  | 0.2 | 466 | Warning
25092 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25094 | El Dorado CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 6743 | 6745 | 0.6 | 405 | Warning
25095 | El Dorado CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6744 |  | 0 | 405 | Warning
25096 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25097 | El Dorado CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6748 | 0 | 405 | Warning
25098 | El Dorado CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6747 | 6749 | 0 | 405 | Warning
25099 | El Dorado CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6748 |  | 0 | 405 | Warning
25100 | El Dorado CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25101 | El Dorado CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6752 | 0 | 362 | Warning
25102 | El Dorado CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6751 | 6753 | 0 | 362 | Warning
25103 | El Dorado CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6752 |  | 0 | 362 | Warning
25104 | El Dorado CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25105 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25106 | El Dorado CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.36 | 298 | Warning
25107 | El Dorado CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.59 | 357 | Warning
25108 | El Dorado CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 6759SS | 0.6 | 405 | Warning
25110 | El Dorado CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 6759 |  | 0.4 | 357 | Warning
25115 | El Dorado CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.84 | 485 | Warning
25117 | El Dorado CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 6766 |  | 0.6 | 485 | Warning
25118 | El Dorado CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.22 | 298 | Warning
25120 | El Dorado CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 6769SS | 6771,6774,6772SF+30d | 0.6 | 298 | Warning
25121 | El Dorado CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6770 |  | 0 | 298 | Warning
25122 | El Dorado CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6770SF+30d |  | 0 | 298 | Warning
25123 | El Dorado CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25124 | El Dorado CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6770 |  | 0 | 345 | Warning
25125 | El Dorado CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.41 | 445 | Warning
25127 | El Dorado CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 6776SS | 6778SS | 0.6 | 485 | Warning
25128 | El Dorado CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 6777SS |  | 0.6 | 445 | Warning
25136 | El Dorado CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
25138 | El Dorado CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 6787SS | 6792,6789 | 0.2 | 298 | Warning
25139 | El Dorado CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6788 |  | 0 | 298 | Warning
25140 | El Dorado CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
25141 | El Dorado CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25142 | El Dorado CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6788 |  | 0 | 345 | Warning
25143 | El Dorado CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25144 | El Dorado CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25145 | El Dorado CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25146 | El Dorado CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25147 | El Dorado CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25148 | El Dorado CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25149 | El Dorado CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25150 | El Dorado CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25151 | El Dorado CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25152 | El Dorado CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25153 | El Dorado CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25154 | El Dorado CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25155 | El Dorado CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25158 | El Dorado CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25159 | El Dorado CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25160 | El Dorado CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25161 | El Dorado CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
25162 | El Dorado CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6821 | 0 | 234 | Warning
25163 | El Dorado CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6822 | 0 | 234 | Warning
25165 | El Dorado CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
25166 | El Dorado CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6827SF+30d |  | 0 | 309 | Warning
25167 | El Dorado CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6828SF+30d |  | 0 | 309 | Warning
25168 | El Dorado CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6829SF+30d |  | 0 | 309 | Warning
25169 | El Dorado CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6830SF+30d |  | 0 | 309 | Warning
25170 | El Dorado CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6831SF+30d |  | 0 | 309 | Warning
25171 | El Dorado CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6812 |  | 0 | 234 | Warning
25172 | El Dorado CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6813 |  | 0 | 234 | Warning
25173 | El Dorado CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
25174 | El Dorado CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6833FS+12d | 0 | 240 | Warning
25175 | El Dorado CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25176 | El Dorado CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6833SF+60d | 0 | 250 | Warning
25177 | El Dorado CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6816SF+30d | 0 | 240 | Warning
25178 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6817SF+30d | 0 | 240 | Warning
25179 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6818SF+30d | 0 | 240 | Warning
25180 | El Dorado CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6819SF+30d | 0 | 240 | Warning
25181 | El Dorado CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6820SF+30d | 0 | 240 | Warning
25182 | El Dorado CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25183 | El Dorado CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6824FS+12d,6826SF+60d |  | 0 | 240 | Warning
25186 | Glenn CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25191 | Glenn CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25192 | Glenn CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25193 | Glenn CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25194 | Glenn CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25196 | Glenn CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
25197 | Glenn CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25219 | Glenn CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25220 | Glenn CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25221 | Glenn CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25222 | Glenn CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25223 | Glenn CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25224 | Glenn CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25225 | Glenn CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25226 | Glenn CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25227 | Glenn CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25228 | Glenn CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25229 | Glenn CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25230 | Glenn CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25231 | Glenn CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25238 | Glenn CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
25239 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6890SS | 0 | 414 | Warning
25240 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 6889SS |  | 0 | 414 | Warning
25241 | Glenn CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 6892SS | 0 | 362 | Warning
25242 | Glenn CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 6891SS |  | 0 | 362 | Warning
25243 | Glenn CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25244 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6895SS | 0 | 352 | Warning
25245 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 6894SS |  | 0 | 352 | Warning
25246 | Glenn CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25247 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6898SS | 0 | 288 | Warning
25248 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6897SS |  | 0 | 288 | Warning
25249 | Glenn CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25250 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6901SS | 0 | 268 | Warning
25251 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 6900SS |  | 0 | 268 | Warning
25252 | Glenn CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25253 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6904SS | 0 | 246 | Warning
25254 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 6903SS |  | 0 | 246 | Warning
25255 | Glenn CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25256 | Glenn CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.51 | 234 | Warning
25259 | Glenn CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 6908 |  | 0.6 | 234 | Warning
25263 | Glenn CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25267 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25269 | Glenn CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 6918 | 6920 | 0.4 | 405 | Warning
25270 | Glenn CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 6919 |  | 0 | 405 | Warning
25271 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25272 | Glenn CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6923 | 0 | 405 | Warning
25273 | Glenn CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 6922 | 6924 | 0 | 405 | Warning
25274 | Glenn CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 6923 |  | 0 | 405 | Warning
25275 | Glenn CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25276 | Glenn CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6927 | 0 | 362 | Warning
25277 | Glenn CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 6926 | 6928 | 0 | 362 | Warning
25278 | Glenn CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 6927 |  | 0 | 362 | Warning
25279 | Glenn CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25280 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25281 | Glenn CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.5 | 298 | Warning
25282 | Glenn CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
25285 | Glenn CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 6934 |  | 0 | 357 | Warning
25293 | Glenn CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
25295 | Glenn CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 6944SS | 6946,6949,6947SF+30d | 0 | 298 | Warning
25296 | Glenn CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6945 |  | 0 | 298 | Warning
25297 | Glenn CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6945SF+30d |  | 0 | 298 | Warning
25298 | Glenn CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25299 | Glenn CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6945 |  | 0 | 345 | Warning
25300 | Glenn CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
25303 | Glenn CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 6952SS |  | 0.4 | 445 | Warning
25311 | Glenn CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.37 | 298 | Warning
25314 | Glenn CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 6963 |  | 0 | 298 | Warning
25315 | Glenn CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
25316 | Glenn CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25317 | Glenn CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 6963 |  | 0 | 345 | Warning
25318 | Glenn CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25319 | Glenn CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25320 | Glenn CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25321 | Glenn CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25322 | Glenn CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25323 | Glenn CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25324 | Glenn CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25325 | Glenn CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25326 | Glenn CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25327 | Glenn CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25328 | Glenn CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25329 | Glenn CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25330 | Glenn CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25333 | Glenn CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25334 | Glenn CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25335 | Glenn CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25336 | Glenn CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
25337 | Glenn CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6996 | 0 | 234 | Warning
25338 | Glenn CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6997 | 0 | 234 | Warning
25340 | Glenn CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
25341 | Glenn CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7002SF+30d |  | 0 | 309 | Warning
25342 | Glenn CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7003SF+30d |  | 0 | 309 | Warning
25343 | Glenn CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7004SF+30d |  | 0 | 309 | Warning
25344 | Glenn CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7005SF+30d |  | 0 | 309 | Warning
25345 | Glenn CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7006SF+30d |  | 0 | 309 | Warning
25346 | Glenn CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6987 |  | 0 | 234 | Warning
25347 | Glenn CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 6988 |  | 0 | 234 | Warning
25348 | Glenn CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
25349 | Glenn CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7008FS+12d | 0 | 240 | Warning
25350 | Glenn CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25351 | Glenn CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7008SF+60d | 0 | 250 | Warning
25352 | Glenn CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6991SF+30d | 0 | 240 | Warning
25353 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6992SF+30d | 0 | 240 | Warning
25354 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6993SF+30d | 0 | 240 | Warning
25355 | Glenn CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6994SF+30d | 0 | 240 | Warning
25356 | Glenn CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6995SF+30d | 0 | 240 | Warning
25357 | Glenn CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25358 | Glenn CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 6999FS+12d,7001SF+60d |  | 0 | 240 | Warning
25361 | Humboldt CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25366 | Humboldt CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25367 | Humboldt CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25368 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25369 | Humboldt CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25371 | Humboldt CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
25372 | Humboldt CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25394 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25395 | Humboldt CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25396 | Humboldt CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25397 | Humboldt CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25398 | Humboldt CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25399 | Humboldt CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25400 | Humboldt CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25401 | Humboldt CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25402 | Humboldt CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25403 | Humboldt CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25404 | Humboldt CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25405 | Humboldt CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25406 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25413 | Humboldt CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
25414 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7065SS | 0 | 414 | Warning
25415 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7064SS |  | 0 | 414 | Warning
25416 | Humboldt CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 7067SS | 0 | 362 | Warning
25417 | Humboldt CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 7066SS |  | 0 | 362 | Warning
25418 | Humboldt CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25419 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7070SS | 0 | 352 | Warning
25420 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7069SS |  | 0 | 352 | Warning
25421 | Humboldt CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25422 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7073SS | 0 | 288 | Warning
25423 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7072SS |  | 0 | 288 | Warning
25424 | Humboldt CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25425 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7076SS | 0 | 268 | Warning
25426 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7075SS |  | 0 | 268 | Warning
25427 | Humboldt CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25428 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7079SS | 0 | 246 | Warning
25429 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7078SS |  | 0 | 246 | Warning
25430 | Humboldt CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25431 | Humboldt CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.33 | 234 | Warning
25434 | Humboldt CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7083 |  | 0.2 | 234 | Warning
25438 | Humboldt CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25441 | Humboldt CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 7090 |  | 0.2 | 466 | Warning
25442 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25444 | Humboldt CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7093 | 7095 | 0 | 405 | Warning
25445 | Humboldt CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7094 |  | 0 | 405 | Warning
25446 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25447 | Humboldt CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7098 | 0.6 | 405 | Warning
25448 | Humboldt CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7097 | 7099 | 0 | 405 | Warning
25449 | Humboldt CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7098 |  | 0 | 405 | Warning
25450 | Humboldt CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25451 | Humboldt CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7102 | 0 | 362 | Warning
25452 | Humboldt CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7101 | 7103 | 0 | 362 | Warning
25453 | Humboldt CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7102 |  | 0 | 362 | Warning
25454 | Humboldt CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25455 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25456 | Humboldt CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.46 | 298 | Warning
25457 | Humboldt CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
25460 | Humboldt CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 7109 |  | 0 | 357 | Warning
25468 | Humboldt CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
25470 | Humboldt CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 7119SS | 7121,7124,7122SF+30d | 0 | 298 | Warning
25471 | Humboldt CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7120 |  | 0 | 298 | Warning
25472 | Humboldt CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7120SF+30d |  | 0 | 298 | Warning
25473 | Humboldt CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25474 | Humboldt CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7120 |  | 0 | 345 | Warning
25475 | Humboldt CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.85 | 445 | Warning
25478 | Humboldt CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7127SS |  | 0.6 | 445 | Warning
25486 | Humboldt CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
25488 | Humboldt CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 7137SS | 7142,7139 | 0 | 298 | Warning
25489 | Humboldt CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7138 |  | 0 | 298 | Warning
25490 | Humboldt CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
25491 | Humboldt CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25492 | Humboldt CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7138 |  | 0 | 345 | Warning
25493 | Humboldt CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25494 | Humboldt CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25495 | Humboldt CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25496 | Humboldt CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25497 | Humboldt CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25498 | Humboldt CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25499 | Humboldt CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25500 | Humboldt CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25501 | Humboldt CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25502 | Humboldt CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25503 | Humboldt CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25504 | Humboldt CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25505 | Humboldt CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25508 | Humboldt CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25509 | Humboldt CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25510 | Humboldt CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25511 | Humboldt CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
25512 | Humboldt CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7171 | 0 | 234 | Warning
25513 | Humboldt CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7172 | 0 | 234 | Warning
25515 | Humboldt CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
25516 | Humboldt CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7177SF+30d |  | 0 | 309 | Warning
25517 | Humboldt CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7178SF+30d |  | 0 | 309 | Warning
25518 | Humboldt CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7179SF+30d |  | 0 | 309 | Warning
25519 | Humboldt CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7180SF+30d |  | 0 | 309 | Warning
25520 | Humboldt CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7181SF+30d |  | 0 | 309 | Warning
25521 | Humboldt CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7162 |  | 0 | 234 | Warning
25522 | Humboldt CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7163 |  | 0 | 234 | Warning
25523 | Humboldt CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
25524 | Humboldt CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7183FS+12d | 0 | 240 | Warning
25525 | Humboldt CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25526 | Humboldt CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7183SF+60d | 0 | 250 | Warning
25527 | Humboldt CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7166SF+30d | 0 | 240 | Warning
25528 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7167SF+30d | 0 | 240 | Warning
25529 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7168SF+30d | 0 | 240 | Warning
25530 | Humboldt CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7169SF+30d | 0 | 240 | Warning
25531 | Humboldt CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7170SF+30d | 0 | 240 | Warning
25532 | Humboldt CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25533 | Humboldt CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 7174FS+12d,7176SF+60d |  | 0 | 240 | Warning
25536 | Imperial CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25541 | Imperial CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25542 | Imperial CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25543 | Imperial CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25544 | Imperial CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25546 | Imperial CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
25547 | Imperial CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25569 | Imperial CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25570 | Imperial CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25571 | Imperial CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25572 | Imperial CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25573 | Imperial CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25574 | Imperial CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25575 | Imperial CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25576 | Imperial CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25577 | Imperial CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25578 | Imperial CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25579 | Imperial CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25580 | Imperial CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25581 | Imperial CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25588 | Imperial CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
25589 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7240SS | 0 | 414 | Warning
25590 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7239SS |  | 0 | 414 | Warning
25591 | Imperial CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 7242SS | 0 | 362 | Warning
25592 | Imperial CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 7241SS |  | 0 | 362 | Warning
25593 | Imperial CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25594 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7245SS | 0 | 352 | Warning
25595 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7244SS |  | 0 | 352 | Warning
25596 | Imperial CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25597 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7248SS | 0 | 288 | Warning
25598 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7247SS |  | 0 | 288 | Warning
25599 | Imperial CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25600 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7251SS | 0 | 268 | Warning
25601 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7250SS |  | 0 | 268 | Warning
25602 | Imperial CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25603 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7254SS | 0 | 246 | Warning
25604 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7253SS |  | 0 | 246 | Warning
25605 | Imperial CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25606 | Imperial CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.48 | 234 | Warning
25609 | Imperial CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7258 |  | 0.6 | 234 | Warning
25613 | Imperial CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25616 | Imperial CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 7265 |  | 0.2 | 466 | Warning
25617 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25619 | Imperial CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7268 | 7270 | 0.2 | 405 | Warning
25620 | Imperial CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7269 |  | 0 | 405 | Warning
25621 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25622 | Imperial CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7273 | 0.2 | 405 | Warning
25623 | Imperial CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7272 | 7274 | 0 | 405 | Warning
25624 | Imperial CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7273 |  | 0 | 405 | Warning
25625 | Imperial CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25626 | Imperial CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7277 | 0 | 362 | Warning
25627 | Imperial CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7276 | 7278 | 0 | 362 | Warning
25628 | Imperial CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7277 |  | 0 | 362 | Warning
25629 | Imperial CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25630 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25631 | Imperial CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 398 | 298d |  |  | 0.23 | 298 | Warning
25632 | Imperial CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.32 | 445 | Warning
25633 | Imperial CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 7284SS | 0.4 | 485 | Warning
25634 | Imperial CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 7283SS | 7285SS | 0.4 | 485 | Warning
25635 | Imperial CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7284SS |  | 0.2 | 445 | Warning
25643 | Imperial CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
25646 | Imperial CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7295 |  | 0 | 298 | Warning
25647 | Imperial CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
25648 | Imperial CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25649 | Imperial CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7295 |  | 0.2 | 345 | Warning
25650 | Imperial CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25651 | Imperial CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25652 | Imperial CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25653 | Imperial CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25654 | Imperial CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25655 | Imperial CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25656 | Imperial CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25657 | Imperial CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25658 | Imperial CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25659 | Imperial CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25660 | Imperial CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25661 | Imperial CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25662 | Imperial CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25665 | Imperial CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25666 | Imperial CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25667 | Imperial CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25668 | Imperial CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
25669 | Imperial CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7328 | 0 | 234 | Warning
25670 | Imperial CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7329 | 0 | 234 | Warning
25672 | Imperial CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
25673 | Imperial CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7334SF+30d |  | 0 | 309 | Warning
25674 | Imperial CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7335SF+30d |  | 0 | 309 | Warning
25675 | Imperial CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7336SF+30d |  | 0 | 309 | Warning
25676 | Imperial CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7337SF+30d |  | 0 | 309 | Warning
25677 | Imperial CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7338SF+30d |  | 0 | 309 | Warning
25678 | Imperial CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7319 |  | 0 | 234 | Warning
25679 | Imperial CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7320 |  | 0 | 234 | Warning
25680 | Imperial CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
25681 | Imperial CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7340FS+12d | 0 | 240 | Warning
25682 | Imperial CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25683 | Imperial CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7340SF+60d | 0 | 250 | Warning
25684 | Imperial CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7323SF+30d | 0 | 240 | Warning
25685 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7324SF+30d | 0 | 240 | Warning
25686 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7325SF+30d | 0 | 240 | Warning
25687 | Imperial CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7326SF+30d | 0 | 240 | Warning
25688 | Imperial CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7327SF+30d | 0 | 240 | Warning
25689 | Imperial CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25690 | Imperial CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 7331FS+12d,7333SF+60d |  | 0 | 240 | Warning
25693 | Inyo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25698 | Inyo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25699 | Inyo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25700 | Inyo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25701 | Inyo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25703 | Inyo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
25704 | Inyo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25726 | Inyo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25727 | Inyo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25728 | Inyo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25729 | Inyo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25730 | Inyo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25731 | Inyo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25732 | Inyo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25733 | Inyo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25734 | Inyo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25735 | Inyo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25736 | Inyo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25737 | Inyo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25738 | Inyo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25745 | Inyo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
25746 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7397SS | 0 | 414 | Warning
25747 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7396SS |  | 0 | 414 | Warning
25748 | Inyo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 7399SS | 0 | 362 | Warning
25749 | Inyo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 7398SS |  | 0 | 362 | Warning
25750 | Inyo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25751 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7402SS | 0 | 352 | Warning
25752 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7401SS |  | 0 | 352 | Warning
25753 | Inyo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25754 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7405SS | 0 | 288 | Warning
25755 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7404SS |  | 0 | 288 | Warning
25756 | Inyo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25757 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7408SS | 0 | 268 | Warning
25758 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7407SS |  | 0 | 268 | Warning
25759 | Inyo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25760 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7411SS | 0 | 246 | Warning
25761 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7410SS |  | 0 | 246 | Warning
25762 | Inyo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25763 | Inyo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.32 | 234 | Warning
25766 | Inyo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7415 |  | 0.2 | 234 | Warning
25770 | Inyo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25773 | Inyo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 7422 |  | 0.2 | 466 | Warning
25774 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25776 | Inyo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7425 | 7427 | 0.2 | 405 | Warning
25777 | Inyo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7426 |  | 0 | 405 | Warning
25778 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25779 | Inyo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7430 | 0.2 | 405 | Warning
25780 | Inyo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7429 | 7431 | 0 | 405 | Warning
25781 | Inyo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7430 |  | 0 | 405 | Warning
25782 | Inyo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25783 | Inyo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7434 | 0 | 362 | Warning
25784 | Inyo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7433 | 7435 | 0 | 362 | Warning
25785 | Inyo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7434 |  | 0 | 362 | Warning
25786 | Inyo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25787 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25788 | Inyo CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 398 | 298d |  |  | 0.34 | 298 | Warning
25789 | Inyo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
25792 | Inyo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7441SS |  | 0.4 | 445 | Warning
25800 | Inyo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
25802 | Inyo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 7451SS | 7456,7453 | 0.2 | 298 | Warning
25803 | Inyo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7452 |  | 0 | 298 | Warning
25804 | Inyo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
25805 | Inyo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25806 | Inyo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7452 |  | 0 | 345 | Warning
25807 | Inyo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25808 | Inyo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25809 | Inyo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25810 | Inyo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25811 | Inyo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25812 | Inyo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25813 | Inyo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25814 | Inyo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25815 | Inyo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25816 | Inyo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25817 | Inyo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25818 | Inyo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25819 | Inyo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25822 | Inyo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25823 | Inyo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25824 | Inyo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25825 | Inyo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
25826 | Inyo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7485 | 0 | 234 | Warning
25827 | Inyo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7486 | 0 | 234 | Warning
25829 | Inyo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
25830 | Inyo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7491SF+30d |  | 0 | 309 | Warning
25831 | Inyo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7492SF+30d |  | 0 | 309 | Warning
25832 | Inyo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7493SF+30d |  | 0 | 309 | Warning
25833 | Inyo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7494SF+30d |  | 0 | 309 | Warning
25834 | Inyo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7495SF+30d |  | 0 | 309 | Warning
25835 | Inyo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7476 |  | 0 | 234 | Warning
25836 | Inyo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7477 |  | 0 | 234 | Warning
25837 | Inyo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
25838 | Inyo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7497FS+12d | 0 | 240 | Warning
25839 | Inyo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
25840 | Inyo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7497SF+60d | 0 | 250 | Warning
25841 | Inyo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7480SF+30d | 0 | 240 | Warning
25842 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7481SF+30d | 0 | 240 | Warning
25843 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7482SF+30d | 0 | 240 | Warning
25844 | Inyo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7483SF+30d | 0 | 240 | Warning
25845 | Inyo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7484SF+30d | 0 | 240 | Warning
25846 | Inyo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
25847 | Inyo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 7488FS+12d,7490SF+60d |  | 0 | 240 | Warning
25850 | Kern CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
25855 | Kern CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
25856 | Kern CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
25857 | Kern CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
25858 | Kern CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
25860 | Kern CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
25861 | Kern CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
25883 | Kern CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
25884 | Kern CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
25885 | Kern CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
25886 | Kern CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
25887 | Kern CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
25888 | Kern CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
25889 | Kern CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
25890 | Kern CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
25891 | Kern CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
25892 | Kern CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
25893 | Kern CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
25894 | Kern CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25895 | Kern CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
25902 | Kern CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
25903 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7554SS | 0 | 414 | Warning
25904 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7553SS |  | 0 | 414 | Warning
25905 | Kern CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 7556SS | 0 | 362 | Warning
25906 | Kern CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 7555SS |  | 0 | 362 | Warning
25907 | Kern CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
25908 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7559SS | 0 | 352 | Warning
25909 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7558SS |  | 0 | 352 | Warning
25910 | Kern CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
25911 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7562SS | 0 | 288 | Warning
25912 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7561SS |  | 0 | 288 | Warning
25913 | Kern CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
25914 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7565SS | 0 | 268 | Warning
25915 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7564SS |  | 0 | 268 | Warning
25916 | Kern CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
25917 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7568SS | 0 | 246 | Warning
25918 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7567SS |  | 0 | 246 | Warning
25919 | Kern CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
25920 | Kern CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.31 | 234 | Warning
25923 | Kern CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7572 |  | 0.2 | 234 | Warning
25927 | Kern CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25930 | Kern CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 7579 |  | 0.2 | 466 | Warning
25931 | Kern CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25933 | Kern CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7582 | 7584 | 0 | 405 | Warning
25934 | Kern CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7583 |  | 0 | 405 | Warning
25935 | Kern CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25936 | Kern CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7587 | 0.2 | 405 | Warning
25937 | Kern CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7586 | 7588 | 0 | 405 | Warning
25938 | Kern CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7587 |  | 0 | 405 | Warning
25939 | Kern CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
25940 | Kern CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7591 | 0 | 362 | Warning
25941 | Kern CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7590 | 7592 | 0 | 362 | Warning
25942 | Kern CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7591 |  | 0 | 362 | Warning
25943 | Kern CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
25944 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
25945 | Kern CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
25946 | Kern CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
25949 | Kern CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 7598 |  | 0 | 357 | Warning
25954 | Kern CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
25956 | Kern CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 7605 |  | 0 | 485 | Warning
25957 | Kern CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
25959 | Kern CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 7608SS | 7610,7613,7611SF+30d | 0 | 298 | Warning
25960 | Kern CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7609 |  | 0 | 298 | Warning
25961 | Kern CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7609SF+30d |  | 0 | 298 | Warning
25962 | Kern CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25963 | Kern CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7609 |  | 0 | 345 | Warning
25964 | Kern CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
25967 | Kern CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7616SS |  | 0 | 445 | Warning
25975 | Kern CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
25977 | Kern CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 7626SS | 7631,7628 | 0 | 298 | Warning
25978 | Kern CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7627 |  | 0 | 298 | Warning
25979 | Kern CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
25980 | Kern CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
25981 | Kern CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7627 |  | 0 | 345 | Warning
25982 | Kern CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
25983 | Kern CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25984 | Kern CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25985 | Kern CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25986 | Kern CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25987 | Kern CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25988 | Kern CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25989 | Kern CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25990 | Kern CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25991 | Kern CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25992 | Kern CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25993 | Kern CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
25994 | Kern CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
25997 | Kern CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
25998 | Kern CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
25999 | Kern CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26000 | Kern CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26001 | Kern CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7660 | 0 | 234 | Warning
26002 | Kern CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7661 | 0 | 234 | Warning
26004 | Kern CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26005 | Kern CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7666SF+30d |  | 0 | 309 | Warning
26006 | Kern CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7667SF+30d |  | 0 | 309 | Warning
26007 | Kern CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7668SF+30d |  | 0 | 309 | Warning
26008 | Kern CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7669SF+30d |  | 0 | 309 | Warning
26009 | Kern CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7670SF+30d |  | 0 | 309 | Warning
26010 | Kern CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7651 |  | 0 | 234 | Warning
26011 | Kern CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7652 |  | 0 | 234 | Warning
26012 | Kern CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26013 | Kern CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7672FS+12d | 0 | 240 | Warning
26014 | Kern CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26015 | Kern CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7672SF+60d | 0 | 250 | Warning
26016 | Kern CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7655SF+30d | 0 | 240 | Warning
26017 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7656SF+30d | 0 | 240 | Warning
26018 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7657SF+30d | 0 | 240 | Warning
26019 | Kern CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7658SF+30d | 0 | 240 | Warning
26020 | Kern CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7659SF+30d | 0 | 240 | Warning
26021 | Kern CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26022 | Kern CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 7663FS+12d,7665SF+60d |  | 0 | 240 | Warning
26025 | Lake CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.6 | 245 | Warning
26030 | Lake CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.4 | 405 | Warning
26031 | Lake CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26032 | Lake CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26033 | Lake CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26035 | Lake CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
26036 | Lake CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26058 | Lake CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26059 | Lake CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26060 | Lake CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26061 | Lake CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26062 | Lake CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26063 | Lake CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26064 | Lake CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26065 | Lake CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26066 | Lake CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26067 | Lake CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26068 | Lake CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26069 | Lake CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26070 | Lake CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26077 | Lake CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
26078 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7729SS | 0 | 414 | Warning
26079 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7728SS |  | 0 | 414 | Warning
26080 | Lake CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 299d | 3885FS+29d | 7731 | 0 | 299 | Warning
26081 | Lake CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | May 4, 2026 8:00 AM | July 31, 2026 5:00 PM | 63 | 299d | 7730 |  | 0 | 299 | Warning
26082 | Lake CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26083 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7734SS | 0 | 352 | Warning
26084 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7733SS |  | 0 | 352 | Warning
26085 | Lake CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26086 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7737SS | 0 | 288 | Warning
26087 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7736SS |  | 0 | 288 | Warning
26088 | Lake CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26089 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7740SS | 0 | 268 | Warning
26090 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7739SS |  | 0 | 268 | Warning
26091 | Lake CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26092 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7743SS | 0 | 246 | Warning
26093 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7742SS |  | 0 | 246 | Warning
26094 | Lake CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26095 | Lake CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.47 | 234 | Warning
26098 | Lake CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7747 |  | 0.6 | 234 | Warning
26102 | Lake CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26105 | Lake CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 7754 |  | 0.4 | 466 | Warning
26106 | Lake CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26108 | Lake CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7757 | 7759 | 0 | 405 | Warning
26109 | Lake CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7758 |  | 0 | 405 | Warning
26110 | Lake CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26111 | Lake CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7762 | 0 | 405 | Warning
26112 | Lake CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7761 | 7763 | 0 | 405 | Warning
26113 | Lake CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7762 |  | 0 | 405 | Warning
26114 | Lake CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26115 | Lake CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7766 | 0 | 362 | Warning
26116 | Lake CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7765 | 7767 | 0 | 362 | Warning
26117 | Lake CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7766 |  | 0 | 362 | Warning
26118 | Lake CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26119 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26120 | Lake CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.29 | 298 | Warning
26121 | Lake CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
26123 | Lake CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 7772SS | 7774 | 0.2 | 357 | Warning
26124 | Lake CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 7773 |  | 0 | 357 | Warning
26132 | Lake CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
26134 | Lake CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 7783SS | 7785,7788,7786SF+30d | 0 | 298 | Warning
26135 | Lake CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7784 |  | 0 | 298 | Warning
26136 | Lake CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7784SF+30d |  | 0 | 298 | Warning
26137 | Lake CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26138 | Lake CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7784 |  | 0 | 345 | Warning
26139 | Lake CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.31 | 445 | Warning
26141 | Lake CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d | 7790SS | 7792SS | 0 | 445 | Warning
26142 | Lake CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7791SS |  | 0 | 445 | Warning
26147 | Lake CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.84 | 508 | Warning
26149 | Lake CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 7798 |  | 0.6 | 508 | Warning
26150 | Lake CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.05 | 298 | Warning
26151 | Lake CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 7795,7802SS | 0.6 | 508 | Warning
26152 | Lake CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 7801SS | 7806,7803 | 0 | 298 | Warning
26153 | Lake CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7802 |  | 0 | 298 | Warning
26154 | Lake CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
26155 | Lake CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26156 | Lake CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7802 |  | 0 | 345 | Warning
26157 | Lake CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
26158 | Lake CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26159 | Lake CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26160 | Lake CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26161 | Lake CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26162 | Lake CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26163 | Lake CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26164 | Lake CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26165 | Lake CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26166 | Lake CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26167 | Lake CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26168 | Lake CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26169 | Lake CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
26172 | Lake CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
26173 | Lake CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
26174 | Lake CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26175 | Lake CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26176 | Lake CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7835 | 0 | 234 | Warning
26177 | Lake CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7836 | 0 | 234 | Warning
26179 | Lake CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26180 | Lake CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7841SF+30d |  | 0 | 309 | Warning
26181 | Lake CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7842SF+30d |  | 0 | 309 | Warning
26182 | Lake CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7843SF+30d |  | 0 | 309 | Warning
26183 | Lake CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7844SF+30d |  | 0 | 309 | Warning
26184 | Lake CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7845SF+30d |  | 0 | 309 | Warning
26185 | Lake CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7826 |  | 0 | 234 | Warning
26186 | Lake CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7827 |  | 0 | 234 | Warning
26187 | Lake CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26188 | Lake CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7847FS+12d | 0 | 240 | Warning
26189 | Lake CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26190 | Lake CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7847SF+60d | 0 | 250 | Warning
26191 | Lake CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7830SF+30d | 0 | 240 | Warning
26192 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7831SF+30d | 0 | 240 | Warning
26193 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7832SF+30d | 0 | 240 | Warning
26194 | Lake CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7833SF+30d | 0 | 240 | Warning
26195 | Lake CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7834SF+30d | 0 | 240 | Warning
26196 | Lake CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26197 | Lake CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 7838FS+12d,7840SF+60d |  | 0 | 240 | Warning
26200 | Lassen CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
26205 | Lassen CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
26206 | Lassen CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26207 | Lassen CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26208 | Lassen CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26210 | Lassen CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
26211 | Lassen CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26233 | Lassen CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26234 | Lassen CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26235 | Lassen CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26236 | Lassen CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26237 | Lassen CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26238 | Lassen CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26239 | Lassen CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26240 | Lassen CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26241 | Lassen CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26242 | Lassen CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26243 | Lassen CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26244 | Lassen CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26245 | Lassen CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26252 | Lassen CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
26253 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7904SS | 0 | 414 | Warning
26254 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 7903SS |  | 0 | 414 | Warning
26255 | Lassen CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 7906SS | 0 | 362 | Warning
26256 | Lassen CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 7905SS |  | 0 | 362 | Warning
26257 | Lassen CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26258 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7909SS | 0 | 352 | Warning
26259 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 7908SS |  | 0 | 352 | Warning
26260 | Lassen CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26261 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7912SS | 0 | 288 | Warning
26262 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7911SS |  | 0 | 288 | Warning
26263 | Lassen CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26264 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7915SS | 0 | 268 | Warning
26265 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 7914SS |  | 0 | 268 | Warning
26266 | Lassen CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26267 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7918SS | 0 | 246 | Warning
26268 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 7917SS |  | 0 | 246 | Warning
26269 | Lassen CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26270 | Lassen CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.52 | 234 | Warning
26273 | Lassen CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 7922 |  | 0.6 | 234 | Warning
26277 | Lassen CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26281 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26283 | Lassen CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 7932 | 7934 | 0 | 405 | Warning
26284 | Lassen CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 7933 |  | 0 | 405 | Warning
26285 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26286 | Lassen CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7937 | 0.95 | 405 | Warning
26287 | Lassen CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 7936 | 7938 | 0 | 405 | Warning
26288 | Lassen CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 7937 |  | 0 | 405 | Warning
26289 | Lassen CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26290 | Lassen CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7941 | 0 | 362 | Warning
26291 | Lassen CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 7940 | 7942 | 0 | 362 | Warning
26292 | Lassen CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 7941 |  | 0 | 362 | Warning
26293 | Lassen CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26294 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26295 | Lassen CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
26296 | Lassen CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
26297 | Lassen CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 7948SS | 0.8 | 405 | Warning
26298 | Lassen CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 7947SS | 7949 | 0.4 | 357 | Warning
26299 | Lassen CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 7948 |  | 0 | 357 | Warning
26307 | Lassen CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
26309 | Lassen CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 7958SS | 7960,7963,7961SF+30d | 0 | 298 | Warning
26310 | Lassen CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 7959 |  | 0 | 298 | Warning
26311 | Lassen CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7959SF+30d |  | 0 | 298 | Warning
26312 | Lassen CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26313 | Lassen CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 7959 |  | 0 | 345 | Warning
26314 | Lassen CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
26317 | Lassen CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 7966SS |  | 0.4 | 445 | Warning
26325 | Lassen CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
26326 | Lassen CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26327 | Lassen CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26328 | Lassen CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26329 | Lassen CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26330 | Lassen CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26331 | Lassen CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26332 | Lassen CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26333 | Lassen CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26334 | Lassen CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26335 | Lassen CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26336 | Lassen CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26337 | Lassen CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
26340 | Lassen CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
26341 | Lassen CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
26342 | Lassen CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26343 | Lassen CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26344 | Lassen CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8003 | 0 | 234 | Warning
26345 | Lassen CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8004 | 0 | 234 | Warning
26347 | Lassen CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26348 | Lassen CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8009SF+30d |  | 0 | 309 | Warning
26349 | Lassen CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8010SF+30d |  | 0 | 309 | Warning
26350 | Lassen CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8011SF+30d |  | 0 | 309 | Warning
26351 | Lassen CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8012SF+30d |  | 0 | 309 | Warning
26352 | Lassen CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8013SF+30d |  | 0 | 309 | Warning
26353 | Lassen CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7994 |  | 0 | 234 | Warning
26354 | Lassen CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 7995 |  | 0 | 234 | Warning
26355 | Lassen CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26356 | Lassen CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8015FS+12d | 0 | 240 | Warning
26357 | Lassen CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26358 | Lassen CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8015SF+60d | 0 | 250 | Warning
26359 | Lassen CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7998SF+30d | 0 | 240 | Warning
26360 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7999SF+30d | 0 | 240 | Warning
26361 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8000SF+30d | 0 | 240 | Warning
26362 | Lassen CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8001SF+30d | 0 | 240 | Warning
26363 | Lassen CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8002SF+30d | 0 | 240 | Warning
26364 | Lassen CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26365 | Lassen CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8006FS+12d,8008SF+60d |  | 0 | 240 | Warning
26368 | Los Angeles CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
26373 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
26374 | Los Angeles CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26375 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26376 | Los Angeles CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26378 | Los Angeles CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
26379 | Los Angeles CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26401 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26402 | Los Angeles CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26403 | Los Angeles CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26404 | Los Angeles CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26405 | Los Angeles CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26406 | Los Angeles CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26407 | Los Angeles CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26408 | Los Angeles CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26409 | Los Angeles CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26410 | Los Angeles CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26411 | Los Angeles CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26412 | Los Angeles CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26413 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26420 | Los Angeles CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
26421 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8072SS | 0 | 414 | Warning
26422 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8071SS |  | 0 | 414 | Warning
26423 | Los Angeles CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8074SS | 0 | 362 | Warning
26424 | Los Angeles CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8073SS |  | 0 | 362 | Warning
26425 | Los Angeles CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26426 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8077SS | 0 | 352 | Warning
26427 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8076SS |  | 0 | 352 | Warning
26428 | Los Angeles CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26429 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8080SS | 0 | 288 | Warning
26430 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8079SS |  | 0 | 288 | Warning
26431 | Los Angeles CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26432 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8083SS | 0 | 268 | Warning
26433 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8082SS |  | 0 | 268 | Warning
26434 | Los Angeles CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26435 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8086SS | 0 | 246 | Warning
26436 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8085SS |  | 0 | 246 | Warning
26437 | Los Angeles CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26438 | Los Angeles CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.39 | 234 | Warning
26441 | Los Angeles CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8090 |  | 0.4 | 234 | Warning
26445 | Los Angeles CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26448 | Los Angeles CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 8097 |  | 0.2 | 466 | Warning
26449 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26451 | Los Angeles CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8100 | 8102 | 0 | 405 | Warning
26452 | Los Angeles CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8101 |  | 0 | 405 | Warning
26453 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26454 | Los Angeles CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8105 | 0 | 405 | Warning
26455 | Los Angeles CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8104 | 8106 | 0 | 405 | Warning
26456 | Los Angeles CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8105 |  | 0 | 405 | Warning
26457 | Los Angeles CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26458 | Los Angeles CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8109 | 0 | 362 | Warning
26459 | Los Angeles CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8108 | 8110 | 0 | 362 | Warning
26460 | Los Angeles CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8109 |  | 0 | 362 | Warning
26461 | Los Angeles CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26462 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26463 | Los Angeles CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.26 | 298 | Warning
26464 | Los Angeles CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.29 | 357 | Warning
26465 | Los Angeles CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 8116SS | 0.4 | 405 | Warning
26466 | Los Angeles CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 8115SS | 8117 | 0.2 | 357 | Warning
26467 | Los Angeles CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 8116 |  | 0 | 357 | Warning
26472 | Los Angeles CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.12 | 485 | Warning
26473 | Los Angeles CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 485d | 8121 | 8124,8126SS | 0.2 | 485 | Warning
26474 | Los Angeles CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 8123 |  | 0 | 485 | Warning
26475 | Los Angeles CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.01 | 298 | Warning
26476 | Los Angeles CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 8123SS | 8127SS | 0.2 | 508 | Warning
26477 | Los Angeles CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 8126SS | 8128,8131,8129SF+30d | 0 | 298 | Warning
26478 | Los Angeles CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8127 |  | 0 | 298 | Warning
26479 | Los Angeles CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8127SF+30d |  | 0 | 298 | Warning
26480 | Los Angeles CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26481 | Los Angeles CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8127 |  | 0 | 345 | Warning
26482 | Los Angeles CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
26485 | Los Angeles CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 8134SS |  | 0 | 445 | Warning
26493 | Los Angeles CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.11 | 298 | Warning
26494 | Los Angeles CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 8138,8145SS | 0.6 | 508 | Warning
26495 | Los Angeles CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 8144SS | 8149,8146 | 0.2 | 298 | Warning
26496 | Los Angeles CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8145 |  | 0 | 298 | Warning
26497 | Los Angeles CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
26498 | Los Angeles CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26499 | Los Angeles CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8145 |  | 0 | 345 | Warning
26500 | Los Angeles CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
26501 | Los Angeles CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26502 | Los Angeles CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26503 | Los Angeles CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26504 | Los Angeles CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26505 | Los Angeles CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26506 | Los Angeles CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26507 | Los Angeles CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26508 | Los Angeles CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26509 | Los Angeles CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26510 | Los Angeles CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26511 | Los Angeles CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26512 | Los Angeles CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
26515 | Los Angeles CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
26516 | Los Angeles CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
26517 | Los Angeles CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26518 | Los Angeles CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26519 | Los Angeles CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8178 | 0 | 234 | Warning
26520 | Los Angeles CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8179 | 0 | 234 | Warning
26522 | Los Angeles CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26523 | Los Angeles CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8184SF+30d |  | 0 | 309 | Warning
26524 | Los Angeles CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8185SF+30d |  | 0 | 309 | Warning
26525 | Los Angeles CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8186SF+30d |  | 0 | 309 | Warning
26526 | Los Angeles CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8187SF+30d |  | 0 | 309 | Warning
26527 | Los Angeles CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8188SF+30d |  | 0 | 309 | Warning
26528 | Los Angeles CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8169 |  | 0 | 234 | Warning
26529 | Los Angeles CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8170 |  | 0 | 234 | Warning
26530 | Los Angeles CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26531 | Los Angeles CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8190FS+12d | 0 | 240 | Warning
26532 | Los Angeles CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26533 | Los Angeles CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8190SF+60d | 0 | 250 | Warning
26534 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8173SF+30d | 0 | 240 | Warning
26535 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8174SF+30d | 0 | 240 | Warning
26536 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8175SF+30d | 0 | 240 | Warning
26537 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8176SF+30d | 0 | 240 | Warning
26538 | Los Angeles CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8177SF+30d | 0 | 240 | Warning
26539 | Los Angeles CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26540 | Los Angeles CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8181FS+12d,8183SF+60d |  | 0 | 240 | Warning
26543 | Madera CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
26548 | Madera CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
26549 | Madera CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26550 | Madera CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26551 | Madera CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26553 | Madera CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
26554 | Madera CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26576 | Madera CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26577 | Madera CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26578 | Madera CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26579 | Madera CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26580 | Madera CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26581 | Madera CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26582 | Madera CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26583 | Madera CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26584 | Madera CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26585 | Madera CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26586 | Madera CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26587 | Madera CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26588 | Madera CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26595 | Madera CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
26596 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8247SS | 0 | 414 | Warning
26597 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8246SS |  | 0 | 414 | Warning
26598 | Madera CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8249SS | 0 | 362 | Warning
26599 | Madera CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8248SS |  | 0 | 362 | Warning
26600 | Madera CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26601 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8252SS | 0 | 352 | Warning
26602 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8251SS |  | 0 | 352 | Warning
26603 | Madera CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26604 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8255SS | 0 | 288 | Warning
26605 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8254SS |  | 0 | 288 | Warning
26606 | Madera CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26607 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8258SS | 0 | 268 | Warning
26608 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8257SS |  | 0 | 268 | Warning
26609 | Madera CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26610 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8261SS | 0 | 246 | Warning
26611 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8260SS |  | 0 | 246 | Warning
26612 | Madera CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26613 | Madera CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.48 | 234 | Warning
26616 | Madera CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8265 |  | 0.6 | 234 | Warning
26620 | Madera CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26623 | Madera CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 8272 |  | 0.2 | 466 | Warning
26624 | Madera CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26626 | Madera CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8275 | 8277 | 0.2 | 405 | Warning
26627 | Madera CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8276 |  | 0 | 405 | Warning
26628 | Madera CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26629 | Madera CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8280 | 0.2 | 405 | Warning
26630 | Madera CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8279 | 8281 | 0 | 405 | Warning
26631 | Madera CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8280 |  | 0 | 405 | Warning
26632 | Madera CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26633 | Madera CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8284 | 0 | 362 | Warning
26634 | Madera CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8283 | 8285 | 0 | 362 | Warning
26635 | Madera CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8284 |  | 0 | 362 | Warning
26636 | Madera CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26637 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26638 | Madera CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.48 | 298 | Warning
26646 | Madera CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
26648 | Madera CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 8297 |  | 0.2 | 485 | Warning
26649 | Madera CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
26651 | Madera CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 8300SS | 8302,8305,8303SF+30d | 0 | 298 | Warning
26652 | Madera CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8301 |  | 0 | 298 | Warning
26653 | Madera CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8301SF+30d |  | 0 | 298 | Warning
26654 | Madera CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26655 | Madera CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8301 |  | 0 | 345 | Warning
26667 | Madera CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
26669 | Madera CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 8318SS | 8323,8320 | 0 | 298 | Warning
26670 | Madera CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8319 |  | 0 | 298 | Warning
26671 | Madera CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
26672 | Madera CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26673 | Madera CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8319 |  | 0 | 345 | Warning
26674 | Madera CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
26675 | Madera CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26676 | Madera CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26677 | Madera CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26678 | Madera CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26679 | Madera CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26680 | Madera CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26681 | Madera CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26682 | Madera CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26683 | Madera CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26684 | Madera CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26685 | Madera CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26686 | Madera CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
26689 | Madera CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
26690 | Madera CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
26691 | Madera CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26692 | Madera CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26693 | Madera CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8352 | 0 | 234 | Warning
26694 | Madera CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8353 | 0 | 234 | Warning
26696 | Madera CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26697 | Madera CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8358SF+30d |  | 0 | 309 | Warning
26698 | Madera CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8359SF+30d |  | 0 | 309 | Warning
26699 | Madera CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8360SF+30d |  | 0 | 309 | Warning
26700 | Madera CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8361SF+30d |  | 0 | 309 | Warning
26701 | Madera CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8362SF+30d |  | 0 | 309 | Warning
26702 | Madera CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8343 |  | 0 | 234 | Warning
26703 | Madera CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8344 |  | 0 | 234 | Warning
26704 | Madera CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26705 | Madera CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8364FS+12d | 0 | 240 | Warning
26706 | Madera CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26707 | Madera CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8364SF+60d | 0 | 250 | Warning
26708 | Madera CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8347SF+30d | 0 | 240 | Warning
26709 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8348SF+30d | 0 | 240 | Warning
26710 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8349SF+30d | 0 | 240 | Warning
26711 | Madera CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8350SF+30d | 0 | 240 | Warning
26712 | Madera CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8351SF+30d | 0 | 240 | Warning
26713 | Madera CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26714 | Madera CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8355FS+12d,8357SF+60d |  | 0 | 240 | Warning
26717 | Marin CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
26722 | Marin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
26723 | Marin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26724 | Marin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26725 | Marin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26727 | Marin CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
26728 | Marin CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26750 | Marin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26751 | Marin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26752 | Marin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26753 | Marin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26754 | Marin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26755 | Marin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26756 | Marin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26757 | Marin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26758 | Marin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26759 | Marin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26760 | Marin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26761 | Marin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26762 | Marin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26769 | Marin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
26770 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8421SS | 0 | 414 | Warning
26771 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8420SS |  | 0 | 414 | Warning
26772 | Marin CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8423SS | 0 | 362 | Warning
26773 | Marin CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8422SS |  | 0 | 362 | Warning
26774 | Marin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26775 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8426SS | 0 | 352 | Warning
26776 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8425SS |  | 0 | 352 | Warning
26777 | Marin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26778 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8429SS | 0 | 288 | Warning
26779 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8428SS |  | 0 | 288 | Warning
26780 | Marin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26781 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8432SS | 0 | 268 | Warning
26782 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8431SS |  | 0 | 268 | Warning
26783 | Marin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26784 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8435SS | 0 | 246 | Warning
26785 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8434SS |  | 0 | 246 | Warning
26786 | Marin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26787 | Marin CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.58 | 234 | Warning
26790 | Marin CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8439 |  | 0.8 | 234 | Warning
26794 | Marin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26797 | Marin CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 8446 |  | 0.2 | 466 | Warning
26798 | Marin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26800 | Marin CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8449 | 8451 | 0.2 | 405 | Warning
26801 | Marin CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8450 |  | 0 | 405 | Warning
26802 | Marin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26804 | Marin CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8453 | 8455 | 0 | 405 | Warning
26805 | Marin CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8454 |  | 0 | 405 | Warning
26806 | Marin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26807 | Marin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8458 | 0 | 362 | Warning
26808 | Marin CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8457 | 8459 | 0 | 362 | Warning
26809 | Marin CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8458 |  | 0 | 362 | Warning
26810 | Marin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26811 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26812 | Marin CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.46 | 298 | Warning
26813 | Marin CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
26816 | Marin CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 8465 |  | 0.6 | 357 | Warning
26824 | Marin CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
26826 | Marin CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 8475SS | 8477,8480,8478SF+30d | 0.2 | 298 | Warning
26827 | Marin CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8476 |  | 0 | 298 | Warning
26828 | Marin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8476SF+30d |  | 0 | 298 | Warning
26829 | Marin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26830 | Marin CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8476 |  | 0 | 345 | Warning
26831 | Marin CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.57 | 445 | Warning
26833 | Marin CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 8482SS | 8484SS | 0.6 | 485 | Warning
26834 | Marin CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 8483SS |  | 0.2 | 445 | Warning
26842 | Marin CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
26844 | Marin CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 8493SS | 8498,8495 | 0.2 | 298 | Warning
26845 | Marin CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8494 |  | 0 | 298 | Warning
26846 | Marin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
26847 | Marin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
26848 | Marin CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8494 |  | 0 | 345 | Warning
26849 | Marin CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
26850 | Marin CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26851 | Marin CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26852 | Marin CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26853 | Marin CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26854 | Marin CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26855 | Marin CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26856 | Marin CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26857 | Marin CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26858 | Marin CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26859 | Marin CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26860 | Marin CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
26861 | Marin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
26864 | Marin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | 384 | Warning
26865 | Marin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0.2 | 320 | Warning
26866 | Marin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26867 | Marin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
26868 | Marin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8527 | 0 | 234 | Warning
26869 | Marin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8528 | 0 | 234 | Warning
26871 | Marin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
26872 | Marin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8533SF+30d |  | 0 | 309 | Warning
26873 | Marin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8534SF+30d |  | 0 | 309 | Warning
26874 | Marin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8535SF+30d |  | 0 | 309 | Warning
26875 | Marin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8536SF+30d |  | 0 | 309 | Warning
26876 | Marin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8537SF+30d |  | 0 | 309 | Warning
26877 | Marin CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8518 |  | 0 | 234 | Warning
26878 | Marin CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8519 |  | 0 | 234 | Warning
26879 | Marin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
26880 | Marin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8539FS+12d | 0 | 240 | Warning
26881 | Marin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
26882 | Marin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8539SF+60d | 0 | 250 | Warning
26883 | Marin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8522SF+30d | 0 | 240 | Warning
26884 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8523SF+30d | 0 | 240 | Warning
26885 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8524SF+30d | 0 | 240 | Warning
26886 | Marin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8525SF+30d | 0 | 240 | Warning
26887 | Marin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8526SF+30d | 0 | 240 | Warning
26888 | Marin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
26889 | Marin CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8530FS+12d,8532SF+60d |  | 0 | 240 | Warning
26892 | Mariposa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
26897 | Mariposa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
26898 | Mariposa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
26899 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
26900 | Mariposa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
26902 | Mariposa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
26903 | Mariposa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
26925 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
26926 | Mariposa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
26927 | Mariposa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
26928 | Mariposa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
26929 | Mariposa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
26930 | Mariposa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
26931 | Mariposa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
26932 | Mariposa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
26933 | Mariposa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
26934 | Mariposa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
26935 | Mariposa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
26936 | Mariposa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26937 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
26944 | Mariposa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
26945 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8596SS | 0 | 414 | Warning
26946 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8595SS |  | 0 | 414 | Warning
26947 | Mariposa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8598SS | 0 | 362 | Warning
26948 | Mariposa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8597SS |  | 0 | 362 | Warning
26949 | Mariposa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
26950 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8601SS | 0 | 352 | Warning
26951 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8600SS |  | 0 | 352 | Warning
26952 | Mariposa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
26953 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8604SS | 0 | 288 | Warning
26954 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8603SS |  | 0 | 288 | Warning
26955 | Mariposa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
26956 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8607SS | 0 | 268 | Warning
26957 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8606SS |  | 0 | 268 | Warning
26958 | Mariposa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
26959 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8610SS | 0 | 246 | Warning
26960 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8609SS |  | 0 | 246 | Warning
26961 | Mariposa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
26962 | Mariposa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.33 | 234 | Warning
26965 | Mariposa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8614 |  | 0.2 | 234 | Warning
26969 | Mariposa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26972 | Mariposa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 8621 |  | 0 | 466 | Warning
26973 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26975 | Mariposa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8624 | 8626 | 0.2 | 405 | Warning
26976 | Mariposa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8625 |  | 0 | 405 | Warning
26977 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26979 | Mariposa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8628 | 8630 | 0 | 405 | Warning
26980 | Mariposa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8629 |  | 0 | 405 | Warning
26981 | Mariposa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
26982 | Mariposa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8633 | 0 | 362 | Warning
26983 | Mariposa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8632 | 8634 | 0 | 362 | Warning
26984 | Mariposa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8633 |  | 0 | 362 | Warning
26985 | Mariposa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
26986 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
26987 | Mariposa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.43 | 298 | Warning
26988 | Mariposa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
26991 | Mariposa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 8640 |  | 0 | 357 | Warning
26999 | Mariposa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
27001 | Mariposa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 8650SS | 8652,8655,8653SF+30d | 0 | 298 | Warning
27002 | Mariposa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8651 |  | 0 | 298 | Warning
27003 | Mariposa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8651SF+30d |  | 0 | 298 | Warning
27004 | Mariposa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27005 | Mariposa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8651 |  | 0 | 345 | Warning
27006 | Mariposa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
27009 | Mariposa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 8658SS |  | 0 | 445 | Warning
27017 | Mariposa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
27019 | Mariposa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 8668SS | 8673,8670 | 0 | 298 | Warning
27020 | Mariposa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8669 |  | 0 | 298 | Warning
27021 | Mariposa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
27022 | Mariposa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27023 | Mariposa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8669 |  | 0 | 345 | Warning
27024 | Mariposa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27025 | Mariposa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27026 | Mariposa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27027 | Mariposa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27028 | Mariposa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27029 | Mariposa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27030 | Mariposa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27031 | Mariposa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27032 | Mariposa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27033 | Mariposa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27034 | Mariposa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27035 | Mariposa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27036 | Mariposa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27039 | Mariposa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
27040 | Mariposa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27041 | Mariposa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27042 | Mariposa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27043 | Mariposa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8702 | 0 | 234 | Warning
27044 | Mariposa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8703 | 0 | 234 | Warning
27046 | Mariposa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27047 | Mariposa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8708SF+30d |  | 0 | 309 | Warning
27048 | Mariposa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8709SF+30d |  | 0 | 309 | Warning
27049 | Mariposa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8710SF+30d |  | 0 | 309 | Warning
27050 | Mariposa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8711SF+30d |  | 0 | 309 | Warning
27051 | Mariposa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8712SF+30d |  | 0 | 309 | Warning
27052 | Mariposa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8693 |  | 0 | 234 | Warning
27053 | Mariposa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8694 |  | 0 | 234 | Warning
27054 | Mariposa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27055 | Mariposa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8714FS+12d | 0 | 240 | Warning
27056 | Mariposa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27057 | Mariposa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8714SF+60d | 0 | 250 | Warning
27058 | Mariposa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8697SF+30d | 0 | 240 | Warning
27059 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8698SF+30d | 0 | 240 | Warning
27060 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8699SF+30d | 0 | 240 | Warning
27061 | Mariposa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8700SF+30d | 0 | 240 | Warning
27062 | Mariposa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8701SF+30d | 0 | 240 | Warning
27063 | Mariposa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27064 | Mariposa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8705FS+12d,8707SF+60d |  | 0 | 240 | Warning
27067 | Mendocino CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
27072 | Mendocino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
27073 | Mendocino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27074 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27075 | Mendocino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27077 | Mendocino CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
27078 | Mendocino CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
27100 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
27101 | Mendocino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27102 | Mendocino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27103 | Mendocino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27104 | Mendocino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27105 | Mendocino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27106 | Mendocino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27107 | Mendocino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27108 | Mendocino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27109 | Mendocino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27110 | Mendocino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27111 | Mendocino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27112 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27119 | Mendocino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
27120 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8771SS | 0 | 414 | Warning
27121 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8770SS |  | 0 | 414 | Warning
27122 | Mendocino CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8773SS | 0 | 362 | Warning
27123 | Mendocino CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8772SS |  | 0 | 362 | Warning
27124 | Mendocino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27125 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8776SS | 0 | 352 | Warning
27126 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8775SS |  | 0 | 352 | Warning
27127 | Mendocino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27128 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8779SS | 0 | 288 | Warning
27129 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8778SS |  | 0 | 288 | Warning
27130 | Mendocino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27131 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8782SS | 0 | 268 | Warning
27132 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8781SS |  | 0 | 268 | Warning
27133 | Mendocino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27134 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8785SS | 0 | 246 | Warning
27135 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8784SS |  | 0 | 246 | Warning
27136 | Mendocino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27137 | Mendocino CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.42 | 234 | Warning
27140 | Mendocino CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8789 |  | 0.4 | 234 | Warning
27144 | Mendocino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27148 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27150 | Mendocino CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8799 | 8801 | 0 | 405 | Warning
27151 | Mendocino CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8800 |  | 0 | 405 | Warning
27152 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27153 | Mendocino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8804 | 0 | 405 | Warning
27154 | Mendocino CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8803 | 8805 | 0 | 405 | Warning
27155 | Mendocino CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8804 |  | 0 | 405 | Warning
27156 | Mendocino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27157 | Mendocino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8808 | 0 | 362 | Warning
27158 | Mendocino CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8807 | 8809 | 0 | 362 | Warning
27159 | Mendocino CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8808 |  | 0 | 362 | Warning
27160 | Mendocino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
27161 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
27162 | Mendocino CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.05 | 298 | Warning
27163 | Mendocino CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0 | 357 | Warning
27164 | Mendocino CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d |  | 8815SS | 0 | 357 | Warning
27165 | Mendocino CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 8814SS | 8816 | 0 | 357 | Warning
27166 | Mendocino CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 8815 |  | 0 | 357 | Warning
27167 | Mendocino CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 44 | 592d |  |  | 0.6 | 592 | Warning
27168 | Mendocino CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 | 544d |  |  | 0.14 | 544 | Warning
27169 | Mendocino CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | January 6, 2025 8:00 AM | April 8, 2025 5:00 PM | 64 | 630d |  |  | 0.2 | 630 | Warning
27170 | Mendocino CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | January 6, 2025 8:00 AM | February 13, 2025 5:00 PM | 28 | 420d |  | 8822 | 0 | 420 | Warning
27171 | Mendocino CW-Determine priority for Organization-specific custom reports | February 14, 2025 8:00 AM | May 9, 2025 5:00 PM | 59 | 420d |  |  | 0 | 420 | Warning
27172 | Mendocino CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | February 14, 2025 8:00 AM | April 8, 2025 5:00 PM | 36 | 420d | 8820 | 8823,8825SS | 0 | 420 | Warning
27173 | Mendocino CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | April 9, 2025 8:00 AM | May 9, 2025 5:00 PM | 23 | 607d | 8822 |  | 0 | 607 | Warning
27174 | Mendocino CW-Execute plan for transition of custom reports from Business Objects to Tableau | February 14, 2025 8:00 AM | August 3, 2026 5:00 PM | 368 | 298d |  |  | 0 | 298 | Warning
27175 | Mendocino CW-Develop Plan for Timeline of Reports Creation in Tableau | February 14, 2025 8:00 AM | April 8, 2025 5:00 PM | 36 | 420d | 8822SS | 8826SS | 0 | 420 | Warning
27176 | Mendocino CW-Create organization-specific reports for process simulation bulk upload | February 14, 2025 8:00 AM | November 3, 2025 5:00 PM | 182 | 420d | 8825SS | 8827,8830,8828SF+30d | 0 | 420 | Warning
27177 | Mendocino CW-Continue development of organization-specific reports for production bulk upload, if necessary | November 4, 2025 8:00 AM | February 6, 2026 5:00 PM | 64 | 420d | 8826 |  | 0 | 420 | Warning
27178 | Mendocino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8826SF+30d |  | 0 | 298 | Warning
27179 | Mendocino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27180 | Mendocino CW-POC or Organization Leadership to sign off on report creation completion | November 4, 2025 8:00 AM | November 28, 2025 5:00 PM | 17 | 467d | 8826 |  | 0 | 467 | Warning
27181 | Mendocino CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0 | 445 | Warning
27182 | Mendocino CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d |  | 8833SS | 0 | 445 | Warning
27183 | Mendocino CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d | 8832SS | 8834SS | 0 | 445 | Warning
27184 | Mendocino CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 8833SS |  | 0 | 445 | Warning
27189 | Mendocino CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0 | 508 | Warning
27190 | Mendocino CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 30 | 508d | 8838 | 8841 | 0 | 508 | Warning
27191 | Mendocino CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 8840 |  | 0 | 508 | Warning
27192 | Mendocino CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0 | 298 | Warning
27193 | Mendocino CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 298d |  | 8837,8844SS | 0 | 298 | Warning
27194 | Mendocino CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 8843SS | 8848,8845 | 0 | 298 | Warning
27195 | Mendocino CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 8844 |  | 0 | 298 | Warning
27196 | Mendocino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
27197 | Mendocino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27198 | Mendocino CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 8844 |  | 0 | 345 | Warning
27199 | Mendocino CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27200 | Mendocino CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27201 | Mendocino CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27202 | Mendocino CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27203 | Mendocino CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27204 | Mendocino CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27205 | Mendocino CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27206 | Mendocino CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27207 | Mendocino CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27208 | Mendocino CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27209 | Mendocino CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27210 | Mendocino CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27211 | Mendocino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27214 | Mendocino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
27215 | Mendocino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27216 | Mendocino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27217 | Mendocino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27218 | Mendocino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8877 | 0 | 234 | Warning
27219 | Mendocino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8878 | 0 | 234 | Warning
27221 | Mendocino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27222 | Mendocino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8883SF+30d |  | 0 | 309 | Warning
27223 | Mendocino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8884SF+30d |  | 0 | 309 | Warning
27224 | Mendocino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8885SF+30d |  | 0 | 309 | Warning
27225 | Mendocino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8886SF+30d |  | 0 | 309 | Warning
27226 | Mendocino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8887SF+30d |  | 0 | 309 | Warning
27227 | Mendocino CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8868 |  | 0 | 234 | Warning
27228 | Mendocino CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 8869 |  | 0 | 234 | Warning
27229 | Mendocino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27230 | Mendocino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8889FS+12d | 0 | 240 | Warning
27231 | Mendocino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27232 | Mendocino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8889SF+60d | 0 | 250 | Warning
27233 | Mendocino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8872SF+30d | 0 | 240 | Warning
27234 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8873SF+30d | 0 | 240 | Warning
27235 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8874SF+30d | 0 | 240 | Warning
27236 | Mendocino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8875SF+30d | 0 | 240 | Warning
27237 | Mendocino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8876SF+30d | 0 | 240 | Warning
27238 | Mendocino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27239 | Mendocino CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 8880FS+12d,8882SF+60d |  | 0 | 240 | Warning
27242 | Merced CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
27247 | Merced CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
27248 | Merced CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27249 | Merced CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27250 | Merced CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27252 | Merced CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
27253 | Merced CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
27275 | Merced CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
27276 | Merced CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27277 | Merced CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27278 | Merced CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27279 | Merced CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27280 | Merced CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27281 | Merced CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27282 | Merced CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27283 | Merced CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27284 | Merced CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27285 | Merced CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27286 | Merced CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27287 | Merced CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27294 | Merced CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
27295 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8946SS | 0 | 414 | Warning
27296 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 8945SS |  | 0 | 414 | Warning
27297 | Merced CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 8948SS | 0 | 362 | Warning
27298 | Merced CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 8947SS |  | 0 | 362 | Warning
27299 | Merced CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27300 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8951SS | 0 | 352 | Warning
27301 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 8950SS |  | 0 | 352 | Warning
27302 | Merced CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27303 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8954SS | 0 | 288 | Warning
27304 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8953SS |  | 0 | 288 | Warning
27305 | Merced CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27306 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8957SS | 0 | 268 | Warning
27307 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 8956SS |  | 0 | 268 | Warning
27308 | Merced CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27309 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8960SS | 0 | 246 | Warning
27310 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 8959SS |  | 0 | 246 | Warning
27311 | Merced CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27312 | Merced CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.44 | 234 | Warning
27315 | Merced CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 8964 |  | 0.4 | 234 | Warning
27319 | Merced CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27322 | Merced CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 8971 |  | 0.2 | 466 | Warning
27323 | Merced CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27325 | Merced CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 8974 | 8976 | 0.2 | 405 | Warning
27326 | Merced CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 8975 |  | 0 | 405 | Warning
27327 | Merced CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27329 | Merced CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 8978 | 8980 | 0 | 405 | Warning
27330 | Merced CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 8979 |  | 0 | 405 | Warning
27331 | Merced CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27333 | Merced CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 8982 | 8984 | 0 | 362 | Warning
27334 | Merced CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 8983 |  | 0 | 362 | Warning
27335 | Merced CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
27336 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
27337 | Merced CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.41 | 298 | Warning
27338 | Merced CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.65 | 357 | Warning
27340 | Merced CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 8989SS | 8991 | 0.36 | 357 | Warning
27341 | Merced CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 8990 |  | 0 | 357 | Warning
27349 | Merced CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
27351 | Merced CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 9000SS | 9002,9005,9003SF+30d | 0.2 | 298 | Warning
27352 | Merced CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9001 |  | 0 | 298 | Warning
27353 | Merced CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9001SF+30d |  | 0 | 298 | Warning
27354 | Merced CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27355 | Merced CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9001 |  | 0 | 345 | Warning
27356 | Merced CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
27359 | Merced CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 9008SS |  | 0.4 | 445 | Warning
27367 | Merced CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
27369 | Merced CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 9018SS | 9023,9020 | 0.2 | 298 | Warning
27370 | Merced CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9019 |  | 0 | 298 | Warning
27371 | Merced CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
27372 | Merced CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27373 | Merced CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9019 |  | 0 | 345 | Warning
27374 | Merced CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27375 | Merced CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27376 | Merced CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27377 | Merced CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27378 | Merced CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27379 | Merced CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27380 | Merced CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27381 | Merced CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27382 | Merced CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27383 | Merced CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27384 | Merced CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27385 | Merced CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27386 | Merced CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27389 | Merced CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
27390 | Merced CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27391 | Merced CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27392 | Merced CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27393 | Merced CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9052 | 0 | 234 | Warning
27394 | Merced CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9053 | 0 | 234 | Warning
27396 | Merced CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27397 | Merced CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9058SF+30d |  | 0 | 309 | Warning
27398 | Merced CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9059SF+30d |  | 0 | 309 | Warning
27399 | Merced CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9060SF+30d |  | 0 | 309 | Warning
27400 | Merced CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9061SF+30d |  | 0 | 309 | Warning
27401 | Merced CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9062SF+30d |  | 0 | 309 | Warning
27402 | Merced CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9043 |  | 0 | 234 | Warning
27403 | Merced CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9044 |  | 0 | 234 | Warning
27404 | Merced CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27405 | Merced CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9064FS+12d | 0 | 240 | Warning
27406 | Merced CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27407 | Merced CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9064SF+60d | 0 | 250 | Warning
27408 | Merced CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9047SF+30d | 0 | 240 | Warning
27409 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9048SF+30d | 0 | 240 | Warning
27410 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9049SF+30d | 0 | 240 | Warning
27411 | Merced CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9050SF+30d | 0 | 240 | Warning
27412 | Merced CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9051SF+30d | 0 | 240 | Warning
27413 | Merced CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27414 | Merced CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9055FS+12d,9057SF+60d |  | 0 | 240 | Warning
27417 | Modoc CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
27422 | Modoc CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
27423 | Modoc CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27424 | Modoc CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27425 | Modoc CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27427 | Modoc CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.4 | 235 | Warning
27428 | Modoc CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
27451 | Modoc CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27452 | Modoc CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27453 | Modoc CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27454 | Modoc CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27455 | Modoc CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27456 | Modoc CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27457 | Modoc CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27458 | Modoc CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27459 | Modoc CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27460 | Modoc CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27461 | Modoc CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27462 | Modoc CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27469 | Modoc CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
27470 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9121SS | 0 | 414 | Warning
27471 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9120SS |  | 0 | 414 | Warning
27472 | Modoc CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9123SS | 0 | 362 | Warning
27473 | Modoc CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9122SS |  | 0 | 362 | Warning
27474 | Modoc CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27475 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9126SS | 0 | 352 | Warning
27476 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9125SS |  | 0 | 352 | Warning
27477 | Modoc CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27478 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9129SS | 0 | 288 | Warning
27479 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9128SS |  | 0 | 288 | Warning
27480 | Modoc CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27481 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9132SS | 0 | 268 | Warning
27482 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9131SS |  | 0 | 268 | Warning
27483 | Modoc CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27484 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9135SS | 0 | 246 | Warning
27485 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9134SS |  | 0 | 246 | Warning
27486 | Modoc CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27487 | Modoc CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.54 | 234 | Warning
27490 | Modoc CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9139 |  | 0.6 | 234 | Warning
27494 | Modoc CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27498 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27501 | Modoc CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 9150 |  | 0 | 405 | Warning
27502 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27503 | Modoc CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9154 | 0.8 | 405 | Warning
27504 | Modoc CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 9153 | 9155 | 0 | 405 | Warning
27505 | Modoc CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 9154 |  | 0 | 405 | Warning
27506 | Modoc CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27507 | Modoc CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9158 | 0 | 362 | Warning
27508 | Modoc CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 9157 | 9159 | 0 | 362 | Warning
27509 | Modoc CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 9158 |  | 0 | 362 | Warning
27510 | Modoc CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
27511 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
27512 | Modoc CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 398 | 298d |  |  | 0.22 | 298 | Warning
27519 | Modoc CW-Execute plan for transition of custom reports from Business Objects to Tableau | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0.03 | 298 | Warning
27520 | Modoc CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 64 | 299d |  |  | 0 | 299 | Warning
27521 | Modoc CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
27522 | Modoc CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27523 | Modoc CW-POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0.8 | 346 | Warning
27530 | Modoc CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27531 | Modoc CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27532 | Modoc CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27533 | Modoc CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27534 | Modoc CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27535 | Modoc CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27536 | Modoc CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27537 | Modoc CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27538 | Modoc CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27539 | Modoc CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27540 | Modoc CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27541 | Modoc CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27542 | Modoc CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27545 | Modoc CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
27546 | Modoc CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27547 | Modoc CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27548 | Modoc CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27549 | Modoc CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9208 | 0 | 234 | Warning
27550 | Modoc CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9209 | 0 | 234 | Warning
27552 | Modoc CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27553 | Modoc CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9214SF+30d |  | 0 | 309 | Warning
27554 | Modoc CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9215SF+30d |  | 0 | 309 | Warning
27555 | Modoc CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9216SF+30d |  | 0 | 309 | Warning
27556 | Modoc CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9217SF+30d |  | 0 | 309 | Warning
27557 | Modoc CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9218SF+30d |  | 0 | 309 | Warning
27558 | Modoc CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9199 |  | 0 | 234 | Warning
27559 | Modoc CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9200 |  | 0 | 234 | Warning
27560 | Modoc CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27561 | Modoc CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9220FS+12d | 0 | 240 | Warning
27562 | Modoc CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27563 | Modoc CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9220SF+60d | 0 | 250 | Warning
27564 | Modoc CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9203SF+30d | 0 | 240 | Warning
27565 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9204SF+30d | 0 | 240 | Warning
27566 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9205SF+30d | 0 | 240 | Warning
27567 | Modoc CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9206SF+30d | 0 | 240 | Warning
27568 | Modoc CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9207SF+30d | 0 | 240 | Warning
27569 | Modoc CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27570 | Modoc CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9211FS+12d,9213SF+60d |  | 0 | 240 | Warning
27573 | Mono CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
27578 | Mono CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
27579 | Mono CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27580 | Mono CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27581 | Mono CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27583 | Mono CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.4 | 235 | Warning
27584 | Mono CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
27607 | Mono CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27608 | Mono CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27609 | Mono CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27610 | Mono CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27611 | Mono CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27612 | Mono CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27613 | Mono CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27614 | Mono CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27615 | Mono CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27616 | Mono CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27617 | Mono CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27618 | Mono CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27625 | Mono CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
27626 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9277SS | 0 | 414 | Warning
27627 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9276SS |  | 0 | 414 | Warning
27628 | Mono CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9279SS | 0 | 362 | Warning
27629 | Mono CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9278SS |  | 0 | 362 | Warning
27630 | Mono CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27631 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9282SS | 0 | 352 | Warning
27632 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9281SS |  | 0 | 352 | Warning
27633 | Mono CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27634 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9285SS | 0 | 288 | Warning
27635 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9284SS |  | 0 | 288 | Warning
27636 | Mono CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27637 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9288SS | 0 | 268 | Warning
27638 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9287SS |  | 0 | 268 | Warning
27639 | Mono CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27640 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9291SS | 0 | 246 | Warning
27641 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9290SS |  | 0 | 246 | Warning
27642 | Mono CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27643 | Mono CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.33 | 234 | Warning
27646 | Mono CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9295 |  | 0.2 | 234 | Warning
27650 | Mono CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27653 | Mono CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 9302 |  | 0 | 466 | Warning
27654 | Mono CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27656 | Mono CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 9305 | 9307 | 0.2 | 405 | Warning
27657 | Mono CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 9306 |  | 0 | 405 | Warning
27658 | Mono CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27660 | Mono CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 9309 | 9311 | 0 | 405 | Warning
27661 | Mono CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 9310 |  | 0 | 405 | Warning
27662 | Mono CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27663 | Mono CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9314 | 0 | 362 | Warning
27664 | Mono CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 9313 | 9315 | 0 | 362 | Warning
27665 | Mono CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 9314 |  | 0 | 362 | Warning
27666 | Mono CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
27667 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
27668 | Mono CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.27 | 298 | Warning
27669 | Mono CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.48 | 357 | Warning
27671 | Mono CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 9320SS | 9322 | 0 | 357 | Warning
27672 | Mono CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 9321 |  | 0 | 357 | Warning
27680 | Mono CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
27682 | Mono CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 9331SS | 9333,9336,9334SF+30d | 0 | 298 | Warning
27683 | Mono CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9332 |  | 0 | 298 | Warning
27684 | Mono CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9332SF+30d |  | 0 | 298 | Warning
27685 | Mono CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27686 | Mono CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9332 |  | 0 | 345 | Warning
27694 | Mono CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
27696 | Mono CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 9345SS | 9350,9347 | 0 | 298 | Warning
27697 | Mono CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9346 |  | 0 | 298 | Warning
27698 | Mono CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
27699 | Mono CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27700 | Mono CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9346 |  | 0 | 345 | Warning
27701 | Mono CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27702 | Mono CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27703 | Mono CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27704 | Mono CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27705 | Mono CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27706 | Mono CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27707 | Mono CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27708 | Mono CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27709 | Mono CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27710 | Mono CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27711 | Mono CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27712 | Mono CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27713 | Mono CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27716 | Mono CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | 384 | Warning
27717 | Mono CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27718 | Mono CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27719 | Mono CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27720 | Mono CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9379 | 0 | 234 | Warning
27721 | Mono CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9380 | 0 | 234 | Warning
27723 | Mono CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27724 | Mono CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9385SF+30d |  | 0 | 309 | Warning
27725 | Mono CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9386SF+30d |  | 0 | 309 | Warning
27726 | Mono CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9387SF+30d |  | 0 | 309 | Warning
27727 | Mono CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9388SF+30d |  | 0 | 309 | Warning
27728 | Mono CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9389SF+30d |  | 0 | 309 | Warning
27729 | Mono CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9370 |  | 0 | 234 | Warning
27730 | Mono CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9371 |  | 0 | 234 | Warning
27731 | Mono CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27732 | Mono CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9391FS+12d | 0 | 240 | Warning
27733 | Mono CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27734 | Mono CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9391SF+60d | 0 | 250 | Warning
27735 | Mono CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9374SF+30d | 0 | 240 | Warning
27736 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9375SF+30d | 0 | 240 | Warning
27737 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9376SF+30d | 0 | 240 | Warning
27738 | Mono CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9377SF+30d | 0 | 240 | Warning
27739 | Mono CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9378SF+30d | 0 | 240 | Warning
27740 | Mono CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27741 | Mono CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9382FS+12d,9384SF+60d |  | 0 | 240 | Warning
27744 | Monterey CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
27749 | Monterey CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
27750 | Monterey CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27751 | Monterey CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27752 | Monterey CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27754 | Monterey CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.43 | 235 | Warning
27755 | Monterey CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
27778 | Monterey CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27779 | Monterey CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27780 | Monterey CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27781 | Monterey CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27782 | Monterey CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27783 | Monterey CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27784 | Monterey CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27785 | Monterey CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27786 | Monterey CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27787 | Monterey CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27788 | Monterey CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27789 | Monterey CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27796 | Monterey CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | 445 | Warning
27797 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9448SS | 0 | 414 | Warning
27798 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9447SS |  | 0 | 414 | Warning
27799 | Monterey CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9450SS | 0 | 362 | Warning
27800 | Monterey CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9449SS |  | 0 | 362 | Warning
27801 | Monterey CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27802 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9453SS | 0 | 352 | Warning
27803 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9452SS |  | 0 | 352 | Warning
27804 | Monterey CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27805 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9456SS | 0 | 288 | Warning
27806 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9455SS |  | 0 | 288 | Warning
27807 | Monterey CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27808 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9459SS | 0 | 268 | Warning
27809 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9458SS |  | 0 | 268 | Warning
27810 | Monterey CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27811 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9462SS | 0 | 246 | Warning
27812 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9461SS |  | 0 | 246 | Warning
27813 | Monterey CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27814 | Monterey CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.5 | 234 | Warning
27817 | Monterey CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9466 |  | 0.6 | 234 | Warning
27821 | Monterey CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27824 | Monterey CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 9473 |  | 0.2 | 466 | Warning
27825 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27827 | Monterey CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 9476 | 9478 | 0.4 | 405 | Warning
27828 | Monterey CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 9477 |  | 0 | 405 | Warning
27829 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27831 | Monterey CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 9480 | 9482 | 0 | 405 | Warning
27832 | Monterey CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 9481 |  | 0 | 405 | Warning
27833 | Monterey CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27834 | Monterey CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9485 | 0 | 362 | Warning
27835 | Monterey CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 9484 | 9486 | 0 | 362 | Warning
27836 | Monterey CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 9485 |  | 0 | 362 | Warning
27837 | Monterey CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
27838 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
27839 | Monterey CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.51 | 298 | Warning
27840 | Monterey CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.93 | 357 | Warning
27841 | Monterey CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 9492SS | 0.95 | 405 | Warning
27843 | Monterey CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 9492 |  | 0.6 | 357 | Warning
27848 | Monterey CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
27850 | Monterey CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 9499 |  | 0.2 | 485 | Warning
27851 | Monterey CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
27853 | Monterey CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 9502SS | 9504,9507,9505SF+30d | 0.2 | 298 | Warning
27854 | Monterey CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9503 |  | 0 | 298 | Warning
27855 | Monterey CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9503SF+30d |  | 0 | 298 | Warning
27856 | Monterey CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27857 | Monterey CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9503 |  | 0 | 345 | Warning
27869 | Monterey CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.25 | 298 | Warning
27871 | Monterey CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 9520SS | 9525,9522 | 0.6 | 298 | Warning
27872 | Monterey CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9521 |  | 0 | 298 | Warning
27873 | Monterey CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
27874 | Monterey CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
27875 | Monterey CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9521 |  | 0 | 345 | Warning
27876 | Monterey CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
27877 | Monterey CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27878 | Monterey CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27879 | Monterey CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27880 | Monterey CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27881 | Monterey CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27882 | Monterey CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27883 | Monterey CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27884 | Monterey CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27885 | Monterey CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27886 | Monterey CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27887 | Monterey CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
27888 | Monterey CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
27891 | Monterey CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | 384 | Warning
27892 | Monterey CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
27893 | Monterey CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27894 | Monterey CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
27895 | Monterey CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9554 | 0 | 234 | Warning
27896 | Monterey CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9555 | 0 | 234 | Warning
27898 | Monterey CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
27899 | Monterey CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9560SF+30d |  | 0 | 309 | Warning
27900 | Monterey CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9561SF+30d |  | 0 | 309 | Warning
27901 | Monterey CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9562SF+30d |  | 0 | 309 | Warning
27902 | Monterey CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9563SF+30d |  | 0 | 309 | Warning
27903 | Monterey CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9564SF+30d |  | 0 | 309 | Warning
27904 | Monterey CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9545 |  | 0 | 234 | Warning
27905 | Monterey CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9546 |  | 0 | 234 | Warning
27906 | Monterey CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
27907 | Monterey CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9566FS+12d | 0 | 240 | Warning
27908 | Monterey CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
27909 | Monterey CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9566SF+60d | 0 | 250 | Warning
27910 | Monterey CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9549SF+30d | 0 | 240 | Warning
27911 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9550SF+30d | 0 | 240 | Warning
27912 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9551SF+30d | 0 | 240 | Warning
27913 | Monterey CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9552SF+30d | 0 | 240 | Warning
27914 | Monterey CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9553SF+30d | 0 | 240 | Warning
27915 | Monterey CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
27916 | Monterey CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9557FS+12d,9559SF+60d |  | 0 | 240 | Warning
27919 | Napa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.63 | 245 | Warning
27924 | Napa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.6 | 405 | Warning
27925 | Napa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
27926 | Napa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
27927 | Napa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
27929 | Napa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
27930 | Napa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
27952 | Napa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
27953 | Napa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
27954 | Napa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
27955 | Napa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
27956 | Napa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
27957 | Napa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
27958 | Napa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
27959 | Napa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
27960 | Napa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
27961 | Napa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
27962 | Napa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
27963 | Napa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27964 | Napa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
27971 | Napa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
27972 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9623SS | 0 | 414 | Warning
27973 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9622SS |  | 0 | 414 | Warning
27974 | Napa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9625SS | 0 | 362 | Warning
27975 | Napa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9624SS |  | 0 | 362 | Warning
27976 | Napa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
27977 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9628SS | 0 | 352 | Warning
27978 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9627SS |  | 0 | 352 | Warning
27979 | Napa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
27980 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9631SS | 0 | 288 | Warning
27981 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9630SS |  | 0 | 288 | Warning
27982 | Napa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
27983 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9634SS | 0 | 268 | Warning
27984 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9633SS |  | 0 | 268 | Warning
27985 | Napa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
27986 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9637SS | 0 | 246 | Warning
27987 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9636SS |  | 0 | 246 | Warning
27988 | Napa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
27989 | Napa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.46 | 234 | Warning
27992 | Napa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9641 |  | 0.6 | 234 | Warning
27996 | Napa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
27999 | Napa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 9648 |  | 0.2 | 466 | Warning
28000 | Napa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28002 | Napa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 9651 | 9653 | 0 | 405 | Warning
28003 | Napa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 9652 |  | 0 | 405 | Warning
28004 | Napa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28005 | Napa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9656 | 0 | 405 | Warning
28006 | Napa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 9655 | 9657 | 0 | 405 | Warning
28007 | Napa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 9656 |  | 0 | 405 | Warning
28008 | Napa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28009 | Napa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9660 | 0 | 362 | Warning
28010 | Napa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 9659 | 9661 | 0 | 362 | Warning
28011 | Napa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 9660 |  | 0 | 362 | Warning
28012 | Napa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28013 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28014 | Napa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.45 | 298 | Warning
28015 | Napa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.96 | 357 | Warning
28018 | Napa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 9667 |  | 0.2 | 357 | Warning
28023 | Napa CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
28025 | Napa CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 9674 |  | 0 | 485 | Warning
28026 | Napa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
28028 | Napa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 9677SS | 9679,9682,9680SF+30d | 0 | 298 | Warning
28029 | Napa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9678 |  | 0 | 298 | Warning
28030 | Napa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9678SF+30d |  | 0 | 298 | Warning
28031 | Napa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28032 | Napa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9678 |  | 0 | 345 | Warning
28033 | Napa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
28036 | Napa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 9685SS |  | 0.4 | 445 | Warning
28044 | Napa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
28046 | Napa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 9695SS | 9700,9697 | 0 | 298 | Warning
28047 | Napa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9696 |  | 0 | 298 | Warning
28048 | Napa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
28049 | Napa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28050 | Napa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9696 |  | 0 | 345 | Warning
28051 | Napa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
28052 | Napa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28053 | Napa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28054 | Napa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28055 | Napa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28056 | Napa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28057 | Napa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28058 | Napa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28059 | Napa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28060 | Napa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28061 | Napa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28062 | Napa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28063 | Napa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28066 | Napa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28067 | Napa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28068 | Napa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28069 | Napa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28070 | Napa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9729 | 0 | 234 | Warning
28071 | Napa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9730 | 0 | 234 | Warning
28073 | Napa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28074 | Napa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9735SF+30d |  | 0 | 309 | Warning
28075 | Napa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9736SF+30d |  | 0 | 309 | Warning
28076 | Napa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9737SF+30d |  | 0 | 309 | Warning
28077 | Napa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9738SF+30d |  | 0 | 309 | Warning
28078 | Napa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9739SF+30d |  | 0 | 309 | Warning
28079 | Napa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9720 |  | 0 | 234 | Warning
28080 | Napa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9721 |  | 0 | 234 | Warning
28081 | Napa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28082 | Napa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9741FS+12d | 0 | 240 | Warning
28083 | Napa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28084 | Napa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9741SF+60d | 0 | 250 | Warning
28085 | Napa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9724SF+30d | 0 | 240 | Warning
28086 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9725SF+30d | 0 | 240 | Warning
28087 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9726SF+30d | 0 | 240 | Warning
28088 | Napa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9727SF+30d | 0 | 240 | Warning
28089 | Napa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9728SF+30d | 0 | 240 | Warning
28090 | Napa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28091 | Napa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9732FS+12d,9734SF+60d |  | 0 | 240 | Warning
28094 | Nevada CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28099 | Nevada CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28100 | Nevada CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28101 | Nevada CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28102 | Nevada CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28104 | Nevada CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
28105 | Nevada CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
28127 | Nevada CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
28128 | Nevada CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
28129 | Nevada CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
28130 | Nevada CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
28131 | Nevada CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
28132 | Nevada CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
28133 | Nevada CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
28134 | Nevada CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
28135 | Nevada CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28136 | Nevada CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
28137 | Nevada CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
28138 | Nevada CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28139 | Nevada CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
28146 | Nevada CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
28147 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9798SS | 0 | 414 | Warning
28148 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9797SS |  | 0 | 414 | Warning
28149 | Nevada CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9800SS | 0 | 362 | Warning
28150 | Nevada CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9799SS |  | 0 | 362 | Warning
28151 | Nevada CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
28152 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9803SS | 0 | 352 | Warning
28153 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9802SS |  | 0 | 352 | Warning
28154 | Nevada CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
28155 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9806SS | 0 | 288 | Warning
28156 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9805SS |  | 0 | 288 | Warning
28157 | Nevada CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
28158 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9809SS | 0 | 268 | Warning
28159 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9808SS |  | 0 | 268 | Warning
28160 | Nevada CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28161 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9812SS | 0 | 246 | Warning
28162 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9811SS |  | 0 | 246 | Warning
28163 | Nevada CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
28164 | Nevada CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.49 | 234 | Warning
28167 | Nevada CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9816 |  | 0.6 | 234 | Warning
28171 | Nevada CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28174 | Nevada CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 9823 |  | 0.2 | 466 | Warning
28175 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28177 | Nevada CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 9826 | 9828 | 0.8 | 405 | Warning
28178 | Nevada CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 9827 |  | 0 | 405 | Warning
28179 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28180 | Nevada CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9831 | 0.2 | 405 | Warning
28181 | Nevada CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 9830 | 9832 | 0 | 405 | Warning
28182 | Nevada CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 9831 |  | 0 | 405 | Warning
28183 | Nevada CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28184 | Nevada CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9835 | 0 | 362 | Warning
28185 | Nevada CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 9834 | 9836 | 0 | 362 | Warning
28186 | Nevada CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 9835 |  | 0 | 362 | Warning
28187 | Nevada CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28188 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28189 | Nevada CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.55 | 298 | Warning
28190 | Nevada CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.96 | 357 | Warning
28193 | Nevada CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 9842 |  | 0.2 | 357 | Warning
28201 | Nevada CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
28203 | Nevada CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 9852SS | 9854,9857,9855SF+30d | 0.2 | 298 | Warning
28204 | Nevada CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9853 |  | 0 | 298 | Warning
28205 | Nevada CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9853SF+30d |  | 0 | 298 | Warning
28206 | Nevada CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28207 | Nevada CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9853 |  | 0 | 345 | Warning
28219 | Nevada CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
28221 | Nevada CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 9870SS | 9875,9872 | 0.2 | 298 | Warning
28222 | Nevada CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 9871 |  | 0 | 298 | Warning
28223 | Nevada CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
28224 | Nevada CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28225 | Nevada CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 9871 |  | 0 | 345 | Warning
28226 | Nevada CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 363d |  |  | 0.2 | 363 | Warning
28227 | Nevada CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28228 | Nevada CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28229 | Nevada CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28230 | Nevada CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28231 | Nevada CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28232 | Nevada CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28233 | Nevada CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28234 | Nevada CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28235 | Nevada CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28236 | Nevada CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28237 | Nevada CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28238 | Nevada CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28241 | Nevada CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28242 | Nevada CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28243 | Nevada CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28244 | Nevada CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28245 | Nevada CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9904 | 0 | 234 | Warning
28246 | Nevada CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9905 | 0 | 234 | Warning
28248 | Nevada CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28249 | Nevada CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9910SF+30d |  | 0 | 309 | Warning
28250 | Nevada CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9911SF+30d |  | 0 | 309 | Warning
28251 | Nevada CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9912SF+30d |  | 0 | 309 | Warning
28252 | Nevada CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9913SF+30d |  | 0 | 309 | Warning
28253 | Nevada CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9914SF+30d |  | 0 | 309 | Warning
28254 | Nevada CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9895 |  | 0 | 234 | Warning
28255 | Nevada CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 9896 |  | 0 | 234 | Warning
28256 | Nevada CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28257 | Nevada CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9916FS+12d | 0 | 240 | Warning
28258 | Nevada CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28259 | Nevada CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9916SF+60d | 0 | 250 | Warning
28260 | Nevada CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9899SF+30d | 0 | 240 | Warning
28261 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9900SF+30d | 0 | 240 | Warning
28262 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9901SF+30d | 0 | 240 | Warning
28263 | Nevada CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9902SF+30d | 0 | 240 | Warning
28264 | Nevada CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9903SF+30d | 0 | 240 | Warning
28265 | Nevada CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28266 | Nevada CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 9907FS+12d,9909SF+60d |  | 0 | 240 | Warning
28269 | Orange CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28274 | Orange CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28275 | Orange CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28276 | Orange CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28277 | Orange CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28279 | Orange CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
28280 | Orange CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
28302 | Orange CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
28303 | Orange CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
28304 | Orange CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
28305 | Orange CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
28306 | Orange CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
28307 | Orange CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
28308 | Orange CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
28309 | Orange CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
28310 | Orange CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28311 | Orange CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
28312 | Orange CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
28313 | Orange CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28314 | Orange CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
28321 | Orange CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
28322 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9973SS | 0 | 414 | Warning
28323 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 9972SS |  | 0 | 414 | Warning
28324 | Orange CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 9975SS | 0 | 362 | Warning
28325 | Orange CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 9974SS |  | 0 | 362 | Warning
28326 | Orange CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
28327 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9978SS | 0 | 352 | Warning
28328 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 9977SS |  | 0 | 352 | Warning
28329 | Orange CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
28330 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9981SS | 0 | 288 | Warning
28331 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9980SS |  | 0 | 288 | Warning
28332 | Orange CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
28333 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9984SS | 0 | 268 | Warning
28334 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 9983SS |  | 0 | 268 | Warning
28335 | Orange CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28336 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9987SS | 0 | 246 | Warning
28337 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 9986SS |  | 0 | 246 | Warning
28338 | Orange CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
28339 | Orange CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.48 | 234 | Warning
28342 | Orange CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 9991 |  | 0.6 | 234 | Warning
28346 | Orange CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28349 | Orange CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 9998 |  | 0.2 | 466 | Warning
28350 | Orange CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28352 | Orange CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10001 | 10003 | 0.2 | 405 | Warning
28353 | Orange CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10002 |  | 0 | 405 | Warning
28354 | Orange CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28355 | Orange CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10006 | 0.2 | 405 | Warning
28356 | Orange CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10005 | 10007 | 0 | 405 | Warning
28357 | Orange CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10006 |  | 0 | 405 | Warning
28358 | Orange CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28359 | Orange CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10010 | 0 | 362 | Warning
28360 | Orange CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10009 | 10011 | 0 | 362 | Warning
28361 | Orange CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10010 |  | 0 | 362 | Warning
28362 | Orange CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28363 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28364 | Orange CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.37 | 298 | Warning
28365 | Orange CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.67 | 357 | Warning
28366 | Orange CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 10017SS | 0.8 | 405 | Warning
28367 | Orange CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 10016SS | 10018 | 0.6 | 357 | Warning
28368 | Orange CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10017 |  | 0 | 357 | Warning
28373 | Orange CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
28375 | Orange CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 10024 |  | 0.2 | 485 | Warning
28376 | Orange CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
28378 | Orange CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 10027SS | 10029,10032,10030SF+30d | 0 | 298 | Warning
28379 | Orange CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10028 |  | 0 | 298 | Warning
28380 | Orange CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10028SF+30d |  | 0 | 298 | Warning
28381 | Orange CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28382 | Orange CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10028 |  | 0 | 345 | Warning
28383 | Orange CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.71 | 445 | Warning
28385 | Orange CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 10034SS | 10036SS | 0.8 | 485 | Warning
28386 | Orange CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 10035SS |  | 0.4 | 445 | Warning
28391 | Orange CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.75 | 508 | Warning
28393 | Orange CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 10042 |  | 0.4 | 508 | Warning
28394 | Orange CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
28396 | Orange CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 10045SS | 10050,10047 | 0 | 298 | Warning
28397 | Orange CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10046 |  | 0 | 298 | Warning
28398 | Orange CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
28399 | Orange CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28400 | Orange CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10046 |  | 0 | 345 | Warning
28401 | Orange CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
28402 | Orange CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28403 | Orange CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28404 | Orange CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28405 | Orange CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28406 | Orange CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28407 | Orange CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28408 | Orange CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28409 | Orange CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28410 | Orange CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28411 | Orange CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28412 | Orange CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28413 | Orange CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28416 | Orange CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28417 | Orange CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28418 | Orange CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28419 | Orange CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28420 | Orange CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10079 | 0 | 234 | Warning
28421 | Orange CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10080 | 0 | 234 | Warning
28423 | Orange CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28424 | Orange CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10085SF+30d |  | 0 | 309 | Warning
28425 | Orange CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10086SF+30d |  | 0 | 309 | Warning
28426 | Orange CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10087SF+30d |  | 0 | 309 | Warning
28427 | Orange CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10088SF+30d |  | 0 | 309 | Warning
28428 | Orange CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10089SF+30d |  | 0 | 309 | Warning
28429 | Orange CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10070 |  | 0 | 234 | Warning
28430 | Orange CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10071 |  | 0 | 234 | Warning
28431 | Orange CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28432 | Orange CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10091FS+12d | 0 | 240 | Warning
28433 | Orange CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28434 | Orange CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10091SF+60d | 0 | 250 | Warning
28435 | Orange CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10074SF+30d | 0 | 240 | Warning
28436 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10075SF+30d | 0 | 240 | Warning
28437 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10076SF+30d | 0 | 240 | Warning
28438 | Orange CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10077SF+30d | 0 | 240 | Warning
28439 | Orange CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10078SF+30d | 0 | 240 | Warning
28440 | Orange CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28441 | Orange CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10082FS+12d,10084SF+60d |  | 0 | 240 | Warning
28444 | Placer CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28449 | Placer CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28450 | Placer CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28451 | Placer CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28452 | Placer CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28454 | Placer CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
28455 | Placer CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
28477 | Placer CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
28478 | Placer CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
28479 | Placer CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
28480 | Placer CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
28481 | Placer CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
28482 | Placer CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
28483 | Placer CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
28484 | Placer CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
28485 | Placer CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28486 | Placer CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
28487 | Placer CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
28488 | Placer CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28489 | Placer CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
28496 | Placer CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
28497 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10148SS | 0 | 414 | Warning
28498 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 10147SS |  | 0 | 414 | Warning
28499 | Placer CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 10150SS | 0 | 362 | Warning
28500 | Placer CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 10149SS |  | 0 | 362 | Warning
28501 | Placer CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
28502 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10153SS | 0 | 352 | Warning
28503 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 10152SS |  | 0 | 352 | Warning
28504 | Placer CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
28505 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10156SS | 0 | 288 | Warning
28506 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10155SS |  | 0 | 288 | Warning
28507 | Placer CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
28508 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10159SS | 0 | 268 | Warning
28509 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 10158SS |  | 0 | 268 | Warning
28510 | Placer CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28511 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10162SS | 0 | 246 | Warning
28512 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 10161SS |  | 0 | 246 | Warning
28513 | Placer CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
28514 | Placer CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.66 | 234 | Warning
28521 | Placer CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28524 | Placer CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 10173 |  | 0.4 | 466 | Warning
28525 | Placer CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28527 | Placer CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10176 | 10178 | 0.8 | 405 | Warning
28528 | Placer CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10177 |  | 0 | 405 | Warning
28529 | Placer CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28530 | Placer CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10181 | 0.2 | 405 | Warning
28531 | Placer CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10180 | 10182 | 0 | 405 | Warning
28532 | Placer CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10181 |  | 0 | 405 | Warning
28533 | Placer CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28534 | Placer CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10185 | 0 | 362 | Warning
28535 | Placer CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10184 | 10186 | 0 | 362 | Warning
28536 | Placer CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10185 |  | 0 | 362 | Warning
28537 | Placer CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28538 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28539 | Placer CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.57 | 298 | Warning
28540 | Placer CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.99 | 357 | Warning
28543 | Placer CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10192 |  | 0.8 | 357 | Warning
28551 | Placer CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
28553 | Placer CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 10202SS | 10204,10207,10205SF+30d | 0.2 | 298 | Warning
28554 | Placer CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10203 |  | 0 | 298 | Warning
28555 | Placer CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10203SF+30d |  | 0 | 298 | Warning
28556 | Placer CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28557 | Placer CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10203 |  | 0 | 345 | Warning
28558 | Placer CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
28561 | Placer CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 10210SS |  | 0.4 | 445 | Warning
28569 | Placer CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.43 | 298 | Warning
28572 | Placer CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10221 |  | 0 | 298 | Warning
28573 | Placer CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
28574 | Placer CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28575 | Placer CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10221 |  | 0 | 345 | Warning
28576 | Placer CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 363d |  |  | 0.2 | 363 | Warning
28577 | Placer CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28578 | Placer CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28579 | Placer CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28580 | Placer CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28581 | Placer CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28582 | Placer CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28583 | Placer CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28584 | Placer CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28585 | Placer CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28586 | Placer CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28587 | Placer CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
28588 | Placer CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28591 | Placer CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28592 | Placer CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28593 | Placer CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28594 | Placer CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28595 | Placer CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10254 | 0 | 234 | Warning
28596 | Placer CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10255 | 0 | 234 | Warning
28598 | Placer CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28599 | Placer CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10260SF+30d |  | 0 | 309 | Warning
28600 | Placer CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10261SF+30d |  | 0 | 309 | Warning
28601 | Placer CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10262SF+30d |  | 0 | 309 | Warning
28602 | Placer CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10263SF+30d |  | 0 | 309 | Warning
28603 | Placer CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10264SF+30d |  | 0 | 309 | Warning
28604 | Placer CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10245 |  | 0 | 234 | Warning
28605 | Placer CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10246 |  | 0 | 234 | Warning
28606 | Placer CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28607 | Placer CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10266FS+12d | 0 | 240 | Warning
28608 | Placer CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28609 | Placer CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10266SF+60d | 0 | 250 | Warning
28610 | Placer CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10249SF+30d | 0 | 240 | Warning
28611 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10250SF+30d | 0 | 240 | Warning
28612 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10251SF+30d | 0 | 240 | Warning
28613 | Placer CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10252SF+30d | 0 | 240 | Warning
28614 | Placer CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10253SF+30d | 0 | 240 | Warning
28615 | Placer CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28616 | Placer CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10257FS+12d,10259SF+60d |  | 0 | 240 | Warning
28619 | Plumas CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28624 | Plumas CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28625 | Plumas CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28626 | Plumas CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28627 | Plumas CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28629 | Plumas CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
28630 | Plumas CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
28652 | Plumas CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
28653 | Plumas CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
28654 | Plumas CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
28655 | Plumas CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
28656 | Plumas CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
28657 | Plumas CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
28658 | Plumas CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
28659 | Plumas CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
28660 | Plumas CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28661 | Plumas CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
28662 | Plumas CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
28663 | Plumas CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28664 | Plumas CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
28671 | Plumas CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
28672 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10323SS | 0 | 414 | Warning
28673 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 10322SS |  | 0 | 414 | Warning
28674 | Plumas CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 10325SS | 0 | 362 | Warning
28675 | Plumas CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 10324SS |  | 0 | 362 | Warning
28676 | Plumas CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
28677 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10328SS | 0 | 352 | Warning
28678 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 10327SS |  | 0 | 352 | Warning
28679 | Plumas CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
28680 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10331SS | 0 | 288 | Warning
28681 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10330SS |  | 0 | 288 | Warning
28682 | Plumas CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
28683 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10334SS | 0 | 268 | Warning
28684 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 10333SS |  | 0 | 268 | Warning
28685 | Plumas CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28686 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10337SS | 0 | 246 | Warning
28687 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 10336SS |  | 0 | 246 | Warning
28688 | Plumas CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
28689 | Plumas CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.42 | 234 | Warning
28692 | Plumas CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 10341 |  | 0.4 | 234 | Warning
28696 | Plumas CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28699 | Plumas CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 10348 |  | 0.2 | 466 | Warning
28700 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28702 | Plumas CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10351 | 10353 | 0.2 | 405 | Warning
28703 | Plumas CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10352 |  | 0 | 405 | Warning
28704 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28706 | Plumas CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10355 | 10357 | 0 | 405 | Warning
28707 | Plumas CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10356 |  | 0 | 405 | Warning
28708 | Plumas CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28709 | Plumas CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10360 | 0 | 362 | Warning
28710 | Plumas CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10359 | 10361 | 0 | 362 | Warning
28711 | Plumas CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10360 |  | 0 | 362 | Warning
28712 | Plumas CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28713 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28714 | Plumas CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.5 | 298 | Warning
28715 | Plumas CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
28718 | Plumas CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10367 |  | 0 | 357 | Warning
28723 | Plumas CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
28725 | Plumas CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 10374 |  | 0 | 485 | Warning
28726 | Plumas CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
28728 | Plumas CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 10377SS | 10379,10382,10380SF+30d | 0.2 | 298 | Warning
28729 | Plumas CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10378 |  | 0 | 298 | Warning
28730 | Plumas CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10378SF+30d |  | 0 | 298 | Warning
28731 | Plumas CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28732 | Plumas CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10378 |  | 0 | 345 | Warning
28744 | Plumas CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
28746 | Plumas CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 10395SS | 10400,10397 | 0.2 | 298 | Warning
28747 | Plumas CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10396 |  | 0 | 298 | Warning
28748 | Plumas CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
28749 | Plumas CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28750 | Plumas CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10396 |  | 0 | 345 | Warning
28751 | Plumas CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
28752 | Plumas CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28753 | Plumas CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28754 | Plumas CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28755 | Plumas CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28756 | Plumas CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28757 | Plumas CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28758 | Plumas CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28759 | Plumas CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28760 | Plumas CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28761 | Plumas CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28762 | Plumas CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28763 | Plumas CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28766 | Plumas CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28767 | Plumas CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28768 | Plumas CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28769 | Plumas CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28770 | Plumas CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10429 | 0 | 234 | Warning
28771 | Plumas CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10430 | 0 | 234 | Warning
28773 | Plumas CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28774 | Plumas CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10435SF+30d |  | 0 | 309 | Warning
28775 | Plumas CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10436SF+30d |  | 0 | 309 | Warning
28776 | Plumas CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10437SF+30d |  | 0 | 309 | Warning
28777 | Plumas CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10438SF+30d |  | 0 | 309 | Warning
28778 | Plumas CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10439SF+30d |  | 0 | 309 | Warning
28779 | Plumas CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10420 |  | 0 | 234 | Warning
28780 | Plumas CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10421 |  | 0 | 234 | Warning
28781 | Plumas CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28782 | Plumas CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10441FS+12d | 0 | 240 | Warning
28783 | Plumas CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28784 | Plumas CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10441SF+60d | 0 | 250 | Warning
28785 | Plumas CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10424SF+30d | 0 | 240 | Warning
28786 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10425SF+30d | 0 | 240 | Warning
28787 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10426SF+30d | 0 | 240 | Warning
28788 | Plumas CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10427SF+30d | 0 | 240 | Warning
28789 | Plumas CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10428SF+30d | 0 | 240 | Warning
28790 | Plumas CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28791 | Plumas CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10432FS+12d,10434SF+60d |  | 0 | 240 | Warning
28794 | Sacramento CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28799 | Sacramento CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28800 | Sacramento CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28801 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28802 | Sacramento CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28804 | Sacramento CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
28805 | Sacramento CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
28827 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
28828 | Sacramento CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
28829 | Sacramento CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
28830 | Sacramento CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
28831 | Sacramento CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
28832 | Sacramento CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
28833 | Sacramento CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
28834 | Sacramento CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
28835 | Sacramento CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28836 | Sacramento CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
28837 | Sacramento CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
28838 | Sacramento CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28839 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
28846 | Sacramento CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
28847 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10498SS | 0 | 414 | Warning
28848 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 10497SS |  | 0 | 414 | Warning
28849 | Sacramento CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 10500SS | 0 | 362 | Warning
28850 | Sacramento CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 10499SS |  | 0 | 362 | Warning
28851 | Sacramento CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
28852 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10503SS | 0 | 352 | Warning
28853 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 10502SS |  | 0 | 352 | Warning
28854 | Sacramento CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
28855 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10506SS | 0 | 288 | Warning
28856 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10505SS |  | 0 | 288 | Warning
28857 | Sacramento CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
28858 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10509SS | 0 | 268 | Warning
28859 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 10508SS |  | 0 | 268 | Warning
28860 | Sacramento CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
28861 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10512SS | 0 | 246 | Warning
28862 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 10511SS |  | 0 | 246 | Warning
28863 | Sacramento CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
28864 | Sacramento CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.49 | 234 | Warning
28867 | Sacramento CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 10516 |  | 0.6 | 234 | Warning
28871 | Sacramento CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28874 | Sacramento CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 10523 |  | 0.2 | 466 | Warning
28875 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28877 | Sacramento CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10526 | 10528 | 0 | 405 | Warning
28878 | Sacramento CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10527 |  | 0 | 405 | Warning
28879 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28881 | Sacramento CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10530 | 10532 | 0 | 405 | Warning
28882 | Sacramento CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10531 |  | 0 | 405 | Warning
28883 | Sacramento CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
28884 | Sacramento CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10535 | 0 | 362 | Warning
28885 | Sacramento CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10534 | 10536 | 0 | 362 | Warning
28886 | Sacramento CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10535 |  | 0 | 362 | Warning
28887 | Sacramento CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
28888 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
28889 | Sacramento CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
28890 | Sacramento CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
28893 | Sacramento CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10542 |  | 0 | 357 | Warning
28898 | Sacramento CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
28900 | Sacramento CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 10549 |  | 0 | 485 | Warning
28901 | Sacramento CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
28903 | Sacramento CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 10552SS | 10554,10557,10555SF+30d | 0 | 298 | Warning
28904 | Sacramento CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10553 |  | 0 | 298 | Warning
28905 | Sacramento CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10553SF+30d |  | 0 | 298 | Warning
28906 | Sacramento CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28907 | Sacramento CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10553 |  | 0 | 345 | Warning
28908 | Sacramento CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
28911 | Sacramento CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 10560SS |  | 0 | 445 | Warning
28919 | Sacramento CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
28921 | Sacramento CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 10570SS | 10575,10572 | 0 | 298 | Warning
28922 | Sacramento CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10571 |  | 0 | 298 | Warning
28923 | Sacramento CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
28924 | Sacramento CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
28925 | Sacramento CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10571 |  | 0 | 345 | Warning
28926 | Sacramento CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
28927 | Sacramento CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28928 | Sacramento CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28929 | Sacramento CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28930 | Sacramento CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28931 | Sacramento CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28932 | Sacramento CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28933 | Sacramento CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28934 | Sacramento CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28935 | Sacramento CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28936 | Sacramento CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28937 | Sacramento CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
28938 | Sacramento CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
28941 | Sacramento CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
28942 | Sacramento CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
28943 | Sacramento CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
28944 | Sacramento CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
28945 | Sacramento CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10604 | 0 | 234 | Warning
28946 | Sacramento CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10605 | 0 | 234 | Warning
28948 | Sacramento CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
28949 | Sacramento CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10610SF+30d |  | 0 | 309 | Warning
28950 | Sacramento CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10611SF+30d |  | 0 | 309 | Warning
28951 | Sacramento CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10612SF+30d |  | 0 | 309 | Warning
28952 | Sacramento CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10613SF+30d |  | 0 | 309 | Warning
28953 | Sacramento CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10614SF+30d |  | 0 | 309 | Warning
28954 | Sacramento CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10595 |  | 0 | 234 | Warning
28955 | Sacramento CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10596 |  | 0 | 234 | Warning
28956 | Sacramento CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
28957 | Sacramento CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10616FS+12d | 0 | 240 | Warning
28958 | Sacramento CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
28959 | Sacramento CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10616SF+60d | 0 | 250 | Warning
28960 | Sacramento CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10599SF+30d | 0 | 240 | Warning
28961 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10600SF+30d | 0 | 240 | Warning
28962 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10601SF+30d | 0 | 240 | Warning
28963 | Sacramento CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10602SF+30d | 0 | 240 | Warning
28964 | Sacramento CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10603SF+30d | 0 | 240 | Warning
28965 | Sacramento CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
28966 | Sacramento CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10607FS+12d,10609SF+60d |  | 0 | 240 | Warning
28969 | San Benito CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
28974 | San Benito CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
28975 | San Benito CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
28976 | San Benito CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
28977 | San Benito CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
28979 | San Benito CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
28980 | San Benito CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29002 | San Benito CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29003 | San Benito CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29004 | San Benito CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29005 | San Benito CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29006 | San Benito CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29007 | San Benito CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29008 | San Benito CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29009 | San Benito CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29010 | San Benito CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29011 | San Benito CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29012 | San Benito CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29013 | San Benito CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29014 | San Benito CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29021 | San Benito CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29022 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10673SS | 0 | 414 | Warning
29023 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 10672SS |  | 0 | 414 | Warning
29024 | San Benito CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 10675SS | 0 | 362 | Warning
29025 | San Benito CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 10674SS |  | 0 | 362 | Warning
29026 | San Benito CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29027 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10678SS | 0 | 352 | Warning
29028 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 10677SS |  | 0 | 352 | Warning
29029 | San Benito CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29030 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10681SS | 0 | 288 | Warning
29031 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10680SS |  | 0 | 288 | Warning
29032 | San Benito CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29033 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10684SS | 0 | 268 | Warning
29034 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 10683SS |  | 0 | 268 | Warning
29035 | San Benito CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29036 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10687SS | 0 | 246 | Warning
29037 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 10686SS |  | 0 | 246 | Warning
29038 | San Benito CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29039 | San Benito CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.42 | 234 | Warning
29042 | San Benito CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 10691 |  | 0.4 | 234 | Warning
29046 | San Benito CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29049 | San Benito CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 10698 |  | 0.2 | 466 | Warning
29050 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29052 | San Benito CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10701 | 10703 | 0.2 | 405 | Warning
29053 | San Benito CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10702 |  | 0 | 405 | Warning
29054 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29056 | San Benito CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10705 | 10707 | 0 | 405 | Warning
29057 | San Benito CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10706 |  | 0 | 405 | Warning
29058 | San Benito CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29059 | San Benito CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10710 | 0 | 362 | Warning
29060 | San Benito CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10709 | 10711 | 0 | 362 | Warning
29061 | San Benito CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10710 |  | 0 | 362 | Warning
29062 | San Benito CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29063 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29064 | San Benito CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.53 | 298 | Warning
29065 | San Benito CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
29068 | San Benito CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10717 |  | 0 | 357 | Warning
29073 | San Benito CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
29075 | San Benito CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 10724 |  | 0.2 | 485 | Warning
29076 | San Benito CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.66 | 298 | Warning
29079 | San Benito CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10728 |  | 0 | 298 | Warning
29081 | San Benito CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29082 | San Benito CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10728 |  | 0 | 345 | Warning
29083 | San Benito CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.68 | 445 | Warning
29085 | San Benito CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 10734SS | 10736SS | 0.95 | 485 | Warning
29086 | San Benito CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 10735SS |  | 0.2 | 445 | Warning
29091 | San Benito CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.67 | 508 | Warning
29093 | San Benito CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 10742 |  | 0.2 | 508 | Warning
29094 | San Benito CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.14 | 298 | Warning
29095 | San Benito CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 10739,10746SS | 0.2 | 508 | Warning
29096 | San Benito CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 10745SS | 10750,10747 | 0.2 | 298 | Warning
29097 | San Benito CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10746 |  | 0 | 298 | Warning
29098 | San Benito CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
29099 | San Benito CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29100 | San Benito CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10746 |  | 0 | 345 | Warning
29101 | San Benito CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29102 | San Benito CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29103 | San Benito CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29104 | San Benito CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29105 | San Benito CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29106 | San Benito CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29107 | San Benito CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29108 | San Benito CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29109 | San Benito CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29110 | San Benito CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29111 | San Benito CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29112 | San Benito CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29113 | San Benito CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29116 | San Benito CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29117 | San Benito CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29118 | San Benito CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29119 | San Benito CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29120 | San Benito CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10779 | 0 | 234 | Warning
29121 | San Benito CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10780 | 0 | 234 | Warning
29123 | San Benito CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29124 | San Benito CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10785SF+30d |  | 0 | 309 | Warning
29125 | San Benito CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10786SF+30d |  | 0 | 309 | Warning
29126 | San Benito CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10787SF+30d |  | 0 | 309 | Warning
29127 | San Benito CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10788SF+30d |  | 0 | 309 | Warning
29128 | San Benito CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10789SF+30d |  | 0 | 309 | Warning
29129 | San Benito CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10770 |  | 0 | 234 | Warning
29130 | San Benito CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10771 |  | 0 | 234 | Warning
29131 | San Benito CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
29132 | San Benito CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10791FS+12d | 0 | 240 | Warning
29133 | San Benito CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
29134 | San Benito CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10791SF+60d | 0 | 250 | Warning
29135 | San Benito CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10774SF+30d | 0 | 240 | Warning
29136 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10775SF+30d | 0 | 240 | Warning
29137 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10776SF+30d | 0 | 240 | Warning
29138 | San Benito CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10777SF+30d | 0 | 240 | Warning
29139 | San Benito CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10778SF+30d | 0 | 240 | Warning
29140 | San Benito CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
29141 | San Benito CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10782FS+12d,10784SF+60d |  | 0 | 240 | Warning
29144 | San Bernardino CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
29149 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
29150 | San Bernardino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
29151 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
29152 | San Bernardino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
29154 | San Bernardino CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
29155 | San Bernardino CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29177 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29178 | San Bernardino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29179 | San Bernardino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29180 | San Bernardino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29181 | San Bernardino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29182 | San Bernardino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29183 | San Bernardino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29184 | San Bernardino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29185 | San Bernardino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29186 | San Bernardino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29187 | San Bernardino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29188 | San Bernardino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29189 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29196 | San Bernardino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29197 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10848SS | 0 | 414 | Warning
29198 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 10847SS |  | 0 | 414 | Warning
29199 | San Bernardino CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 10850SS | 0 | 362 | Warning
29200 | San Bernardino CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 10849SS |  | 0 | 362 | Warning
29201 | San Bernardino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29202 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10853SS | 0 | 352 | Warning
29203 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 10852SS |  | 0 | 352 | Warning
29204 | San Bernardino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29205 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10856SS | 0 | 288 | Warning
29206 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10855SS |  | 0 | 288 | Warning
29207 | San Bernardino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29208 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10859SS | 0 | 268 | Warning
29209 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 10858SS |  | 0 | 268 | Warning
29210 | San Bernardino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29211 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10862SS | 0 | 246 | Warning
29212 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 10861SS |  | 0 | 246 | Warning
29213 | San Bernardino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29214 | San Bernardino CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.32 | 234 | Warning
29217 | San Bernardino CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 10866 |  | 0.2 | 234 | Warning
29221 | San Bernardino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29224 | San Bernardino CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 10873 |  | 0.2 | 466 | Warning
29225 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29227 | San Bernardino CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 10876 | 10878 | 0.2 | 405 | Warning
29228 | San Bernardino CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 10877 |  | 0 | 405 | Warning
29229 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29230 | San Bernardino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10881 | 0.2 | 405 | Warning
29231 | San Bernardino CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 10880 | 10882 | 0 | 405 | Warning
29232 | San Bernardino CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 10881 |  | 0 | 405 | Warning
29233 | San Bernardino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29234 | San Bernardino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10885 | 0 | 362 | Warning
29235 | San Bernardino CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 10884 | 10886 | 0 | 362 | Warning
29236 | San Bernardino CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 10885 |  | 0 | 362 | Warning
29237 | San Bernardino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29238 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29239 | San Bernardino CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.48 | 298 | Warning
29240 | San Bernardino CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
29243 | San Bernardino CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 10892 |  | 0.6 | 357 | Warning
29248 | San Bernardino CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.98 | 485 | Warning
29250 | San Bernardino CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 10899 |  | 0.95 | 485 | Warning
29251 | San Bernardino CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
29253 | San Bernardino CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 10902SS | 10904,10907,10905SF+30d | 0.2 | 298 | Warning
29254 | San Bernardino CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10903 |  | 0 | 298 | Warning
29255 | San Bernardino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10903SF+30d |  | 0 | 298 | Warning
29256 | San Bernardino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29257 | San Bernardino CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10903 |  | 0 | 345 | Warning
29258 | San Bernardino CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.71 | 445 | Warning
29259 | San Bernardino CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 10910SS | 0.8 | 485 | Warning
29261 | San Bernardino CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 10910SS |  | 0.4 | 445 | Warning
29269 | San Bernardino CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
29271 | San Bernardino CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 10920SS | 10925,10922 | 0.2 | 298 | Warning
29272 | San Bernardino CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 10921 |  | 0 | 298 | Warning
29273 | San Bernardino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
29274 | San Bernardino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29275 | San Bernardino CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 10921 |  | 0 | 345 | Warning
29276 | San Bernardino CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29277 | San Bernardino CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29278 | San Bernardino CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29279 | San Bernardino CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29280 | San Bernardino CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29281 | San Bernardino CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29282 | San Bernardino CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29283 | San Bernardino CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29284 | San Bernardino CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29285 | San Bernardino CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29286 | San Bernardino CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29287 | San Bernardino CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29288 | San Bernardino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29291 | San Bernardino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29292 | San Bernardino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29293 | San Bernardino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29294 | San Bernardino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29295 | San Bernardino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10954 | 0 | 234 | Warning
29296 | San Bernardino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10955 | 0 | 234 | Warning
29298 | San Bernardino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29299 | San Bernardino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10960SF+30d |  | 0 | 309 | Warning
29300 | San Bernardino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10961SF+30d |  | 0 | 309 | Warning
29301 | San Bernardino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10962SF+30d |  | 0 | 309 | Warning
29302 | San Bernardino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10963SF+30d |  | 0 | 309 | Warning
29303 | San Bernardino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10964SF+30d |  | 0 | 309 | Warning
29304 | San Bernardino CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10945 |  | 0 | 234 | Warning
29305 | San Bernardino CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 10946 |  | 0 | 234 | Warning
29306 | San Bernardino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
29307 | San Bernardino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10966FS+12d | 0 | 240 | Warning
29308 | San Bernardino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
29309 | San Bernardino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10966SF+60d | 0 | 250 | Warning
29310 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10949SF+30d | 0 | 240 | Warning
29311 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10950SF+30d | 0 | 240 | Warning
29312 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10951SF+30d | 0 | 240 | Warning
29313 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10952SF+30d | 0 | 240 | Warning
29314 | San Bernardino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10953SF+30d | 0 | 240 | Warning
29315 | San Bernardino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
29316 | San Bernardino CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 10957FS+12d,10959SF+60d |  | 0 | 240 | Warning
29319 | San Francisco CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
29324 | San Francisco CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
29325 | San Francisco CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
29326 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
29327 | San Francisco CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
29329 | San Francisco CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
29330 | San Francisco CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29352 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29353 | San Francisco CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29354 | San Francisco CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29355 | San Francisco CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29356 | San Francisco CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29357 | San Francisco CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29358 | San Francisco CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29359 | San Francisco CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29360 | San Francisco CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29361 | San Francisco CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29362 | San Francisco CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29363 | San Francisco CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29364 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29371 | San Francisco CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29372 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11023SS | 0 | 414 | Warning
29373 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11022SS |  | 0 | 414 | Warning
29374 | San Francisco CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 11025SS | 0 | 362 | Warning
29375 | San Francisco CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 11024SS |  | 0 | 362 | Warning
29376 | San Francisco CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29377 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11028SS | 0 | 352 | Warning
29378 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11027SS |  | 0 | 352 | Warning
29379 | San Francisco CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29380 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11031SS | 0 | 288 | Warning
29381 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11030SS |  | 0 | 288 | Warning
29382 | San Francisco CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29383 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11034SS | 0 | 268 | Warning
29384 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11033SS |  | 0 | 268 | Warning
29385 | San Francisco CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29386 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11037SS | 0 | 246 | Warning
29387 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11036SS |  | 0 | 246 | Warning
29388 | San Francisco CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29389 | San Francisco CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.58 | 234 | Warning
29392 | San Francisco CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11041 |  | 0.8 | 234 | Warning
29396 | San Francisco CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29399 | San Francisco CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 11048 |  | 0.2 | 466 | Warning
29400 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29402 | San Francisco CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11051 | 11053 | 0.4 | 405 | Warning
29403 | San Francisco CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11052 |  | 0 | 405 | Warning
29404 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29405 | San Francisco CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11056 | 0.8 | 405 | Warning
29406 | San Francisco CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11055 | 11057 | 0 | 405 | Warning
29407 | San Francisco CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11056 |  | 0 | 405 | Warning
29408 | San Francisco CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29409 | San Francisco CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11060 | 0 | 362 | Warning
29410 | San Francisco CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11059 | 11061 | 0 | 362 | Warning
29411 | San Francisco CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11060 |  | 0 | 362 | Warning
29412 | San Francisco CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29413 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29414 | San Francisco CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.45 | 298 | Warning
29426 | San Francisco CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
29428 | San Francisco CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11077SS | 11079,11082,11080SF+30d | 0.2 | 298 | Warning
29429 | San Francisco CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11078 |  | 0 | 298 | Warning
29430 | San Francisco CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11078SF+30d |  | 0 | 298 | Warning
29431 | San Francisco CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29432 | San Francisco CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11078 |  | 0 | 345 | Warning
29433 | San Francisco CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
29436 | San Francisco CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 11085SS |  | 0 | 445 | Warning
29444 | San Francisco CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
29446 | San Francisco CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11095SS | 11100,11097 | 0 | 298 | Warning
29447 | San Francisco CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11096 |  | 0 | 298 | Warning
29448 | San Francisco CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
29449 | San Francisco CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29450 | San Francisco CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11096 |  | 0 | 345 | Warning
29451 | San Francisco CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29452 | San Francisco CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29453 | San Francisco CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29454 | San Francisco CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29455 | San Francisco CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29456 | San Francisco CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29457 | San Francisco CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29458 | San Francisco CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29459 | San Francisco CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29460 | San Francisco CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29461 | San Francisco CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29462 | San Francisco CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29463 | San Francisco CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29466 | San Francisco CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29467 | San Francisco CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29468 | San Francisco CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29469 | San Francisco CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29470 | San Francisco CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11129 | 0 | 234 | Warning
29471 | San Francisco CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11130 | 0 | 234 | Warning
29473 | San Francisco CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29474 | San Francisco CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11135SF+30d |  | 0 | 309 | Warning
29475 | San Francisco CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11136SF+30d |  | 0 | 309 | Warning
29476 | San Francisco CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11137SF+30d |  | 0 | 309 | Warning
29477 | San Francisco CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11138SF+30d |  | 0 | 309 | Warning
29478 | San Francisco CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11139SF+30d |  | 0 | 309 | Warning
29479 | San Francisco CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11120 |  | 0 | 234 | Warning
29480 | San Francisco CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11121 |  | 0 | 234 | Warning
29481 | San Francisco CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
29482 | San Francisco CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11141FS+12d | 0 | 240 | Warning
29483 | San Francisco CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
29484 | San Francisco CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11141SF+60d | 0 | 250 | Warning
29485 | San Francisco CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11124SF+30d | 0 | 240 | Warning
29486 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11125SF+30d | 0 | 240 | Warning
29487 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11126SF+30d | 0 | 240 | Warning
29488 | San Francisco CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11127SF+30d | 0 | 240 | Warning
29489 | San Francisco CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11128SF+30d | 0 | 240 | Warning
29490 | San Francisco CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
29491 | San Francisco CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 11132FS+12d,11134SF+60d |  | 0 | 240 | Warning
29494 | San Joaquin CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
29499 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
29500 | San Joaquin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
29501 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
29502 | San Joaquin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
29504 | San Joaquin CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
29505 | San Joaquin CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29527 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29528 | San Joaquin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29529 | San Joaquin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29530 | San Joaquin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29531 | San Joaquin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29532 | San Joaquin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29533 | San Joaquin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29534 | San Joaquin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29535 | San Joaquin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29536 | San Joaquin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29537 | San Joaquin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29538 | San Joaquin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29539 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29546 | San Joaquin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29547 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11198SS | 0 | 414 | Warning
29548 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11197SS |  | 0 | 414 | Warning
29549 | San Joaquin CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 299d | 3885FS+29d | 11200 | 0 | 299 | Warning
29550 | San Joaquin CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | May 4, 2026 8:00 AM | July 31, 2026 5:00 PM | 63 | 299d | 11199 |  | 0 | 299 | Warning
29551 | San Joaquin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29552 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11203SS | 0 | 352 | Warning
29553 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11202SS |  | 0 | 352 | Warning
29554 | San Joaquin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29555 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11206SS | 0 | 288 | Warning
29556 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11205SS |  | 0 | 288 | Warning
29557 | San Joaquin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29558 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11209SS | 0 | 268 | Warning
29559 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11208SS |  | 0 | 268 | Warning
29560 | San Joaquin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29561 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11212SS | 0 | 246 | Warning
29562 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11211SS |  | 0 | 246 | Warning
29563 | San Joaquin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29564 | San Joaquin CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.52 | 234 | Warning
29567 | San Joaquin CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11216 |  | 0.6 | 234 | Warning
29571 | San Joaquin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29574 | San Joaquin CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 11223 |  | 0.6 | 466 | Warning
29575 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29577 | San Joaquin CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11226 | 11228 | 0.4 | 405 | Warning
29578 | San Joaquin CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11227 |  | 0 | 405 | Warning
29579 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29581 | San Joaquin CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11230 | 11232 | 0 | 405 | Warning
29582 | San Joaquin CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11231 |  | 0 | 405 | Warning
29583 | San Joaquin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29584 | San Joaquin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11235 | 0 | 362 | Warning
29585 | San Joaquin CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11234 | 11236 | 0 | 362 | Warning
29586 | San Joaquin CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11235 |  | 0 | 362 | Warning
29587 | San Joaquin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29588 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29589 | San Joaquin CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.56 | 298 | Warning
29601 | San Joaquin CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
29603 | San Joaquin CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11252SS | 11254,11257,11255SF+30d | 0.2 | 298 | Warning
29604 | San Joaquin CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11253 |  | 0 | 298 | Warning
29605 | San Joaquin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11253SF+30d |  | 0 | 298 | Warning
29606 | San Joaquin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29607 | San Joaquin CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11253 |  | 0 | 345 | Warning
29619 | San Joaquin CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.46 | 298 | Warning
29621 | San Joaquin CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11270SS | 11275,11272 | 0.6 | 298 | Warning
29622 | San Joaquin CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11271 |  | 0 | 298 | Warning
29623 | San Joaquin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.6 | 298 | Warning
29624 | San Joaquin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29625 | San Joaquin CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11271 |  | 0 | 345 | Warning
29626 | San Joaquin CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29627 | San Joaquin CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29628 | San Joaquin CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29629 | San Joaquin CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29630 | San Joaquin CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29631 | San Joaquin CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29632 | San Joaquin CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29633 | San Joaquin CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29634 | San Joaquin CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29635 | San Joaquin CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29636 | San Joaquin CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29637 | San Joaquin CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29638 | San Joaquin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29641 | San Joaquin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29642 | San Joaquin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29643 | San Joaquin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29644 | San Joaquin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29645 | San Joaquin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11304 | 0 | 234 | Warning
29646 | San Joaquin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11305 | 0 | 234 | Warning
29648 | San Joaquin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29649 | San Joaquin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11310SF+30d |  | 0 | 309 | Warning
29650 | San Joaquin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11311SF+30d |  | 0 | 309 | Warning
29651 | San Joaquin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11312SF+30d |  | 0 | 309 | Warning
29652 | San Joaquin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11313SF+30d |  | 0 | 309 | Warning
29653 | San Joaquin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11314SF+30d |  | 0 | 309 | Warning
29654 | San Joaquin CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11295 |  | 0 | 234 | Warning
29655 | San Joaquin CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11296 |  | 0 | 234 | Warning
29656 | San Joaquin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
29657 | San Joaquin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11316FS+12d | 0 | 240 | Warning
29658 | San Joaquin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
29659 | San Joaquin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11316SF+60d | 0 | 250 | Warning
29660 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11299SF+30d | 0 | 240 | Warning
29661 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11300SF+30d | 0 | 240 | Warning
29662 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11301SF+30d | 0 | 240 | Warning
29663 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11302SF+30d | 0 | 240 | Warning
29664 | San Joaquin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11303SF+30d | 0 | 240 | Warning
29665 | San Joaquin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
29666 | San Joaquin CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 11307FS+12d,11309SF+60d |  | 0 | 240 | Warning
29669 | San Luis Obispo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
29674 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
29675 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
29676 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
29677 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
29679 | San Luis Obispo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
29680 | San Luis Obispo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29702 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29703 | San Luis Obispo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29704 | San Luis Obispo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29705 | San Luis Obispo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29706 | San Luis Obispo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29707 | San Luis Obispo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29708 | San Luis Obispo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29709 | San Luis Obispo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29710 | San Luis Obispo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29711 | San Luis Obispo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29712 | San Luis Obispo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29713 | San Luis Obispo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29714 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29721 | San Luis Obispo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29722 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11373SS | 0 | 414 | Warning
29723 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11372SS |  | 0 | 414 | Warning
29724 | San Luis Obispo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 11375SS | 0 | 362 | Warning
29725 | San Luis Obispo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 11374SS |  | 0 | 362 | Warning
29726 | San Luis Obispo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29727 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11378SS | 0 | 352 | Warning
29728 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11377SS |  | 0 | 352 | Warning
29729 | San Luis Obispo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29730 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11381SS | 0 | 288 | Warning
29731 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11380SS |  | 0 | 288 | Warning
29732 | San Luis Obispo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29733 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11384SS | 0 | 268 | Warning
29734 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11383SS |  | 0 | 268 | Warning
29735 | San Luis Obispo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29736 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11387SS | 0 | 246 | Warning
29737 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11386SS |  | 0 | 246 | Warning
29738 | San Luis Obispo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29739 | San Luis Obispo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.4 | 234 | Warning
29742 | San Luis Obispo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11391 |  | 0.4 | 234 | Warning
29746 | San Luis Obispo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29749 | San Luis Obispo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 11398 |  | 0.2 | 466 | Warning
29750 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29752 | San Luis Obispo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11401 | 11403 | 0.4 | 405 | Warning
29753 | San Luis Obispo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11402 |  | 0 | 405 | Warning
29754 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29755 | San Luis Obispo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11406 | 0.2 | 405 | Warning
29756 | San Luis Obispo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11405 | 11407 | 0 | 405 | Warning
29757 | San Luis Obispo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11406 |  | 0 | 405 | Warning
29758 | San Luis Obispo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29759 | San Luis Obispo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11410 | 0 | 362 | Warning
29760 | San Luis Obispo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11409 | 11411 | 0 | 362 | Warning
29761 | San Luis Obispo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11410 |  | 0 | 362 | Warning
29762 | San Luis Obispo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29763 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29764 | San Luis Obispo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.44 | 298 | Warning
29765 | San Luis Obispo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
29768 | San Luis Obispo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 11417 |  | 0.6 | 357 | Warning
29776 | San Luis Obispo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.03 | 298 | Warning
29777 | San Luis Obispo CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 11424SS | 11428SS | 0.6 | 508 | Warning
29778 | San Luis Obispo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11427SS | 11429,11432,11430SF+30d | 0 | 298 | Warning
29779 | San Luis Obispo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11428 |  | 0 | 298 | Warning
29780 | San Luis Obispo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11428SF+30d |  | 0 | 298 | Warning
29781 | San Luis Obispo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29782 | San Luis Obispo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11428 |  | 0 | 345 | Warning
29783 | San Luis Obispo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
29786 | San Luis Obispo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 11435SS |  | 0.2 | 445 | Warning
29794 | San Luis Obispo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
29796 | San Luis Obispo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11445SS | 11450,11447 | 0 | 298 | Warning
29797 | San Luis Obispo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11446 |  | 0 | 298 | Warning
29798 | San Luis Obispo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
29799 | San Luis Obispo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29800 | San Luis Obispo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11446 |  | 0 | 345 | Warning
29801 | San Luis Obispo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29802 | San Luis Obispo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29803 | San Luis Obispo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29804 | San Luis Obispo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29805 | San Luis Obispo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29806 | San Luis Obispo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29807 | San Luis Obispo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29808 | San Luis Obispo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29809 | San Luis Obispo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29810 | San Luis Obispo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29811 | San Luis Obispo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29812 | San Luis Obispo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29813 | San Luis Obispo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29816 | San Luis Obispo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29817 | San Luis Obispo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29818 | San Luis Obispo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29819 | San Luis Obispo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29820 | San Luis Obispo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11479 | 0 | 234 | Warning
29821 | San Luis Obispo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11480 | 0 | 234 | Warning
29823 | San Luis Obispo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29824 | San Luis Obispo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11485SF+30d |  | 0 | 309 | Warning
29825 | San Luis Obispo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11486SF+30d |  | 0 | 309 | Warning
29826 | San Luis Obispo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11487SF+30d |  | 0 | 309 | Warning
29827 | San Luis Obispo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11488SF+30d |  | 0 | 309 | Warning
29828 | San Luis Obispo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11489SF+30d |  | 0 | 309 | Warning
29829 | San Luis Obispo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11470 |  | 0 | 234 | Warning
29830 | San Luis Obispo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11471 |  | 0 | 234 | Warning
29831 | San Luis Obispo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
29832 | San Luis Obispo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11491FS+12d | 0 | 240 | Warning
29833 | San Luis Obispo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
29834 | San Luis Obispo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11491SF+60d | 0 | 250 | Warning
29835 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11474SF+30d | 0 | 240 | Warning
29836 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11475SF+30d | 0 | 240 | Warning
29837 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11476SF+30d | 0 | 240 | Warning
29838 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11477SF+30d | 0 | 240 | Warning
29839 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11478SF+30d | 0 | 240 | Warning
29840 | San Luis Obispo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
29841 | San Luis Obispo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 11482FS+12d,11484SF+60d |  | 0 | 240 | Warning
29844 | Santa Barbara CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
29849 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
29850 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
29851 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
29852 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
29854 | Santa Barbara CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
29855 | Santa Barbara CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
29877 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
29878 | Santa Barbara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
29879 | Santa Barbara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
29880 | Santa Barbara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
29881 | Santa Barbara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
29882 | Santa Barbara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
29883 | Santa Barbara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
29884 | Santa Barbara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
29885 | Santa Barbara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29886 | Santa Barbara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
29887 | Santa Barbara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
29888 | Santa Barbara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29889 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
29896 | Santa Barbara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
29897 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11548SS | 0 | 414 | Warning
29898 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11547SS |  | 0 | 414 | Warning
29899 | Santa Barbara CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 11550SS | 0 | 362 | Warning
29900 | Santa Barbara CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 11549SS |  | 0 | 362 | Warning
29901 | Santa Barbara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
29902 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11553SS | 0 | 352 | Warning
29903 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11552SS |  | 0 | 352 | Warning
29904 | Santa Barbara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
29905 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11556SS | 0 | 288 | Warning
29906 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11555SS |  | 0 | 288 | Warning
29907 | Santa Barbara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
29908 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11559SS | 0 | 268 | Warning
29909 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11558SS |  | 0 | 268 | Warning
29910 | Santa Barbara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
29911 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11562SS | 0 | 246 | Warning
29912 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11561SS |  | 0 | 246 | Warning
29913 | Santa Barbara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
29914 | Santa Barbara CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.37 | 234 | Warning
29917 | Santa Barbara CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11566 |  | 0.4 | 234 | Warning
29920 | Santa Barbara CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM | 43 | 550d |  |  | 0.4 | 550 | Warning
29921 | Santa Barbara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29924 | Santa Barbara CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 11573 |  | 0 | 466 | Warning
29925 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29927 | Santa Barbara CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11576 | 11578 | 0.2 | 405 | Warning
29928 | Santa Barbara CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11577 |  | 0 | 405 | Warning
29929 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29930 | Santa Barbara CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11581 | 0.2 | 405 | Warning
29931 | Santa Barbara CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11580 | 11582 | 0 | 405 | Warning
29932 | Santa Barbara CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11581 |  | 0 | 405 | Warning
29933 | Santa Barbara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
29934 | Santa Barbara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11585 | 0 | 362 | Warning
29935 | Santa Barbara CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11584 | 11586 | 0 | 362 | Warning
29936 | Santa Barbara CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11585 |  | 0 | 362 | Warning
29937 | Santa Barbara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
29938 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
29939 | Santa Barbara CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.47 | 298 | Warning
29951 | Santa Barbara CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.03 | 298 | Warning
29952 | Santa Barbara CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 11599SS | 11603SS | 0.6 | 508 | Warning
29953 | Santa Barbara CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11602SS | 11604,11607,11605SF+30d | 0 | 298 | Warning
29954 | Santa Barbara CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11603 |  | 0 | 298 | Warning
29955 | Santa Barbara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11603SF+30d |  | 0 | 298 | Warning
29956 | Santa Barbara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29957 | Santa Barbara CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11603 |  | 0 | 345 | Warning
29958 | Santa Barbara CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.92 | 445 | Warning
29961 | Santa Barbara CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 11610SS |  | 0.8 | 445 | Warning
29969 | Santa Barbara CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.05 | 298 | Warning
29970 | Santa Barbara CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 11614,11621SS | 0.6 | 508 | Warning
29971 | Santa Barbara CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11620SS | 11625,11622 | 0 | 298 | Warning
29972 | Santa Barbara CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11621 |  | 0 | 298 | Warning
29973 | Santa Barbara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
29974 | Santa Barbara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
29975 | Santa Barbara CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11621 |  | 0 | 345 | Warning
29976 | Santa Barbara CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
29977 | Santa Barbara CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29978 | Santa Barbara CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29979 | Santa Barbara CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29980 | Santa Barbara CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29981 | Santa Barbara CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29982 | Santa Barbara CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29983 | Santa Barbara CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29984 | Santa Barbara CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29985 | Santa Barbara CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29986 | Santa Barbara CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29987 | Santa Barbara CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
29988 | Santa Barbara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
29991 | Santa Barbara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
29992 | Santa Barbara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
29993 | Santa Barbara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
29994 | Santa Barbara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
29995 | Santa Barbara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11654 | 0 | 234 | Warning
29996 | Santa Barbara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11655 | 0 | 234 | Warning
29998 | Santa Barbara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
29999 | Santa Barbara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11660SF+30d |  | 0 | 309 | Warning
30000 | Santa Barbara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11661SF+30d |  | 0 | 309 | Warning
30001 | Santa Barbara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11662SF+30d |  | 0 | 309 | Warning
30002 | Santa Barbara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11663SF+30d |  | 0 | 309 | Warning
30003 | Santa Barbara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11664SF+30d |  | 0 | 309 | Warning
30004 | Santa Barbara CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11645 |  | 0 | 234 | Warning
30005 | Santa Barbara CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11646 |  | 0 | 234 | Warning
30006 | Santa Barbara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30007 | Santa Barbara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11666FS+12d | 0 | 240 | Warning
30008 | Santa Barbara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30009 | Santa Barbara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11666SF+60d | 0 | 250 | Warning
30010 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11649SF+30d | 0 | 240 | Warning
30011 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11650SF+30d | 0 | 240 | Warning
30012 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11651SF+30d | 0 | 240 | Warning
30013 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11652SF+30d | 0 | 240 | Warning
30014 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11653SF+30d | 0 | 240 | Warning
30015 | Santa Barbara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30016 | Santa Barbara CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 11657FS+12d,11659SF+60d |  | 0 | 240 | Warning
30019 | Santa Clara CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30024 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30025 | Santa Clara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30026 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30027 | Santa Clara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30029 | Santa Clara CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
30030 | Santa Clara CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
30052 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
30053 | Santa Clara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30054 | Santa Clara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30055 | Santa Clara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30056 | Santa Clara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30057 | Santa Clara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30058 | Santa Clara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30059 | Santa Clara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30060 | Santa Clara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30061 | Santa Clara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30062 | Santa Clara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30063 | Santa Clara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30064 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30071 | Santa Clara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
30072 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11723SS | 0 | 414 | Warning
30073 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11722SS |  | 0 | 414 | Warning
30074 | Santa Clara CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 11725SS | 0 | 362 | Warning
30075 | Santa Clara CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 11724SS |  | 0 | 362 | Warning
30076 | Santa Clara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30077 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11728SS | 0 | 352 | Warning
30078 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11727SS |  | 0 | 352 | Warning
30079 | Santa Clara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30080 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11731SS | 0 | 288 | Warning
30081 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11730SS |  | 0 | 288 | Warning
30082 | Santa Clara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30083 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11734SS | 0 | 268 | Warning
30084 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11733SS |  | 0 | 268 | Warning
30085 | Santa Clara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30086 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11737SS | 0 | 246 | Warning
30087 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11736SS |  | 0 | 246 | Warning
30088 | Santa Clara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30089 | Santa Clara CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.5 | 234 | Warning
30092 | Santa Clara CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11741 |  | 0.6 | 234 | Warning
30096 | Santa Clara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30099 | Santa Clara CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 11748 |  | 0.2 | 466 | Warning
30100 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30102 | Santa Clara CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11751 | 11753 | 0.4 | 405 | Warning
30103 | Santa Clara CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11752 |  | 0 | 405 | Warning
30104 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30106 | Santa Clara CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11755 | 11757 | 0 | 405 | Warning
30107 | Santa Clara CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11756 |  | 0 | 405 | Warning
30108 | Santa Clara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30109 | Santa Clara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11760 | 0 | 362 | Warning
30110 | Santa Clara CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11759 | 11761 | 0 | 362 | Warning
30111 | Santa Clara CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11760 |  | 0 | 362 | Warning
30112 | Santa Clara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30113 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30114 | Santa Clara CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
30115 | Santa Clara CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.76 | 357 | Warning
30116 | Santa Clara CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 11767SS | 0.8 | 405 | Warning
30117 | Santa Clara CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 11766SS | 11768 | 0.8 | 357 | Warning
30118 | Santa Clara CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 11767 |  | 0 | 357 | Warning
30126 | Santa Clara CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
30128 | Santa Clara CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11777SS | 11779,11782,11780SF+30d | 0.2 | 298 | Warning
30129 | Santa Clara CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11778 |  | 0 | 298 | Warning
30130 | Santa Clara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11778SF+30d |  | 0 | 298 | Warning
30131 | Santa Clara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30132 | Santa Clara CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11778 |  | 0 | 345 | Warning
30133 | Santa Clara CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.77 | 445 | Warning
30136 | Santa Clara CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 11785SS |  | 0.4 | 445 | Warning
30144 | Santa Clara CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.14 | 298 | Warning
30146 | Santa Clara CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11795SS | 11800,11797 | 0.2 | 298 | Warning
30147 | Santa Clara CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11796 |  | 0 | 298 | Warning
30148 | Santa Clara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
30149 | Santa Clara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30150 | Santa Clara CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11796 |  | 0 | 345 | Warning
30151 | Santa Clara CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
30152 | Santa Clara CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30153 | Santa Clara CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30154 | Santa Clara CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30155 | Santa Clara CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30156 | Santa Clara CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30157 | Santa Clara CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30158 | Santa Clara CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30159 | Santa Clara CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30160 | Santa Clara CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30161 | Santa Clara CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30162 | Santa Clara CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30163 | Santa Clara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
30166 | Santa Clara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
30167 | Santa Clara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
30168 | Santa Clara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30169 | Santa Clara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
30170 | Santa Clara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11829 | 0 | 234 | Warning
30171 | Santa Clara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11830 | 0 | 234 | Warning
30173 | Santa Clara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
30174 | Santa Clara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11835SF+30d |  | 0 | 309 | Warning
30175 | Santa Clara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11836SF+30d |  | 0 | 309 | Warning
30176 | Santa Clara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11837SF+30d |  | 0 | 309 | Warning
30177 | Santa Clara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11838SF+30d |  | 0 | 309 | Warning
30178 | Santa Clara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11839SF+30d |  | 0 | 309 | Warning
30179 | Santa Clara CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11820 |  | 0 | 234 | Warning
30180 | Santa Clara CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11821 |  | 0 | 234 | Warning
30181 | Santa Clara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30182 | Santa Clara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11841FS+12d | 0 | 240 | Warning
30183 | Santa Clara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30184 | Santa Clara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11841SF+60d | 0 | 250 | Warning
30185 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11824SF+30d | 0 | 240 | Warning
30186 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11825SF+30d | 0 | 240 | Warning
30187 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11826SF+30d | 0 | 240 | Warning
30188 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11827SF+30d | 0 | 240 | Warning
30189 | Santa Clara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11828SF+30d | 0 | 240 | Warning
30190 | Santa Clara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30191 | Santa Clara CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 11832FS+12d,11834SF+60d |  | 0 | 240 | Warning
30194 | Santa Cruz CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30199 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30200 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30201 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30202 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30204 | Santa Cruz CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
30205 | Santa Cruz CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
30227 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
30228 | Santa Cruz CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30229 | Santa Cruz CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30230 | Santa Cruz CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30231 | Santa Cruz CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30232 | Santa Cruz CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30233 | Santa Cruz CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30234 | Santa Cruz CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30235 | Santa Cruz CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30236 | Santa Cruz CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30237 | Santa Cruz CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30238 | Santa Cruz CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30239 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30246 | Santa Cruz CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
30247 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11898SS | 0 | 414 | Warning
30248 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 11897SS |  | 0 | 414 | Warning
30249 | Santa Cruz CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 11900SS | 0 | 362 | Warning
30250 | Santa Cruz CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 11899SS |  | 0 | 362 | Warning
30251 | Santa Cruz CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30252 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11903SS | 0 | 352 | Warning
30253 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 11902SS |  | 0 | 352 | Warning
30254 | Santa Cruz CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30255 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11906SS | 0 | 288 | Warning
30256 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11905SS |  | 0 | 288 | Warning
30257 | Santa Cruz CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30258 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11909SS | 0 | 268 | Warning
30259 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 11908SS |  | 0 | 268 | Warning
30260 | Santa Cruz CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30261 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11912SS | 0 | 246 | Warning
30262 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 11911SS |  | 0 | 246 | Warning
30263 | Santa Cruz CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30264 | Santa Cruz CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.43 | 234 | Warning
30267 | Santa Cruz CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 11916 |  | 0.4 | 234 | Warning
30271 | Santa Cruz CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30275 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30277 | Santa Cruz CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 11926 | 11928 | 0.2 | 405 | Warning
30278 | Santa Cruz CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 11927 |  | 0 | 405 | Warning
30279 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30280 | Santa Cruz CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11931 | 0.2 | 405 | Warning
30281 | Santa Cruz CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 11930 | 11932 | 0 | 405 | Warning
30282 | Santa Cruz CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 11931 |  | 0 | 405 | Warning
30283 | Santa Cruz CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30284 | Santa Cruz CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11935 | 0 | 362 | Warning
30285 | Santa Cruz CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 11934 | 11936 | 0 | 362 | Warning
30286 | Santa Cruz CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 11935 |  | 0 | 362 | Warning
30287 | Santa Cruz CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30288 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30289 | Santa Cruz CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.33 | 298 | Warning
30290 | Santa Cruz CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
30291 | Santa Cruz CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 11942SS | 0.6 | 405 | Warning
30292 | Santa Cruz CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 11941SS | 11943 | 0.6 | 357 | Warning
30293 | Santa Cruz CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 11942 |  | 0 | 357 | Warning
30298 | Santa Cruz CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
30300 | Santa Cruz CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 11949 |  | 0.2 | 485 | Warning
30301 | Santa Cruz CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.07 | 298 | Warning
30302 | Santa Cruz CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 11949SS | 11953SS | 0.2 | 508 | Warning
30303 | Santa Cruz CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 11952SS | 11954,11957,11955SF+30d | 0.2 | 298 | Warning
30304 | Santa Cruz CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11953 |  | 0 | 298 | Warning
30305 | Santa Cruz CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11953SF+30d |  | 0 | 298 | Warning
30306 | Santa Cruz CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30307 | Santa Cruz CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11953 |  | 0 | 345 | Warning
30308 | Santa Cruz CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.51 | 445 | Warning
30309 | Santa Cruz CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 11960SS | 0.6 | 485 | Warning
30310 | Santa Cruz CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 11959SS | 11961SS | 0.8 | 485 | Warning
30311 | Santa Cruz CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 11960SS |  | 0.2 | 445 | Warning
30319 | Santa Cruz CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.14 | 298 | Warning
30320 | Santa Cruz CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 11964,11971SS | 0.2 | 508 | Warning
30321 | Santa Cruz CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 11970SS | 11975,11972 | 0.2 | 298 | Warning
30322 | Santa Cruz CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 11971 |  | 0 | 298 | Warning
30323 | Santa Cruz CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
30324 | Santa Cruz CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30325 | Santa Cruz CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 11971 |  | 0 | 345 | Warning
30326 | Santa Cruz CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
30327 | Santa Cruz CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30328 | Santa Cruz CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30329 | Santa Cruz CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30330 | Santa Cruz CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30331 | Santa Cruz CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30332 | Santa Cruz CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30333 | Santa Cruz CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30334 | Santa Cruz CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30335 | Santa Cruz CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30336 | Santa Cruz CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30337 | Santa Cruz CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30338 | Santa Cruz CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
30341 | Santa Cruz CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
30342 | Santa Cruz CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
30343 | Santa Cruz CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30344 | Santa Cruz CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
30345 | Santa Cruz CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12004 | 0 | 234 | Warning
30346 | Santa Cruz CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12005 | 0 | 234 | Warning
30348 | Santa Cruz CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
30349 | Santa Cruz CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12010SF+30d |  | 0 | 309 | Warning
30350 | Santa Cruz CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12011SF+30d |  | 0 | 309 | Warning
30351 | Santa Cruz CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12012SF+30d |  | 0 | 309 | Warning
30352 | Santa Cruz CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12013SF+30d |  | 0 | 309 | Warning
30353 | Santa Cruz CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12014SF+30d |  | 0 | 309 | Warning
30354 | Santa Cruz CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11995 |  | 0 | 234 | Warning
30355 | Santa Cruz CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 11996 |  | 0 | 234 | Warning
30356 | Santa Cruz CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30357 | Santa Cruz CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12016FS+12d | 0 | 240 | Warning
30358 | Santa Cruz CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30359 | Santa Cruz CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12016SF+60d | 0 | 250 | Warning
30360 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11999SF+30d | 0 | 240 | Warning
30361 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12000SF+30d | 0 | 240 | Warning
30362 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12001SF+30d | 0 | 240 | Warning
30363 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12002SF+30d | 0 | 240 | Warning
30364 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12003SF+30d | 0 | 240 | Warning
30365 | Santa Cruz CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30366 | Santa Cruz CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12007FS+12d,12009SF+60d |  | 0 | 240 | Warning
30369 | Shasta CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30374 | Shasta CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30375 | Shasta CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30376 | Shasta CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30377 | Shasta CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30379 | Shasta CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
30380 | Shasta CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
30403 | Shasta CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30404 | Shasta CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30405 | Shasta CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30406 | Shasta CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30407 | Shasta CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30408 | Shasta CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30409 | Shasta CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30410 | Shasta CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30411 | Shasta CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30412 | Shasta CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30413 | Shasta CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30414 | Shasta CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30421 | Shasta CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
30422 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12073SS | 0 | 414 | Warning
30423 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12072SS |  | 0 | 414 | Warning
30424 | Shasta CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 12075SS | 0 | 362 | Warning
30425 | Shasta CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 12074SS |  | 0 | 362 | Warning
30426 | Shasta CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30427 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12078SS | 0 | 352 | Warning
30428 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12077SS |  | 0 | 352 | Warning
30429 | Shasta CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30430 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12081SS | 0 | 288 | Warning
30431 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12080SS |  | 0 | 288 | Warning
30432 | Shasta CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30433 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12084SS | 0 | 268 | Warning
30434 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12083SS |  | 0 | 268 | Warning
30435 | Shasta CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30436 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12087SS | 0 | 246 | Warning
30437 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12086SS |  | 0 | 246 | Warning
30438 | Shasta CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30439 | Shasta CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.31 | 234 | Warning
30442 | Shasta CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12091 |  | 0.2 | 234 | Warning
30446 | Shasta CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30449 | Shasta CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12098 |  | 0.2 | 466 | Warning
30450 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30452 | Shasta CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12101 | 12103 | 0.2 | 405 | Warning
30453 | Shasta CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12102 |  | 0 | 405 | Warning
30454 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30455 | Shasta CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12106 | 0 | 405 | Warning
30456 | Shasta CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12105 | 12107 | 0 | 405 | Warning
30457 | Shasta CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12106 |  | 0 | 405 | Warning
30458 | Shasta CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30459 | Shasta CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12110 | 0 | 362 | Warning
30460 | Shasta CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12109 | 12111 | 0 | 362 | Warning
30461 | Shasta CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12110 |  | 0 | 362 | Warning
30462 | Shasta CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30463 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30464 | Shasta CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.43 | 298 | Warning
30465 | Shasta CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.96 | 357 | Warning
30468 | Shasta CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 12117 |  | 0.2 | 357 | Warning
30473 | Shasta CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
30475 | Shasta CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 12124 |  | 0.2 | 485 | Warning
30476 | Shasta CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
30478 | Shasta CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12127SS | 12129,12132,12130SF+30d | 0.2 | 298 | Warning
30479 | Shasta CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12128 |  | 0 | 298 | Warning
30480 | Shasta CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12128SF+30d |  | 0 | 298 | Warning
30481 | Shasta CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30482 | Shasta CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12128 |  | 0 | 345 | Warning
30483 | Shasta CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.45 | 445 | Warning
30485 | Shasta CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 12134SS | 12136SS | 0.2 | 485 | Warning
30486 | Shasta CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 12135SS |  | 0.2 | 445 | Warning
30491 | Shasta CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.98 | 508 | Warning
30493 | Shasta CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 12142 |  | 0.95 | 508 | Warning
30494 | Shasta CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
30496 | Shasta CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 12145SS | 12150,12147 | 0.2 | 298 | Warning
30497 | Shasta CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12146 |  | 0 | 298 | Warning
30498 | Shasta CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
30499 | Shasta CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30500 | Shasta CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12146 |  | 0 | 345 | Warning
30501 | Shasta CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
30502 | Shasta CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30503 | Shasta CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30504 | Shasta CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30505 | Shasta CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30506 | Shasta CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30507 | Shasta CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30508 | Shasta CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30509 | Shasta CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30510 | Shasta CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30511 | Shasta CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30512 | Shasta CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30513 | Shasta CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
30516 | Shasta CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
30517 | Shasta CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
30518 | Shasta CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30519 | Shasta CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
30520 | Shasta CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12179 | 0 | 234 | Warning
30521 | Shasta CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12180 | 0 | 234 | Warning
30523 | Shasta CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
30524 | Shasta CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12185SF+30d |  | 0 | 309 | Warning
30525 | Shasta CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12186SF+30d |  | 0 | 309 | Warning
30526 | Shasta CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12187SF+30d |  | 0 | 309 | Warning
30527 | Shasta CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12188SF+30d |  | 0 | 309 | Warning
30528 | Shasta CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12189SF+30d |  | 0 | 309 | Warning
30529 | Shasta CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12170 |  | 0 | 234 | Warning
30530 | Shasta CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12171 |  | 0 | 234 | Warning
30531 | Shasta CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30532 | Shasta CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12191FS+12d | 0 | 240 | Warning
30533 | Shasta CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30534 | Shasta CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12191SF+60d | 0 | 250 | Warning
30535 | Shasta CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12174SF+30d | 0 | 240 | Warning
30536 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12175SF+30d | 0 | 240 | Warning
30537 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12176SF+30d | 0 | 240 | Warning
30538 | Shasta CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12177SF+30d | 0 | 240 | Warning
30539 | Shasta CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12178SF+30d | 0 | 240 | Warning
30540 | Shasta CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30541 | Shasta CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12182FS+12d,12184SF+60d |  | 0 | 240 | Warning
30544 | Sierra CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30549 | Sierra CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30550 | Sierra CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30551 | Sierra CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30552 | Sierra CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30554 | Sierra CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
30555 | Sierra CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
30577 | Sierra CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
30578 | Sierra CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30579 | Sierra CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30580 | Sierra CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30581 | Sierra CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30582 | Sierra CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30583 | Sierra CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30584 | Sierra CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30585 | Sierra CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30586 | Sierra CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30587 | Sierra CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30588 | Sierra CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30589 | Sierra CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30596 | Sierra CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
30597 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12248SS | 0 | 414 | Warning
30598 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12247SS |  | 0 | 414 | Warning
30599 | Sierra CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 3885FS+29d | 12250SS | 0 | 362 | Warning
30600 | Sierra CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 12249SS |  | 0 | 362 | Warning
30601 | Sierra CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30602 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12253SS | 0 | 352 | Warning
30603 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12252SS |  | 0 | 352 | Warning
30604 | Sierra CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30605 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12256SS | 0 | 288 | Warning
30606 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12255SS |  | 0 | 288 | Warning
30607 | Sierra CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30608 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12259SS | 0 | 268 | Warning
30609 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12258SS |  | 0 | 268 | Warning
30610 | Sierra CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30611 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12262SS | 0 | 246 | Warning
30612 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12261SS |  | 0 | 246 | Warning
30613 | Sierra CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30614 | Sierra CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.5 | 234 | Warning
30617 | Sierra CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12266 |  | 0.6 | 234 | Warning
30621 | Sierra CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30624 | Sierra CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12273 |  | 0.2 | 466 | Warning
30625 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30627 | Sierra CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12276 | 12278 | 0.4 | 405 | Warning
30628 | Sierra CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12277 |  | 0 | 405 | Warning
30629 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30631 | Sierra CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12280 | 12282 | 0 | 405 | Warning
30632 | Sierra CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12281 |  | 0 | 405 | Warning
30633 | Sierra CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30634 | Sierra CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12285 | 0 | 362 | Warning
30635 | Sierra CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12284 | 12286 | 0 | 362 | Warning
30636 | Sierra CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12285 |  | 0 | 362 | Warning
30637 | Sierra CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30638 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30639 | Sierra CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 398 | 298d |  |  | 0.27 | 298 | Warning
30641 | Sierra CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.84 | 485 | Warning
30643 | Sierra CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 12292 |  | 0.6 | 485 | Warning
30644 | Sierra CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
30646 | Sierra CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12295SS | 12297,12300,12298SF+30d | 0 | 298 | Warning
30647 | Sierra CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12296 |  | 0 | 298 | Warning
30648 | Sierra CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12296SF+30d |  | 0 | 298 | Warning
30649 | Sierra CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30650 | Sierra CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12296 |  | 0 | 345 | Warning
30657 | Sierra CW-Determine priority for Organization-specific custom Forms | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d |  |  | 0.6 | 508 | Warning
30658 | Sierra CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d |  |  | 0.6 | 508 | Warning
30659 | Sierra CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
30660 | Sierra CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 64 | 299d |  |  | 0 | 299 | Warning
30661 | Sierra CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
30662 | Sierra CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30663 | Sierra CW-POC or Organization Leadership to sign off on form completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | 346 | Warning
30664 | Sierra CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 363d |  |  | 0.2 | 363 | Warning
30665 | Sierra CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30666 | Sierra CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30667 | Sierra CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30668 | Sierra CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30669 | Sierra CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30670 | Sierra CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30671 | Sierra CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30672 | Sierra CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30673 | Sierra CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30674 | Sierra CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30675 | Sierra CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
30676 | Sierra CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
30679 | Sierra CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
30680 | Sierra CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
30681 | Sierra CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30682 | Sierra CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
30683 | Sierra CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12342 | 0 | 234 | Warning
30684 | Sierra CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12343 | 0 | 234 | Warning
30686 | Sierra CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
30687 | Sierra CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12348SF+30d |  | 0 | 309 | Warning
30688 | Sierra CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12349SF+30d |  | 0 | 309 | Warning
30689 | Sierra CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12350SF+30d |  | 0 | 309 | Warning
30690 | Sierra CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12351SF+30d |  | 0 | 309 | Warning
30691 | Sierra CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12352SF+30d |  | 0 | 309 | Warning
30692 | Sierra CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12333 |  | 0 | 234 | Warning
30693 | Sierra CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12334 |  | 0 | 234 | Warning
30694 | Sierra CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30695 | Sierra CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12354FS+12d | 0 | 240 | Warning
30696 | Sierra CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30697 | Sierra CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12354SF+60d | 0 | 250 | Warning
30698 | Sierra CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12337SF+30d | 0 | 240 | Warning
30699 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12338SF+30d | 0 | 240 | Warning
30700 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12339SF+30d | 0 | 240 | Warning
30701 | Sierra CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12340SF+30d | 0 | 240 | Warning
30702 | Sierra CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12341SF+30d | 0 | 240 | Warning
30703 | Sierra CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30704 | Sierra CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12345FS+12d,12347SF+60d |  | 0 | 240 | Warning
30707 | Siskiyou CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30712 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30713 | Siskiyou CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30714 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30715 | Siskiyou CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30717 | Siskiyou CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
30718 | Siskiyou CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
30741 | Siskiyou CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30742 | Siskiyou CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30743 | Siskiyou CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30744 | Siskiyou CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30745 | Siskiyou CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30746 | Siskiyou CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30747 | Siskiyou CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30748 | Siskiyou CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30749 | Siskiyou CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30750 | Siskiyou CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30751 | Siskiyou CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30752 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30759 | Siskiyou CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
30760 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12411SS | 0 | 414 | Warning
30761 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12410SS |  | 0 | 414 | Warning
30762 | Siskiyou CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
30763 | Siskiyou CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
30764 | Siskiyou CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30765 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12416SS | 0 | 352 | Warning
30766 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12415SS |  | 0 | 352 | Warning
30767 | Siskiyou CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30768 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12419SS | 0 | 288 | Warning
30769 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12418SS |  | 0 | 288 | Warning
30770 | Siskiyou CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30771 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12422SS | 0 | 268 | Warning
30772 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12421SS |  | 0 | 268 | Warning
30773 | Siskiyou CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30774 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12425SS | 0 | 246 | Warning
30775 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12424SS |  | 0 | 246 | Warning
30776 | Siskiyou CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30777 | Siskiyou CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.4 | 234 | Warning
30780 | Siskiyou CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12429 |  | 0.4 | 234 | Warning
30784 | Siskiyou CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30787 | Siskiyou CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12436 |  | 0.2 | 466 | Warning
30788 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30790 | Siskiyou CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12439 | 12441 | 0.4 | 405 | Warning
30791 | Siskiyou CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12440 |  | 0 | 405 | Warning
30792 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30793 | Siskiyou CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12444 | 0.2 | 405 | Warning
30794 | Siskiyou CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12443 | 12445 | 0 | 405 | Warning
30795 | Siskiyou CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12444 |  | 0 | 405 | Warning
30796 | Siskiyou CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30797 | Siskiyou CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12448 | 0 | 362 | Warning
30798 | Siskiyou CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12447 | 12449 | 0 | 362 | Warning
30799 | Siskiyou CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12448 |  | 0 | 362 | Warning
30800 | Siskiyou CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30801 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30802 | Siskiyou CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.45 | 298 | Warning
30803 | Siskiyou CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
30806 | Siskiyou CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 12455 |  | 0.6 | 357 | Warning
30811 | Siskiyou CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
30813 | Siskiyou CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 12462 |  | 0.2 | 485 | Warning
30814 | Siskiyou CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
30816 | Siskiyou CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12465SS | 12467,12470,12468SF+30d | 0.2 | 298 | Warning
30817 | Siskiyou CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12466 |  | 0 | 298 | Warning
30818 | Siskiyou CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12466SF+30d |  | 0 | 298 | Warning
30819 | Siskiyou CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30820 | Siskiyou CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12466 |  | 0 | 345 | Warning
30821 | Siskiyou CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.57 | 445 | Warning
30823 | Siskiyou CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 12472SS | 12474SS | 0.6 | 485 | Warning
30824 | Siskiyou CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 12473SS |  | 0.2 | 445 | Warning
30829 | Siskiyou CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.84 | 508 | Warning
30831 | Siskiyou CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 12480 |  | 0.6 | 508 | Warning
30832 | Siskiyou CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
30834 | Siskiyou CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 12483SS | 12488,12485 | 0.2 | 298 | Warning
30835 | Siskiyou CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12484 |  | 0 | 298 | Warning
30836 | Siskiyou CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
30837 | Siskiyou CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30838 | Siskiyou CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12484 |  | 0 | 345 | Warning
30839 | Siskiyou CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
30840 | Siskiyou CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30841 | Siskiyou CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30842 | Siskiyou CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30843 | Siskiyou CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30844 | Siskiyou CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30845 | Siskiyou CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30846 | Siskiyou CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30847 | Siskiyou CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30848 | Siskiyou CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30849 | Siskiyou CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30850 | Siskiyou CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
30851 | Siskiyou CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
30854 | Siskiyou CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
30855 | Siskiyou CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
30856 | Siskiyou CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30857 | Siskiyou CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
30858 | Siskiyou CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12517 | 0 | 234 | Warning
30859 | Siskiyou CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12518 | 0 | 234 | Warning
30861 | Siskiyou CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
30862 | Siskiyou CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12523SF+30d |  | 0 | 309 | Warning
30863 | Siskiyou CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12524SF+30d |  | 0 | 309 | Warning
30864 | Siskiyou CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12525SF+30d |  | 0 | 309 | Warning
30865 | Siskiyou CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12526SF+30d |  | 0 | 309 | Warning
30866 | Siskiyou CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12527SF+30d |  | 0 | 309 | Warning
30867 | Siskiyou CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12508 |  | 0 | 234 | Warning
30868 | Siskiyou CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12509 |  | 0 | 234 | Warning
30869 | Siskiyou CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
30870 | Siskiyou CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12529FS+12d | 0 | 240 | Warning
30871 | Siskiyou CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
30872 | Siskiyou CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12529SF+60d | 0 | 250 | Warning
30873 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12512SF+30d | 0 | 240 | Warning
30874 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12513SF+30d | 0 | 240 | Warning
30875 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12514SF+30d | 0 | 240 | Warning
30876 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12515SF+30d | 0 | 240 | Warning
30877 | Siskiyou CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12516SF+30d | 0 | 240 | Warning
30878 | Siskiyou CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
30879 | Siskiyou CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12520FS+12d,12522SF+60d |  | 0 | 240 | Warning
30882 | Solano CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
30887 | Solano CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
30888 | Solano CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
30889 | Solano CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
30890 | Solano CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
30892 | Solano CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
30893 | Solano CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
30915 | Solano CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
30916 | Solano CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
30917 | Solano CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
30918 | Solano CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
30919 | Solano CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
30920 | Solano CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
30921 | Solano CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
30922 | Solano CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
30923 | Solano CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
30924 | Solano CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
30925 | Solano CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
30926 | Solano CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30927 | Solano CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
30934 | Solano CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
30935 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 12586SS | 0.2 | 424 | Warning
30936 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12585SS |  | 0 | 414 | Warning
30937 | Solano CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
30938 | Solano CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
30939 | Solano CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
30940 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12591SS | 0 | 352 | Warning
30941 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12590SS |  | 0 | 352 | Warning
30942 | Solano CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
30943 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12594SS | 0 | 288 | Warning
30944 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12593SS |  | 0 | 288 | Warning
30945 | Solano CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
30946 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12597SS | 0 | 268 | Warning
30947 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12596SS |  | 0 | 268 | Warning
30948 | Solano CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
30949 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12600SS | 0 | 246 | Warning
30950 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12599SS |  | 0 | 246 | Warning
30951 | Solano CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
30952 | Solano CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.58 | 234 | Warning
30955 | Solano CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12604 |  | 0.8 | 234 | Warning
30959 | Solano CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30962 | Solano CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12611 |  | 0.2 | 466 | Warning
30963 | Solano CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30965 | Solano CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12614 | 12616 | 0.2 | 405 | Warning
30966 | Solano CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12615 |  | 0 | 405 | Warning
30967 | Solano CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30969 | Solano CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12618 | 12620 | 0.2 | 405 | Warning
30970 | Solano CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12619 |  | 0 | 405 | Warning
30971 | Solano CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
30972 | Solano CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12623 | 0 | 362 | Warning
30973 | Solano CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12622 | 12624 | 0 | 362 | Warning
30974 | Solano CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12623 |  | 0 | 362 | Warning
30975 | Solano CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
30976 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
30977 | Solano CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.48 | 298 | Warning
30978 | Solano CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
30981 | Solano CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 12630 |  | 0 | 357 | Warning
30989 | Solano CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.18 | 298 | Warning
30991 | Solano CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12640SS | 12642,12645,12643SF+30d | 0.2 | 298 | Warning
30992 | Solano CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12641 |  | 0 | 298 | Warning
30993 | Solano CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12641SF+30d |  | 0.2 | 298 | Warning
30994 | Solano CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
30995 | Solano CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12641 |  | 0 | 345 | Warning
30996 | Solano CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
30999 | Solano CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 12648SS |  | 0.2 | 445 | Warning
31007 | Solano CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
31009 | Solano CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 12658SS | 12663,12660 | 0.2 | 298 | Warning
31010 | Solano CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12659 |  | 0 | 298 | Warning
31011 | Solano CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
31012 | Solano CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31013 | Solano CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12659 |  | 0 | 345 | Warning
31014 | Solano CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
31015 | Solano CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31016 | Solano CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31017 | Solano CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31018 | Solano CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31019 | Solano CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31020 | Solano CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31021 | Solano CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31022 | Solano CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31023 | Solano CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31024 | Solano CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31025 | Solano CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31026 | Solano CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31029 | Solano CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | 384 | Warning
31030 | Solano CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0.2 | 320 | Warning
31031 | Solano CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31032 | Solano CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31033 | Solano CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12692 | 0 | 234 | Warning
31034 | Solano CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12693 | 0 | 234 | Warning
31036 | Solano CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31037 | Solano CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12698SF+30d |  | 0 | 309 | Warning
31038 | Solano CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12699SF+30d |  | 0 | 309 | Warning
31039 | Solano CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12700SF+30d |  | 0 | 309 | Warning
31040 | Solano CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12701SF+30d |  | 0 | 309 | Warning
31041 | Solano CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12702SF+30d |  | 0 | 309 | Warning
31042 | Solano CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12683 |  | 0 | 234 | Warning
31043 | Solano CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12684 |  | 0 | 234 | Warning
31044 | Solano CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31045 | Solano CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12704FS+12d | 0 | 240 | Warning
31046 | Solano CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31047 | Solano CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12704SF+60d | 0 | 250 | Warning
31048 | Solano CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12687SF+30d | 0 | 240 | Warning
31049 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12688SF+30d | 0 | 240 | Warning
31050 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12689SF+30d | 0 | 240 | Warning
31051 | Solano CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12690SF+30d | 0 | 240 | Warning
31052 | Solano CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12691SF+30d | 0 | 240 | Warning
31053 | Solano CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31054 | Solano CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12695FS+12d,12697SF+60d |  | 0 | 240 | Warning
31057 | Sonoma CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31062 | Sonoma CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31063 | Sonoma CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31064 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31065 | Sonoma CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31067 | Sonoma CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
31068 | Sonoma CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31090 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31091 | Sonoma CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31092 | Sonoma CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31093 | Sonoma CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31094 | Sonoma CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31095 | Sonoma CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31096 | Sonoma CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31097 | Sonoma CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31098 | Sonoma CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31099 | Sonoma CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31100 | Sonoma CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31101 | Sonoma CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31102 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31109 | Sonoma CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
31110 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12761SS | 0 | 414 | Warning
31111 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12760SS |  | 0 | 414 | Warning
31112 | Sonoma CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31113 | Sonoma CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31114 | Sonoma CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31115 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12766SS | 0 | 352 | Warning
31116 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12765SS |  | 0 | 352 | Warning
31117 | Sonoma CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31118 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12769SS | 0 | 288 | Warning
31119 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12768SS |  | 0 | 288 | Warning
31120 | Sonoma CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31121 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12772SS | 0 | 268 | Warning
31122 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12771SS |  | 0 | 268 | Warning
31123 | Sonoma CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31124 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12775SS | 0 | 246 | Warning
31125 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12774SS |  | 0 | 246 | Warning
31126 | Sonoma CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
31127 | Sonoma CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.48 | 234 | Warning
31130 | Sonoma CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12779 |  | 0.6 | 234 | Warning
31134 | Sonoma CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31137 | Sonoma CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12786 |  | 0 | 466 | Warning
31138 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31140 | Sonoma CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12789 | 12791 | 0 | 405 | Warning
31141 | Sonoma CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12790 |  | 0 | 405 | Warning
31142 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31143 | Sonoma CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12794 | 0 | 405 | Warning
31144 | Sonoma CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12793 | 12795 | 0 | 405 | Warning
31145 | Sonoma CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12794 |  | 0 | 405 | Warning
31146 | Sonoma CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31148 | Sonoma CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12797 | 12799 | 0 | 362 | Warning
31149 | Sonoma CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12798 |  | 0 | 362 | Warning
31150 | Sonoma CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
31151 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
31152 | Sonoma CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.32 | 298 | Warning
31153 | Sonoma CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.76 | 357 | Warning
31155 | Sonoma CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 12804SS | 12806 | 0.6 | 357 | Warning
31156 | Sonoma CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 12805 |  | 0 | 357 | Warning
31161 | Sonoma CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
31163 | Sonoma CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 12812 |  | 0 | 485 | Warning
31164 | Sonoma CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.04 | 298 | Warning
31165 | Sonoma CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 12812SS | 12816SS | 0.8 | 508 | Warning
31166 | Sonoma CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12815SS | 12817,12820,12818SF+30d | 0 | 298 | Warning
31167 | Sonoma CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12816 |  | 0 | 298 | Warning
31168 | Sonoma CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12816SF+30d |  | 0 | 298 | Warning
31169 | Sonoma CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31170 | Sonoma CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12816 |  | 0 | 345 | Warning
31171 | Sonoma CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.31 | 445 | Warning
31173 | Sonoma CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d | 12822SS | 12824SS | 0 | 445 | Warning
31174 | Sonoma CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 12823SS |  | 0 | 445 | Warning
31179 | Sonoma CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.64 | 508 | Warning
31181 | Sonoma CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 12830 |  | 0.2 | 508 | Warning
31182 | Sonoma CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.02 | 298 | Warning
31183 | Sonoma CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 12827,12834SS | 0.2 | 508 | Warning
31184 | Sonoma CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 12833SS | 12838,12835 | 0 | 298 | Warning
31185 | Sonoma CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12834 |  | 0 | 298 | Warning
31186 | Sonoma CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
31187 | Sonoma CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31188 | Sonoma CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12834 |  | 0 | 345 | Warning
31189 | Sonoma CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
31190 | Sonoma CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31191 | Sonoma CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31192 | Sonoma CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31193 | Sonoma CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31194 | Sonoma CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31195 | Sonoma CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31196 | Sonoma CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31197 | Sonoma CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31198 | Sonoma CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31199 | Sonoma CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31200 | Sonoma CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31201 | Sonoma CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31204 | Sonoma CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
31205 | Sonoma CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
31206 | Sonoma CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31207 | Sonoma CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31208 | Sonoma CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12867 | 0 | 234 | Warning
31209 | Sonoma CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12868 | 0 | 234 | Warning
31211 | Sonoma CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31212 | Sonoma CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12873SF+30d |  | 0 | 309 | Warning
31213 | Sonoma CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12874SF+30d |  | 0 | 309 | Warning
31214 | Sonoma CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12875SF+30d |  | 0 | 309 | Warning
31215 | Sonoma CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12876SF+30d |  | 0 | 309 | Warning
31216 | Sonoma CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12877SF+30d |  | 0 | 309 | Warning
31217 | Sonoma CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12858 |  | 0 | 234 | Warning
31218 | Sonoma CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 12859 |  | 0 | 234 | Warning
31219 | Sonoma CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31220 | Sonoma CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12879FS+12d | 0 | 240 | Warning
31221 | Sonoma CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31222 | Sonoma CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12879SF+60d | 0 | 250 | Warning
31223 | Sonoma CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12862SF+30d | 0 | 240 | Warning
31224 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12863SF+30d | 0 | 240 | Warning
31225 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12864SF+30d | 0 | 240 | Warning
31226 | Sonoma CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12865SF+30d | 0 | 240 | Warning
31227 | Sonoma CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12866SF+30d | 0 | 240 | Warning
31228 | Sonoma CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31229 | Sonoma CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 12870FS+12d,12872SF+60d |  | 0 | 240 | Warning
31232 | Stanislaus CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31237 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31238 | Stanislaus CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31239 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31240 | Stanislaus CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31242 | Stanislaus CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
31243 | Stanislaus CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31265 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31266 | Stanislaus CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31267 | Stanislaus CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31268 | Stanislaus CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31269 | Stanislaus CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31270 | Stanislaus CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31271 | Stanislaus CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31272 | Stanislaus CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31273 | Stanislaus CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31274 | Stanislaus CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31275 | Stanislaus CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31276 | Stanislaus CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31277 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31284 | Stanislaus CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
31285 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12936SS | 0 | 414 | Warning
31286 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 12935SS |  | 0 | 414 | Warning
31287 | Stanislaus CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31288 | Stanislaus CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31289 | Stanislaus CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31290 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12941SS | 0 | 352 | Warning
31291 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 12940SS |  | 0 | 352 | Warning
31292 | Stanislaus CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31293 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12944SS | 0 | 288 | Warning
31294 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12943SS |  | 0 | 288 | Warning
31295 | Stanislaus CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31296 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12947SS | 0 | 268 | Warning
31297 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 12946SS |  | 0 | 268 | Warning
31298 | Stanislaus CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31299 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12950SS | 0 | 246 | Warning
31300 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 12949SS |  | 0 | 246 | Warning
31301 | Stanislaus CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
31302 | Stanislaus CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.37 | 234 | Warning
31305 | Stanislaus CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 12954 |  | 0.2 | 234 | Warning
31309 | Stanislaus CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31312 | Stanislaus CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 12961 |  | 0.2 | 466 | Warning
31313 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31315 | Stanislaus CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 12964 | 12966 | 0.2 | 405 | Warning
31316 | Stanislaus CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 12965 |  | 0 | 405 | Warning
31317 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31319 | Stanislaus CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 12968 | 12970 | 0 | 405 | Warning
31320 | Stanislaus CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 12969 |  | 0 | 405 | Warning
31321 | Stanislaus CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31322 | Stanislaus CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12973 | 0.95 | 362 | Warning
31323 | Stanislaus CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 12972 | 12974 | 0 | 362 | Warning
31324 | Stanislaus CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 12973 |  | 0 | 362 | Warning
31325 | Stanislaus CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
31326 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
31327 | Stanislaus CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.54 | 298 | Warning
31328 | Stanislaus CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
31331 | Stanislaus CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 12980 |  | 0 | 357 | Warning
31336 | Stanislaus CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
31338 | Stanislaus CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 12987 |  | 0 | 485 | Warning
31339 | Stanislaus CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.17 | 298 | Warning
31341 | Stanislaus CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 12990SS | 12992,12995,12993SF+30d | 0.4 | 298 | Warning
31342 | Stanislaus CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 12991 |  | 0 | 298 | Warning
31343 | Stanislaus CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12991SF+30d |  | 0 | 298 | Warning
31344 | Stanislaus CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31345 | Stanislaus CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 12991 |  | 0 | 345 | Warning
31357 | Stanislaus CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.38 | 298 | Warning
31359 | Stanislaus CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 13008SS | 13013,13010 | 0.8 | 298 | Warning
31360 | Stanislaus CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13009 |  | 0 | 298 | Warning
31361 | Stanislaus CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
31362 | Stanislaus CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31363 | Stanislaus CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13009 |  | 0 | 345 | Warning
31364 | Stanislaus CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
31365 | Stanislaus CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31366 | Stanislaus CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31367 | Stanislaus CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31368 | Stanislaus CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31369 | Stanislaus CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31370 | Stanislaus CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31371 | Stanislaus CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31372 | Stanislaus CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31373 | Stanislaus CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31374 | Stanislaus CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31375 | Stanislaus CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31376 | Stanislaus CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31379 | Stanislaus CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
31380 | Stanislaus CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
31381 | Stanislaus CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31382 | Stanislaus CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31383 | Stanislaus CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13042 | 0 | 234 | Warning
31384 | Stanislaus CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13043 | 0 | 234 | Warning
31386 | Stanislaus CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31387 | Stanislaus CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13048SF+30d |  | 0 | 309 | Warning
31388 | Stanislaus CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13049SF+30d |  | 0 | 309 | Warning
31389 | Stanislaus CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13050SF+30d |  | 0 | 309 | Warning
31390 | Stanislaus CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13051SF+30d |  | 0 | 309 | Warning
31391 | Stanislaus CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13052SF+30d |  | 0 | 309 | Warning
31392 | Stanislaus CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13033 |  | 0 | 234 | Warning
31393 | Stanislaus CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13034 |  | 0 | 234 | Warning
31394 | Stanislaus CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31395 | Stanislaus CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13054FS+12d | 0 | 240 | Warning
31396 | Stanislaus CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31397 | Stanislaus CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13054SF+60d | 0 | 250 | Warning
31398 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13037SF+30d | 0 | 240 | Warning
31399 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13038SF+30d | 0 | 240 | Warning
31400 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13039SF+30d | 0 | 240 | Warning
31401 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13040SF+30d | 0 | 240 | Warning
31402 | Stanislaus CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13041SF+30d | 0 | 240 | Warning
31403 | Stanislaus CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31404 | Stanislaus CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13045FS+12d,13047SF+60d |  | 0 | 240 | Warning
31407 | Sutter CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31412 | Sutter CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31413 | Sutter CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31414 | Sutter CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31415 | Sutter CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31417 | Sutter CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
31418 | Sutter CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31440 | Sutter CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31441 | Sutter CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31442 | Sutter CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31443 | Sutter CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31444 | Sutter CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31445 | Sutter CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31446 | Sutter CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31447 | Sutter CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31448 | Sutter CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31449 | Sutter CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31450 | Sutter CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31451 | Sutter CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31452 | Sutter CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31459 | Sutter CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
31460 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13111SS | 0 | 414 | Warning
31461 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13110SS |  | 0 | 414 | Warning
31462 | Sutter CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31463 | Sutter CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31464 | Sutter CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31465 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13116SS | 0 | 352 | Warning
31466 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13115SS |  | 0 | 352 | Warning
31467 | Sutter CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31468 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13119SS | 0 | 288 | Warning
31469 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13118SS |  | 0 | 288 | Warning
31470 | Sutter CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31471 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13122SS | 0 | 268 | Warning
31472 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13121SS |  | 0 | 268 | Warning
31473 | Sutter CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31474 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13125SS | 0 | 246 | Warning
31475 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13124SS |  | 0 | 246 | Warning
31476 | Sutter CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
31477 | Sutter CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.4 | 234 | Warning
31480 | Sutter CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 13129 |  | 0.4 | 234 | Warning
31484 | Sutter CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31487 | Sutter CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 13136 |  | 0.2 | 466 | Warning
31488 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31490 | Sutter CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 13139 | 13141 | 0.2 | 405 | Warning
31491 | Sutter CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 13140 |  | 0 | 405 | Warning
31492 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31493 | Sutter CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13144 | 0.2 | 405 | Warning
31494 | Sutter CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 13143 | 13145 | 0 | 405 | Warning
31495 | Sutter CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 13144 |  | 0 | 405 | Warning
31496 | Sutter CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31497 | Sutter CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13148 | 0 | 362 | Warning
31498 | Sutter CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 13147 | 13149 | 0 | 362 | Warning
31499 | Sutter CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 13148 |  | 0 | 362 | Warning
31500 | Sutter CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
31501 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
31502 | Sutter CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.46 | 298 | Warning
31503 | Sutter CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
31506 | Sutter CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 13155 |  | 0 | 357 | Warning
31511 | Sutter CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
31513 | Sutter CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 13162 |  | 0 | 485 | Warning
31514 | Sutter CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
31516 | Sutter CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 13165SS | 13167,13170,13168SF+30d | 0.2 | 298 | Warning
31517 | Sutter CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13166 |  | 0 | 298 | Warning
31518 | Sutter CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13166SF+30d |  | 0 | 298 | Warning
31519 | Sutter CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31520 | Sutter CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13166 |  | 0 | 345 | Warning
31521 | Sutter CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
31524 | Sutter CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 13173SS |  | 0.2 | 445 | Warning
31532 | Sutter CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
31534 | Sutter CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 13183SS | 13188,13185 | 0.2 | 298 | Warning
31535 | Sutter CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13184 |  | 0 | 298 | Warning
31536 | Sutter CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
31537 | Sutter CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31538 | Sutter CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13184 |  | 0 | 345 | Warning
31539 | Sutter CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
31540 | Sutter CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31541 | Sutter CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31542 | Sutter CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31543 | Sutter CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31544 | Sutter CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31545 | Sutter CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31546 | Sutter CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31547 | Sutter CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31548 | Sutter CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31549 | Sutter CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31550 | Sutter CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31551 | Sutter CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31552 | Sutter CW-Training | April 1, 2021 8:00 AM | November 2, 2026 5:00 PM | 1404 | 234d |  |  | 0.02 | 234 | Warning
31553 | Sutter CW-Develop the CARES V1 Organization Training Plan | April 1, 2021 8:00 AM | December 28, 2021 5:00 PM | 188 | 1261d |  | 13210 | 0.2 | 1261 | Warning
31554 | Sutter CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
31555 | Sutter CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
31556 | Sutter CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31557 | Sutter CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31558 | Sutter CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13217 | 0 | 234 | Warning
31559 | Sutter CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13218 | 0 | 234 | Warning
31560 | Sutter CW-Execute the CARES V1 Organization Training Plan | December 29, 2021 8:00 AM | September 27, 2022 5:00 PM | 189 | 1261d | 13203 |  | 0 | 1261 | Warning
31561 | Sutter CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31562 | Sutter CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13223SF+30d |  | 0 | 309 | Warning
31563 | Sutter CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13224SF+30d |  | 0 | 309 | Warning
31564 | Sutter CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13225SF+30d |  | 0 | 309 | Warning
31565 | Sutter CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13226SF+30d |  | 0 | 309 | Warning
31566 | Sutter CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13227SF+30d |  | 0 | 309 | Warning
31567 | Sutter CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13208 |  | 0 | 234 | Warning
31568 | Sutter CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13209 |  | 0 | 234 | Warning
31569 | Sutter CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31570 | Sutter CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13229FS+12d | 0 | 240 | Warning
31571 | Sutter CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31572 | Sutter CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13229SF+60d | 0 | 250 | Warning
31573 | Sutter CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13212SF+30d | 0 | 240 | Warning
31574 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13213SF+30d | 0 | 240 | Warning
31575 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13214SF+30d | 0 | 240 | Warning
31576 | Sutter CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13215SF+30d | 0 | 240 | Warning
31577 | Sutter CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13216SF+30d | 0 | 240 | Warning
31578 | Sutter CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31579 | Sutter CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13220FS+12d,13222SF+60d |  | 0 | 240 | Warning
31582 | Tehama CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31587 | Tehama CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31588 | Tehama CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31589 | Tehama CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31590 | Tehama CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31592 | Tehama CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
31593 | Tehama CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31615 | Tehama CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31616 | Tehama CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31617 | Tehama CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31618 | Tehama CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31619 | Tehama CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31620 | Tehama CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31621 | Tehama CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31622 | Tehama CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31623 | Tehama CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31624 | Tehama CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31625 | Tehama CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31626 | Tehama CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31627 | Tehama CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31634 | Tehama CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
31635 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13286SS | 0 | 414 | Warning
31636 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13285SS |  | 0 | 414 | Warning
31637 | Tehama CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31638 | Tehama CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31639 | Tehama CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31640 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13291SS | 0 | 352 | Warning
31641 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13290SS |  | 0 | 352 | Warning
31642 | Tehama CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31643 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13294SS | 0 | 288 | Warning
31644 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13293SS |  | 0 | 288 | Warning
31645 | Tehama CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31646 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13297SS | 0 | 268 | Warning
31647 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13296SS |  | 0 | 268 | Warning
31648 | Tehama CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31649 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13300SS | 0 | 246 | Warning
31650 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13299SS |  | 0 | 246 | Warning
31651 | Tehama CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
31652 | Tehama CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.51 | 234 | Warning
31655 | Tehama CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 13304 |  | 0.6 | 234 | Warning
31659 | Tehama CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31663 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31665 | Tehama CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 13314 | 13316 | 0.4 | 405 | Warning
31666 | Tehama CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 13315 |  | 0 | 405 | Warning
31667 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31668 | Tehama CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13319 | 0 | 405 | Warning
31669 | Tehama CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 13318 | 13320 | 0 | 405 | Warning
31670 | Tehama CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 13319 |  | 0 | 405 | Warning
31671 | Tehama CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31672 | Tehama CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13323 | 0 | 362 | Warning
31673 | Tehama CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 13322 | 13324 | 0 | 362 | Warning
31674 | Tehama CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 13323 |  | 0 | 362 | Warning
31675 | Tehama CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
31676 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
31677 | Tehama CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.63 | 298 | Warning
31678 | Tehama CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
31681 | Tehama CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 13330 |  | 0 | 357 | Warning
31689 | Tehama CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
31691 | Tehama CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 13340SS | 13342,13345,13343SF+30d | 0 | 298 | Warning
31692 | Tehama CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13341 |  | 0 | 298 | Warning
31693 | Tehama CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13341SF+30d |  | 0 | 298 | Warning
31694 | Tehama CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31695 | Tehama CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13341 |  | 0 | 345 | Warning
31707 | Tehama CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.7 | 298 | Warning
31710 | Tehama CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13359 |  | 0 | 298 | Warning
31712 | Tehama CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31713 | Tehama CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13359 |  | 0 | 345 | Warning
31714 | Tehama CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 363d |  |  | 0.2 | 363 | Warning
31715 | Tehama CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31716 | Tehama CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31717 | Tehama CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31718 | Tehama CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31719 | Tehama CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31720 | Tehama CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31721 | Tehama CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31722 | Tehama CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31723 | Tehama CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31724 | Tehama CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31725 | Tehama CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
31726 | Tehama CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31729 | Tehama CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
31730 | Tehama CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
31731 | Tehama CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31732 | Tehama CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31733 | Tehama CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13392 | 0 | 234 | Warning
31734 | Tehama CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13393 | 0 | 234 | Warning
31736 | Tehama CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31737 | Tehama CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13398SF+30d |  | 0 | 309 | Warning
31738 | Tehama CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13399SF+30d |  | 0 | 309 | Warning
31739 | Tehama CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13400SF+30d |  | 0 | 309 | Warning
31740 | Tehama CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13401SF+30d |  | 0 | 309 | Warning
31741 | Tehama CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13402SF+30d |  | 0 | 309 | Warning
31742 | Tehama CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13383 |  | 0 | 234 | Warning
31743 | Tehama CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13384 |  | 0 | 234 | Warning
31744 | Tehama CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31745 | Tehama CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13404FS+12d | 0 | 240 | Warning
31746 | Tehama CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31747 | Tehama CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13404SF+60d | 0 | 250 | Warning
31748 | Tehama CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13387SF+30d | 0 | 240 | Warning
31749 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13388SF+30d | 0 | 240 | Warning
31750 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13389SF+30d | 0 | 240 | Warning
31751 | Tehama CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13390SF+30d | 0 | 240 | Warning
31752 | Tehama CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13391SF+30d | 0 | 240 | Warning
31753 | Tehama CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31754 | Tehama CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13395FS+12d,13397SF+60d |  | 0 | 240 | Warning
31757 | Trinity CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31762 | Trinity CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31763 | Trinity CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31764 | Trinity CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31765 | Trinity CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31767 | Trinity CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
31768 | Trinity CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31790 | Trinity CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31791 | Trinity CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31792 | Trinity CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31793 | Trinity CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31794 | Trinity CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31795 | Trinity CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31796 | Trinity CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31797 | Trinity CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31798 | Trinity CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31799 | Trinity CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31800 | Trinity CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31801 | Trinity CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31802 | Trinity CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31809 | Trinity CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
31810 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13461SS | 0 | 414 | Warning
31811 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13460SS |  | 0 | 414 | Warning
31812 | Trinity CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31813 | Trinity CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31814 | Trinity CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31815 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13466SS | 0 | 352 | Warning
31816 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13465SS |  | 0 | 352 | Warning
31817 | Trinity CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31818 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13469SS | 0 | 288 | Warning
31819 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13468SS |  | 0 | 288 | Warning
31820 | Trinity CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31821 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13472SS | 0 | 268 | Warning
31822 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13471SS |  | 0 | 268 | Warning
31823 | Trinity CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31824 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13475SS | 0 | 246 | Warning
31825 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13474SS |  | 0 | 246 | Warning
31826 | Trinity CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
31827 | Trinity CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.37 | 234 | Warning
31830 | Trinity CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 13479 |  | 0.2 | 234 | Warning
31834 | Trinity CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31838 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31840 | Trinity CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 13489 | 13491 | 0.2 | 405 | Warning
31841 | Trinity CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 13490 |  | 0 | 405 | Warning
31842 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31844 | Trinity CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 13493 | 13495 | 0 | 405 | Warning
31845 | Trinity CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 13494 |  | 0 | 405 | Warning
31846 | Trinity CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
31847 | Trinity CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13498 | 0 | 362 | Warning
31848 | Trinity CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 13497 | 13499 | 0 | 362 | Warning
31849 | Trinity CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 13498 |  | 0 | 362 | Warning
31850 | Trinity CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
31851 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
31852 | Trinity CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.22 | 298 | Warning
31853 | Trinity CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.19 | 357 | Warning
31854 | Trinity CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 13505SS | 0.2 | 405 | Warning
31855 | Trinity CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 13504SS | 13506 | 0.2 | 357 | Warning
31856 | Trinity CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 13505 |  | 0 | 357 | Warning
31864 | Trinity CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
31866 | Trinity CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 13515SS | 13517,13520,13518SF+30d | 0.2 | 298 | Warning
31867 | Trinity CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13516 |  | 0 | 298 | Warning
31868 | Trinity CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13516SF+30d |  | 0 | 298 | Warning
31869 | Trinity CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31870 | Trinity CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13516 |  | 0 | 345 | Warning
31871 | Trinity CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.2 | 445 | Warning
31872 | Trinity CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 13523SS | 0.2 | 485 | Warning
31873 | Trinity CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 13522SS | 13524SS | 0.2 | 485 | Warning
31874 | Trinity CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 13523SS |  | 0.2 | 445 | Warning
31882 | Trinity CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
31884 | Trinity CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 13533SS | 13538,13535 | 0.2 | 298 | Warning
31885 | Trinity CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13534 |  | 0 | 298 | Warning
31886 | Trinity CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
31887 | Trinity CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
31888 | Trinity CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13534 |  | 0 | 345 | Warning
31889 | Trinity CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
31890 | Trinity CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31891 | Trinity CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31892 | Trinity CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31893 | Trinity CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31894 | Trinity CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31895 | Trinity CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31896 | Trinity CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31897 | Trinity CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31898 | Trinity CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31899 | Trinity CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31900 | Trinity CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
31901 | Trinity CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
31904 | Trinity CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
31905 | Trinity CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
31906 | Trinity CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31907 | Trinity CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
31908 | Trinity CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13567 | 0 | 234 | Warning
31909 | Trinity CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13568 | 0 | 234 | Warning
31911 | Trinity CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
31912 | Trinity CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13573SF+30d |  | 0 | 309 | Warning
31913 | Trinity CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13574SF+30d |  | 0 | 309 | Warning
31914 | Trinity CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13575SF+30d |  | 0 | 309 | Warning
31915 | Trinity CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13576SF+30d |  | 0 | 309 | Warning
31916 | Trinity CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13577SF+30d |  | 0 | 309 | Warning
31917 | Trinity CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13558 |  | 0 | 234 | Warning
31918 | Trinity CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13559 |  | 0 | 234 | Warning
31919 | Trinity CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
31920 | Trinity CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13579FS+12d | 0 | 240 | Warning
31921 | Trinity CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
31922 | Trinity CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13579SF+60d | 0 | 250 | Warning
31923 | Trinity CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13562SF+30d | 0 | 240 | Warning
31924 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13563SF+30d | 0 | 240 | Warning
31925 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13564SF+30d | 0 | 240 | Warning
31926 | Trinity CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13565SF+30d | 0 | 240 | Warning
31927 | Trinity CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13566SF+30d | 0 | 240 | Warning
31928 | Trinity CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
31929 | Trinity CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13570FS+12d,13572SF+60d |  | 0 | 240 | Warning
31932 | Tulare CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
31937 | Tulare CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
31938 | Tulare CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
31939 | Tulare CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
31940 | Tulare CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
31942 | Tulare CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
31943 | Tulare CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
31965 | Tulare CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
31966 | Tulare CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
31967 | Tulare CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
31968 | Tulare CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
31969 | Tulare CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
31970 | Tulare CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
31971 | Tulare CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
31972 | Tulare CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
31973 | Tulare CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
31974 | Tulare CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
31975 | Tulare CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
31976 | Tulare CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31977 | Tulare CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
31984 | Tulare CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
31985 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13636SS | 0 | 414 | Warning
31986 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13635SS |  | 0 | 414 | Warning
31987 | Tulare CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31988 | Tulare CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
31989 | Tulare CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
31990 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13641SS | 0 | 352 | Warning
31991 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13640SS |  | 0 | 352 | Warning
31992 | Tulare CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
31993 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13644SS | 0 | 288 | Warning
31994 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13643SS |  | 0 | 288 | Warning
31995 | Tulare CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
31996 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13647SS | 0 | 268 | Warning
31997 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13646SS |  | 0 | 268 | Warning
31998 | Tulare CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
31999 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13650SS | 0 | 246 | Warning
32000 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13649SS |  | 0 | 246 | Warning
32001 | Tulare CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
32002 | Tulare CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.39 | 234 | Warning
32005 | Tulare CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 13654 |  | 0.4 | 234 | Warning
32009 | Tulare CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32012 | Tulare CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 13661 |  | 0.2 | 466 | Warning
32013 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32015 | Tulare CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 13664 | 13666 | 0 | 405 | Warning
32016 | Tulare CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 13665 |  | 0 | 405 | Warning
32017 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32018 | Tulare CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13669 | 0.2 | 405 | Warning
32019 | Tulare CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 13668 | 13670 | 0 | 405 | Warning
32020 | Tulare CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 13669 |  | 0 | 405 | Warning
32021 | Tulare CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32022 | Tulare CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13673 | 0 | 362 | Warning
32023 | Tulare CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 13672 | 13674 | 0 | 362 | Warning
32024 | Tulare CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 13673 |  | 0 | 362 | Warning
32025 | Tulare CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32026 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32027 | Tulare CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.44 | 298 | Warning
32039 | Tulare CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
32041 | Tulare CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 13690SS | 13692,13695,13693SF+30d | 0 | 298 | Warning
32042 | Tulare CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13691 |  | 0 | 298 | Warning
32043 | Tulare CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13691SF+30d |  | 0 | 298 | Warning
32044 | Tulare CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32045 | Tulare CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13691 |  | 0 | 345 | Warning
32046 | Tulare CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
32049 | Tulare CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 13698SS |  | 0 | 445 | Warning
32057 | Tulare CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
32059 | Tulare CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 13708SS | 13713,13710 | 0 | 298 | Warning
32060 | Tulare CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13709 |  | 0 | 298 | Warning
32061 | Tulare CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
32062 | Tulare CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32063 | Tulare CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13709 |  | 0 | 345 | Warning
32064 | Tulare CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
32065 | Tulare CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32066 | Tulare CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32067 | Tulare CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32068 | Tulare CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32069 | Tulare CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32070 | Tulare CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32071 | Tulare CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32072 | Tulare CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32073 | Tulare CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32074 | Tulare CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32075 | Tulare CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32076 | Tulare CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
32079 | Tulare CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32080 | Tulare CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32081 | Tulare CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32082 | Tulare CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
32083 | Tulare CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13742 | 0 | 234 | Warning
32084 | Tulare CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13743 | 0 | 234 | Warning
32086 | Tulare CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32087 | Tulare CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13748SF+30d |  | 0 | 309 | Warning
32088 | Tulare CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13749SF+30d |  | 0 | 309 | Warning
32089 | Tulare CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13750SF+30d |  | 0 | 309 | Warning
32090 | Tulare CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13751SF+30d |  | 0 | 309 | Warning
32091 | Tulare CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13752SF+30d |  | 0 | 309 | Warning
32092 | Tulare CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13733 |  | 0 | 234 | Warning
32093 | Tulare CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13734 |  | 0 | 234 | Warning
32094 | Tulare CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
32095 | Tulare CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13754FS+12d | 0 | 240 | Warning
32096 | Tulare CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
32097 | Tulare CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13754SF+60d | 0 | 250 | Warning
32098 | Tulare CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13737SF+30d | 0 | 240 | Warning
32099 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13738SF+30d | 0 | 240 | Warning
32100 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13739SF+30d | 0 | 240 | Warning
32101 | Tulare CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13740SF+30d | 0 | 240 | Warning
32102 | Tulare CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13741SF+30d | 0 | 240 | Warning
32103 | Tulare CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32104 | Tulare CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13745FS+12d,13747SF+60d |  | 0 | 240 | Warning
32107 | Yolo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.58 | 245 | Warning
32112 | Yolo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.2 | 405 | Warning
32113 | Yolo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32114 | Yolo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
32115 | Yolo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
32117 | Yolo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
32118 | Yolo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
32140 | Yolo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
32141 | Yolo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
32142 | Yolo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
32143 | Yolo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
32144 | Yolo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
32145 | Yolo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
32146 | Yolo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
32147 | Yolo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
32148 | Yolo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32149 | Yolo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
32150 | Yolo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
32151 | Yolo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32152 | Yolo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
32159 | Yolo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
32160 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13811SS | 0 | 414 | Warning
32161 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13810SS |  | 0 | 414 | Warning
32162 | Yolo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32163 | Yolo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32164 | Yolo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
32165 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13816SS | 0 | 352 | Warning
32166 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13815SS |  | 0 | 352 | Warning
32167 | Yolo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
32168 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13819SS | 0 | 288 | Warning
32169 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13818SS |  | 0 | 288 | Warning
32170 | Yolo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
32171 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13822SS | 0 | 268 | Warning
32172 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13821SS |  | 0 | 268 | Warning
32173 | Yolo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32174 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13825SS | 0 | 246 | Warning
32175 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13824SS |  | 0 | 246 | Warning
32176 | Yolo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
32177 | Yolo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.53 | 234 | Warning
32180 | Yolo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 13829 |  | 0.6 | 234 | Warning
32184 | Yolo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32188 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32190 | Yolo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 13839 | 13841 | 0.4 | 405 | Warning
32191 | Yolo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 13840 |  | 0 | 405 | Warning
32192 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32194 | Yolo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 13843 | 13845 | 0 | 405 | Warning
32195 | Yolo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 13844 |  | 0 | 405 | Warning
32196 | Yolo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32197 | Yolo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13848 | 0 | 362 | Warning
32198 | Yolo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 13847 | 13849 | 0 | 362 | Warning
32199 | Yolo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 13848 |  | 0 | 362 | Warning
32200 | Yolo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32201 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32202 | Yolo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
32203 | Yolo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.94 | 357 | Warning
32206 | Yolo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 13855 |  | 0.2 | 357 | Warning
32211 | Yolo CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.69 | 485 | Warning
32213 | Yolo CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 13862 |  | 0.2 | 485 | Warning
32214 | Yolo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.01 | 298 | Warning
32215 | Yolo CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 13862SS | 13866SS | 0.2 | 508 | Warning
32216 | Yolo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 13865SS | 13867,13870,13868SF+30d | 0 | 298 | Warning
32217 | Yolo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13866 |  | 0 | 298 | Warning
32218 | Yolo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13866SF+30d |  | 0 | 298 | Warning
32219 | Yolo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32220 | Yolo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13866 |  | 0 | 345 | Warning
32221 | Yolo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.68 | 445 | Warning
32223 | Yolo CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 13872SS | 13874SS | 0.95 | 485 | Warning
32224 | Yolo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 13873SS |  | 0.2 | 445 | Warning
32232 | Yolo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.05 | 298 | Warning
32233 | Yolo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 13877,13884SS | 0.6 | 508 | Warning
32234 | Yolo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 13883SS | 13888,13885 | 0 | 298 | Warning
32235 | Yolo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 13884 |  | 0 | 298 | Warning
32236 | Yolo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
32237 | Yolo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32238 | Yolo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 13884 |  | 0 | 345 | Warning
32239 | Yolo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
32240 | Yolo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32241 | Yolo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32242 | Yolo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32243 | Yolo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32244 | Yolo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32245 | Yolo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32246 | Yolo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32247 | Yolo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32248 | Yolo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32249 | Yolo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32250 | Yolo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32251 | Yolo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
32254 | Yolo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32255 | Yolo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32256 | Yolo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32257 | Yolo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
32258 | Yolo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13917 | 0 | 234 | Warning
32259 | Yolo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13918 | 0 | 234 | Warning
32261 | Yolo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32262 | Yolo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13923SF+30d |  | 0 | 309 | Warning
32263 | Yolo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13924SF+30d |  | 0 | 309 | Warning
32264 | Yolo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13925SF+30d |  | 0 | 309 | Warning
32265 | Yolo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13926SF+30d |  | 0 | 309 | Warning
32266 | Yolo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13927SF+30d |  | 0 | 309 | Warning
32267 | Yolo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13908 |  | 0 | 234 | Warning
32268 | Yolo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 13909 |  | 0 | 234 | Warning
32269 | Yolo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
32270 | Yolo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13929FS+12d | 0 | 240 | Warning
32271 | Yolo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
32272 | Yolo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13929SF+60d | 0 | 250 | Warning
32273 | Yolo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13912SF+30d | 0 | 240 | Warning
32274 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13913SF+30d | 0 | 240 | Warning
32275 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13914SF+30d | 0 | 240 | Warning
32276 | Yolo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13915SF+30d | 0 | 240 | Warning
32277 | Yolo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13916SF+30d | 0 | 240 | Warning
32278 | Yolo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32279 | Yolo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 13920FS+12d,13922SF+60d |  | 0 | 240 | Warning
32282 | Yuba CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM | 703 | 245d |  |  | 0.55 | 245 | Warning
32287 | Yuba CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32288 | Yuba CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32289 | Yuba CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
32290 | Yuba CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | 245 | Warning
32292 | Yuba CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
32293 | Yuba CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
32315 | Yuba CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
32316 | Yuba CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
32317 | Yuba CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
32318 | Yuba CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
32319 | Yuba CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
32320 | Yuba CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
32321 | Yuba CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
32322 | Yuba CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
32323 | Yuba CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32324 | Yuba CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
32325 | Yuba CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
32326 | Yuba CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32327 | Yuba CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
32334 | Yuba CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
32335 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13986SS | 0 | 414 | Warning
32336 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 13985SS |  | 0 | 414 | Warning
32337 | Yuba CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32338 | Yuba CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32339 | Yuba CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
32340 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13991SS | 0 | 352 | Warning
32341 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d | 13990SS |  | 0 | 352 | Warning
32342 | Yuba CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
32343 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13994SS | 0 | 288 | Warning
32344 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13993SS |  | 0 | 288 | Warning
32345 | Yuba CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
32346 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13997SS | 0 | 268 | Warning
32347 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 13996SS |  | 0 | 268 | Warning
32348 | Yuba CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32349 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 14000SS | 0 | 246 | Warning
32350 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 13999SS |  | 0 | 246 | Warning
32351 | Yuba CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
32352 | Yuba CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 673 | 234d |  |  | 0.49 | 234 | Warning
32355 | Yuba CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 631 | 234d | 14004 |  | 0.6 | 234 | Warning
32359 | Yuba CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32362 | Yuba CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14011 |  | 0.2 | 466 | Warning
32363 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32365 | Yuba CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14014 | 14016 | 0.8 | 405 | Warning
32366 | Yuba CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14015 |  | 0 | 405 | Warning
32367 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32368 | Yuba CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14019 | 0.2 | 405 | Warning
32369 | Yuba CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14018 | 14020 | 0 | 405 | Warning
32370 | Yuba CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14019 |  | 0 | 405 | Warning
32371 | Yuba CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32372 | Yuba CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14023 | 0 | 362 | Warning
32373 | Yuba CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14022 | 14024 | 0 | 362 | Warning
32374 | Yuba CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14023 |  | 0 | 362 | Warning
32375 | Yuba CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32376 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32377 | Yuba CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.55 | 298 | Warning
32378 | Yuba CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.99 | 357 | Warning
32381 | Yuba CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 14030 |  | 0.8 | 357 | Warning
32389 | Yuba CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
32391 | Yuba CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14040SS | 14042,14045,14043SF+30d | 0.2 | 298 | Warning
32392 | Yuba CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14041 |  | 0 | 298 | Warning
32393 | Yuba CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14041SF+30d |  | 0 | 298 | Warning
32394 | Yuba CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32395 | Yuba CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14041 |  | 0 | 345 | Warning
32396 | Yuba CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.92 | 445 | Warning
32399 | Yuba CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 14048SS |  | 0.8 | 445 | Warning
32407 | Yuba CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
32409 | Yuba CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14058SS | 14063,14060 | 0.2 | 298 | Warning
32410 | Yuba CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14059 |  | 0 | 298 | Warning
32411 | Yuba CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
32412 | Yuba CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32413 | Yuba CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14059 |  | 0 | 345 | Warning
32414 | Yuba CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 363d |  |  | 0.2 | 363 | Warning
32415 | Yuba CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32416 | Yuba CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32417 | Yuba CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32418 | Yuba CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32419 | Yuba CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32420 | Yuba CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32421 | Yuba CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32422 | Yuba CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32423 | Yuba CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32424 | Yuba CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32425 | Yuba CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0.2 | 362 | Warning
32426 | Yuba CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
32429 | Yuba CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32430 | Yuba CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32431 | Yuba CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32432 | Yuba CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | 321 | Warning
32433 | Yuba CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 14092 | 0 | 234 | Warning
32434 | Yuba CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 14093 | 0 | 234 | Warning
32436 | Yuba CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32437 | Yuba CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14098SF+30d |  | 0 | 309 | Warning
32438 | Yuba CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14099SF+30d |  | 0 | 309 | Warning
32439 | Yuba CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14100SF+30d |  | 0 | 309 | Warning
32440 | Yuba CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14101SF+30d |  | 0 | 309 | Warning
32441 | Yuba CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14102SF+30d |  | 0 | 309 | Warning
32442 | Yuba CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 14083 |  | 0 | 234 | Warning
32443 | Yuba CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 14084 |  | 0 | 234 | Warning
32444 | Yuba CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
32445 | Yuba CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 14104FS+12d | 0 | 240 | Warning
32446 | Yuba CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
32447 | Yuba CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 14104SF+60d | 0 | 250 | Warning
32448 | Yuba CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14087SF+30d | 0 | 240 | Warning
32449 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14088SF+30d | 0 | 240 | Warning
32450 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14089SF+30d | 0 | 240 | Warning
32451 | Yuba CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14090SF+30d | 0 | 240 | Warning
32452 | Yuba CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14091SF+30d | 0 | 240 | Warning
32453 | Yuba CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32454 | Yuba CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 14095FS+12d,14097SF+60d |  | 0 | 240 | Warning
32455 | CARES V1 - Butte CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.36 | 235 | Warning
32456 | Butte CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
32457 | Butte CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
32462 | Butte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32463 | Butte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32464 | Butte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
32465 | Butte CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
32466 | Butte CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
32467 | Butte CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
32489 | Butte CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
32490 | Butte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
32491 | Butte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
32492 | Butte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
32493 | Butte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
32494 | Butte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
32495 | Butte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
32496 | Butte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
32497 | Butte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32498 | Butte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
32499 | Butte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
32500 | Butte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32501 | Butte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
32508 | Butte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
32509 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14160SS | 0 | 414 | Warning
32510 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 14159SS |  | 0 | 414 | Warning
32511 | Butte CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32512 | Butte CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32513 | Butte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
32514 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14165SS | 0 | 385 | Warning
32515 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14164SS |  | 0 | 371 | Warning
32516 | Butte CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
32517 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14168SS | 0 | 343 | Warning
32518 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14167SS |  | 0 | 332 | Warning
32519 | Butte CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
32520 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14171SS | 0 | 321 | Warning
32521 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14170SS |  | 0 | 311 | Warning
32522 | Butte CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
32523 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14174SS | 0 | 299 | Warning
32524 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14173SS |  | 0 | 289 | Warning
32525 | Butte CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
32526 | Butte CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.35 | 277 | Warning
32529 | Butte CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14178 |  | 0.2 | 277 | Warning
32533 | Butte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32536 | Butte CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14185 |  | 0.2 | 466 | Warning
32537 | Butte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32539 | Butte CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14188 | 14190 | 0.2 | 405 | Warning
32540 | Butte CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14189 |  | 0 | 405 | Warning
32541 | Butte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32543 | Butte CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14192 | 14194 | 0 | 405 | Warning
32544 | Butte CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14193 |  | 0 | 405 | Warning
32545 | Butte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32546 | Butte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14197 | 0 | 362 | Warning
32547 | Butte CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14196 | 14198 | 0 | 362 | Warning
32548 | Butte CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14197 |  | 0 | 362 | Warning
32549 | Butte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32550 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32551 | Butte CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.46 | 298 | Warning
32552 | Butte CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
32555 | Butte CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 14204 |  | 0 | 357 | Warning
32560 | Butte CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
32562 | Butte CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 14211 |  | 0 | 485 | Warning
32563 | Butte CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
32565 | Butte CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14214SS | 14216,14219,14217SF+30d | 0.2 | 298 | Warning
32566 | Butte CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14215 |  | 0 | 298 | Warning
32567 | Butte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14215SF+30d |  | 0 | 298 | Warning
32568 | Butte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32569 | Butte CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14215 |  | 0 | 345 | Warning
32570 | Butte CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
32573 | Butte CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 14222SS |  | 0.2 | 445 | Warning
32581 | Butte CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
32583 | Butte CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14232SS | 14237,14234 | 0.2 | 298 | Warning
32584 | Butte CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14233 |  | 0 | 298 | Warning
32585 | Butte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
32586 | Butte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32587 | Butte CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14233 |  | 0 | 345 | Warning
32588 | Butte CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
32589 | Butte CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32590 | Butte CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32591 | Butte CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32592 | Butte CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32593 | Butte CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32594 | Butte CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32595 | Butte CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32596 | Butte CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32597 | Butte CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32598 | Butte CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32599 | Butte CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32600 | Butte CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
32601 | Butte CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
32602 | Butte CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14259 | 0.2 | 256 | Warning
32603 | Butte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32604 | Butte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32605 | Butte CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32606 | Butte CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32607 | Butte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14266 | 0 | 273 | Warning
32608 | Butte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14267 | 0 | 273 | Warning
32609 | Butte CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 14252 |  | 0 | 256 | Warning
32610 | Butte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32611 | Butte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14272SF+30d | 0 | 333 | Warning
32612 | Butte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14273SF+30d | 0 | 333 | Warning
32613 | Butte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14274SF+30d | 0 | 333 | Warning
32614 | Butte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14275SF+30d | 0 | 333 | Warning
32615 | Butte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14276SF+30d | 0 | 333 | Warning
32616 | Butte CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14257 |  | 0 | 273 | Warning
32617 | Butte CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14258 |  | 0 | 273 | Warning
32618 | Butte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
32619 | Butte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14278FS+12d | 0 | 279 | Warning
32620 | Butte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32621 | Butte CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14278SF+60d | 0 | 299 | Warning
32622 | Butte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14261SF+30d |  | 0 | 299 | Warning
32623 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14262SF+30d |  | 0 | 299 | Warning
32624 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14263SF+30d |  | 0 | 299 | Warning
32625 | Butte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14264SF+30d |  | 0 | 299 | Warning
32626 | Butte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14265SF+30d |  | 0 | 299 | Warning
32627 | Butte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32628 | Butte CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14269FS+12d,14271SF+60d |  | 0 | 279 | Warning
32629 | CARES V1 - Fresno CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
32630 | Fresno CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
32631 | Fresno CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
32636 | Fresno CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32637 | Fresno CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32638 | Fresno CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
32639 | Fresno CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
32640 | Fresno CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
32641 | Fresno CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
32663 | Fresno CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
32664 | Fresno CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
32665 | Fresno CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
32666 | Fresno CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
32667 | Fresno CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
32668 | Fresno CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
32669 | Fresno CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
32670 | Fresno CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
32671 | Fresno CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32672 | Fresno CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
32673 | Fresno CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
32674 | Fresno CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32675 | Fresno CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
32682 | Fresno CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
32683 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14334SS | 0 | 414 | Warning
32684 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 14333SS |  | 0 | 414 | Warning
32685 | Fresno CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32686 | Fresno CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32687 | Fresno CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
32688 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14339SS | 0 | 385 | Warning
32689 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14338SS |  | 0 | 371 | Warning
32690 | Fresno CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
32691 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14342SS | 0 | 343 | Warning
32692 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14341SS |  | 0 | 332 | Warning
32693 | Fresno CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
32694 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14345SS | 0 | 321 | Warning
32695 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14344SS |  | 0 | 311 | Warning
32696 | Fresno CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
32697 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14348SS | 0 | 299 | Warning
32698 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14347SS |  | 0 | 289 | Warning
32699 | Fresno CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
32700 | Fresno CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.48 | 277 | Warning
32703 | Fresno CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14352 |  | 0.6 | 277 | Warning
32707 | Fresno CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32710 | Fresno CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14359 |  | 0.4 | 466 | Warning
32711 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32713 | Fresno CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14362 | 14364 | 0.2 | 405 | Warning
32714 | Fresno CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14363 |  | 0 | 405 | Warning
32715 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32716 | Fresno CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14367 | 0.2 | 405 | Warning
32717 | Fresno CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14366 | 14368 | 0 | 405 | Warning
32718 | Fresno CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14367 |  | 0 | 405 | Warning
32719 | Fresno CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32720 | Fresno CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14371 | 0 | 362 | Warning
32721 | Fresno CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14370 | 14372 | 0 | 362 | Warning
32722 | Fresno CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14371 |  | 0 | 362 | Warning
32723 | Fresno CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32724 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32725 | Fresno CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.49 | 298 | Warning
32737 | Fresno CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
32739 | Fresno CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14388SS | 14390,14393,14391SF+30d | 0 | 298 | Warning
32740 | Fresno CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14389 |  | 0 | 298 | Warning
32741 | Fresno CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14389SF+30d |  | 0 | 298 | Warning
32742 | Fresno CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32743 | Fresno CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14389 |  | 0 | 345 | Warning
32755 | Fresno CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
32757 | Fresno CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14406SS | 14411,14408 | 0 | 298 | Warning
32758 | Fresno CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14407 |  | 0 | 298 | Warning
32759 | Fresno CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
32760 | Fresno CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32761 | Fresno CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14407 |  | 0 | 345 | Warning
32762 | Fresno CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
32763 | Fresno CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32764 | Fresno CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32765 | Fresno CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32766 | Fresno CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32767 | Fresno CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32768 | Fresno CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32769 | Fresno CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32770 | Fresno CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32771 | Fresno CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32772 | Fresno CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32773 | Fresno CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32774 | Fresno CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
32775 | Fresno CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
32776 | Fresno CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14433 | 0.2 | 256 | Warning
32777 | Fresno CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32778 | Fresno CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32779 | Fresno CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32780 | Fresno CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32781 | Fresno CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14440 | 0 | 273 | Warning
32782 | Fresno CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14441 | 0 | 273 | Warning
32783 | Fresno CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 14426 |  | 0 | 256 | Warning
32784 | Fresno CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32785 | Fresno CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14446SF+30d | 0 | 333 | Warning
32786 | Fresno CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14447SF+30d | 0 | 333 | Warning
32787 | Fresno CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14448SF+30d | 0 | 333 | Warning
32788 | Fresno CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14449SF+30d | 0 | 333 | Warning
32789 | Fresno CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14450SF+30d | 0 | 333 | Warning
32790 | Fresno CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14431 |  | 0 | 273 | Warning
32791 | Fresno CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14432 |  | 0 | 273 | Warning
32792 | Fresno CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
32793 | Fresno CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14452FS+12d | 0 | 279 | Warning
32794 | Fresno CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32795 | Fresno CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14452SF+60d | 0 | 299 | Warning
32796 | Fresno CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14435SF+30d |  | 0 | 299 | Warning
32797 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14436SF+30d |  | 0 | 299 | Warning
32798 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14437SF+30d |  | 0 | 299 | Warning
32799 | Fresno CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14438SF+30d |  | 0 | 299 | Warning
32800 | Fresno CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14439SF+30d |  | 0 | 299 | Warning
32801 | Fresno CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32802 | Fresno CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14443FS+12d,14445SF+60d |  | 0 | 279 | Warning
32803 | CARES V1 - San Diego CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.33 | 235 | Warning
32804 | San Diego CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
32805 | San Diego CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
32810 | San Diego CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32811 | San Diego CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32812 | San Diego CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
32813 | San Diego CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
32814 | San Diego CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.4 | 235 | Warning
32815 | San Diego CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
32838 | San Diego CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
32839 | San Diego CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
32840 | San Diego CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
32841 | San Diego CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
32842 | San Diego CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
32843 | San Diego CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
32844 | San Diego CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
32845 | San Diego CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32846 | San Diego CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
32847 | San Diego CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
32848 | San Diego CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
32849 | San Diego CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
32856 | San Diego CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
32857 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14508SS | 0 | 414 | Warning
32858 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 14507SS |  | 0 | 414 | Warning
32859 | San Diego CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32860 | San Diego CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
32861 | San Diego CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
32862 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14513SS | 0 | 385 | Warning
32863 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14512SS |  | 0 | 371 | Warning
32864 | San Diego CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
32865 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14516SS | 0 | 343 | Warning
32866 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14515SS |  | 0 | 332 | Warning
32867 | San Diego CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
32868 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14519SS | 0 | 321 | Warning
32869 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14518SS |  | 0 | 311 | Warning
32870 | San Diego CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
32871 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14522SS | 0 | 299 | Warning
32872 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14521SS |  | 0 | 289 | Warning
32873 | San Diego CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
32874 | San Diego CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.33 | 277 | Warning
32877 | San Diego CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14526 |  | 0.2 | 277 | Warning
32881 | San Diego CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32884 | San Diego CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14533 |  | 0.2 | 466 | Warning
32885 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32887 | San Diego CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14536 | 14538 | 0.2 | 405 | Warning
32888 | San Diego CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14537 |  | 0 | 405 | Warning
32889 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32890 | San Diego CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14541 | 0.6 | 405 | Warning
32891 | San Diego CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14540 | 14542 | 0 | 405 | Warning
32892 | San Diego CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14541 |  | 0 | 405 | Warning
32893 | San Diego CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
32894 | San Diego CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14545 | 0 | 362 | Warning
32895 | San Diego CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14544 | 14546 | 0 | 362 | Warning
32896 | San Diego CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14545 |  | 0 | 362 | Warning
32897 | San Diego CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
32898 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
32899 | San Diego CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.41 | 298 | Warning
32900 | San Diego CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
32903 | San Diego CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 14552 |  | 0 | 357 | Warning
32911 | San Diego CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.01 | 298 | Warning
32912 | San Diego CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 14559SS | 14563SS | 0.2 | 508 | Warning
32913 | San Diego CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14562SS | 14564,14567,14565SF+30d | 0 | 298 | Warning
32914 | San Diego CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14563 |  | 0 | 298 | Warning
32915 | San Diego CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14563SF+30d |  | 0 | 298 | Warning
32916 | San Diego CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32917 | San Diego CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14563 |  | 0 | 345 | Warning
32918 | San Diego CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.62 | 445 | Warning
32921 | San Diego CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 14570SS |  | 0 | 445 | Warning
32929 | San Diego CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.02 | 298 | Warning
32930 | San Diego CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 14574,14581SS | 0.2 | 508 | Warning
32931 | San Diego CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14580SS | 14585,14582 | 0 | 298 | Warning
32932 | San Diego CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14581 |  | 0 | 298 | Warning
32933 | San Diego CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
32934 | San Diego CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
32935 | San Diego CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14581 |  | 0 | 345 | Warning
32936 | San Diego CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
32937 | San Diego CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32938 | San Diego CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32939 | San Diego CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32940 | San Diego CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32941 | San Diego CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32942 | San Diego CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32943 | San Diego CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32944 | San Diego CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32945 | San Diego CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32946 | San Diego CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32947 | San Diego CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
32948 | San Diego CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
32949 | San Diego CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0 | 256 | Warning
32950 | San Diego CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14607 | 0 | 256 | Warning
32951 | San Diego CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
32952 | San Diego CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
32953 | San Diego CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32954 | San Diego CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32955 | San Diego CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14614 | 0 | 273 | Warning
32956 | San Diego CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14615 | 0 | 273 | Warning
32957 | San Diego CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 14600 |  | 0 | 256 | Warning
32958 | San Diego CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
32959 | San Diego CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14620SF+30d | 0 | 333 | Warning
32960 | San Diego CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14621SF+30d | 0 | 333 | Warning
32961 | San Diego CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14622SF+30d | 0 | 333 | Warning
32962 | San Diego CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14623SF+30d | 0 | 333 | Warning
32963 | San Diego CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14624SF+30d | 0 | 333 | Warning
32964 | San Diego CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14605 |  | 0 | 273 | Warning
32965 | San Diego CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14606 |  | 0 | 273 | Warning
32966 | San Diego CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
32967 | San Diego CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14626FS+12d | 0 | 279 | Warning
32968 | San Diego CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
32969 | San Diego CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14626SF+60d | 0 | 299 | Warning
32970 | San Diego CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14609SF+30d |  | 0 | 299 | Warning
32971 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14610SF+30d |  | 0 | 299 | Warning
32972 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14611SF+30d |  | 0 | 299 | Warning
32973 | San Diego CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14612SF+30d |  | 0 | 299 | Warning
32974 | San Diego CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14613SF+30d |  | 0 | 299 | Warning
32975 | San Diego CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
32976 | San Diego CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14617FS+12d,14619SF+60d |  | 0 | 279 | Warning
32977 | CARES V1 - San Mateo CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.37 | 235 | Warning
32978 | San Mateo CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
32979 | San Mateo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
32984 | San Mateo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
32985 | San Mateo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
32986 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
32987 | San Mateo CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
32988 | San Mateo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
32989 | San Mateo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
33011 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
33012 | San Mateo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33013 | San Mateo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33014 | San Mateo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33015 | San Mateo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33016 | San Mateo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33017 | San Mateo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33018 | San Mateo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33019 | San Mateo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33020 | San Mateo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33021 | San Mateo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33022 | San Mateo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33023 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33030 | San Mateo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
33031 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14682SS | 0 | 414 | Warning
33032 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 14681SS |  | 0 | 414 | Warning
33033 | San Mateo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33034 | San Mateo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33035 | San Mateo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33036 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14687SS | 0 | 385 | Warning
33037 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14686SS |  | 0 | 371 | Warning
33038 | San Mateo CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33039 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14690SS | 0 | 343 | Warning
33040 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14689SS |  | 0 | 332 | Warning
33041 | San Mateo CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33042 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14693SS | 0 | 321 | Warning
33043 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14692SS |  | 0 | 311 | Warning
33044 | San Mateo CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33045 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14696SS | 0 | 299 | Warning
33046 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14695SS |  | 0 | 289 | Warning
33047 | San Mateo CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33048 | San Mateo CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.53 | 277 | Warning
33051 | San Mateo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14700 |  | 0.6 | 277 | Warning
33055 | San Mateo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33058 | San Mateo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14707 |  | 0.2 | 466 | Warning
33059 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33061 | San Mateo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14710 | 14712 | 0.4 | 405 | Warning
33062 | San Mateo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14711 |  | 0 | 405 | Warning
33063 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33065 | San Mateo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14714 | 14716 | 0 | 405 | Warning
33066 | San Mateo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14715 |  | 0 | 405 | Warning
33067 | San Mateo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33069 | San Mateo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14718 | 14720 | 0 | 362 | Warning
33070 | San Mateo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14719 |  | 0 | 362 | Warning
33071 | San Mateo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33072 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33073 | San Mateo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.43 | 298 | Warning
33074 | San Mateo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.79 | 357 | Warning
33077 | San Mateo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 14726 |  | 0.6 | 357 | Warning
33082 | San Mateo CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.77 | 485 | Warning
33084 | San Mateo CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 14733 |  | 0.4 | 485 | Warning
33085 | San Mateo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
33087 | San Mateo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14736SS | 14738,14741,14739SF+30d | 0.2 | 298 | Warning
33088 | San Mateo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14737 |  | 0 | 298 | Warning
33089 | San Mateo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14737SF+30d |  | 0 | 298 | Warning
33090 | San Mateo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33091 | San Mateo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14737 |  | 0 | 345 | Warning
33092 | San Mateo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.7 | 445 | Warning
33095 | San Mateo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 14744SS |  | 0.2 | 445 | Warning
33103 | San Mateo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
33105 | San Mateo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14754SS | 14759,14756 | 0.2 | 298 | Warning
33106 | San Mateo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14755 |  | 0 | 298 | Warning
33107 | San Mateo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
33108 | San Mateo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33109 | San Mateo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14755 |  | 0 | 345 | Warning
33110 | San Mateo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33111 | San Mateo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33112 | San Mateo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33113 | San Mateo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33114 | San Mateo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33115 | San Mateo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33116 | San Mateo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33117 | San Mateo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33118 | San Mateo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33119 | San Mateo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33120 | San Mateo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33121 | San Mateo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33122 | San Mateo CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33123 | San Mateo CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.05 | 256 | Warning
33124 | San Mateo CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14781 | 0.4 | 256 | Warning
33125 | San Mateo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33126 | San Mateo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33127 | San Mateo CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33128 | San Mateo CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33129 | San Mateo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14788 | 0 | 273 | Warning
33130 | San Mateo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14789 | 0 | 273 | Warning
33131 | San Mateo CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 14774 |  | 0 | 256 | Warning
33132 | San Mateo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
33133 | San Mateo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14794SF+30d | 0 | 333 | Warning
33134 | San Mateo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14795SF+30d | 0 | 333 | Warning
33135 | San Mateo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14796SF+30d | 0 | 333 | Warning
33136 | San Mateo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14797SF+30d | 0 | 333 | Warning
33137 | San Mateo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14798SF+30d | 0 | 333 | Warning
33138 | San Mateo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14779 |  | 0 | 273 | Warning
33139 | San Mateo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14780 |  | 0 | 273 | Warning
33140 | San Mateo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
33141 | San Mateo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14800FS+12d | 0 | 279 | Warning
33142 | San Mateo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33143 | San Mateo CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14800SF+60d | 0 | 299 | Warning
33144 | San Mateo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14783SF+30d |  | 0 | 299 | Warning
33145 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14784SF+30d |  | 0 | 299 | Warning
33146 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14785SF+30d |  | 0 | 299 | Warning
33147 | San Mateo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14786SF+30d |  | 0 | 299 | Warning
33148 | San Mateo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14787SF+30d |  | 0 | 299 | Warning
33149 | San Mateo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
33150 | San Mateo CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14791FS+12d,14793SF+60d |  | 0 | 279 | Warning
33151 | CARES V1 - Tuolumne CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.3 | 235 | Warning
33152 | Tuolumne CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
33153 | Tuolumne CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
33158 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33159 | Tuolumne CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
33160 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
33161 | Tuolumne CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
33162 | Tuolumne CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.39 | 235 | Warning
33163 | Tuolumne CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
33186 | Tuolumne CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33187 | Tuolumne CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33188 | Tuolumne CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33189 | Tuolumne CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33190 | Tuolumne CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33191 | Tuolumne CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33192 | Tuolumne CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33193 | Tuolumne CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33194 | Tuolumne CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33195 | Tuolumne CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33196 | Tuolumne CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33197 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33204 | Tuolumne CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
33205 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14856SS | 0 | 414 | Warning
33206 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 14855SS |  | 0 | 414 | Warning
33207 | Tuolumne CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33208 | Tuolumne CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33209 | Tuolumne CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33210 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14861SS | 0 | 385 | Warning
33211 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14860SS |  | 0 | 371 | Warning
33212 | Tuolumne CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33213 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14864SS | 0 | 343 | Warning
33214 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14863SS |  | 0 | 332 | Warning
33215 | Tuolumne CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33216 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14867SS | 0 | 321 | Warning
33217 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14866SS |  | 0 | 311 | Warning
33218 | Tuolumne CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33219 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14870SS | 0 | 299 | Warning
33220 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14869SS |  | 0 | 289 | Warning
33221 | Tuolumne CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33222 | Tuolumne CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.33 | 277 | Warning
33225 | Tuolumne CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14874 |  | 0.2 | 277 | Warning
33229 | Tuolumne CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33232 | Tuolumne CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 14881 |  | 0 | 466 | Warning
33233 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33235 | Tuolumne CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 14884 | 14886 | 0.4 | 405 | Warning
33236 | Tuolumne CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 14885 |  | 0 | 405 | Warning
33237 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33238 | Tuolumne CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14889 | 0.6 | 405 | Warning
33239 | Tuolumne CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 14888 | 14890 | 0 | 405 | Warning
33240 | Tuolumne CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 14889 |  | 0 | 405 | Warning
33241 | Tuolumne CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33242 | Tuolumne CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14893 | 0 | 362 | Warning
33243 | Tuolumne CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 14892 | 14894 | 0 | 362 | Warning
33244 | Tuolumne CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 14893 |  | 0 | 362 | Warning
33245 | Tuolumne CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33246 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33247 | Tuolumne CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.34 | 298 | Warning
33248 | Tuolumne CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.76 | 357 | Warning
33250 | Tuolumne CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 14899SS | 14901 | 0.6 | 357 | Warning
33251 | Tuolumne CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 14900 |  | 0 | 357 | Warning
33259 | Tuolumne CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
33261 | Tuolumne CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 14910SS | 14912,14915,14913SF+30d | 0 | 298 | Warning
33262 | Tuolumne CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14911 |  | 0 | 298 | Warning
33263 | Tuolumne CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14911SF+30d |  | 0 | 298 | Warning
33264 | Tuolumne CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33265 | Tuolumne CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14911 |  | 0 | 345 | Warning
33266 | Tuolumne CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.31 | 445 | Warning
33268 | Tuolumne CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d | 14917SS | 14919SS | 0 | 445 | Warning
33269 | Tuolumne CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 14918SS |  | 0 | 445 | Warning
33277 | Tuolumne CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
33279 | Tuolumne CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 14928SS | 14933,14930 | 0 | 298 | Warning
33280 | Tuolumne CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 14929 |  | 0 | 298 | Warning
33281 | Tuolumne CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
33282 | Tuolumne CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33283 | Tuolumne CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 14929 |  | 0 | 345 | Warning
33284 | Tuolumne CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33285 | Tuolumne CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33286 | Tuolumne CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33287 | Tuolumne CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33288 | Tuolumne CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33289 | Tuolumne CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33290 | Tuolumne CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33291 | Tuolumne CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33292 | Tuolumne CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33293 | Tuolumne CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33294 | Tuolumne CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33295 | Tuolumne CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33296 | Tuolumne CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33297 | Tuolumne CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
33298 | Tuolumne CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14955 | 0.2 | 256 | Warning
33299 | Tuolumne CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33300 | Tuolumne CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33301 | Tuolumne CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33302 | Tuolumne CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33303 | Tuolumne CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14962 | 0 | 273 | Warning
33304 | Tuolumne CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14963 | 0 | 273 | Warning
33305 | Tuolumne CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 14948 |  | 0 | 256 | Warning
33306 | Tuolumne CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
33307 | Tuolumne CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14968SF+30d | 0 | 333 | Warning
33308 | Tuolumne CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14969SF+30d | 0 | 333 | Warning
33309 | Tuolumne CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14970SF+30d | 0 | 333 | Warning
33310 | Tuolumne CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14971SF+30d | 0 | 333 | Warning
33311 | Tuolumne CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14972SF+30d | 0 | 333 | Warning
33312 | Tuolumne CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14953 |  | 0 | 273 | Warning
33313 | Tuolumne CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 14954 |  | 0 | 273 | Warning
33314 | Tuolumne CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
33315 | Tuolumne CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14974FS+12d | 0 | 279 | Warning
33316 | Tuolumne CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33317 | Tuolumne CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14974SF+60d | 0 | 299 | Warning
33318 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14957SF+30d |  | 0 | 299 | Warning
33319 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14958SF+30d |  | 0 | 299 | Warning
33320 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14959SF+30d |  | 0 | 299 | Warning
33321 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14960SF+30d |  | 0 | 299 | Warning
33322 | Tuolumne CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14961SF+30d |  | 0 | 299 | Warning
33323 | Tuolumne CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
33324 | Tuolumne CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14965FS+12d,14967SF+60d |  | 0 | 279 | Warning
33325 | CARES V1 - Calaveras CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.32 | 235 | Warning
33326 | Calaveras CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
33327 | Calaveras CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
33332 | Calaveras CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33333 | Calaveras CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
33334 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
33335 | Calaveras CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
33336 | Calaveras CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
33337 | Calaveras CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
33359 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
33360 | Calaveras CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33361 | Calaveras CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33362 | Calaveras CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33363 | Calaveras CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33364 | Calaveras CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33365 | Calaveras CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33366 | Calaveras CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33367 | Calaveras CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33368 | Calaveras CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33369 | Calaveras CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33370 | Calaveras CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33371 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33378 | Calaveras CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
33379 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15030SS | 0 | 414 | Warning
33380 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15029SS |  | 0 | 414 | Warning
33381 | Calaveras CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33382 | Calaveras CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33383 | Calaveras CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33384 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15035SS | 0 | 385 | Warning
33385 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15034SS |  | 0 | 371 | Warning
33386 | Calaveras CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33387 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15038SS | 0 | 343 | Warning
33388 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15037SS |  | 0 | 332 | Warning
33389 | Calaveras CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33390 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15041SS | 0 | 321 | Warning
33391 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15040SS |  | 0 | 311 | Warning
33392 | Calaveras CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33393 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15044SS | 0 | 299 | Warning
33394 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15043SS |  | 0 | 289 | Warning
33395 | Calaveras CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33396 | Calaveras CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.35 | 277 | Warning
33399 | Calaveras CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15048 |  | 0.2 | 277 | Warning
33403 | Calaveras CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33406 | Calaveras CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 15055 |  | 0.2 | 466 | Warning
33407 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33409 | Calaveras CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 15058 | 15060 | 0.6 | 405 | Warning
33410 | Calaveras CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 15059 |  | 0 | 405 | Warning
33411 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33412 | Calaveras CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15063 | 0.6 | 405 | Warning
33413 | Calaveras CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 15062 | 15064 | 0 | 405 | Warning
33414 | Calaveras CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15063 |  | 0 | 405 | Warning
33415 | Calaveras CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33416 | Calaveras CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15067 | 0 | 362 | Warning
33417 | Calaveras CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 15066 | 15068 | 0 | 362 | Warning
33418 | Calaveras CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 15067 |  | 0 | 362 | Warning
33419 | Calaveras CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33420 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33421 | Calaveras CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.38 | 298 | Warning
33422 | Calaveras CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
33423 | Calaveras CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 15074SS | 0.6 | 405 | Warning
33424 | Calaveras CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d | 15073SS | 15075 | 0.6 | 357 | Warning
33425 | Calaveras CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 15074 |  | 0 | 357 | Warning
33430 | Calaveras CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
33432 | Calaveras CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 15081 |  | 0 | 485 | Warning
33433 | Calaveras CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.11 | 298 | Warning
33435 | Calaveras CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 15084SS | 15086,15089,15087SF+30d | 0.2 | 298 | Warning
33436 | Calaveras CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15085 |  | 0 | 298 | Warning
33437 | Calaveras CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15085SF+30d |  | 0 | 298 | Warning
33438 | Calaveras CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33439 | Calaveras CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15085 |  | 0 | 345 | Warning
33440 | Calaveras CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.72 | 445 | Warning
33441 | Calaveras CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 15092SS | 0.8 | 485 | Warning
33442 | Calaveras CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 15091SS | 15093SS | 0.8 | 485 | Warning
33443 | Calaveras CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 15092SS |  | 0.6 | 445 | Warning
33448 | Calaveras CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.98 | 508 | Warning
33450 | Calaveras CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 15099 |  | 0.95 | 508 | Warning
33451 | Calaveras CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.21 | 298 | Warning
33453 | Calaveras CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 15102SS | 15107,15104 | 0.2 | 298 | Warning
33454 | Calaveras CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15103 |  | 0 | 298 | Warning
33455 | Calaveras CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | 298 | Warning
33456 | Calaveras CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33457 | Calaveras CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15103 |  | 0 | 345 | Warning
33458 | Calaveras CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33459 | Calaveras CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33460 | Calaveras CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33461 | Calaveras CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33462 | Calaveras CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33463 | Calaveras CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33464 | Calaveras CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33465 | Calaveras CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33466 | Calaveras CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33467 | Calaveras CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33468 | Calaveras CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33469 | Calaveras CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33470 | Calaveras CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33471 | Calaveras CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
33472 | Calaveras CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15129 | 0.2 | 256 | Warning
33473 | Calaveras CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33474 | Calaveras CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33475 | Calaveras CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33476 | Calaveras CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33477 | Calaveras CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15136 | 0 | 273 | Warning
33478 | Calaveras CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15137 | 0 | 273 | Warning
33479 | Calaveras CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 15122 |  | 0 | 256 | Warning
33480 | Calaveras CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
33481 | Calaveras CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15142SF+30d | 0 | 333 | Warning
33482 | Calaveras CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15143SF+30d | 0 | 333 | Warning
33483 | Calaveras CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15144SF+30d | 0 | 333 | Warning
33484 | Calaveras CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15145SF+30d | 0 | 333 | Warning
33485 | Calaveras CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15146SF+30d | 0 | 333 | Warning
33486 | Calaveras CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15127 |  | 0 | 273 | Warning
33487 | Calaveras CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15128 |  | 0 | 273 | Warning
33488 | Calaveras CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
33489 | Calaveras CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15148FS+12d | 0 | 279 | Warning
33490 | Calaveras CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33491 | Calaveras CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15148SF+60d | 0 | 299 | Warning
33492 | Calaveras CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15131SF+30d |  | 0 | 299 | Warning
33493 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15132SF+30d |  | 0 | 299 | Warning
33494 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15133SF+30d |  | 0 | 299 | Warning
33495 | Calaveras CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15134SF+30d |  | 0 | 299 | Warning
33496 | Calaveras CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15135SF+30d |  | 0 | 299 | Warning
33497 | Calaveras CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
33498 | Calaveras CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15139FS+12d,15141SF+60d |  | 0 | 279 | Warning
33499 | CARES V1 - Kings CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.36 | 235 | Warning
33500 | Kings CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
33501 | Kings CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
33506 | Kings CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33507 | Kings CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
33508 | Kings CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
33509 | Kings CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
33510 | Kings CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.4 | 235 | Warning
33511 | Kings CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.65 | 235 | Warning
33534 | Kings CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33535 | Kings CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33536 | Kings CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33537 | Kings CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33538 | Kings CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33539 | Kings CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33540 | Kings CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33541 | Kings CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33542 | Kings CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33543 | Kings CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33544 | Kings CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33545 | Kings CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33552 | Kings CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
33553 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15204SS | 0 | 414 | Warning
33554 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15203SS |  | 0 | 414 | Warning
33555 | Kings CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33556 | Kings CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33557 | Kings CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33558 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15209SS | 0 | 385 | Warning
33559 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15208SS |  | 0 | 371 | Warning
33560 | Kings CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33561 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15212SS | 0 | 343 | Warning
33562 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15211SS |  | 0 | 332 | Warning
33563 | Kings CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33564 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15215SS | 0 | 321 | Warning
33565 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15214SS |  | 0 | 311 | Warning
33566 | Kings CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33567 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15218SS | 0 | 299 | Warning
33568 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15217SS |  | 0 | 289 | Warning
33569 | Kings CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33570 | Kings CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.32 | 277 | Warning
33573 | Kings CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15222 |  | 0.2 | 277 | Warning
33577 | Kings CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33580 | Kings CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 15229 |  | 0.2 | 466 | Warning
33581 | Kings CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33583 | Kings CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 15232 | 15234 | 0.2 | 405 | Warning
33584 | Kings CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 15233 |  | 0 | 405 | Warning
33585 | Kings CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33586 | Kings CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15237 | 0.2 | 405 | Warning
33587 | Kings CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 15236 | 15238 | 0 | 405 | Warning
33588 | Kings CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15237 |  | 0 | 405 | Warning
33589 | Kings CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33590 | Kings CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15241 | 0 | 362 | Warning
33591 | Kings CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 15240 | 15242 | 0 | 362 | Warning
33592 | Kings CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 15241 |  | 0 | 362 | Warning
33593 | Kings CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33594 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33595 | Kings CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.47 | 298 | Warning
33596 | Kings CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
33599 | Kings CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 15248 |  | 0.6 | 357 | Warning
33607 | Kings CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
33609 | Kings CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 15258SS | 15260,15263,15261SF+30d | 0 | 298 | Warning
33610 | Kings CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15259 |  | 0 | 298 | Warning
33611 | Kings CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15259SF+30d |  | 0 | 298 | Warning
33612 | Kings CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33613 | Kings CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15259 |  | 0 | 345 | Warning
33614 | Kings CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.85 | 445 | Warning
33617 | Kings CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 15266SS |  | 0.6 | 445 | Warning
33625 | Kings CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
33627 | Kings CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 15276SS | 15281,15278 | 0 | 298 | Warning
33628 | Kings CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15277 |  | 0 | 298 | Warning
33629 | Kings CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
33630 | Kings CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33631 | Kings CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15277 |  | 0 | 345 | Warning
33632 | Kings CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33633 | Kings CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33634 | Kings CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33635 | Kings CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33636 | Kings CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33637 | Kings CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33638 | Kings CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33639 | Kings CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33640 | Kings CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33641 | Kings CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33642 | Kings CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33643 | Kings CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33644 | Kings CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33645 | Kings CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
33646 | Kings CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15303 | 0.2 | 256 | Warning
33647 | Kings CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33648 | Kings CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33649 | Kings CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33650 | Kings CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33651 | Kings CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15310 | 0 | 273 | Warning
33652 | Kings CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15311 | 0 | 273 | Warning
33653 | Kings CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 15296 |  | 0 | 256 | Warning
33654 | Kings CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
33655 | Kings CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15316SF+30d | 0 | 333 | Warning
33656 | Kings CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15317SF+30d | 0 | 333 | Warning
33657 | Kings CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15318SF+30d | 0 | 333 | Warning
33658 | Kings CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15319SF+30d | 0 | 333 | Warning
33659 | Kings CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15320SF+30d | 0 | 333 | Warning
33660 | Kings CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15301 |  | 0 | 273 | Warning
33661 | Kings CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15302 |  | 0 | 273 | Warning
33662 | Kings CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
33663 | Kings CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15322FS+12d | 0 | 279 | Warning
33664 | Kings CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33665 | Kings CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15322SF+60d | 0 | 299 | Warning
33666 | Kings CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15305SF+30d |  | 0 | 299 | Warning
33667 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15306SF+30d |  | 0 | 299 | Warning
33668 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15307SF+30d |  | 0 | 299 | Warning
33669 | Kings CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15308SF+30d |  | 0 | 299 | Warning
33670 | Kings CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15309SF+30d |  | 0 | 299 | Warning
33671 | Kings CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
33672 | Kings CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15313FS+12d,15315SF+60d |  | 0 | 279 | Warning
33673 | CARES V1 - Riverside CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.35 | 235 | Warning
33674 | Riverside CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
33675 | Riverside CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
33680 | Riverside CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33681 | Riverside CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
33682 | Riverside CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
33683 | Riverside CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
33684 | Riverside CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
33685 | Riverside CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
33707 | Riverside CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
33708 | Riverside CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33709 | Riverside CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33710 | Riverside CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33711 | Riverside CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33712 | Riverside CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33713 | Riverside CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33714 | Riverside CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33715 | Riverside CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33716 | Riverside CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33717 | Riverside CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33718 | Riverside CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33719 | Riverside CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33726 | Riverside CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
33727 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15378SS | 0 | 414 | Warning
33728 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15377SS |  | 0 | 414 | Warning
33729 | Riverside CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33730 | Riverside CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33731 | Riverside CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33732 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15383SS | 0 | 385 | Warning
33733 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15382SS |  | 0 | 371 | Warning
33734 | Riverside CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33735 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15386SS | 0 | 343 | Warning
33736 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15385SS |  | 0 | 332 | Warning
33737 | Riverside CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33738 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15389SS | 0 | 321 | Warning
33739 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15388SS |  | 0 | 311 | Warning
33740 | Riverside CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33741 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15392SS | 0 | 299 | Warning
33742 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15391SS |  | 0 | 289 | Warning
33743 | Riverside CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33744 | Riverside CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.41 | 277 | Warning
33747 | Riverside CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15396 |  | 0.4 | 277 | Warning
33751 | Riverside CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33754 | Riverside CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 15403 |  | 0.6 | 466 | Warning
33755 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33757 | Riverside CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 15406 | 15408 | 0.2 | 405 | Warning
33758 | Riverside CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 15407 |  | 0 | 405 | Warning
33759 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33760 | Riverside CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15411 | 0.2 | 405 | Warning
33761 | Riverside CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 15410 | 15412 | 0 | 405 | Warning
33762 | Riverside CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15411 |  | 0 | 405 | Warning
33763 | Riverside CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33764 | Riverside CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15415 | 0 | 362 | Warning
33765 | Riverside CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 15414 | 15416 | 0 | 362 | Warning
33766 | Riverside CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 15415 |  | 0 | 362 | Warning
33767 | Riverside CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33768 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33769 | Riverside CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.42 | 298 | Warning
33770 | Riverside CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.91 | 357 | Warning
33771 | Riverside CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 15422SS | 0.95 | 405 | Warning
33773 | Riverside CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 15422 |  | 0.2 | 357 | Warning
33778 | Riverside CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
33780 | Riverside CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 15429 |  | 0 | 485 | Warning
33781 | Riverside CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.06 | 298 | Warning
33783 | Riverside CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 15432SS | 15434,15437,15435SF+30d | 0 | 298 | Warning
33784 | Riverside CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15433 |  | 0 | 298 | Warning
33785 | Riverside CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15433SF+30d |  | 0 | 298 | Warning
33786 | Riverside CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33787 | Riverside CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15433 |  | 0 | 345 | Warning
33788 | Riverside CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.64 | 445 | Warning
33790 | Riverside CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d | 15439SS | 15441SS | 0.8 | 485 | Warning
33791 | Riverside CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 15440SS |  | 0.2 | 445 | Warning
33796 | Riverside CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM | 51 | 508d |  |  | 0.92 | 508 | Warning
33798 | Riverside CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d | 15447 |  | 0.8 | 508 | Warning
33799 | Riverside CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
33801 | Riverside CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 15450SS | 15455,15452 | 0 | 298 | Warning
33802 | Riverside CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15451 |  | 0 | 298 | Warning
33803 | Riverside CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
33804 | Riverside CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33805 | Riverside CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15451 |  | 0 | 345 | Warning
33806 | Riverside CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33807 | Riverside CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33808 | Riverside CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33809 | Riverside CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33810 | Riverside CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33811 | Riverside CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33812 | Riverside CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33813 | Riverside CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33814 | Riverside CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33815 | Riverside CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33816 | Riverside CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33817 | Riverside CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33818 | Riverside CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33819 | Riverside CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
33820 | Riverside CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15477 | 0.2 | 256 | Warning
33821 | Riverside CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33822 | Riverside CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33823 | Riverside CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33824 | Riverside CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33825 | Riverside CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15484 | 0 | 273 | Warning
33826 | Riverside CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15485 | 0 | 273 | Warning
33827 | Riverside CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 15470 |  | 0 | 256 | Warning
33828 | Riverside CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
33829 | Riverside CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15490SF+30d | 0 | 333 | Warning
33830 | Riverside CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15491SF+30d | 0 | 333 | Warning
33831 | Riverside CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15492SF+30d | 0 | 333 | Warning
33832 | Riverside CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15493SF+30d | 0 | 333 | Warning
33833 | Riverside CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15494SF+30d | 0 | 333 | Warning
33834 | Riverside CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15475 |  | 0 | 273 | Warning
33835 | Riverside CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15476 |  | 0 | 273 | Warning
33836 | Riverside CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
33837 | Riverside CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15496FS+12d | 0 | 279 | Warning
33838 | Riverside CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33839 | Riverside CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15496SF+60d | 0 | 299 | Warning
33840 | Riverside CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15479SF+30d |  | 0 | 299 | Warning
33841 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15480SF+30d |  | 0 | 299 | Warning
33842 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15481SF+30d |  | 0 | 299 | Warning
33843 | Riverside CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15482SF+30d |  | 0 | 299 | Warning
33844 | Riverside CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15483SF+30d |  | 0 | 299 | Warning
33845 | Riverside CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
33846 | Riverside CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15487FS+12d,15489SF+60d |  | 0 | 279 | Warning
33847 | CARES V1 - Ventura CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.37 | 235 | Warning
33848 | Ventura CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.5 | 235 | Warning
33849 | Ventura CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM | 669 | 279d |  |  | 0.58 | 279 | Warning
33854 | Ventura CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33855 | Ventura CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
33856 | Ventura CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
33857 | Ventura CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | 235 | Warning
33858 | Ventura CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.38 | 235 | Warning
33859 | Ventura CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM | 713 | 235d |  |  | 0.62 | 235 | Warning
33881 | Ventura CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | 486 | Warning
33882 | Ventura CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
33883 | Ventura CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
33884 | Ventura CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
33885 | Ventura CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
33886 | Ventura CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
33887 | Ventura CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
33888 | Ventura CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
33889 | Ventura CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
33890 | Ventura CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
33891 | Ventura CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
33892 | Ventura CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
33893 | Ventura CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
33900 | Ventura CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
33901 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15552SS | 0 | 414 | Warning
33902 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15551SS |  | 0 | 414 | Warning
33903 | Ventura CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33904 | Ventura CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
33905 | Ventura CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | 342 | Warning
33906 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15557SS | 0 | 385 | Warning
33907 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15556SS |  | 0 | 371 | Warning
33908 | Ventura CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
33909 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15560SS | 0 | 343 | Warning
33910 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15559SS |  | 0 | 332 | Warning
33911 | Ventura CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
33912 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15563SS | 0 | 321 | Warning
33913 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15562SS |  | 0 | 311 | Warning
33914 | Ventura CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
33915 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15566SS | 0 | 299 | Warning
33916 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15565SS |  | 0 | 289 | Warning
33917 | Ventura CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
33918 | Ventura CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 630 | 277d |  |  | 0.4 | 277 | Warning
33921 | Ventura CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15570 |  | 0.4 | 277 | Warning
33925 | Ventura CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33928 | Ventura CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 15577 |  | 0.2 | 466 | Warning
33929 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33931 | Ventura CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 15580 | 15582 | 0.2 | 405 | Warning
33932 | Ventura CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 15581 |  | 0 | 405 | Warning
33933 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33934 | Ventura CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15585 | 0.4 | 405 | Warning
33935 | Ventura CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 15584 | 15586 | 0 | 405 | Warning
33936 | Ventura CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15585 |  | 0 | 405 | Warning
33937 | Ventura CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
33938 | Ventura CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15589 | 0 | 362 | Warning
33939 | Ventura CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 39 | 362d | 15588 | 15590 | 0 | 362 | Warning
33940 | Ventura CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d | 15589 |  | 0 | 362 | Warning
33941 | Ventura CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
33942 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
33943 | Ventura CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0.46 | 298 | Warning
33944 | Ventura CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.98 | 357 | Warning
33947 | Ventura CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 48 | 357d | 15596 |  | 0.6 | 357 | Warning
33952 | Ventura CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 485d |  |  | 0.61 | 485 | Warning
33954 | Ventura CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d | 15603 |  | 0 | 485 | Warning
33955 | Ventura CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.01 | 298 | Warning
33956 | Ventura CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d | 15603SS | 15607SS | 0.2 | 508 | Warning
33957 | Ventura CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 182 | 298d | 15606SS | 15608,15611,15609SF+30d | 0 | 298 | Warning
33958 | Ventura CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15607 |  | 0 | 298 | Warning
33959 | Ventura CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15607SF+30d |  | 0 | 298 | Warning
33960 | Ventura CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33961 | Ventura CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15607 |  | 0 | 345 | Warning
33962 | Ventura CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d |  |  | 0.92 | 445 | Warning
33965 | Ventura CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 230 | 445d | 15614SS |  | 0.8 | 445 | Warning
33973 | Ventura CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 274 | 298d |  |  | 0.09 | 298 | Warning
33975 | Ventura CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 210 | 298d | 15624SS | 15629,15626 | 0 | 298 | Warning
33976 | Ventura CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 64 | 298d | 15625 |  | 0 | 298 | Warning
33977 | Ventura CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | 298 | Warning
33978 | Ventura CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | 299 | Warning
33979 | Ventura CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15625 |  | 0 | 345 | Warning
33980 | Ventura CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 82 | 362d |  |  | 0 | 362 | Warning
33981 | Ventura CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33982 | Ventura CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33983 | Ventura CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33984 | Ventura CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33985 | Ventura CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33986 | Ventura CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33987 | Ventura CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33988 | Ventura CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33989 | Ventura CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33990 | Ventura CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33991 | Ventura CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
33992 | Ventura CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
33993 | Ventura CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM | 316 | 256d |  |  | 0.02 | 256 | Warning
33994 | Ventura CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15651 | 0.2 | 256 | Warning
33995 | Ventura CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
33996 | Ventura CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
33997 | Ventura CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33998 | Ventura CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
33999 | Ventura CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15658 | 0 | 273 | Warning
34000 | Ventura CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15659 | 0 | 273 | Warning
34001 | Ventura CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 128 | 256d | 15644 |  | 0 | 256 | Warning
34002 | Ventura CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
34003 | Ventura CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15664SF+30d | 0 | 333 | Warning
34004 | Ventura CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15665SF+30d | 0 | 333 | Warning
34005 | Ventura CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15666SF+30d | 0 | 333 | Warning
34006 | Ventura CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15667SF+30d | 0 | 333 | Warning
34007 | Ventura CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15668SF+30d | 0 | 333 | Warning
34008 | Ventura CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15649 |  | 0 | 273 | Warning
34009 | Ventura CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 15650 |  | 0 | 273 | Warning
34010 | Ventura CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
34011 | Ventura CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15670FS+12d | 0 | 279 | Warning
34012 | Ventura CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34013 | Ventura CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15670SF+60d | 0 | 299 | Warning
34014 | Ventura CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15653SF+30d |  | 0 | 299 | Warning
34015 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15654SF+30d |  | 0 | 299 | Warning
34016 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15655SF+30d |  | 0 | 299 | Warning
34017 | Ventura CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15656SF+30d |  | 0 | 299 | Warning
34018 | Ventura CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15657SF+30d |  | 0 | 299 | Warning
34019 | Ventura CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34020 | Ventura CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15661FS+12d,15663SF+60d |  | 0 | 279 | Warning
34028 | Alameda PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34029 | Alameda PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34033 | Alameda PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34034 | Alameda PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34035 | Alameda PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34036 | Alameda PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34037 | Alameda PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34038 | Alameda PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34039 | Alameda PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34040 | Alameda PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34041 | Alameda PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34042 | Alameda PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34043 | Alameda PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34044 | Alameda PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34045 | Alameda PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34054 | Alameda PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34055 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15701SS | 0 | 414 | Warning
34056 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15700SS |  | 0 | 414 | Warning
34057 | Alameda PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15703SS | 0 | 362 | Warning
34058 | Alameda PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15702SS |  | 0 | 362 | Warning
34059 | Alameda PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
34060 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15706SS | 0 | 364 | Warning
34061 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15705SS |  | 0 | 353 | Warning
34062 | Alameda PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
34063 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15709SS | 0 | 300 | Warning
34064 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 15708SS |  | 0 | 288 | Warning
34065 | Alameda PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
34066 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15712SS | 0 | 279 | Warning
34067 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15711SS |  | 0 | 268 | Warning
34068 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15714SS | 0 | 246 | Warning
34069 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15713SS |  | 0 | 246 | Warning
34070 | Alameda PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34071 | Alameda PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
34073 | Alameda PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
34074 | Alameda PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34075 | Alameda PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34076 | Alameda PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
34079 | Alameda PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
34082 | Alameda PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 15725FS-1d |  | 0.2 | 233 | Warning
34085 | Alameda PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15729 |  | 0 | 466 | Warning
34086 | Alameda PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34087 | Alameda PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 15733FS+19d | 0 | 405 | Warning
34088 | Alameda PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 15732FS+19d | 15734 | 0 | 405 | Warning
34089 | Alameda PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15733 |  | 0 | 405 | Warning
34090 | Alameda PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34091 | Alameda PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 15737 | 0 | 363 | Warning
34092 | Alameda PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 15736 | 15738FS-1d | 0 | 363 | Warning
34093 | Alameda PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 15737FS-1d |  | 0 | 363 | Warning
34094 | Alameda PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34095 | Alameda PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34096 | Alameda PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34097 | Alameda PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34098 | Alameda PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15744SS | 0 | 486 | Warning
34099 | Alameda PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15743SS |  | 0 | 424 | Warning
34100 | Alameda PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34101 | Alameda PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34102 | Alameda PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34103 | Alameda PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15749SS | 0 | 486 | Warning
34104 | Alameda PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15748SS | 15763SS | 0 | 466 | Warning
34105 | Alameda PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34106 | Alameda PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34107 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34108 | Alameda PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34109 | Alameda PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 15755SS | 0 | 345 | Warning
34110 | Alameda PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15754SS | 15756SS,15757 | 0 | 345 | Warning
34111 | Alameda PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15755SS | 15757 | 0 | 345 | Warning
34112 | Alameda PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15755,15756 |  | 0 | 345 | Warning
34113 | Alameda PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34114 | Alameda PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34115 | Alameda PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15761SS | 0 | 486 | Warning
34116 | Alameda PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15760SS |  | 0 | 424 | Warning
34117 | Alameda PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34118 | Alameda PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15749SS |  | 0 | 466 | Warning
34119 | Alameda PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34120 | Alameda PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15766SS | 0 | 486 | Warning
34121 | Alameda PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15765SS |  | 0 | 466 | Warning
34122 | Alameda PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34123 | Alameda PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 15769SS+18d | 0 | 373 | Warning
34124 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 15768SS+18d |  | 0 | 373 | Warning
34125 | Alameda PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34126 | Alameda PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 15772SS | 0 | 362 | Warning
34127 | Alameda PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 15771SS |  | 0 | 362 | Warning
34128 | Alameda PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15774 | 0 | 345 | Warning
34129 | Alameda PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15773 |  | 0 | 345 | Warning
34130 | Alameda PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34131 | Alameda PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34132 | Alameda PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 15778SS | 0 | 362 | Warning
34133 | Alameda PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15777SS | 15779SS | 0 | 362 | Warning
34134 | Alameda PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15778SS | 15780SS | 0 | 362 | Warning
34135 | Alameda PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15779SS | 15781SS | 0 | 362 | Warning
34136 | Alameda PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15780SS | 15782SS | 0 | 362 | Warning
34137 | Alameda PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15781SS | 15783SS | 0 | 362 | Warning
34138 | Alameda PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15782SS | 15784SS | 0 | 362 | Warning
34139 | Alameda PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15783SS | 15785SS | 0 | 362 | Warning
34140 | Alameda PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15784SS | 15786SS | 0 | 362 | Warning
34141 | Alameda PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15785SS | 15787SS | 0 | 362 | Warning
34142 | Alameda PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15786SS |  | 0 | 362 | Warning
34143 | Alameda PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
34144 | Alameda PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
34147 | Alameda PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 15791SS |  | 0 | 384 | Warning
34148 | Alameda PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34149 | Alameda PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15802 | 0 | 234 | Warning
34150 | Alameda PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15803 | 0 | 234 | Warning
34152 | Alameda PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34153 | Alameda PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 15799SS,15807SS+20d | 0 | 240 | Warning
34154 | Alameda PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15798SS | 15800SS,15808SS+20d | 0 | 309 | Warning
34155 | Alameda PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15799SS | 15809SS+20d | 0 | 309 | Warning
34156 | Alameda PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34157 | Alameda PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15794 | 15803SS | 0 | 234 | Warning
34158 | Alameda PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15795,15802SS |  | 0 | 234 | Warning
34159 | Alameda PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 15812FS+12d | 0 | 240 | Warning
34160 | Alameda PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15806SS | 0 | 321 | Warning
34161 | Alameda PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 15805SS |  | 0 | 321 | Warning
34162 | Alameda PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15798SS+20d |  | 0 | 240 | Warning
34163 | Alameda PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15799SS+20d |  | 0 | 240 | Warning
34164 | Alameda PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15800SS+20d |  | 0 | 240 | Warning
34165 | Alameda PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 15812SS+44d | 0 | 240 | Warning
34166 | Alameda PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34167 | Alameda PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 15804FS+12d,15810SS+44d |  | 0 | 240 | Warning
34169 | Alpine PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34170 | Alpine PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34174 | Alpine PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34175 | Alpine PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34176 | Alpine PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34177 | Alpine PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34178 | Alpine PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34179 | Alpine PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34180 | Alpine PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34181 | Alpine PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34182 | Alpine PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34183 | Alpine PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34184 | Alpine PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34185 | Alpine PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34186 | Alpine PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34195 | Alpine PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34196 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15842SS | 0 | 414 | Warning
34197 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15841SS |  | 0 | 414 | Warning
34198 | Alpine PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15844SS | 0 | 362 | Warning
34199 | Alpine PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15843SS |  | 0 | 362 | Warning
34200 | Alpine PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
34201 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15847SS | 0 | 364 | Warning
34202 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15846SS |  | 0 | 353 | Warning
34203 | Alpine PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
34204 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15850SS | 0 | 300 | Warning
34205 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 15849SS |  | 0 | 288 | Warning
34206 | Alpine PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
34207 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15853SS | 0 | 279 | Warning
34208 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15852SS |  | 0 | 268 | Warning
34209 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15855SS | 0 | 246 | Warning
34210 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15854SS |  | 0 | 246 | Warning
34211 | Alpine PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34212 | Alpine PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
34214 | Alpine PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
34215 | Alpine PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34216 | Alpine PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34217 | Alpine PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
34220 | Alpine PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.34 | 233 | Warning
34223 | Alpine PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 15866FS-1d |  | 0.6 | 233 | Warning
34226 | Alpine PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15870 |  | 0 | 466 | Warning
34227 | Alpine PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34228 | Alpine PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 15874FS+19d | 0 | 405 | Warning
34229 | Alpine PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 15873FS+19d | 15875 | 0 | 405 | Warning
34230 | Alpine PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 15874 |  | 0 | 405 | Warning
34231 | Alpine PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34232 | Alpine PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 15878 | 0 | 363 | Warning
34233 | Alpine PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 15877 | 15879FS-1d | 0 | 363 | Warning
34234 | Alpine PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 15878FS-1d |  | 0 | 363 | Warning
34235 | Alpine PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34236 | Alpine PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34237 | Alpine PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34238 | Alpine PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34239 | Alpine PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15885SS | 0 | 486 | Warning
34240 | Alpine PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15884SS |  | 0 | 424 | Warning
34241 | Alpine PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34242 | Alpine PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34243 | Alpine PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34244 | Alpine PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15890SS | 0 | 486 | Warning
34245 | Alpine PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15889SS | 15904SS | 0 | 466 | Warning
34246 | Alpine PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34247 | Alpine PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34248 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34249 | Alpine PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34250 | Alpine PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 15896SS | 0 | 345 | Warning
34251 | Alpine PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15895SS | 15897SS,15898 | 0 | 345 | Warning
34252 | Alpine PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15896SS | 15898 | 0 | 345 | Warning
34253 | Alpine PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15896,15897 |  | 0 | 345 | Warning
34254 | Alpine PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34255 | Alpine PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34256 | Alpine PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15902SS | 0 | 486 | Warning
34257 | Alpine PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15901SS |  | 0 | 424 | Warning
34258 | Alpine PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34259 | Alpine PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15890SS |  | 0 | 466 | Warning
34260 | Alpine PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34261 | Alpine PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15907SS | 0 | 486 | Warning
34262 | Alpine PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15906SS |  | 0 | 466 | Warning
34263 | Alpine PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34264 | Alpine PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 15910SS+18d | 0 | 373 | Warning
34265 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 15909SS+18d |  | 0 | 373 | Warning
34266 | Alpine PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34267 | Alpine PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 15913SS | 0 | 362 | Warning
34268 | Alpine PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 15912SS |  | 0 | 362 | Warning
34269 | Alpine PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15915 | 0 | 345 | Warning
34270 | Alpine PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15914 |  | 0 | 345 | Warning
34271 | Alpine PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34272 | Alpine PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34273 | Alpine PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 15919SS | 0 | 362 | Warning
34274 | Alpine PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15918SS | 15920SS | 0 | 362 | Warning
34275 | Alpine PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15919SS | 15921SS | 0 | 362 | Warning
34276 | Alpine PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15920SS | 15922SS | 0 | 362 | Warning
34277 | Alpine PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15921SS | 15923SS | 0 | 362 | Warning
34278 | Alpine PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15922SS | 15924SS | 0 | 362 | Warning
34279 | Alpine PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15923SS | 15925SS | 0 | 362 | Warning
34280 | Alpine PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15924SS | 15926SS | 0 | 362 | Warning
34281 | Alpine PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15925SS | 15927SS | 0 | 362 | Warning
34282 | Alpine PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15926SS | 15928SS | 0 | 362 | Warning
34283 | Alpine PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15927SS |  | 0 | 362 | Warning
34284 | Alpine PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
34285 | Alpine PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
34288 | Alpine PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 15932SS |  | 0 | 384 | Warning
34289 | Alpine PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34290 | Alpine PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15943 | 0 | 234 | Warning
34291 | Alpine PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15944 | 0 | 234 | Warning
34293 | Alpine PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34294 | Alpine PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 15940SS,15948SS+20d | 0 | 240 | Warning
34295 | Alpine PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15939SS | 15941SS,15949SS+20d | 0 | 309 | Warning
34296 | Alpine PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15940SS | 15950SS+20d | 0 | 309 | Warning
34297 | Alpine PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34298 | Alpine PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15935 | 15944SS | 0 | 234 | Warning
34299 | Alpine PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15936,15943SS |  | 0 | 234 | Warning
34300 | Alpine PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 15953FS+12d | 0 | 240 | Warning
34301 | Alpine PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15947SS | 0 | 321 | Warning
34302 | Alpine PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 15946SS |  | 0 | 321 | Warning
34303 | Alpine PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15939SS+20d |  | 0 | 240 | Warning
34304 | Alpine PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15940SS+20d |  | 0 | 240 | Warning
34305 | Alpine PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 15941SS+20d |  | 0 | 240 | Warning
34306 | Alpine PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 15953SS+44d | 0 | 240 | Warning
34307 | Alpine PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34308 | Alpine PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 15945FS+12d,15951SS+44d |  | 0 | 240 | Warning
34310 | Amador PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34311 | Amador PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34315 | Amador PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34316 | Amador PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34317 | Amador PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34318 | Amador PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34319 | Amador PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34320 | Amador PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34321 | Amador PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34322 | Amador PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34323 | Amador PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34324 | Amador PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34325 | Amador PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34326 | Amador PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34327 | Amador PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34336 | Amador PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34337 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15983SS | 0 | 414 | Warning
34338 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15982SS |  | 0 | 414 | Warning
34339 | Amador PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15985SS | 0 | 362 | Warning
34340 | Amador PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15984SS |  | 0 | 362 | Warning
34341 | Amador PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
34342 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15988SS | 0 | 364 | Warning
34343 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15987SS |  | 0 | 353 | Warning
34344 | Amador PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
34345 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15991SS | 0 | 300 | Warning
34346 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 15990SS |  | 0 | 288 | Warning
34347 | Amador PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
34348 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15994SS | 0 | 279 | Warning
34349 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15993SS |  | 0 | 268 | Warning
34350 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15996SS | 0 | 246 | Warning
34351 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15995SS |  | 0 | 246 | Warning
34352 | Amador PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34353 | Amador PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
34355 | Amador PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
34356 | Amador PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34357 | Amador PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34358 | Amador PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
34361 | Amador PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.34 | 233 | Warning
34364 | Amador PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16007FS-1d |  | 0.6 | 233 | Warning
34367 | Amador PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16011 |  | 0 | 466 | Warning
34368 | Amador PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34369 | Amador PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16015FS+19d | 0 | 405 | Warning
34370 | Amador PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16014FS+19d | 16016 | 0 | 405 | Warning
34371 | Amador PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16015 |  | 0 | 405 | Warning
34372 | Amador PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34373 | Amador PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16019 | 0 | 363 | Warning
34374 | Amador PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16018 | 16020FS-1d | 0 | 363 | Warning
34375 | Amador PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16019FS-1d |  | 0 | 363 | Warning
34376 | Amador PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34377 | Amador PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34378 | Amador PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34379 | Amador PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34380 | Amador PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16026SS | 0 | 486 | Warning
34381 | Amador PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16025SS |  | 0 | 424 | Warning
34382 | Amador PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34383 | Amador PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34384 | Amador PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34385 | Amador PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16031SS | 0 | 486 | Warning
34386 | Amador PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16030SS | 16045SS | 0 | 466 | Warning
34387 | Amador PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34388 | Amador PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34389 | Amador PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34390 | Amador PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34391 | Amador PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16037SS | 0 | 345 | Warning
34392 | Amador PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16036SS | 16038SS,16039 | 0 | 345 | Warning
34393 | Amador PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16037SS | 16039 | 0 | 345 | Warning
34394 | Amador PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16037,16038 |  | 0 | 345 | Warning
34395 | Amador PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34396 | Amador PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34397 | Amador PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16043SS | 0 | 486 | Warning
34398 | Amador PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16042SS |  | 0 | 424 | Warning
34399 | Amador PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34400 | Amador PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16031SS |  | 0 | 466 | Warning
34401 | Amador PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34402 | Amador PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16048SS | 0 | 486 | Warning
34403 | Amador PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16047SS |  | 0 | 466 | Warning
34404 | Amador PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34405 | Amador PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16051SS+18d | 0 | 373 | Warning
34406 | Amador PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16050SS+18d |  | 0 | 373 | Warning
34407 | Amador PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34408 | Amador PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16054SS | 0 | 362 | Warning
34409 | Amador PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16053SS |  | 0 | 362 | Warning
34410 | Amador PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16056 | 0 | 345 | Warning
34411 | Amador PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16055 |  | 0 | 345 | Warning
34412 | Amador PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34413 | Amador PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34414 | Amador PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16060SS | 0 | 362 | Warning
34415 | Amador PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16059SS | 16061SS | 0 | 362 | Warning
34416 | Amador PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16060SS | 16062SS | 0 | 362 | Warning
34417 | Amador PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16061SS | 16063SS | 0 | 362 | Warning
34418 | Amador PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16062SS | 16064SS | 0 | 362 | Warning
34419 | Amador PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16063SS | 16065SS | 0 | 362 | Warning
34420 | Amador PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16064SS | 16066SS | 0 | 362 | Warning
34421 | Amador PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16065SS | 16067SS | 0 | 362 | Warning
34422 | Amador PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16066SS | 16068SS | 0 | 362 | Warning
34423 | Amador PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16067SS | 16069SS | 0 | 362 | Warning
34424 | Amador PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16068SS |  | 0 | 362 | Warning
34425 | Amador PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
34426 | Amador PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
34429 | Amador PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16073SS |  | 0 | 384 | Warning
34430 | Amador PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34431 | Amador PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16084 | 0 | 234 | Warning
34432 | Amador PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16085 | 0 | 234 | Warning
34434 | Amador PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34435 | Amador PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16081SS,16089SS+20d | 0 | 240 | Warning
34436 | Amador PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16080SS | 16082SS,16090SS+20d | 0 | 309 | Warning
34437 | Amador PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16081SS | 16091SS+20d | 0 | 309 | Warning
34438 | Amador PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34439 | Amador PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16076 | 16085SS | 0 | 234 | Warning
34440 | Amador PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16077,16084SS |  | 0 | 234 | Warning
34441 | Amador PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16094FS+12d | 0 | 240 | Warning
34442 | Amador PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16088SS | 0 | 321 | Warning
34443 | Amador PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16087SS |  | 0 | 321 | Warning
34444 | Amador PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16080SS+20d |  | 0 | 240 | Warning
34445 | Amador PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16081SS+20d |  | 0 | 240 | Warning
34446 | Amador PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16082SS+20d |  | 0 | 240 | Warning
34447 | Amador PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16094SS+44d | 0 | 240 | Warning
34448 | Amador PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34449 | Amador PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 16086FS+12d,16092SS+44d |  | 0 | 240 | Warning
34451 | Butte PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34452 | Butte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34456 | Butte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34457 | Butte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34458 | Butte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34459 | Butte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34460 | Butte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34461 | Butte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34462 | Butte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34463 | Butte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34464 | Butte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34465 | Butte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34466 | Butte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34467 | Butte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34468 | Butte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34477 | Butte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34478 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16124SS | 0 | 414 | Warning
34479 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16123SS |  | 0 | 414 | Warning
34480 | Butte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16126SS | 0 | 362 | Warning
34481 | Butte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16125SS |  | 0 | 362 | Warning
34482 | Butte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16129SS,16128SS | 0 | 342 | Warning
34483 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 16127SS |  | 0 | 385 | Warning
34484 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 16127SS |  | 0 | 371 | Warning
34485 | Butte PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
34486 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16132SS | 0 | 332 | Warning
34487 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 16131SS |  | 0 | 332 | Warning
34488 | Butte PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
34489 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16135SS | 0 | 311 | Warning
34490 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16134SS |  | 0 | 311 | Warning
34491 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16137SS | 0 | 289 | Warning
34492 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 16136SS |  | 0 | 289 | Warning
34493 | Butte PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
34494 | Butte PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
34495 | Butte PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
34496 | Butte PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
34497 | Butte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34498 | Butte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34499 | Butte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
34500 | Butte PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
34501 | Butte PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.2 | 277 | Warning
34504 | Butte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16147FS-1d |  | 0.2 | 277 | Warning
34507 | Butte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16151 |  | 0 | 466 | Warning
34508 | Butte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34509 | Butte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16155FS+19d | 0 | 405 | Warning
34510 | Butte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16154FS+19d | 16156 | 0 | 405 | Warning
34511 | Butte PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16155 |  | 0 | 405 | Warning
34512 | Butte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34513 | Butte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16159 | 0 | 363 | Warning
34514 | Butte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16158 | 16160FS-1d | 0 | 363 | Warning
34515 | Butte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16159FS-1d |  | 0 | 363 | Warning
34516 | Butte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34517 | Butte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34518 | Butte PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34519 | Butte PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34520 | Butte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16166SS | 0 | 486 | Warning
34521 | Butte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16165SS |  | 0 | 424 | Warning
34522 | Butte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34523 | Butte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34524 | Butte PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34525 | Butte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16171SS | 0 | 486 | Warning
34526 | Butte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16170SS | 16185SS | 0 | 466 | Warning
34527 | Butte PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34528 | Butte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34529 | Butte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34530 | Butte PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34531 | Butte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16177SS | 0 | 345 | Warning
34532 | Butte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16176SS | 16178SS,16179 | 0 | 345 | Warning
34533 | Butte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16177SS | 16179 | 0 | 345 | Warning
34534 | Butte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16177,16178 |  | 0 | 345 | Warning
34535 | Butte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34536 | Butte PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34537 | Butte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16183SS | 0 | 486 | Warning
34538 | Butte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16182SS |  | 0 | 424 | Warning
34539 | Butte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34540 | Butte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16171SS |  | 0 | 466 | Warning
34541 | Butte PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34542 | Butte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16188SS | 0 | 486 | Warning
34543 | Butte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16187SS |  | 0 | 466 | Warning
34544 | Butte PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34545 | Butte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16191SS+18d | 0 | 373 | Warning
34546 | Butte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16190SS+18d |  | 0 | 373 | Warning
34547 | Butte PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34548 | Butte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16194SS | 0 | 362 | Warning
34549 | Butte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16193SS |  | 0 | 362 | Warning
34550 | Butte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16196 | 0 | 345 | Warning
34551 | Butte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16195 |  | 0 | 345 | Warning
34552 | Butte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34553 | Butte PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34554 | Butte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16200SS | 0 | 362 | Warning
34555 | Butte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16199SS | 16201SS | 0 | 362 | Warning
34556 | Butte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16200SS | 16202SS | 0 | 362 | Warning
34557 | Butte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16201SS | 16203SS | 0 | 362 | Warning
34558 | Butte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16202SS | 16204SS | 0 | 362 | Warning
34559 | Butte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16203SS | 16205SS | 0 | 362 | Warning
34560 | Butte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16204SS | 16206SS | 0 | 362 | Warning
34561 | Butte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16205SS | 16207SS | 0 | 362 | Warning
34562 | Butte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16206SS | 16208SS | 0 | 362 | Warning
34563 | Butte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16207SS | 16209SS | 0 | 362 | Warning
34564 | Butte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16208SS |  | 0 | 362 | Warning
34565 | Butte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
34566 | Butte PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
34569 | Butte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16213SS |  | 0 | 384 | Warning
34570 | Butte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34571 | Butte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16224 | 0 | 273 | Warning
34572 | Butte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16225 | 0 | 273 | Warning
34574 | Butte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34575 | Butte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 16221SS,16229SS+20d | 0 | 299 | Warning
34576 | Butte PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 16220SS | 16222SS,16230SS+20d | 0 | 299 | Warning
34577 | Butte PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 16221SS | 16231SS+20d | 0 | 299 | Warning
34578 | Butte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34579 | Butte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16216 | 16225SS | 0 | 273 | Warning
34580 | Butte PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16217,16224SS |  | 0 | 273 | Warning
34581 | Butte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 16234FS+12d | 0 | 279 | Warning
34582 | Butte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16228SS | 0 | 321 | Warning
34583 | Butte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16227SS |  | 0 | 321 | Warning
34584 | Butte PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16220SS+20d |  | 0 | 299 | Warning
34585 | Butte PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16221SS+20d |  | 0 | 299 | Warning
34586 | Butte PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16222SS+20d |  | 0 | 299 | Warning
34587 | Butte PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 16234SS+44d | 0 | 279 | Warning
34588 | Butte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34589 | Butte PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 16226FS+12d,16232SS+44d |  | 0 | 279 | Warning
34591 | Calaveras PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34592 | Calaveras PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34596 | Calaveras PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34597 | Calaveras PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34598 | Calaveras PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34599 | Calaveras PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34600 | Calaveras PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34601 | Calaveras PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34602 | Calaveras PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34603 | Calaveras PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34604 | Calaveras PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34605 | Calaveras PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34606 | Calaveras PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34607 | Calaveras PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34608 | Calaveras PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34617 | Calaveras PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34618 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16264SS | 0 | 414 | Warning
34619 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16263SS |  | 0 | 414 | Warning
34620 | Calaveras PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16266SS | 0 | 362 | Warning
34621 | Calaveras PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16265SS |  | 0 | 362 | Warning
34622 | Calaveras PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16269SS,16268SS | 0 | 342 | Warning
34623 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 16267SS |  | 0 | 385 | Warning
34624 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 16267SS |  | 0 | 371 | Warning
34625 | Calaveras PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
34626 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16272SS | 0 | 332 | Warning
34627 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 16271SS |  | 0 | 332 | Warning
34628 | Calaveras PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
34629 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16275SS | 0 | 311 | Warning
34630 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16274SS |  | 0 | 311 | Warning
34631 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16277SS | 0 | 289 | Warning
34632 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 16276SS |  | 0 | 289 | Warning
34633 | Calaveras PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
34634 | Calaveras PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
34635 | Calaveras PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
34636 | Calaveras PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
34637 | Calaveras PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34638 | Calaveras PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34639 | Calaveras PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
34640 | Calaveras PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
34641 | Calaveras PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.26 | 277 | Warning
34644 | Calaveras PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16287FS-1d |  | 0.4 | 277 | Warning
34647 | Calaveras PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16291 |  | 0 | 466 | Warning
34648 | Calaveras PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34649 | Calaveras PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16295FS+19d | 0 | 405 | Warning
34650 | Calaveras PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16294FS+19d | 16296 | 0 | 405 | Warning
34651 | Calaveras PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16295 |  | 0 | 405 | Warning
34652 | Calaveras PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34653 | Calaveras PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16299 | 0 | 363 | Warning
34654 | Calaveras PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16298 | 16300FS-1d | 0 | 363 | Warning
34655 | Calaveras PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16299FS-1d |  | 0 | 363 | Warning
34656 | Calaveras PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34657 | Calaveras PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34658 | Calaveras PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34659 | Calaveras PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34660 | Calaveras PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16306SS | 0 | 486 | Warning
34661 | Calaveras PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16305SS |  | 0 | 424 | Warning
34662 | Calaveras PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34663 | Calaveras PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34664 | Calaveras PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34665 | Calaveras PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16311SS | 0 | 486 | Warning
34666 | Calaveras PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16310SS | 16325SS | 0 | 466 | Warning
34667 | Calaveras PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34668 | Calaveras PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34669 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34670 | Calaveras PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34671 | Calaveras PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16317SS | 0 | 345 | Warning
34672 | Calaveras PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16316SS | 16318SS,16319 | 0 | 345 | Warning
34673 | Calaveras PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16317SS | 16319 | 0 | 345 | Warning
34674 | Calaveras PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16317,16318 |  | 0 | 345 | Warning
34675 | Calaveras PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34676 | Calaveras PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34677 | Calaveras PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16323SS | 0 | 486 | Warning
34678 | Calaveras PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16322SS |  | 0 | 424 | Warning
34679 | Calaveras PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34680 | Calaveras PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16311SS |  | 0 | 466 | Warning
34681 | Calaveras PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34682 | Calaveras PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16328SS | 0 | 486 | Warning
34683 | Calaveras PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16327SS |  | 0 | 466 | Warning
34684 | Calaveras PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34685 | Calaveras PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16331SS+18d | 0 | 373 | Warning
34686 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16330SS+18d |  | 0 | 373 | Warning
34687 | Calaveras PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34688 | Calaveras PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16334SS | 0 | 362 | Warning
34689 | Calaveras PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16333SS |  | 0 | 362 | Warning
34690 | Calaveras PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16336 | 0 | 345 | Warning
34691 | Calaveras PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16335 |  | 0 | 345 | Warning
34692 | Calaveras PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34693 | Calaveras PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34694 | Calaveras PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16340SS | 0 | 362 | Warning
34695 | Calaveras PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16339SS | 16341SS | 0 | 362 | Warning
34696 | Calaveras PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16340SS | 16342SS | 0 | 362 | Warning
34697 | Calaveras PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16341SS | 16343SS | 0 | 362 | Warning
34698 | Calaveras PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16342SS | 16344SS | 0 | 362 | Warning
34699 | Calaveras PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16343SS | 16345SS | 0 | 362 | Warning
34700 | Calaveras PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16344SS | 16346SS | 0 | 362 | Warning
34701 | Calaveras PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16345SS | 16347SS | 0 | 362 | Warning
34702 | Calaveras PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16346SS | 16348SS | 0 | 362 | Warning
34703 | Calaveras PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16347SS | 16349SS | 0 | 362 | Warning
34704 | Calaveras PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16348SS |  | 0 | 362 | Warning
34705 | Calaveras PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
34706 | Calaveras PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
34709 | Calaveras PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16353SS |  | 0 | 384 | Warning
34710 | Calaveras PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34711 | Calaveras PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16364 | 0 | 273 | Warning
34712 | Calaveras PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16365 | 0 | 273 | Warning
34714 | Calaveras PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34715 | Calaveras PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 16361SS,16369SS+20d | 0 | 299 | Warning
34716 | Calaveras PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 16360SS | 16362SS,16370SS+20d | 0 | 299 | Warning
34717 | Calaveras PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 16361SS | 16371SS+20d | 0 | 299 | Warning
34718 | Calaveras PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34719 | Calaveras PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16356 | 16365SS | 0 | 273 | Warning
34720 | Calaveras PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16357,16364SS |  | 0 | 273 | Warning
34721 | Calaveras PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 16374FS+12d | 0 | 279 | Warning
34722 | Calaveras PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16368SS | 0 | 321 | Warning
34723 | Calaveras PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16367SS |  | 0 | 321 | Warning
34724 | Calaveras PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16360SS+20d |  | 0 | 299 | Warning
34725 | Calaveras PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16361SS+20d |  | 0 | 299 | Warning
34726 | Calaveras PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16362SS+20d |  | 0 | 299 | Warning
34727 | Calaveras PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 16374SS+44d | 0 | 279 | Warning
34728 | Calaveras PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34729 | Calaveras PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 16366FS+12d,16372SS+44d |  | 0 | 279 | Warning
34731 | Colusa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34732 | Colusa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34736 | Colusa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34737 | Colusa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34738 | Colusa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34739 | Colusa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34740 | Colusa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34741 | Colusa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34742 | Colusa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34743 | Colusa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34744 | Colusa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34745 | Colusa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34746 | Colusa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34747 | Colusa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34748 | Colusa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34757 | Colusa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
34758 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16404SS | 0 | 414 | Warning
34759 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16403SS |  | 0 | 414 | Warning
34760 | Colusa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16406SS | 0 | 362 | Warning
34761 | Colusa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16405SS |  | 0 | 362 | Warning
34762 | Colusa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
34763 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16409SS | 0 | 364 | Warning
34764 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16408SS |  | 0 | 353 | Warning
34765 | Colusa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
34766 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16412SS | 0 | 300 | Warning
34767 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 16411SS |  | 0 | 288 | Warning
34768 | Colusa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
34769 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16415SS | 0 | 279 | Warning
34770 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16414SS |  | 0 | 268 | Warning
34771 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16417SS | 0 | 246 | Warning
34772 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16416SS |  | 0 | 246 | Warning
34773 | Colusa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34774 | Colusa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
34776 | Colusa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
34777 | Colusa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34778 | Colusa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34779 | Colusa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
34782 | Colusa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
34785 | Colusa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16428FS-1d |  | 0.2 | 233 | Warning
34788 | Colusa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16432 |  | 0 | 466 | Warning
34789 | Colusa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34790 | Colusa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16436FS+19d | 0 | 405 | Warning
34791 | Colusa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16435FS+19d | 16437 | 0 | 405 | Warning
34792 | Colusa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16436 |  | 0 | 405 | Warning
34793 | Colusa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34794 | Colusa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16440 | 0 | 363 | Warning
34795 | Colusa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16439 | 16441FS-1d | 0 | 363 | Warning
34796 | Colusa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16440FS-1d |  | 0 | 363 | Warning
34797 | Colusa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34798 | Colusa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34799 | Colusa PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
34800 | Colusa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34801 | Colusa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16447SS | 0 | 362 | Warning
34802 | Colusa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16446SS | 16448SS | 0 | 362 | Warning
34803 | Colusa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16447SS | 16449SS | 0 | 362 | Warning
34804 | Colusa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16448SS | 16450SS | 0 | 362 | Warning
34805 | Colusa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16449SS | 16451SS | 0 | 362 | Warning
34806 | Colusa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16450SS | 16452SS | 0 | 362 | Warning
34807 | Colusa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16451SS | 16453SS | 0 | 362 | Warning
34808 | Colusa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16452SS | 16454SS | 0 | 362 | Warning
34809 | Colusa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16453SS | 16455SS | 0 | 362 | Warning
34810 | Colusa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16454SS | 16456SS | 0 | 362 | Warning
34811 | Colusa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16455SS |  | 0 | 362 | Warning
34812 | Colusa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
34813 | Colusa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
34816 | Colusa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16460SS |  | 0 | 384 | Warning
34817 | Colusa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34818 | Colusa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16471 | 0 | 234 | Warning
34819 | Colusa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16472 | 0 | 234 | Warning
34821 | Colusa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34822 | Colusa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16468SS,16476SS+20d | 0 | 240 | Warning
34823 | Colusa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16467SS | 16469SS,16477SS+20d | 0 | 309 | Warning
34824 | Colusa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16468SS | 16478SS+20d | 0 | 309 | Warning
34825 | Colusa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34826 | Colusa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16463 | 16472SS | 0 | 234 | Warning
34827 | Colusa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16464,16471SS |  | 0 | 234 | Warning
34828 | Colusa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16481FS+12d | 0 | 240 | Warning
34829 | Colusa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16475SS | 0 | 321 | Warning
34830 | Colusa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16474SS |  | 0 | 321 | Warning
34831 | Colusa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16467SS+20d |  | 0 | 240 | Warning
34832 | Colusa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16468SS+20d |  | 0 | 240 | Warning
34833 | Colusa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16469SS+20d |  | 0 | 240 | Warning
34834 | Colusa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16481SS+44d | 0 | 240 | Warning
34835 | Colusa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34836 | Colusa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 16473FS+12d,16479SS+44d |  | 0 | 240 | Warning
34838 | Contra Costa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.21 | 235 | Warning
34839 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34843 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34844 | Contra Costa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34845 | Contra Costa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34846 | Contra Costa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34847 | Contra Costa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34848 | Contra Costa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34849 | Contra Costa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34850 | Contra Costa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34851 | Contra Costa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34852 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34853 | Contra Costa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34854 | Contra Costa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34855 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
34864 | Contra Costa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
34865 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16511SS | 0 | 414 | Warning
34866 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16510SS |  | 0 | 414 | Warning
34867 | Contra Costa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16513SS | 0 | 362 | Warning
34868 | Contra Costa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16512SS |  | 0 | 362 | Warning
34869 | Contra Costa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
34870 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16516SS | 0 | 364 | Warning
34871 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16515SS |  | 0 | 353 | Warning
34872 | Contra Costa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
34873 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16519SS | 0 | 300 | Warning
34874 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 16518SS |  | 0 | 288 | Warning
34875 | Contra Costa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
34876 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16522SS | 0 | 279 | Warning
34877 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16521SS |  | 0 | 268 | Warning
34878 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16524SS | 0 | 246 | Warning
34879 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16523SS |  | 0 | 246 | Warning
34880 | Contra Costa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34881 | Contra Costa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
34883 | Contra Costa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
34884 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
34885 | Contra Costa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
34886 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
34889 | Contra Costa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.27 | 233 | Warning
34892 | Contra Costa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16535FS-1d |  | 0.2 | 233 | Warning
34895 | Contra Costa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16539 |  | 0 | 466 | Warning
34896 | Contra Costa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
34897 | Contra Costa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applica | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16543FS+19d | 0 | 405 | Warning
34898 | Contra Costa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16542FS+19d | 16544 | 0 | 405 | Warning
34899 | Contra Costa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16543 |  | 0 | 405 | Warning
34900 | Contra Costa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
34901 | Contra Costa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16547 | 0 | 363 | Warning
34902 | Contra Costa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16546 | 16548FS-1d | 0 | 363 | Warning
34903 | Contra Costa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16547FS-1d |  | 0 | 363 | Warning
34904 | Contra Costa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
34905 | Contra Costa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
34906 | Contra Costa PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
34907 | Contra Costa PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34908 | Contra Costa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16554SS | 0 | 486 | Warning
34909 | Contra Costa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16553SS |  | 0 | 424 | Warning
34910 | Contra Costa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34911 | Contra Costa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34912 | Contra Costa PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34913 | Contra Costa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16559SS | 0 | 486 | Warning
34914 | Contra Costa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16558SS | 16573SS | 0 | 466 | Warning
34915 | Contra Costa PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34916 | Contra Costa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
34917 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
34918 | Contra Costa PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34919 | Contra Costa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16565SS | 0 | 345 | Warning
34920 | Contra Costa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16564SS | 16566SS,16567 | 0 | 345 | Warning
34921 | Contra Costa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16565SS | 16567 | 0 | 345 | Warning
34922 | Contra Costa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16565,16566 |  | 0 | 345 | Warning
34923 | Contra Costa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34924 | Contra Costa PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
34925 | Contra Costa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16571SS | 0 | 486 | Warning
34926 | Contra Costa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16570SS |  | 0 | 424 | Warning
34927 | Contra Costa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
34928 | Contra Costa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16559SS |  | 0 | 466 | Warning
34929 | Contra Costa PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
34930 | Contra Costa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16576SS | 0 | 486 | Warning
34931 | Contra Costa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16575SS |  | 0 | 466 | Warning
34932 | Contra Costa PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
34933 | Contra Costa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16579SS+18d | 0 | 373 | Warning
34934 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16578SS+18d |  | 0 | 373 | Warning
34935 | Contra Costa PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
34936 | Contra Costa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16582SS | 0 | 362 | Warning
34937 | Contra Costa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16581SS |  | 0 | 362 | Warning
34938 | Contra Costa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16584 | 0 | 345 | Warning
34939 | Contra Costa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16583 |  | 0 | 345 | Warning
34940 | Contra Costa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
34941 | Contra Costa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
34942 | Contra Costa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16588SS | 0 | 362 | Warning
34943 | Contra Costa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16587SS | 16589SS | 0 | 362 | Warning
34944 | Contra Costa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16588SS | 16590SS | 0 | 362 | Warning
34945 | Contra Costa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16589SS | 16591SS | 0 | 362 | Warning
34946 | Contra Costa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16590SS | 16592SS | 0 | 362 | Warning
34947 | Contra Costa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16591SS | 16593SS | 0 | 362 | Warning
34948 | Contra Costa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16592SS | 16594SS | 0 | 362 | Warning
34949 | Contra Costa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16593SS | 16595SS | 0 | 362 | Warning
34950 | Contra Costa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16594SS | 16596SS | 0 | 362 | Warning
34951 | Contra Costa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16595SS | 16597SS | 0 | 362 | Warning
34952 | Contra Costa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16596SS |  | 0 | 362 | Warning
34953 | Contra Costa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
34954 | Contra Costa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
34957 | Contra Costa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16601SS |  | 0 | 384 | Warning
34958 | Contra Costa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
34959 | Contra Costa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16612 | 0 | 234 | Warning
34960 | Contra Costa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16613 | 0 | 234 | Warning
34962 | Contra Costa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
34963 | Contra Costa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16609SS,16617SS+20d | 0 | 240 | Warning
34964 | Contra Costa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16608SS | 16610SS,16618SS+20d | 0 | 309 | Warning
34965 | Contra Costa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16609SS | 16619SS+20d | 0 | 309 | Warning
34966 | Contra Costa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
34967 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16604 | 16613SS | 0 | 234 | Warning
34968 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16605,16612SS |  | 0 | 234 | Warning
34969 | Contra Costa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16622FS+12d | 0 | 240 | Warning
34970 | Contra Costa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16616SS | 0 | 321 | Warning
34971 | Contra Costa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16615SS |  | 0 | 321 | Warning
34972 | Contra Costa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16608SS+20d |  | 0 | 240 | Warning
34973 | Contra Costa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16609SS+20d |  | 0 | 240 | Warning
34974 | Contra Costa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16610SS+20d |  | 0 | 240 | Warning
34975 | Contra Costa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16622SS+44d | 0 | 240 | Warning
34976 | Contra Costa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
34977 | Contra Costa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 16614FS+12d,16620SS+44d |  | 0 | 240 | Warning
34979 | Del Norte PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
34980 | Del Norte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
34984 | Del Norte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
34985 | Del Norte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | 467 | Warning
34986 | Del Norte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
34987 | Del Norte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
34988 | Del Norte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
34989 | Del Norte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
34990 | Del Norte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
34991 | Del Norte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
34992 | Del Norte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
34993 | Del Norte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
34994 | Del Norte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
34995 | Del Norte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
34996 | Del Norte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35005 | Del Norte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35006 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16652SS | 0 | 414 | Warning
35007 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16651SS |  | 0 | 414 | Warning
35008 | Del Norte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16654SS | 0 | 362 | Warning
35009 | Del Norte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16653SS |  | 0 | 362 | Warning
35010 | Del Norte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35011 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16657SS | 0 | 364 | Warning
35012 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16656SS |  | 0 | 353 | Warning
35013 | Del Norte PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35014 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16660SS | 0 | 300 | Warning
35015 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 16659SS |  | 0 | 288 | Warning
35016 | Del Norte PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35017 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16663SS | 0 | 279 | Warning
35018 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16662SS |  | 0 | 268 | Warning
35019 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16665SS | 0 | 246 | Warning
35020 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16664SS |  | 0 | 246 | Warning
35021 | Del Norte PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35022 | Del Norte PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35024 | Del Norte PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35025 | Del Norte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35026 | Del Norte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35027 | Del Norte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35030 | Del Norte PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
35033 | Del Norte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16676FS-1d |  | 0.2 | 233 | Warning
35036 | Del Norte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16680 |  | 0 | 466 | Warning
35037 | Del Norte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35038 | Del Norte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16684FS+19d | 0 | 405 | Warning
35039 | Del Norte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16683FS+19d | 16685 | 0 | 405 | Warning
35040 | Del Norte PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16684 |  | 0 | 405 | Warning
35041 | Del Norte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35042 | Del Norte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16688 | 0 | 363 | Warning
35043 | Del Norte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16687 | 16689FS-1d | 0 | 363 | Warning
35044 | Del Norte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16688FS-1d |  | 0 | 363 | Warning
35045 | Del Norte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35046 | Del Norte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35047 | Del Norte PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35048 | Del Norte PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35049 | Del Norte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16695SS | 0 | 486 | Warning
35050 | Del Norte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16694SS |  | 0 | 424 | Warning
35051 | Del Norte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35052 | Del Norte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35053 | Del Norte PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35054 | Del Norte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16700SS | 0 | 486 | Warning
35055 | Del Norte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16699SS | 16714SS | 0 | 466 | Warning
35056 | Del Norte PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35057 | Del Norte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35058 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35059 | Del Norte PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35060 | Del Norte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16706SS | 0 | 345 | Warning
35061 | Del Norte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16705SS | 16707SS,16708 | 0 | 345 | Warning
35062 | Del Norte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16706SS | 16708 | 0 | 345 | Warning
35063 | Del Norte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16706,16707 |  | 0 | 345 | Warning
35064 | Del Norte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35065 | Del Norte PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35066 | Del Norte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16712SS | 0 | 486 | Warning
35067 | Del Norte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16711SS |  | 0 | 424 | Warning
35068 | Del Norte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35069 | Del Norte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16700SS |  | 0 | 466 | Warning
35070 | Del Norte PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35071 | Del Norte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16717SS | 0 | 486 | Warning
35072 | Del Norte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16716SS |  | 0 | 466 | Warning
35073 | Del Norte PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35074 | Del Norte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16720SS+18d | 0 | 373 | Warning
35075 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16719SS+18d |  | 0 | 373 | Warning
35076 | Del Norte PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35077 | Del Norte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16723SS | 0 | 362 | Warning
35078 | Del Norte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16722SS |  | 0 | 362 | Warning
35079 | Del Norte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16725 | 0 | 345 | Warning
35080 | Del Norte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16724 |  | 0 | 345 | Warning
35081 | Del Norte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35082 | Del Norte PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35083 | Del Norte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16729SS | 0 | 362 | Warning
35084 | Del Norte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16728SS | 16730SS | 0 | 362 | Warning
35085 | Del Norte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16729SS | 16731SS | 0 | 362 | Warning
35086 | Del Norte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16730SS | 16732SS | 0 | 362 | Warning
35087 | Del Norte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16731SS | 16733SS | 0 | 362 | Warning
35088 | Del Norte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16732SS | 16734SS | 0 | 362 | Warning
35089 | Del Norte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16733SS | 16735SS | 0 | 362 | Warning
35090 | Del Norte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16734SS | 16736SS | 0 | 362 | Warning
35091 | Del Norte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16735SS | 16737SS | 0 | 362 | Warning
35092 | Del Norte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16736SS | 16738SS | 0 | 362 | Warning
35093 | Del Norte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16737SS |  | 0 | 362 | Warning
35094 | Del Norte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35095 | Del Norte PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35098 | Del Norte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16742SS |  | 0 | 384 | Warning
35099 | Del Norte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35100 | Del Norte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16753 | 0 | 234 | Warning
35101 | Del Norte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16754 | 0 | 234 | Warning
35103 | Del Norte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35104 | Del Norte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16750SS,16758SS+20d | 0 | 240 | Warning
35105 | Del Norte PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16749SS | 16751SS,16759SS+20d | 0 | 309 | Warning
35106 | Del Norte PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16750SS | 16760SS+20d | 0 | 309 | Warning
35107 | Del Norte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35108 | Del Norte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16745 | 16754SS | 0 | 234 | Warning
35109 | Del Norte PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16746,16753SS |  | 0 | 234 | Warning
35110 | Del Norte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16763FS+12d | 0 | 240 | Warning
35111 | Del Norte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16757SS | 0 | 321 | Warning
35112 | Del Norte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16756SS |  | 0 | 321 | Warning
35113 | Del Norte PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16749SS+20d |  | 0 | 240 | Warning
35114 | Del Norte PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16750SS+20d |  | 0 | 240 | Warning
35115 | Del Norte PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16751SS+20d |  | 0 | 240 | Warning
35116 | Del Norte PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16763SS+44d | 0 | 240 | Warning
35117 | Del Norte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35118 | Del Norte PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 16755FS+12d,16761SS+44d |  | 0 | 240 | Warning
35120 | El Dorado PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35121 | El Dorado PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35125 | El Dorado PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35126 | El Dorado PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35127 | El Dorado PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35128 | El Dorado PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35129 | El Dorado PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35130 | El Dorado PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35131 | El Dorado PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35132 | El Dorado PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35133 | El Dorado PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35134 | El Dorado PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35135 | El Dorado PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35136 | El Dorado PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35137 | El Dorado PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35146 | El Dorado PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35147 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16793SS | 0 | 414 | Warning
35148 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16792SS |  | 0 | 414 | Warning
35149 | El Dorado PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16795SS | 0 | 362 | Warning
35150 | El Dorado PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16794SS |  | 0 | 362 | Warning
35151 | El Dorado PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35152 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16798SS | 0 | 364 | Warning
35153 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16797SS |  | 0 | 353 | Warning
35154 | El Dorado PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35155 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16801SS | 0 | 300 | Warning
35156 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 16800SS |  | 0 | 288 | Warning
35157 | El Dorado PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35158 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16804SS | 0 | 279 | Warning
35159 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16803SS |  | 0 | 268 | Warning
35160 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16806SS | 0 | 246 | Warning
35161 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16805SS |  | 0 | 246 | Warning
35162 | El Dorado PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35163 | El Dorado PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35165 | El Dorado PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35166 | El Dorado PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35167 | El Dorado PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35168 | El Dorado PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35171 | El Dorado PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
35174 | El Dorado PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16817FS-1d |  | 0.2 | 233 | Warning
35177 | El Dorado PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16821 |  | 0 | 466 | Warning
35178 | El Dorado PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35179 | El Dorado PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16825FS+19d | 0 | 405 | Warning
35180 | El Dorado PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16824FS+19d | 16826 | 0 | 405 | Warning
35181 | El Dorado PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16825 |  | 0 | 405 | Warning
35182 | El Dorado PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35183 | El Dorado PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16829 | 0 | 363 | Warning
35184 | El Dorado PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16828 | 16830FS-1d | 0 | 363 | Warning
35185 | El Dorado PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16829FS-1d |  | 0 | 363 | Warning
35186 | El Dorado PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35187 | El Dorado PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35188 | El Dorado PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35189 | El Dorado PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35190 | El Dorado PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16836SS | 0 | 486 | Warning
35191 | El Dorado PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16835SS |  | 0 | 424 | Warning
35192 | El Dorado PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35193 | El Dorado PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35194 | El Dorado PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35195 | El Dorado PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16841SS | 0 | 486 | Warning
35196 | El Dorado PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16840SS | 16855SS | 0 | 466 | Warning
35197 | El Dorado PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35198 | El Dorado PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35199 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35200 | El Dorado PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35201 | El Dorado PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16847SS | 0 | 345 | Warning
35202 | El Dorado PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16846SS | 16848SS,16849 | 0 | 345 | Warning
35203 | El Dorado PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16847SS | 16849 | 0 | 345 | Warning
35204 | El Dorado PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16847,16848 |  | 0 | 345 | Warning
35205 | El Dorado PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35206 | El Dorado PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35207 | El Dorado PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16853SS | 0 | 486 | Warning
35208 | El Dorado PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16852SS |  | 0 | 424 | Warning
35209 | El Dorado PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35210 | El Dorado PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16841SS |  | 0 | 466 | Warning
35211 | El Dorado PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35212 | El Dorado PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16858SS | 0 | 486 | Warning
35213 | El Dorado PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16857SS |  | 0 | 466 | Warning
35214 | El Dorado PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35215 | El Dorado PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16861SS+18d | 0 | 373 | Warning
35216 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16860SS+18d |  | 0 | 373 | Warning
35217 | El Dorado PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35218 | El Dorado PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16864SS | 0 | 362 | Warning
35219 | El Dorado PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16863SS |  | 0 | 362 | Warning
35220 | El Dorado PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16866 | 0 | 345 | Warning
35221 | El Dorado PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16865 |  | 0 | 345 | Warning
35222 | El Dorado PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35223 | El Dorado PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35224 | El Dorado PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16870SS | 0 | 362 | Warning
35225 | El Dorado PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16869SS | 16871SS | 0 | 362 | Warning
35226 | El Dorado PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16870SS | 16872SS | 0 | 362 | Warning
35227 | El Dorado PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16871SS | 16873SS | 0 | 362 | Warning
35228 | El Dorado PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16872SS | 16874SS | 0 | 362 | Warning
35229 | El Dorado PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16873SS | 16875SS | 0 | 362 | Warning
35230 | El Dorado PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16874SS | 16876SS | 0 | 362 | Warning
35231 | El Dorado PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16875SS | 16877SS | 0 | 362 | Warning
35232 | El Dorado PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16876SS | 16878SS | 0 | 362 | Warning
35233 | El Dorado PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16877SS | 16879SS | 0 | 362 | Warning
35234 | El Dorado PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16878SS |  | 0 | 362 | Warning
35235 | El Dorado PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35236 | El Dorado PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35239 | El Dorado PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16883SS |  | 0 | 384 | Warning
35240 | El Dorado PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35241 | El Dorado PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16894 | 0 | 234 | Warning
35242 | El Dorado PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16895 | 0 | 234 | Warning
35244 | El Dorado PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35245 | El Dorado PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16891SS,16899SS+20d | 0 | 240 | Warning
35246 | El Dorado PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16890SS | 16892SS,16900SS+20d | 0 | 309 | Warning
35247 | El Dorado PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16891SS | 16901SS+20d | 0 | 309 | Warning
35248 | El Dorado PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35249 | El Dorado PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16886 | 16895SS | 0 | 234 | Warning
35250 | El Dorado PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16887,16894SS |  | 0 | 234 | Warning
35251 | El Dorado PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16904FS+12d | 0 | 240 | Warning
35252 | El Dorado PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16898SS | 0 | 321 | Warning
35253 | El Dorado PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16897SS |  | 0 | 321 | Warning
35254 | El Dorado PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16890SS+20d |  | 0 | 240 | Warning
35255 | El Dorado PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16891SS+20d |  | 0 | 240 | Warning
35256 | El Dorado PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 16892SS+20d |  | 0 | 240 | Warning
35257 | El Dorado PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16904SS+44d | 0 | 240 | Warning
35258 | El Dorado PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35259 | El Dorado PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 16896FS+12d,16902SS+44d |  | 0 | 240 | Warning
35261 | Fresno PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35262 | Fresno PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35266 | Fresno PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35267 | Fresno PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35268 | Fresno PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35269 | Fresno PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35270 | Fresno PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35271 | Fresno PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35272 | Fresno PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35273 | Fresno PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35274 | Fresno PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35275 | Fresno PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35276 | Fresno PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35277 | Fresno PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35278 | Fresno PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35287 | Fresno PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35288 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16934SS | 0 | 414 | Warning
35289 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16933SS |  | 0 | 414 | Warning
35290 | Fresno PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16936SS | 0 | 362 | Warning
35291 | Fresno PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16935SS |  | 0 | 362 | Warning
35292 | Fresno PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16939SS,16938SS | 0 | 342 | Warning
35293 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 16937SS |  | 0 | 385 | Warning
35294 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 16937SS |  | 0 | 371 | Warning
35295 | Fresno PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
35296 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16942SS | 0 | 332 | Warning
35297 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 16941SS |  | 0 | 332 | Warning
35298 | Fresno PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
35299 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16945SS | 0 | 311 | Warning
35300 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16944SS |  | 0 | 311 | Warning
35301 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16947SS | 0 | 289 | Warning
35302 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 16946SS |  | 0 | 289 | Warning
35303 | Fresno PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
35304 | Fresno PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
35305 | Fresno PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
35306 | Fresno PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
35307 | Fresno PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35308 | Fresno PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35309 | Fresno PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
35310 | Fresno PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
35311 | Fresno PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.33 | 277 | Warning
35314 | Fresno PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16957FS-1d |  | 0.6 | 277 | Warning
35317 | Fresno PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16961 |  | 0 | 466 | Warning
35318 | Fresno PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35319 | Fresno PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16965FS+19d | 0 | 405 | Warning
35320 | Fresno PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16964FS+19d | 16966 | 0 | 405 | Warning
35321 | Fresno PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 16965 |  | 0 | 405 | Warning
35322 | Fresno PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35323 | Fresno PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16969 | 0 | 363 | Warning
35324 | Fresno PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16968 | 16970FS-1d | 0 | 363 | Warning
35325 | Fresno PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16969FS-1d |  | 0 | 363 | Warning
35326 | Fresno PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35327 | Fresno PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35328 | Fresno PR - Technical Activities | October 1, 2025 8:00 AM | June 12, 2026 5:00 PM | 175 | 333d |  |  | 0 | 333 | Warning
35329 | Fresno PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35330 | Fresno PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16976SS | 0 | 486 | Warning
35331 | Fresno PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16975SS |  | 0 | 466 | Warning
35332 | Fresno PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35333 | Fresno PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16979SS | 0 | 362 | Warning
35334 | Fresno PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16978SS | 16980SS | 0 | 362 | Warning
35335 | Fresno PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16979SS | 16981SS | 0 | 362 | Warning
35336 | Fresno PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16980SS | 16982SS | 0 | 362 | Warning
35337 | Fresno PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16981SS | 16983SS | 0 | 362 | Warning
35338 | Fresno PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16982SS | 16984SS | 0 | 362 | Warning
35339 | Fresno PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16983SS | 16985SS | 0 | 362 | Warning
35340 | Fresno PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16984SS | 16986SS | 0 | 362 | Warning
35341 | Fresno PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16985SS | 16987SS | 0 | 362 | Warning
35342 | Fresno PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16986SS | 16988SS | 0 | 362 | Warning
35343 | Fresno PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16987SS |  | 0 | 362 | Warning
35344 | Fresno PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
35345 | Fresno PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
35348 | Fresno PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16992SS |  | 0 | 384 | Warning
35349 | Fresno PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35350 | Fresno PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17003 | 0 | 273 | Warning
35351 | Fresno PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17004 | 0 | 273 | Warning
35353 | Fresno PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35354 | Fresno PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 17000SS,17008SS+20d | 0 | 299 | Warning
35355 | Fresno PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 16999SS | 17001SS,17009SS+20d | 0 | 299 | Warning
35356 | Fresno PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 17000SS | 17010SS+20d | 0 | 299 | Warning
35357 | Fresno PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35358 | Fresno PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16995 | 17004SS | 0 | 273 | Warning
35359 | Fresno PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16996,17003SS |  | 0 | 273 | Warning
35360 | Fresno PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 17013FS+12d | 0 | 279 | Warning
35361 | Fresno PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17007SS | 0 | 321 | Warning
35362 | Fresno PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17006SS |  | 0 | 321 | Warning
35363 | Fresno PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 16999SS+20d |  | 0 | 299 | Warning
35364 | Fresno PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 17000SS+20d |  | 0 | 299 | Warning
35365 | Fresno PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 17001SS+20d |  | 0 | 299 | Warning
35366 | Fresno PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 17013SS+44d | 0 | 279 | Warning
35367 | Fresno PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35368 | Fresno PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 17005FS+12d,17011SS+44d |  | 0 | 279 | Warning
35370 | Glenn PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35371 | Glenn PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35375 | Glenn PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35376 | Glenn PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35377 | Glenn PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35378 | Glenn PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35379 | Glenn PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35380 | Glenn PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35381 | Glenn PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35382 | Glenn PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35383 | Glenn PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35384 | Glenn PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35385 | Glenn PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35386 | Glenn PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35387 | Glenn PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35396 | Glenn PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35397 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17043SS | 0 | 414 | Warning
35398 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17042SS |  | 0 | 414 | Warning
35399 | Glenn PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17045SS | 0 | 362 | Warning
35400 | Glenn PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17044SS |  | 0 | 362 | Warning
35401 | Glenn PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35402 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17048SS | 0 | 364 | Warning
35403 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17047SS |  | 0 | 353 | Warning
35404 | Glenn PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35405 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17051SS | 0 | 300 | Warning
35406 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17050SS |  | 0 | 288 | Warning
35407 | Glenn PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35408 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17054SS | 0 | 279 | Warning
35409 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17053SS |  | 0 | 268 | Warning
35410 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17056SS | 0 | 246 | Warning
35411 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17055SS |  | 0 | 246 | Warning
35412 | Glenn PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35413 | Glenn PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35415 | Glenn PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35416 | Glenn PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35417 | Glenn PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35418 | Glenn PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35421 | Glenn PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
35424 | Glenn PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17067FS-1d |  | 0.2 | 233 | Warning
35427 | Glenn PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17071 |  | 0 | 466 | Warning
35428 | Glenn PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35429 | Glenn PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17075FS+19d | 0 | 405 | Warning
35430 | Glenn PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17074FS+19d | 17076 | 0 | 405 | Warning
35431 | Glenn PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17075 |  | 0 | 405 | Warning
35432 | Glenn PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35433 | Glenn PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17079 | 0 | 363 | Warning
35434 | Glenn PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17078 | 17080FS-1d | 0 | 363 | Warning
35435 | Glenn PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17079FS-1d |  | 0 | 363 | Warning
35436 | Glenn PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35437 | Glenn PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35438 | Glenn PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
35439 | Glenn PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35440 | Glenn PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17086SS | 0 | 362 | Warning
35441 | Glenn PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17085SS | 17087SS | 0 | 362 | Warning
35442 | Glenn PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17086SS | 17088SS | 0 | 362 | Warning
35443 | Glenn PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17087SS | 17089SS | 0 | 362 | Warning
35444 | Glenn PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17088SS | 17090SS | 0 | 362 | Warning
35445 | Glenn PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17089SS | 17091SS | 0 | 362 | Warning
35446 | Glenn PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17090SS | 17092SS | 0 | 362 | Warning
35447 | Glenn PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17091SS | 17093SS | 0 | 362 | Warning
35448 | Glenn PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17092SS | 17094SS | 0 | 362 | Warning
35449 | Glenn PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17093SS | 17095SS | 0 | 362 | Warning
35450 | Glenn PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17094SS |  | 0 | 362 | Warning
35451 | Glenn PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35452 | Glenn PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35455 | Glenn PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17099SS |  | 0 | 384 | Warning
35456 | Glenn PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35457 | Glenn PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17110 | 0 | 234 | Warning
35458 | Glenn PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17111 | 0 | 234 | Warning
35460 | Glenn PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35461 | Glenn PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17107SS,17115SS+20d | 0 | 240 | Warning
35462 | Glenn PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17106SS | 17108SS,17116SS+20d | 0 | 309 | Warning
35463 | Glenn PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17107SS | 17117SS+20d | 0 | 309 | Warning
35464 | Glenn PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35465 | Glenn PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17102 | 17111SS | 0 | 234 | Warning
35466 | Glenn PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17103,17110SS |  | 0 | 234 | Warning
35467 | Glenn PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17120FS+12d | 0 | 240 | Warning
35468 | Glenn PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17114SS | 0 | 321 | Warning
35469 | Glenn PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17113SS |  | 0 | 321 | Warning
35470 | Glenn PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17106SS+20d |  | 0 | 240 | Warning
35471 | Glenn PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17107SS+20d |  | 0 | 240 | Warning
35472 | Glenn PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17108SS+20d |  | 0 | 240 | Warning
35473 | Glenn PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17120SS+44d | 0 | 240 | Warning
35474 | Glenn PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35475 | Glenn PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17112FS+12d,17118SS+44d |  | 0 | 240 | Warning
35477 | Humboldt PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35478 | Humboldt PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35482 | Humboldt PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35483 | Humboldt PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35484 | Humboldt PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35485 | Humboldt PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35486 | Humboldt PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35487 | Humboldt PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35488 | Humboldt PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35489 | Humboldt PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35490 | Humboldt PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35491 | Humboldt PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35492 | Humboldt PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35493 | Humboldt PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35494 | Humboldt PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35503 | Humboldt PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35504 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17150SS | 0 | 414 | Warning
35505 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17149SS |  | 0 | 414 | Warning
35506 | Humboldt PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17152SS | 0 | 362 | Warning
35507 | Humboldt PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17151SS |  | 0 | 362 | Warning
35508 | Humboldt PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35509 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17155SS | 0 | 364 | Warning
35510 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17154SS |  | 0 | 353 | Warning
35511 | Humboldt PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35512 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17158SS | 0 | 300 | Warning
35513 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17157SS |  | 0 | 288 | Warning
35514 | Humboldt PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35515 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17161SS | 0 | 279 | Warning
35516 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17160SS |  | 0 | 268 | Warning
35517 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17163SS | 0 | 246 | Warning
35518 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17162SS |  | 0 | 246 | Warning
35519 | Humboldt PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35520 | Humboldt PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35522 | Humboldt PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35523 | Humboldt PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35524 | Humboldt PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35525 | Humboldt PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35528 | Humboldt PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
35531 | Humboldt PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17174FS-1d |  | 0 | 233 | Warning
35534 | Humboldt PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17178 |  | 0 | 466 | Warning
35535 | Humboldt PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35536 | Humboldt PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17182FS+19d | 0 | 405 | Warning
35537 | Humboldt PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17181FS+19d | 17183 | 0 | 405 | Warning
35538 | Humboldt PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17182 |  | 0 | 405 | Warning
35539 | Humboldt PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35540 | Humboldt PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17186 | 0 | 363 | Warning
35541 | Humboldt PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17185 | 17187FS-1d | 0 | 363 | Warning
35542 | Humboldt PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17186FS-1d |  | 0 | 363 | Warning
35543 | Humboldt PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35544 | Humboldt PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35545 | Humboldt PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35546 | Humboldt PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35547 | Humboldt PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17193SS | 0 | 486 | Warning
35548 | Humboldt PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17192SS |  | 0 | 424 | Warning
35549 | Humboldt PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35550 | Humboldt PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35551 | Humboldt PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35552 | Humboldt PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17198SS | 0 | 486 | Warning
35553 | Humboldt PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17197SS | 17212SS | 0 | 466 | Warning
35554 | Humboldt PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35555 | Humboldt PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35556 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35557 | Humboldt PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35558 | Humboldt PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17204SS | 0 | 345 | Warning
35559 | Humboldt PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17203SS | 17205SS,17206 | 0 | 345 | Warning
35560 | Humboldt PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17204SS | 17206 | 0 | 345 | Warning
35561 | Humboldt PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17204,17205 |  | 0 | 345 | Warning
35562 | Humboldt PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35563 | Humboldt PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35564 | Humboldt PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17210SS | 0 | 486 | Warning
35565 | Humboldt PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17209SS |  | 0 | 424 | Warning
35566 | Humboldt PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35567 | Humboldt PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17198SS |  | 0 | 466 | Warning
35568 | Humboldt PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35569 | Humboldt PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17215SS | 0 | 486 | Warning
35570 | Humboldt PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17214SS |  | 0 | 466 | Warning
35571 | Humboldt PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35572 | Humboldt PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17218SS+18d | 0 | 373 | Warning
35573 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17217SS+18d |  | 0 | 373 | Warning
35574 | Humboldt PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35575 | Humboldt PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17221SS | 0 | 362 | Warning
35576 | Humboldt PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17220SS |  | 0 | 362 | Warning
35577 | Humboldt PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17223 | 0 | 345 | Warning
35578 | Humboldt PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17222 |  | 0 | 345 | Warning
35579 | Humboldt PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35580 | Humboldt PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35581 | Humboldt PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17227SS | 0 | 362 | Warning
35582 | Humboldt PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17226SS | 17228SS | 0 | 362 | Warning
35583 | Humboldt PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17227SS | 17229SS | 0 | 362 | Warning
35584 | Humboldt PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17228SS | 17230SS | 0 | 362 | Warning
35585 | Humboldt PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17229SS | 17231SS | 0 | 362 | Warning
35586 | Humboldt PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17230SS | 17232SS | 0 | 362 | Warning
35587 | Humboldt PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17231SS | 17233SS | 0 | 362 | Warning
35588 | Humboldt PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17232SS | 17234SS | 0 | 362 | Warning
35589 | Humboldt PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17233SS | 17235SS | 0 | 362 | Warning
35590 | Humboldt PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17234SS | 17236SS | 0 | 362 | Warning
35591 | Humboldt PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17235SS |  | 0 | 362 | Warning
35592 | Humboldt PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35593 | Humboldt PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35596 | Humboldt PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17240SS |  | 0 | 384 | Warning
35597 | Humboldt PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35598 | Humboldt PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17251 | 0 | 234 | Warning
35599 | Humboldt PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17252 | 0 | 234 | Warning
35601 | Humboldt PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35602 | Humboldt PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17248SS,17256SS+20d | 0 | 240 | Warning
35603 | Humboldt PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17247SS | 17249SS,17257SS+20d | 0 | 309 | Warning
35604 | Humboldt PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17248SS | 17258SS+20d | 0 | 309 | Warning
35605 | Humboldt PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35606 | Humboldt PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17243 | 17252SS | 0 | 234 | Warning
35607 | Humboldt PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17244,17251SS |  | 0 | 234 | Warning
35608 | Humboldt PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17261FS+12d | 0 | 240 | Warning
35609 | Humboldt PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17255SS | 0 | 321 | Warning
35610 | Humboldt PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17254SS |  | 0 | 321 | Warning
35611 | Humboldt PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17247SS+20d |  | 0 | 240 | Warning
35612 | Humboldt PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17248SS+20d |  | 0 | 240 | Warning
35613 | Humboldt PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17249SS+20d |  | 0 | 240 | Warning
35614 | Humboldt PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17261SS+44d | 0 | 240 | Warning
35615 | Humboldt PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35616 | Humboldt PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17253FS+12d,17259SS+44d |  | 0 | 240 | Warning
35618 | Imperial PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35619 | Imperial PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35623 | Imperial PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35624 | Imperial PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35625 | Imperial PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35626 | Imperial PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35627 | Imperial PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35628 | Imperial PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35629 | Imperial PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35630 | Imperial PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35631 | Imperial PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35632 | Imperial PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35633 | Imperial PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35634 | Imperial PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35635 | Imperial PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35644 | Imperial PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35645 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17291SS | 0 | 414 | Warning
35646 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17290SS |  | 0 | 414 | Warning
35647 | Imperial PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17293SS | 0 | 362 | Warning
35648 | Imperial PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17292SS |  | 0 | 362 | Warning
35649 | Imperial PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35650 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17296SS | 0 | 364 | Warning
35651 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17295SS |  | 0 | 353 | Warning
35652 | Imperial PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35653 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17299SS | 0 | 300 | Warning
35654 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17298SS |  | 0 | 288 | Warning
35655 | Imperial PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35656 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17302SS | 0 | 279 | Warning
35657 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17301SS |  | 0 | 268 | Warning
35658 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17304SS | 0 | 246 | Warning
35659 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17303SS |  | 0 | 246 | Warning
35660 | Imperial PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35661 | Imperial PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35663 | Imperial PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35664 | Imperial PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35665 | Imperial PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35666 | Imperial PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35669 | Imperial PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
35672 | Imperial PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17315FS-1d |  | 0 | 233 | Warning
35675 | Imperial PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17319 |  | 0 | 466 | Warning
35676 | Imperial PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35677 | Imperial PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17323FS+19d | 0 | 405 | Warning
35678 | Imperial PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17322FS+19d | 17324 | 0 | 405 | Warning
35679 | Imperial PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17323 |  | 0 | 405 | Warning
35680 | Imperial PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35681 | Imperial PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17327 | 0 | 363 | Warning
35682 | Imperial PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17326 | 17328FS-1d | 0 | 363 | Warning
35683 | Imperial PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17327FS-1d |  | 0 | 363 | Warning
35684 | Imperial PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35685 | Imperial PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35686 | Imperial PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35687 | Imperial PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35688 | Imperial PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17334SS | 0 | 486 | Warning
35689 | Imperial PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17333SS |  | 0 | 424 | Warning
35690 | Imperial PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35691 | Imperial PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35692 | Imperial PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35693 | Imperial PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17339SS | 0 | 486 | Warning
35694 | Imperial PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17338SS | 17353SS | 0 | 466 | Warning
35695 | Imperial PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35696 | Imperial PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35697 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35698 | Imperial PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35699 | Imperial PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17345SS | 0 | 345 | Warning
35700 | Imperial PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17344SS | 17346SS,17347 | 0 | 345 | Warning
35701 | Imperial PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17345SS | 17347 | 0 | 345 | Warning
35702 | Imperial PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17345,17346 |  | 0 | 345 | Warning
35703 | Imperial PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35704 | Imperial PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35705 | Imperial PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17351SS | 0 | 486 | Warning
35706 | Imperial PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17350SS |  | 0 | 424 | Warning
35707 | Imperial PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35708 | Imperial PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17339SS |  | 0 | 466 | Warning
35709 | Imperial PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35710 | Imperial PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17356SS | 0 | 486 | Warning
35711 | Imperial PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17355SS |  | 0 | 466 | Warning
35712 | Imperial PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35713 | Imperial PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17359SS+18d | 0 | 373 | Warning
35714 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17358SS+18d |  | 0 | 373 | Warning
35715 | Imperial PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35716 | Imperial PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17362SS | 0 | 362 | Warning
35717 | Imperial PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17361SS |  | 0 | 362 | Warning
35718 | Imperial PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17364 | 0 | 345 | Warning
35719 | Imperial PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17363 |  | 0 | 345 | Warning
35720 | Imperial PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35721 | Imperial PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35722 | Imperial PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17368SS | 0 | 362 | Warning
35723 | Imperial PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17367SS | 17369SS | 0 | 362 | Warning
35724 | Imperial PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17368SS | 17370SS | 0 | 362 | Warning
35725 | Imperial PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17369SS | 17371SS | 0 | 362 | Warning
35726 | Imperial PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17370SS | 17372SS | 0 | 362 | Warning
35727 | Imperial PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17371SS | 17373SS | 0 | 362 | Warning
35728 | Imperial PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17372SS | 17374SS | 0 | 362 | Warning
35729 | Imperial PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17373SS | 17375SS | 0 | 362 | Warning
35730 | Imperial PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17374SS | 17376SS | 0 | 362 | Warning
35731 | Imperial PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17375SS | 17377SS | 0 | 362 | Warning
35732 | Imperial PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17376SS |  | 0 | 362 | Warning
35733 | Imperial PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35734 | Imperial PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35737 | Imperial PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17381SS |  | 0 | 384 | Warning
35738 | Imperial PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35739 | Imperial PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17392 | 0 | 234 | Warning
35740 | Imperial PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17393 | 0 | 234 | Warning
35742 | Imperial PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35743 | Imperial PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17389SS,17397SS+20d | 0 | 240 | Warning
35744 | Imperial PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17388SS | 17390SS,17398SS+20d | 0 | 309 | Warning
35745 | Imperial PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17389SS | 17399SS+20d | 0 | 309 | Warning
35746 | Imperial PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35747 | Imperial PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17384 | 17393SS | 0 | 234 | Warning
35748 | Imperial PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17385,17392SS |  | 0 | 234 | Warning
35749 | Imperial PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17402FS+12d | 0 | 240 | Warning
35750 | Imperial PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17396SS | 0 | 321 | Warning
35751 | Imperial PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17395SS |  | 0 | 321 | Warning
35752 | Imperial PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17388SS+20d |  | 0 | 240 | Warning
35753 | Imperial PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17389SS+20d |  | 0 | 240 | Warning
35754 | Imperial PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17390SS+20d |  | 0 | 240 | Warning
35755 | Imperial PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17402SS+44d | 0 | 240 | Warning
35756 | Imperial PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35757 | Imperial PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17394FS+12d,17400SS+44d |  | 0 | 240 | Warning
35759 | Inyo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35760 | Inyo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35764 | Inyo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35765 | Inyo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35766 | Inyo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35767 | Inyo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35768 | Inyo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35769 | Inyo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35770 | Inyo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35771 | Inyo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35772 | Inyo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35773 | Inyo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35774 | Inyo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35775 | Inyo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35776 | Inyo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35785 | Inyo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35786 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17432SS | 0 | 414 | Warning
35787 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17431SS |  | 0 | 414 | Warning
35788 | Inyo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17434SS | 0 | 362 | Warning
35789 | Inyo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17433SS |  | 0 | 362 | Warning
35790 | Inyo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35791 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17437SS | 0 | 364 | Warning
35792 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17436SS |  | 0 | 353 | Warning
35793 | Inyo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35794 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17440SS | 0 | 300 | Warning
35795 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17439SS |  | 0 | 288 | Warning
35796 | Inyo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35797 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17443SS | 0 | 279 | Warning
35798 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17442SS |  | 0 | 268 | Warning
35799 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17445SS | 0 | 246 | Warning
35800 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17444SS |  | 0 | 246 | Warning
35801 | Inyo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35802 | Inyo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35804 | Inyo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35805 | Inyo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35806 | Inyo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35807 | Inyo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35810 | Inyo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
35813 | Inyo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17456FS-1d |  | 0 | 233 | Warning
35816 | Inyo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17460 |  | 0 | 466 | Warning
35817 | Inyo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35818 | Inyo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17464FS+19d | 0 | 405 | Warning
35819 | Inyo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17463FS+19d | 17465 | 0 | 405 | Warning
35820 | Inyo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17464 |  | 0 | 405 | Warning
35821 | Inyo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35822 | Inyo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17468 | 0 | 363 | Warning
35823 | Inyo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17467 | 17469FS-1d | 0 | 363 | Warning
35824 | Inyo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17468FS-1d |  | 0 | 363 | Warning
35825 | Inyo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35826 | Inyo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35827 | Inyo PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35828 | Inyo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35829 | Inyo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17475SS | 0 | 486 | Warning
35830 | Inyo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17474SS |  | 0 | 424 | Warning
35831 | Inyo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35832 | Inyo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35833 | Inyo PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35834 | Inyo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17480SS | 0 | 486 | Warning
35835 | Inyo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17479SS | 17494SS | 0 | 466 | Warning
35836 | Inyo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35837 | Inyo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35838 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35839 | Inyo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35840 | Inyo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17486SS | 0 | 345 | Warning
35841 | Inyo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17485SS | 17487SS,17488 | 0 | 345 | Warning
35842 | Inyo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17486SS | 17488 | 0 | 345 | Warning
35843 | Inyo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17486,17487 |  | 0 | 345 | Warning
35844 | Inyo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35845 | Inyo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35846 | Inyo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17492SS | 0 | 486 | Warning
35847 | Inyo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17491SS |  | 0 | 424 | Warning
35848 | Inyo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35849 | Inyo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17480SS |  | 0 | 466 | Warning
35850 | Inyo PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35851 | Inyo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17497SS | 0 | 486 | Warning
35852 | Inyo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17496SS |  | 0 | 466 | Warning
35853 | Inyo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35854 | Inyo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17500SS+18d | 0 | 373 | Warning
35855 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17499SS+18d |  | 0 | 373 | Warning
35856 | Inyo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35857 | Inyo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17503SS | 0 | 362 | Warning
35858 | Inyo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17502SS |  | 0 | 362 | Warning
35859 | Inyo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17505 | 0 | 345 | Warning
35860 | Inyo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17504 |  | 0 | 345 | Warning
35861 | Inyo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35862 | Inyo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
35863 | Inyo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17509SS | 0 | 362 | Warning
35864 | Inyo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17508SS | 17510SS | 0 | 362 | Warning
35865 | Inyo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17509SS | 17511SS | 0 | 362 | Warning
35866 | Inyo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17510SS | 17512SS | 0 | 362 | Warning
35867 | Inyo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17511SS | 17513SS | 0 | 362 | Warning
35868 | Inyo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17512SS | 17514SS | 0 | 362 | Warning
35869 | Inyo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17513SS | 17515SS | 0 | 362 | Warning
35870 | Inyo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17514SS | 17516SS | 0 | 362 | Warning
35871 | Inyo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17515SS | 17517SS | 0 | 362 | Warning
35872 | Inyo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17516SS | 17518SS | 0 | 362 | Warning
35873 | Inyo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17517SS |  | 0 | 362 | Warning
35874 | Inyo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
35875 | Inyo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
35878 | Inyo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17522SS |  | 0 | 384 | Warning
35879 | Inyo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
35880 | Inyo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17533 | 0 | 234 | Warning
35881 | Inyo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17534 | 0 | 234 | Warning
35883 | Inyo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
35884 | Inyo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17530SS,17538SS+20d | 0 | 240 | Warning
35885 | Inyo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17529SS | 17531SS,17539SS+20d | 0 | 309 | Warning
35886 | Inyo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17530SS | 17540SS+20d | 0 | 309 | Warning
35887 | Inyo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
35888 | Inyo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17525 | 17534SS | 0 | 234 | Warning
35889 | Inyo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17526,17533SS |  | 0 | 234 | Warning
35890 | Inyo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17543FS+12d | 0 | 240 | Warning
35891 | Inyo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17537SS | 0 | 321 | Warning
35892 | Inyo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17536SS |  | 0 | 321 | Warning
35893 | Inyo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17529SS+20d |  | 0 | 240 | Warning
35894 | Inyo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17530SS+20d |  | 0 | 240 | Warning
35895 | Inyo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17531SS+20d |  | 0 | 240 | Warning
35896 | Inyo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17543SS+44d | 0 | 240 | Warning
35897 | Inyo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
35898 | Inyo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17535FS+12d,17541SS+44d |  | 0 | 240 | Warning
35900 | Kern PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
35901 | Kern PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
35905 | Kern PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
35906 | Kern PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
35907 | Kern PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
35908 | Kern PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
35909 | Kern PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
35910 | Kern PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
35911 | Kern PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
35912 | Kern PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
35913 | Kern PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
35914 | Kern PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
35915 | Kern PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
35916 | Kern PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35917 | Kern PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
35926 | Kern PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
35927 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17573SS | 0 | 414 | Warning
35928 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17572SS |  | 0 | 414 | Warning
35929 | Kern PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17575SS | 0 | 362 | Warning
35930 | Kern PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17574SS |  | 0 | 362 | Warning
35931 | Kern PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
35932 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17578SS | 0 | 364 | Warning
35933 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17577SS |  | 0 | 353 | Warning
35934 | Kern PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
35935 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17581SS | 0 | 300 | Warning
35936 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17580SS |  | 0 | 288 | Warning
35937 | Kern PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
35938 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17584SS | 0 | 279 | Warning
35939 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17583SS |  | 0 | 268 | Warning
35940 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17586SS | 0 | 246 | Warning
35941 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17585SS |  | 0 | 246 | Warning
35942 | Kern PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
35943 | Kern PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
35945 | Kern PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
35946 | Kern PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
35947 | Kern PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
35948 | Kern PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
35951 | Kern PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
35954 | Kern PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17597FS-1d |  | 0.2 | 233 | Warning
35957 | Kern PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17601 |  | 0 | 466 | Warning
35958 | Kern PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
35959 | Kern PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17605FS+19d | 0 | 405 | Warning
35960 | Kern PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17604FS+19d | 17606 | 0 | 405 | Warning
35961 | Kern PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17605 |  | 0 | 405 | Warning
35962 | Kern PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
35963 | Kern PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17609 | 0 | 363 | Warning
35964 | Kern PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17608 | 17610FS-1d | 0 | 363 | Warning
35965 | Kern PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17609FS-1d |  | 0 | 363 | Warning
35966 | Kern PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
35967 | Kern PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
35968 | Kern PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
35969 | Kern PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35970 | Kern PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17616SS | 0 | 486 | Warning
35971 | Kern PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17615SS |  | 0 | 424 | Warning
35972 | Kern PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35973 | Kern PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35974 | Kern PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35975 | Kern PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17621SS | 0 | 486 | Warning
35976 | Kern PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17620SS | 17635SS | 0 | 466 | Warning
35977 | Kern PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35978 | Kern PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
35979 | Kern PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
35980 | Kern PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35981 | Kern PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17627SS | 0 | 345 | Warning
35982 | Kern PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17626SS | 17628SS,17629 | 0 | 345 | Warning
35983 | Kern PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17627SS | 17629 | 0 | 345 | Warning
35984 | Kern PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17627,17628 |  | 0 | 345 | Warning
35985 | Kern PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
35986 | Kern PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
35987 | Kern PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17633SS | 0 | 486 | Warning
35988 | Kern PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17632SS |  | 0 | 424 | Warning
35989 | Kern PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
35990 | Kern PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17621SS |  | 0 | 466 | Warning
35991 | Kern PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
35992 | Kern PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17638SS | 0 | 486 | Warning
35993 | Kern PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17637SS |  | 0 | 466 | Warning
35994 | Kern PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
35995 | Kern PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17641SS+18d | 0 | 373 | Warning
35996 | Kern PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17640SS+18d |  | 0 | 373 | Warning
35997 | Kern PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
35998 | Kern PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17644SS | 0 | 362 | Warning
35999 | Kern PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17643SS |  | 0 | 362 | Warning
36000 | Kern PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17646 | 0 | 345 | Warning
36001 | Kern PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17645 |  | 0 | 345 | Warning
36002 | Kern PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36003 | Kern PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36004 | Kern PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17650SS | 0 | 362 | Warning
36005 | Kern PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17649SS | 17651SS | 0 | 362 | Warning
36006 | Kern PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17650SS | 17652SS | 0 | 362 | Warning
36007 | Kern PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17651SS | 17653SS | 0 | 362 | Warning
36008 | Kern PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17652SS | 17654SS | 0 | 362 | Warning
36009 | Kern PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17653SS | 17655SS | 0 | 362 | Warning
36010 | Kern PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17654SS | 17656SS | 0 | 362 | Warning
36011 | Kern PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17655SS | 17657SS | 0 | 362 | Warning
36012 | Kern PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17656SS | 17658SS | 0 | 362 | Warning
36013 | Kern PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17657SS | 17659SS | 0 | 362 | Warning
36014 | Kern PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17658SS |  | 0 | 362 | Warning
36015 | Kern PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36016 | Kern PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36019 | Kern PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17663SS |  | 0 | 384 | Warning
36020 | Kern PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36021 | Kern PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17674 | 0 | 234 | Warning
36022 | Kern PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17675 | 0 | 234 | Warning
36024 | Kern PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36025 | Kern PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17671SS,17679SS+20d | 0 | 240 | Warning
36026 | Kern PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17670SS | 17672SS,17680SS+20d | 0 | 309 | Warning
36027 | Kern PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17671SS | 17681SS+20d | 0 | 309 | Warning
36028 | Kern PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36029 | Kern PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17666 | 17675SS | 0 | 234 | Warning
36030 | Kern PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17667,17674SS |  | 0 | 234 | Warning
36031 | Kern PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17684FS+12d | 0 | 240 | Warning
36032 | Kern PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17678SS | 0 | 321 | Warning
36033 | Kern PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17677SS |  | 0 | 321 | Warning
36034 | Kern PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17670SS+20d |  | 0 | 240 | Warning
36035 | Kern PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17671SS+20d |  | 0 | 240 | Warning
36036 | Kern PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17672SS+20d |  | 0 | 240 | Warning
36037 | Kern PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17684SS+44d | 0 | 240 | Warning
36038 | Kern PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36039 | Kern PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17676FS+12d,17682SS+44d |  | 0 | 240 | Warning
36041 | Kings PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
36042 | Kings PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
36047 | Kings PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36048 | Kings PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36049 | Kings PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36050 | Kings PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36051 | Kings PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36052 | Kings PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36053 | Kings PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36054 | Kings PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36055 | Kings PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36056 | Kings PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36057 | Kings PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36058 | Kings PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36067 | Kings PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
36068 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17714SS | 0 | 414 | Warning
36069 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17713SS |  | 0 | 414 | Warning
36070 | Kings PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17716SS | 0 | 362 | Warning
36071 | Kings PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17715SS |  | 0 | 362 | Warning
36072 | Kings PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 17719SS,17718SS | 0 | 342 | Warning
36073 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 17717SS |  | 0 | 385 | Warning
36074 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 17717SS |  | 0 | 371 | Warning
36075 | Kings PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
36076 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 17722SS | 0 | 332 | Warning
36077 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 17721SS |  | 0 | 332 | Warning
36078 | Kings PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
36079 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 17725SS | 0 | 311 | Warning
36080 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 17724SS |  | 0 | 311 | Warning
36081 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 17727SS | 0 | 289 | Warning
36082 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 17726SS |  | 0 | 289 | Warning
36083 | Kings PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
36084 | Kings PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
36085 | Kings PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
36086 | Kings PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
36087 | Kings PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36088 | Kings PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36089 | Kings PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
36090 | Kings PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
36091 | Kings PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.21 | 277 | Warning
36094 | Kings PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 17737FS-1d |  | 0.2 | 277 | Warning
36097 | Kings PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17741 |  | 0.2 | 466 | Warning
36098 | Kings PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36099 | Kings PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17745FS+19d | 0.2 | 405 | Warning
36100 | Kings PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17744FS+19d | 17746 | 0 | 405 | Warning
36101 | Kings PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17745 |  | 0 | 405 | Warning
36102 | Kings PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36103 | Kings PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17749 | 0 | 363 | Warning
36104 | Kings PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17748 | 17750FS-1d | 0 | 363 | Warning
36105 | Kings PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17749FS-1d |  | 0 | 363 | Warning
36106 | Kings PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36107 | Kings PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36108 | Kings PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36109 | Kings PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36110 | Kings PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17756SS | 0 | 486 | Warning
36111 | Kings PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17755SS |  | 0 | 424 | Warning
36112 | Kings PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36113 | Kings PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | 466 | Warning
36114 | Kings PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36115 | Kings PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17761SS | 0 | 486 | Warning
36116 | Kings PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17760SS | 17775SS | 0 | 466 | Warning
36117 | Kings PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36118 | Kings PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36119 | Kings PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36120 | Kings PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36121 | Kings PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17767SS | 0 | 345 | Warning
36122 | Kings PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17766SS | 17768SS,17769 | 0 | 345 | Warning
36123 | Kings PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17767SS | 17769 | 0 | 345 | Warning
36124 | Kings PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17767,17768 |  | 0 | 345 | Warning
36125 | Kings PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36126 | Kings PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36127 | Kings PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17773SS | 0 | 486 | Warning
36128 | Kings PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17772SS |  | 0 | 424 | Warning
36129 | Kings PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36130 | Kings PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17761SS |  | 0 | 466 | Warning
36131 | Kings PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36132 | Kings PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17778SS | 0 | 486 | Warning
36133 | Kings PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17777SS |  | 0 | 466 | Warning
36134 | Kings PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36135 | Kings PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17781SS+18d | 0 | 373 | Warning
36136 | Kings PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17780SS+18d |  | 0 | 373 | Warning
36137 | Kings PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36138 | Kings PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17784SS | 0 | 362 | Warning
36139 | Kings PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17783SS |  | 0 | 362 | Warning
36140 | Kings PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17786 | 0 | 345 | Warning
36141 | Kings PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17785 |  | 0 | 345 | Warning
36142 | Kings PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36143 | Kings PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36144 | Kings PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17790SS | 0 | 362 | Warning
36145 | Kings PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17789SS | 17791SS | 0 | 362 | Warning
36146 | Kings PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17790SS | 17792SS | 0 | 362 | Warning
36147 | Kings PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17791SS | 17793SS | 0 | 362 | Warning
36148 | Kings PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17792SS | 17794SS | 0 | 362 | Warning
36149 | Kings PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17793SS | 17795SS | 0 | 362 | Warning
36150 | Kings PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17794SS | 17796SS | 0 | 362 | Warning
36151 | Kings PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17795SS | 17797SS | 0 | 362 | Warning
36152 | Kings PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17796SS | 17798SS | 0 | 362 | Warning
36153 | Kings PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17797SS | 17799SS | 0 | 362 | Warning
36154 | Kings PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17798SS |  | 0 | 362 | Warning
36155 | Kings PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
36156 | Kings PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
36159 | Kings PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17803SS |  | 0 | 384 | Warning
36160 | Kings PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36161 | Kings PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17814 | 0 | 273 | Warning
36162 | Kings PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17815 | 0 | 273 | Warning
36164 | Kings PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36165 | Kings PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 17811SS,17819SS+20d | 0 | 299 | Warning
36166 | Kings PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 17810SS | 17812SS,17820SS+20d | 0 | 299 | Warning
36167 | Kings PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 17811SS | 17821SS+20d | 0 | 299 | Warning
36168 | Kings PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36169 | Kings PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 17806 | 17815SS | 0 | 273 | Warning
36170 | Kings PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 17807,17814SS |  | 0 | 273 | Warning
36171 | Kings PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 17824FS+12d | 0 | 279 | Warning
36172 | Kings PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17818SS | 0 | 321 | Warning
36173 | Kings PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17817SS |  | 0 | 321 | Warning
36174 | Kings PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 17810SS+20d |  | 0 | 299 | Warning
36175 | Kings PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 17811SS+20d |  | 0 | 299 | Warning
36176 | Kings PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 17812SS+20d |  | 0 | 299 | Warning
36177 | Kings PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 17824SS+44d | 0 | 279 | Warning
36178 | Kings PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36179 | Kings PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 17816FS+12d,17822SS+44d |  | 0 | 279 | Warning
36181 | Lake PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
36182 | Lake PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
36186 | Lake PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
36187 | Lake PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36188 | Lake PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36189 | Lake PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36190 | Lake PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36191 | Lake PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36192 | Lake PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36193 | Lake PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36194 | Lake PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36195 | Lake PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36196 | Lake PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36197 | Lake PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36198 | Lake PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36207 | Lake PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
36208 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17854SS | 0 | 414 | Warning
36209 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17853SS |  | 0 | 414 | Warning
36210 | Lake PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17856SS | 0 | 362 | Warning
36211 | Lake PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17855SS |  | 0 | 362 | Warning
36212 | Lake PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36213 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17859SS | 0 | 364 | Warning
36214 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17858SS |  | 0 | 353 | Warning
36215 | Lake PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36216 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17862SS | 0 | 300 | Warning
36217 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 17861SS |  | 0 | 288 | Warning
36218 | Lake PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36219 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17865SS | 0 | 279 | Warning
36220 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17864SS |  | 0 | 268 | Warning
36221 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17867SS | 0 | 246 | Warning
36222 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17866SS |  | 0 | 246 | Warning
36223 | Lake PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36224 | Lake PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36226 | Lake PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36227 | Lake PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36228 | Lake PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36229 | Lake PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36232 | Lake PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
36235 | Lake PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17878FS-1d |  | 0.2 | 233 | Warning
36238 | Lake PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17882 |  | 0 | 466 | Warning
36239 | Lake PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36240 | Lake PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17886FS+19d | 0 | 405 | Warning
36241 | Lake PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17885FS+19d | 17887 | 0 | 405 | Warning
36242 | Lake PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 17886 |  | 0 | 405 | Warning
36243 | Lake PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36244 | Lake PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17890 | 0 | 363 | Warning
36245 | Lake PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17889 | 17891FS-1d | 0 | 363 | Warning
36246 | Lake PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17890FS-1d |  | 0 | 363 | Warning
36247 | Lake PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36248 | Lake PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36249 | Lake PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36250 | Lake PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36251 | Lake PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17897SS | 0 | 486 | Warning
36252 | Lake PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17896SS |  | 0 | 424 | Warning
36253 | Lake PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36254 | Lake PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36255 | Lake PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36256 | Lake PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17902SS | 0 | 486 | Warning
36257 | Lake PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17901SS | 17916SS | 0 | 466 | Warning
36258 | Lake PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36259 | Lake PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36260 | Lake PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36261 | Lake PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36262 | Lake PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17908SS | 0 | 345 | Warning
36263 | Lake PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17907SS | 17909SS,17910 | 0 | 345 | Warning
36264 | Lake PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17908SS | 17910 | 0 | 345 | Warning
36265 | Lake PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17908,17909 |  | 0 | 345 | Warning
36266 | Lake PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36267 | Lake PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36268 | Lake PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17914SS | 0 | 486 | Warning
36269 | Lake PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17913SS |  | 0 | 424 | Warning
36270 | Lake PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36271 | Lake PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17902SS |  | 0 | 466 | Warning
36272 | Lake PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36273 | Lake PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17919SS | 0 | 486 | Warning
36274 | Lake PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17918SS |  | 0 | 466 | Warning
36275 | Lake PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36276 | Lake PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17922SS+18d | 0 | 373 | Warning
36277 | Lake PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17921SS+18d |  | 0 | 373 | Warning
36278 | Lake PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36279 | Lake PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17925SS | 0 | 362 | Warning
36280 | Lake PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17924SS |  | 0 | 362 | Warning
36281 | Lake PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17927 | 0 | 345 | Warning
36282 | Lake PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17926 |  | 0 | 345 | Warning
36283 | Lake PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36284 | Lake PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36285 | Lake PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17931SS | 0 | 362 | Warning
36286 | Lake PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17930SS | 17932SS | 0 | 362 | Warning
36287 | Lake PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17931SS | 17933SS | 0 | 362 | Warning
36288 | Lake PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17932SS | 17934SS | 0 | 362 | Warning
36289 | Lake PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17933SS | 17935SS | 0 | 362 | Warning
36290 | Lake PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17934SS | 17936SS | 0 | 362 | Warning
36291 | Lake PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17935SS | 17937SS | 0 | 362 | Warning
36292 | Lake PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17936SS | 17938SS | 0 | 362 | Warning
36293 | Lake PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17937SS | 17939SS | 0 | 362 | Warning
36294 | Lake PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17938SS | 17940SS | 0 | 362 | Warning
36295 | Lake PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17939SS |  | 0 | 362 | Warning
36296 | Lake PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36297 | Lake PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36300 | Lake PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17944SS |  | 0 | 384 | Warning
36301 | Lake PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36302 | Lake PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17955 | 0 | 234 | Warning
36303 | Lake PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17956 | 0 | 234 | Warning
36305 | Lake PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36306 | Lake PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17952SS,17960SS+20d | 0 | 240 | Warning
36307 | Lake PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17951SS | 17953SS,17961SS+20d | 0 | 309 | Warning
36308 | Lake PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17952SS | 17962SS+20d | 0 | 309 | Warning
36309 | Lake PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36310 | Lake PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17947 | 17956SS | 0 | 234 | Warning
36311 | Lake PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17948,17955SS |  | 0 | 234 | Warning
36312 | Lake PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17965FS+12d | 0 | 240 | Warning
36313 | Lake PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17959SS | 0 | 321 | Warning
36314 | Lake PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17958SS |  | 0 | 321 | Warning
36315 | Lake PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17951SS+20d |  | 0 | 240 | Warning
36316 | Lake PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17952SS+20d |  | 0 | 240 | Warning
36317 | Lake PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 17953SS+20d |  | 0 | 240 | Warning
36318 | Lake PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17965SS+44d | 0 | 240 | Warning
36319 | Lake PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36320 | Lake PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 17957FS+12d,17963SS+44d |  | 0 | 240 | Warning
36322 | Lassen PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
36323 | Lassen PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
36328 | Lassen PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36329 | Lassen PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36330 | Lassen PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36331 | Lassen PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36332 | Lassen PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36333 | Lassen PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36334 | Lassen PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36335 | Lassen PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36336 | Lassen PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36337 | Lassen PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36338 | Lassen PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36339 | Lassen PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36348 | Lassen PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
36349 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17995SS | 0 | 414 | Warning
36350 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17994SS |  | 0 | 414 | Warning
36351 | Lassen PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17997SS | 0 | 362 | Warning
36352 | Lassen PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17996SS |  | 0 | 362 | Warning
36353 | Lassen PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36354 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18000SS | 0 | 364 | Warning
36355 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17999SS |  | 0 | 353 | Warning
36356 | Lassen PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36357 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18003SS | 0 | 300 | Warning
36358 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18002SS |  | 0 | 288 | Warning
36359 | Lassen PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36360 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18006SS | 0 | 279 | Warning
36361 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18005SS |  | 0 | 268 | Warning
36362 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18008SS | 0 | 246 | Warning
36363 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18007SS |  | 0 | 246 | Warning
36364 | Lassen PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36365 | Lassen PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36367 | Lassen PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36368 | Lassen PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36369 | Lassen PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36370 | Lassen PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36373 | Lassen PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.15 | 233 | Warning
36375 | Lassen PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d |  |  | 0.2 | 233 | Warning
36378 | Lassen PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18022 |  | 0 | 466 | Warning
36379 | Lassen PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36380 | Lassen PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18026FS+19d | 0 | 405 | Warning
36381 | Lassen PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18025FS+19d | 18027 | 0 | 405 | Warning
36382 | Lassen PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18026 |  | 0 | 405 | Warning
36383 | Lassen PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36384 | Lassen PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18030 | 0 | 363 | Warning
36385 | Lassen PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18029 | 18031FS-1d | 0 | 363 | Warning
36386 | Lassen PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18030FS-1d |  | 0 | 363 | Warning
36387 | Lassen PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36388 | Lassen PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36389 | Lassen PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36390 | Lassen PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36391 | Lassen PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18037SS | 0 | 486 | Warning
36392 | Lassen PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18036SS |  | 0 | 424 | Warning
36393 | Lassen PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36394 | Lassen PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36395 | Lassen PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36396 | Lassen PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18042SS | 0 | 486 | Warning
36397 | Lassen PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18041SS | 18056SS | 0 | 466 | Warning
36398 | Lassen PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36399 | Lassen PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36400 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36401 | Lassen PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36402 | Lassen PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18048SS | 0 | 345 | Warning
36403 | Lassen PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18047SS | 18049SS,18050 | 0 | 345 | Warning
36404 | Lassen PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18048SS | 18050 | 0 | 345 | Warning
36405 | Lassen PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18048,18049 |  | 0 | 345 | Warning
36406 | Lassen PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36407 | Lassen PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36408 | Lassen PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18054SS | 0 | 486 | Warning
36409 | Lassen PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18053SS |  | 0 | 424 | Warning
36410 | Lassen PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36411 | Lassen PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18042SS |  | 0 | 466 | Warning
36412 | Lassen PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36413 | Lassen PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18059SS | 0 | 486 | Warning
36414 | Lassen PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18058SS |  | 0 | 466 | Warning
36415 | Lassen PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36416 | Lassen PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18062SS+18d | 0 | 373 | Warning
36417 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18061SS+18d |  | 0 | 373 | Warning
36418 | Lassen PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36419 | Lassen PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18065SS | 0 | 362 | Warning
36420 | Lassen PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18064SS |  | 0 | 362 | Warning
36421 | Lassen PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18067 | 0 | 345 | Warning
36422 | Lassen PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18066 |  | 0 | 345 | Warning
36423 | Lassen PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36424 | Lassen PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36425 | Lassen PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18071SS | 0 | 362 | Warning
36426 | Lassen PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18070SS | 18072SS | 0 | 362 | Warning
36427 | Lassen PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18071SS | 18073SS | 0 | 362 | Warning
36428 | Lassen PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18072SS | 18074SS | 0 | 362 | Warning
36429 | Lassen PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18073SS | 18075SS | 0 | 362 | Warning
36430 | Lassen PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18074SS | 18076SS | 0 | 362 | Warning
36431 | Lassen PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18075SS | 18077SS | 0 | 362 | Warning
36432 | Lassen PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18076SS | 18078SS | 0 | 362 | Warning
36433 | Lassen PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18077SS | 18079SS | 0 | 362 | Warning
36434 | Lassen PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18078SS | 18080SS | 0 | 362 | Warning
36435 | Lassen PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18079SS |  | 0 | 362 | Warning
36436 | Lassen PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36437 | Lassen PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36440 | Lassen PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18084SS |  | 0 | 384 | Warning
36441 | Lassen PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36442 | Lassen PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18095 | 0 | 234 | Warning
36443 | Lassen PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18096 | 0 | 234 | Warning
36445 | Lassen PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36446 | Lassen PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18092SS,18100SS+20d | 0 | 240 | Warning
36447 | Lassen PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18091SS | 18093SS,18101SS+20d | 0 | 309 | Warning
36448 | Lassen PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18092SS | 18102SS+20d | 0 | 309 | Warning
36449 | Lassen PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36450 | Lassen PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18087 | 18096SS | 0 | 234 | Warning
36451 | Lassen PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18088,18095SS |  | 0 | 234 | Warning
36452 | Lassen PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18105FS+12d | 0 | 240 | Warning
36453 | Lassen PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18099SS | 0 | 321 | Warning
36454 | Lassen PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18098SS |  | 0 | 321 | Warning
36455 | Lassen PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18091SS+20d |  | 0 | 240 | Warning
36456 | Lassen PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18092SS+20d |  | 0 | 240 | Warning
36457 | Lassen PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18093SS+20d |  | 0 | 240 | Warning
36458 | Lassen PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18105SS+44d | 0 | 240 | Warning
36459 | Lassen PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36460 | Lassen PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18097FS+12d,18103SS+44d |  | 0 | 240 | Warning
36462 | Los Angeles PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
36463 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
36468 | Los Angeles PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36469 | Los Angeles PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36470 | Los Angeles PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36471 | Los Angeles PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36472 | Los Angeles PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36473 | Los Angeles PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36474 | Los Angeles PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36475 | Los Angeles PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36476 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36477 | Los Angeles PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36478 | Los Angeles PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36479 | Los Angeles PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36488 | Los Angeles PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
36489 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18135SS | 0 | 414 | Warning
36490 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18134SS |  | 0 | 414 | Warning
36491 | Los Angeles PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18137SS | 0 | 362 | Warning
36492 | Los Angeles PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18136SS |  | 0 | 362 | Warning
36493 | Los Angeles PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36494 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18140SS | 0 | 364 | Warning
36495 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18139SS |  | 0 | 353 | Warning
36496 | Los Angeles PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36497 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18143SS | 0 | 300 | Warning
36498 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18142SS |  | 0 | 288 | Warning
36499 | Los Angeles PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36500 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18146SS | 0 | 279 | Warning
36501 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18145SS |  | 0 | 268 | Warning
36502 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18148SS | 0 | 246 | Warning
36503 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18147SS |  | 0 | 246 | Warning
36504 | Los Angeles PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36505 | Los Angeles PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36507 | Los Angeles PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36508 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36509 | Los Angeles PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36510 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36513 | Los Angeles PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.21 | 233 | Warning
36516 | Los Angeles PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18159FS-1d |  | 0.2 | 233 | Warning
36519 | Los Angeles PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18163 |  | 0.2 | 466 | Warning
36520 | Los Angeles PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36521 | Los Angeles PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18167FS+19d | 0.2 | 405 | Warning
36522 | Los Angeles PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18166FS+19d | 18168 | 0 | 405 | Warning
36523 | Los Angeles PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18167 |  | 0 | 405 | Warning
36524 | Los Angeles PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36525 | Los Angeles PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18171 | 0 | 363 | Warning
36526 | Los Angeles PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18170 | 18172FS-1d | 0 | 363 | Warning
36527 | Los Angeles PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18171FS-1d |  | 0 | 363 | Warning
36528 | Los Angeles PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36529 | Los Angeles PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36530 | Los Angeles PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36531 | Los Angeles PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36532 | Los Angeles PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18178SS | 0 | 486 | Warning
36533 | Los Angeles PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18177SS |  | 0 | 424 | Warning
36534 | Los Angeles PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36535 | Los Angeles PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36536 | Los Angeles PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36537 | Los Angeles PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18183SS | 0 | 486 | Warning
36538 | Los Angeles PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18182SS | 18197SS | 0 | 466 | Warning
36539 | Los Angeles PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36540 | Los Angeles PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36541 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36542 | Los Angeles PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36543 | Los Angeles PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18189SS | 0 | 345 | Warning
36544 | Los Angeles PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18188SS | 18190SS,18191 | 0 | 345 | Warning
36545 | Los Angeles PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18189SS | 18191 | 0 | 345 | Warning
36546 | Los Angeles PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18189,18190 |  | 0 | 345 | Warning
36547 | Los Angeles PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36548 | Los Angeles PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36549 | Los Angeles PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18195SS | 0 | 486 | Warning
36550 | Los Angeles PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18194SS |  | 0 | 424 | Warning
36551 | Los Angeles PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36552 | Los Angeles PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18183SS |  | 0 | 466 | Warning
36553 | Los Angeles PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36554 | Los Angeles PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18200SS | 0 | 486 | Warning
36555 | Los Angeles PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18199SS |  | 0 | 466 | Warning
36556 | Los Angeles PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36557 | Los Angeles PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18203SS+18d | 0 | 373 | Warning
36558 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18202SS+18d |  | 0 | 373 | Warning
36559 | Los Angeles PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36560 | Los Angeles PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18206SS | 0 | 362 | Warning
36561 | Los Angeles PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18205SS |  | 0 | 362 | Warning
36562 | Los Angeles PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18208 | 0 | 345 | Warning
36563 | Los Angeles PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18207 |  | 0 | 345 | Warning
36564 | Los Angeles PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36565 | Los Angeles PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36566 | Los Angeles PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18212SS | 0 | 362 | Warning
36567 | Los Angeles PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18211SS | 18213SS | 0 | 362 | Warning
36568 | Los Angeles PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18212SS | 18214SS | 0 | 362 | Warning
36569 | Los Angeles PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18213SS | 18215SS | 0 | 362 | Warning
36570 | Los Angeles PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18214SS | 18216SS | 0 | 362 | Warning
36571 | Los Angeles PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18215SS | 18217SS | 0 | 362 | Warning
36572 | Los Angeles PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18216SS | 18218SS | 0 | 362 | Warning
36573 | Los Angeles PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18217SS | 18219SS | 0 | 362 | Warning
36574 | Los Angeles PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18218SS | 18220SS | 0 | 362 | Warning
36575 | Los Angeles PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18219SS | 18221SS | 0 | 362 | Warning
36576 | Los Angeles PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18220SS |  | 0 | 362 | Warning
36577 | Los Angeles PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36578 | Los Angeles PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36581 | Los Angeles PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18225SS |  | 0 | 384 | Warning
36582 | Los Angeles PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36583 | Los Angeles PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18236 | 0 | 234 | Warning
36584 | Los Angeles PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18237 | 0 | 234 | Warning
36586 | Los Angeles PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36587 | Los Angeles PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18233SS,18241SS+20d | 0 | 240 | Warning
36588 | Los Angeles PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18232SS | 18234SS,18242SS+20d | 0 | 309 | Warning
36589 | Los Angeles PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18233SS | 18243SS+20d | 0 | 309 | Warning
36590 | Los Angeles PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36591 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18228 | 18237SS | 0 | 234 | Warning
36592 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18229,18236SS |  | 0 | 234 | Warning
36593 | Los Angeles PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18246FS+12d | 0 | 240 | Warning
36594 | Los Angeles PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18240SS | 0 | 321 | Warning
36595 | Los Angeles PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18239SS |  | 0 | 321 | Warning
36596 | Los Angeles PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18232SS+20d |  | 0 | 240 | Warning
36597 | Los Angeles PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18233SS+20d |  | 0 | 240 | Warning
36598 | Los Angeles PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18234SS+20d |  | 0 | 240 | Warning
36599 | Los Angeles PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18246SS+44d | 0 | 240 | Warning
36600 | Los Angeles PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36601 | Los Angeles PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18238FS+12d,18244SS+44d |  | 0 | 240 | Warning
36603 | Madera PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
36604 | Madera PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
36608 | Madera PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
36609 | Madera PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36610 | Madera PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36611 | Madera PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36612 | Madera PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36613 | Madera PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36614 | Madera PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36615 | Madera PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36616 | Madera PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36617 | Madera PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36618 | Madera PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36619 | Madera PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36620 | Madera PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36629 | Madera PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
36630 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18276SS | 0 | 414 | Warning
36631 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18275SS |  | 0 | 414 | Warning
36632 | Madera PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18278SS | 0 | 362 | Warning
36633 | Madera PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18277SS |  | 0 | 362 | Warning
36634 | Madera PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36635 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18281SS | 0 | 364 | Warning
36636 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18280SS |  | 0 | 353 | Warning
36637 | Madera PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36638 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18284SS | 0 | 300 | Warning
36639 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18283SS |  | 0 | 288 | Warning
36640 | Madera PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36641 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18287SS | 0 | 279 | Warning
36642 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18286SS |  | 0 | 268 | Warning
36643 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18289SS | 0 | 246 | Warning
36644 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18288SS |  | 0 | 246 | Warning
36645 | Madera PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36646 | Madera PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36648 | Madera PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36649 | Madera PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36650 | Madera PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36651 | Madera PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36654 | Madera PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.15 | 233 | Warning
36657 | Madera PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18300FS-1d |  | 0 | 233 | Warning
36660 | Madera PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18304 |  | 0 | 466 | Warning
36661 | Madera PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36663 | Madera PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18307FS+19d | 18309 | 0 | 405 | Warning
36664 | Madera PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18308 |  | 0 | 405 | Warning
36665 | Madera PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36666 | Madera PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18312 | 0 | 363 | Warning
36667 | Madera PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18311 | 18313FS-1d | 0 | 363 | Warning
36668 | Madera PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18312FS-1d |  | 0 | 363 | Warning
36669 | Madera PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36670 | Madera PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36671 | Madera PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36672 | Madera PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36673 | Madera PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18319SS | 0 | 486 | Warning
36674 | Madera PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18318SS |  | 0 | 424 | Warning
36675 | Madera PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36676 | Madera PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36677 | Madera PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36678 | Madera PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18324SS | 0 | 486 | Warning
36679 | Madera PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18323SS | 18338SS | 0 | 466 | Warning
36680 | Madera PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36681 | Madera PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36682 | Madera PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36683 | Madera PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36684 | Madera PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18330SS | 0 | 345 | Warning
36685 | Madera PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18329SS | 18331SS,18332 | 0 | 345 | Warning
36686 | Madera PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18330SS | 18332 | 0 | 345 | Warning
36687 | Madera PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18330,18331 |  | 0 | 345 | Warning
36688 | Madera PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36689 | Madera PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36690 | Madera PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18336SS | 0 | 486 | Warning
36691 | Madera PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18335SS |  | 0 | 424 | Warning
36692 | Madera PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36693 | Madera PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18324SS |  | 0 | 466 | Warning
36694 | Madera PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36695 | Madera PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18341SS | 0 | 486 | Warning
36696 | Madera PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18340SS |  | 0 | 466 | Warning
36697 | Madera PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36698 | Madera PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18344SS+18d | 0 | 373 | Warning
36699 | Madera PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18343SS+18d |  | 0 | 373 | Warning
36700 | Madera PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36701 | Madera PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18347SS | 0 | 362 | Warning
36702 | Madera PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18346SS |  | 0 | 362 | Warning
36703 | Madera PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18349 | 0 | 345 | Warning
36704 | Madera PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18348 |  | 0 | 345 | Warning
36705 | Madera PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36706 | Madera PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36707 | Madera PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18353SS | 0 | 362 | Warning
36708 | Madera PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18352SS | 18354SS | 0 | 362 | Warning
36709 | Madera PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18353SS | 18355SS | 0 | 362 | Warning
36710 | Madera PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18354SS | 18356SS | 0 | 362 | Warning
36711 | Madera PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18355SS | 18357SS | 0 | 362 | Warning
36712 | Madera PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18356SS | 18358SS | 0 | 362 | Warning
36713 | Madera PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18357SS | 18359SS | 0 | 362 | Warning
36714 | Madera PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18358SS | 18360SS | 0 | 362 | Warning
36715 | Madera PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18359SS | 18361SS | 0 | 362 | Warning
36716 | Madera PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18360SS | 18362SS | 0 | 362 | Warning
36717 | Madera PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18361SS |  | 0 | 362 | Warning
36718 | Madera PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36719 | Madera PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36722 | Madera PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18366SS |  | 0 | 384 | Warning
36723 | Madera PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36724 | Madera PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18377 | 0 | 234 | Warning
36725 | Madera PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18378 | 0 | 234 | Warning
36727 | Madera PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36728 | Madera PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18374SS,18382SS+20d | 0 | 240 | Warning
36729 | Madera PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18373SS | 18375SS,18383SS+20d | 0 | 309 | Warning
36730 | Madera PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18374SS | 18384SS+20d | 0 | 309 | Warning
36731 | Madera PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36732 | Madera PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18369 | 18378SS | 0 | 234 | Warning
36733 | Madera PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18370,18377SS |  | 0 | 234 | Warning
36734 | Madera PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18387FS+12d | 0 | 240 | Warning
36735 | Madera PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18381SS | 0 | 321 | Warning
36736 | Madera PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18380SS |  | 0 | 321 | Warning
36737 | Madera PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18373SS+20d |  | 0 | 240 | Warning
36738 | Madera PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18374SS+20d |  | 0 | 240 | Warning
36739 | Madera PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18375SS+20d |  | 0 | 240 | Warning
36740 | Madera PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18387SS+44d | 0 | 240 | Warning
36741 | Madera PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36742 | Madera PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18379FS+12d,18385SS+44d |  | 0 | 240 | Warning
36744 | Marin PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.2 | 235 | Warning
36745 | Marin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
36749 | Marin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
36750 | Marin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36751 | Marin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36752 | Marin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36753 | Marin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36754 | Marin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36755 | Marin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36756 | Marin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36757 | Marin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36758 | Marin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36759 | Marin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36760 | Marin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36761 | Marin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36770 | Marin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
36771 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18417SS | 0 | 414 | Warning
36772 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18416SS |  | 0 | 414 | Warning
36773 | Marin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18419SS | 0 | 362 | Warning
36774 | Marin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18418SS |  | 0 | 362 | Warning
36775 | Marin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36776 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18422SS | 0 | 364 | Warning
36777 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18421SS |  | 0 | 353 | Warning
36778 | Marin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36779 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18425SS | 0 | 300 | Warning
36780 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18424SS |  | 0 | 288 | Warning
36781 | Marin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36782 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18428SS | 0 | 279 | Warning
36783 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18427SS |  | 0 | 268 | Warning
36784 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18430SS | 0 | 246 | Warning
36785 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18429SS |  | 0 | 246 | Warning
36786 | Marin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36787 | Marin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36789 | Marin PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36790 | Marin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36791 | Marin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36792 | Marin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36795 | Marin PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.21 | 233 | Warning
36798 | Marin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18441FS-1d |  | 0.2 | 233 | Warning
36801 | Marin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18445 |  | 0.2 | 466 | Warning
36802 | Marin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36803 | Marin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18449FS+19d | 0 | 405 | Warning
36804 | Marin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18448FS+19d | 18450 | 0 | 405 | Warning
36805 | Marin PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18449 |  | 0 | 405 | Warning
36806 | Marin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36807 | Marin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18453 | 0 | 363 | Warning
36808 | Marin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18452 | 18454FS-1d | 0 | 363 | Warning
36809 | Marin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18453FS-1d |  | 0 | 363 | Warning
36810 | Marin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36811 | Marin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36812 | Marin PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
36813 | Marin PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36814 | Marin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18460SS | 0 | 486 | Warning
36815 | Marin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18459SS |  | 0 | 424 | Warning
36816 | Marin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36817 | Marin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36818 | Marin PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36819 | Marin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18465SS | 0 | 486 | Warning
36820 | Marin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18464SS | 18479SS | 0 | 466 | Warning
36821 | Marin PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36822 | Marin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
36823 | Marin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
36824 | Marin PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36825 | Marin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18471SS | 0 | 345 | Warning
36826 | Marin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18470SS | 18472SS,18473 | 0 | 345 | Warning
36827 | Marin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18471SS | 18473 | 0 | 345 | Warning
36828 | Marin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18471,18472 |  | 0 | 345 | Warning
36829 | Marin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36830 | Marin PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
36831 | Marin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18477SS | 0 | 486 | Warning
36832 | Marin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18476SS |  | 0 | 424 | Warning
36833 | Marin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
36834 | Marin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18465SS |  | 0 | 466 | Warning
36835 | Marin PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
36836 | Marin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18482SS | 0 | 486 | Warning
36837 | Marin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18481SS |  | 0 | 466 | Warning
36838 | Marin PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
36839 | Marin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18485SS+18d | 0 | 373 | Warning
36840 | Marin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18484SS+18d |  | 0 | 373 | Warning
36841 | Marin PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
36842 | Marin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18488SS | 0 | 362 | Warning
36843 | Marin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18487SS |  | 0 | 362 | Warning
36844 | Marin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18490 | 0 | 345 | Warning
36845 | Marin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18489 |  | 0 | 345 | Warning
36846 | Marin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
36847 | Marin PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36848 | Marin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18494SS | 0 | 362 | Warning
36849 | Marin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18493SS | 18495SS | 0 | 362 | Warning
36850 | Marin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18494SS | 18496SS | 0 | 362 | Warning
36851 | Marin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18495SS | 18497SS | 0 | 362 | Warning
36852 | Marin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18496SS | 18498SS | 0 | 362 | Warning
36853 | Marin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18497SS | 18499SS | 0 | 362 | Warning
36854 | Marin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18498SS | 18500SS | 0 | 362 | Warning
36855 | Marin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18499SS | 18501SS | 0 | 362 | Warning
36856 | Marin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18500SS | 18502SS | 0 | 362 | Warning
36857 | Marin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18501SS | 18503SS | 0 | 362 | Warning
36858 | Marin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18502SS |  | 0 | 362 | Warning
36859 | Marin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36860 | Marin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36863 | Marin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18507SS |  | 0 | 384 | Warning
36864 | Marin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36865 | Marin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18518 | 0 | 234 | Warning
36866 | Marin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18519 | 0 | 234 | Warning
36868 | Marin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36869 | Marin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18515SS,18523SS+20d | 0 | 240 | Warning
36870 | Marin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18514SS | 18516SS,18524SS+20d | 0 | 309 | Warning
36871 | Marin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18515SS | 18525SS+20d | 0 | 309 | Warning
36872 | Marin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36873 | Marin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18510 | 18519SS | 0 | 234 | Warning
36874 | Marin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18511,18518SS |  | 0 | 234 | Warning
36875 | Marin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18528FS+12d | 0 | 240 | Warning
36876 | Marin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18522SS | 0 | 321 | Warning
36877 | Marin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18521SS |  | 0 | 321 | Warning
36878 | Marin PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18514SS+20d |  | 0 | 240 | Warning
36879 | Marin PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18515SS+20d |  | 0 | 240 | Warning
36880 | Marin PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18516SS+20d |  | 0 | 240 | Warning
36881 | Marin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18528SS+44d | 0 | 240 | Warning
36882 | Marin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36883 | Marin PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18520FS+12d,18526SS+44d |  | 0 | 240 | Warning
36885 | Mariposa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
36886 | Mariposa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
36890 | Mariposa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
36891 | Mariposa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36892 | Mariposa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
36893 | Mariposa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
36894 | Mariposa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
36895 | Mariposa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
36896 | Mariposa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
36897 | Mariposa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
36898 | Mariposa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
36899 | Mariposa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
36900 | Mariposa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
36901 | Mariposa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36902 | Mariposa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
36911 | Mariposa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
36912 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18558SS | 0 | 414 | Warning
36913 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18557SS |  | 0 | 414 | Warning
36914 | Mariposa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18560SS | 0 | 362 | Warning
36915 | Mariposa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18559SS |  | 0 | 362 | Warning
36916 | Mariposa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
36917 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18563SS | 0 | 364 | Warning
36918 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18562SS |  | 0 | 353 | Warning
36919 | Mariposa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
36920 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18566SS | 0 | 300 | Warning
36921 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18565SS |  | 0 | 288 | Warning
36922 | Mariposa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
36923 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18569SS | 0 | 279 | Warning
36924 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18568SS |  | 0 | 268 | Warning
36925 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18571SS | 0 | 246 | Warning
36926 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18570SS |  | 0 | 246 | Warning
36927 | Mariposa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
36928 | Mariposa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
36930 | Mariposa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
36931 | Mariposa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
36932 | Mariposa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
36933 | Mariposa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
36936 | Mariposa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.22 | 233 | Warning
36939 | Mariposa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18582FS-1d |  | 0.2 | 233 | Warning
36942 | Mariposa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18586 |  | 0 | 466 | Warning
36943 | Mariposa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
36945 | Mariposa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18589FS+19d | 18591 | 0 | 405 | Warning
36946 | Mariposa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18590 |  | 0 | 405 | Warning
36947 | Mariposa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
36948 | Mariposa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18594 | 0 | 363 | Warning
36949 | Mariposa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18593 | 18595FS-1d | 0 | 363 | Warning
36950 | Mariposa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18594FS-1d |  | 0 | 363 | Warning
36951 | Mariposa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
36952 | Mariposa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
36953 | Mariposa PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
36954 | Mariposa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
36955 | Mariposa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18601SS | 0 | 362 | Warning
36956 | Mariposa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18600SS | 18602SS | 0 | 362 | Warning
36957 | Mariposa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18601SS | 18603SS | 0 | 362 | Warning
36958 | Mariposa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18602SS | 18604SS | 0 | 362 | Warning
36959 | Mariposa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18603SS | 18605SS | 0 | 362 | Warning
36960 | Mariposa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18604SS | 18606SS | 0 | 362 | Warning
36961 | Mariposa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18605SS | 18607SS | 0 | 362 | Warning
36962 | Mariposa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18606SS | 18608SS | 0 | 362 | Warning
36963 | Mariposa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18607SS | 18609SS | 0 | 362 | Warning
36964 | Mariposa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18608SS | 18610SS | 0 | 362 | Warning
36965 | Mariposa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18609SS |  | 0 | 362 | Warning
36966 | Mariposa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
36967 | Mariposa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
36970 | Mariposa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18614SS |  | 0 | 384 | Warning
36971 | Mariposa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
36972 | Mariposa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18625 | 0 | 234 | Warning
36973 | Mariposa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18626 | 0 | 234 | Warning
36975 | Mariposa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
36976 | Mariposa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18622SS,18630SS+20d | 0 | 240 | Warning
36977 | Mariposa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18621SS | 18623SS,18631SS+20d | 0 | 309 | Warning
36978 | Mariposa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18622SS | 18632SS+20d | 0 | 309 | Warning
36979 | Mariposa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
36980 | Mariposa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18617 | 18626SS | 0 | 234 | Warning
36981 | Mariposa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18618,18625SS |  | 0 | 234 | Warning
36982 | Mariposa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18635FS+12d | 0 | 240 | Warning
36983 | Mariposa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18629SS | 0 | 321 | Warning
36984 | Mariposa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18628SS |  | 0 | 321 | Warning
36985 | Mariposa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18621SS+20d |  | 0 | 240 | Warning
36986 | Mariposa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18622SS+20d |  | 0 | 240 | Warning
36987 | Mariposa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18623SS+20d |  | 0 | 240 | Warning
36988 | Mariposa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18635SS+44d | 0 | 240 | Warning
36989 | Mariposa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
36990 | Mariposa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18627FS+12d,18633SS+44d |  | 0 | 240 | Warning
36992 | Mendocino PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
36993 | Mendocino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
36997 | Mendocino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
36998 | Mendocino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
36999 | Mendocino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37000 | Mendocino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37001 | Mendocino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37002 | Mendocino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37003 | Mendocino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37004 | Mendocino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37005 | Mendocino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37006 | Mendocino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37007 | Mendocino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37008 | Mendocino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37009 | Mendocino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37018 | Mendocino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
37019 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18665SS | 0 | 414 | Warning
37020 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18664SS |  | 0 | 414 | Warning
37021 | Mendocino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18667SS | 0 | 362 | Warning
37022 | Mendocino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18666SS |  | 0 | 362 | Warning
37023 | Mendocino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37024 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18670SS | 0 | 364 | Warning
37025 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18669SS |  | 0 | 353 | Warning
37026 | Mendocino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37027 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18673SS | 0 | 300 | Warning
37028 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18672SS |  | 0 | 288 | Warning
37029 | Mendocino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37030 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18676SS | 0 | 279 | Warning
37031 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18675SS |  | 0 | 268 | Warning
37032 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18678SS | 0 | 246 | Warning
37033 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18677SS |  | 0 | 246 | Warning
37034 | Mendocino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37035 | Mendocino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37037 | Mendocino PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37038 | Mendocino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37039 | Mendocino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37040 | Mendocino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37043 | Mendocino PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.17 | 233 | Warning
37045 | Mendocino PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 528d |  |  | 0 | 528 | Warning
37046 | Mendocino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18689FS-1d |  | 0.2 | 233 | Warning
37049 | Mendocino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18693 |  | 0 | 466 | Warning
37050 | Mendocino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37051 | Mendocino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18697FS+19d | 0 | 405 | Warning
37052 | Mendocino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18696FS+19d | 18698 | 0 | 405 | Warning
37053 | Mendocino PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18697 |  | 0 | 405 | Warning
37054 | Mendocino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37055 | Mendocino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18701 | 0 | 363 | Warning
37056 | Mendocino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18700 | 18702FS-1d | 0 | 363 | Warning
37057 | Mendocino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18701FS-1d |  | 0 | 363 | Warning
37058 | Mendocino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37059 | Mendocino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37060 | Mendocino PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
37061 | Mendocino PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37062 | Mendocino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18708SS | 0 | 486 | Warning
37063 | Mendocino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18707SS |  | 0 | 424 | Warning
37064 | Mendocino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37065 | Mendocino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37066 | Mendocino PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37067 | Mendocino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18713SS | 0 | 486 | Warning
37068 | Mendocino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18712SS | 18727SS | 0 | 466 | Warning
37069 | Mendocino PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37070 | Mendocino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37071 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37072 | Mendocino PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37073 | Mendocino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18719SS | 0 | 345 | Warning
37074 | Mendocino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18718SS | 18720SS,18721 | 0 | 345 | Warning
37075 | Mendocino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18719SS | 18721 | 0 | 345 | Warning
37076 | Mendocino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18719,18720 |  | 0 | 345 | Warning
37077 | Mendocino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37078 | Mendocino PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37079 | Mendocino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18725SS | 0 | 486 | Warning
37080 | Mendocino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18724SS |  | 0 | 424 | Warning
37081 | Mendocino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37082 | Mendocino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18713SS |  | 0 | 466 | Warning
37083 | Mendocino PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37084 | Mendocino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18730SS | 0 | 486 | Warning
37085 | Mendocino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18729SS |  | 0 | 466 | Warning
37086 | Mendocino PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37087 | Mendocino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18733SS+18d | 0 | 373 | Warning
37088 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18732SS+18d |  | 0 | 373 | Warning
37089 | Mendocino PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37090 | Mendocino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18736SS | 0 | 362 | Warning
37091 | Mendocino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18735SS |  | 0 | 362 | Warning
37092 | Mendocino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18738 | 0 | 345 | Warning
37093 | Mendocino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18737 |  | 0 | 345 | Warning
37094 | Mendocino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37095 | Mendocino PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37096 | Mendocino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18742SS | 0 | 362 | Warning
37097 | Mendocino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18741SS | 18743SS | 0 | 362 | Warning
37098 | Mendocino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18742SS | 18744SS | 0 | 362 | Warning
37099 | Mendocino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18743SS | 18745SS | 0 | 362 | Warning
37100 | Mendocino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18744SS | 18746SS | 0 | 362 | Warning
37101 | Mendocino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18745SS | 18747SS | 0 | 362 | Warning
37102 | Mendocino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18746SS | 18748SS | 0 | 362 | Warning
37103 | Mendocino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18747SS | 18749SS | 0 | 362 | Warning
37104 | Mendocino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18748SS | 18750SS | 0 | 362 | Warning
37105 | Mendocino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18749SS | 18751SS | 0 | 362 | Warning
37106 | Mendocino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18750SS |  | 0 | 362 | Warning
37107 | Mendocino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37108 | Mendocino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37111 | Mendocino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18755SS |  | 0 | 384 | Warning
37112 | Mendocino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37113 | Mendocino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18766 | 0 | 234 | Warning
37114 | Mendocino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18767 | 0 | 234 | Warning
37116 | Mendocino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37117 | Mendocino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18763SS,18771SS+20d | 0 | 240 | Warning
37118 | Mendocino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18762SS | 18764SS,18772SS+20d | 0 | 309 | Warning
37119 | Mendocino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18763SS | 18773SS+20d | 0 | 309 | Warning
37120 | Mendocino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37121 | Mendocino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18758 | 18767SS | 0 | 234 | Warning
37122 | Mendocino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18759,18766SS |  | 0 | 234 | Warning
37123 | Mendocino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18776FS+12d | 0 | 240 | Warning
37124 | Mendocino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18770SS | 0 | 321 | Warning
37125 | Mendocino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18769SS |  | 0 | 321 | Warning
37126 | Mendocino PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18762SS+20d |  | 0 | 240 | Warning
37127 | Mendocino PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18763SS+20d |  | 0 | 240 | Warning
37128 | Mendocino PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18764SS+20d |  | 0 | 240 | Warning
37129 | Mendocino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18776SS+44d | 0 | 240 | Warning
37130 | Mendocino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37131 | Mendocino PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18768FS+12d,18774SS+44d |  | 0 | 240 | Warning
37133 | Merced PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.2 | 235 | Warning
37134 | Merced PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
37138 | Merced PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
37139 | Merced PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37140 | Merced PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37141 | Merced PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37142 | Merced PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37143 | Merced PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37144 | Merced PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37145 | Merced PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37146 | Merced PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37147 | Merced PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37148 | Merced PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37149 | Merced PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37150 | Merced PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37159 | Merced PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
37160 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18806SS | 0 | 414 | Warning
37161 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18805SS |  | 0 | 414 | Warning
37162 | Merced PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18808SS | 0 | 362 | Warning
37163 | Merced PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18807SS |  | 0 | 362 | Warning
37164 | Merced PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37165 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18811SS | 0 | 364 | Warning
37166 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18810SS |  | 0 | 353 | Warning
37167 | Merced PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37168 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18814SS | 0 | 300 | Warning
37169 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18813SS |  | 0 | 288 | Warning
37170 | Merced PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37171 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18817SS | 0 | 279 | Warning
37172 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18816SS |  | 0 | 268 | Warning
37173 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18819SS | 0 | 246 | Warning
37174 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18818SS |  | 0 | 246 | Warning
37175 | Merced PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37176 | Merced PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37178 | Merced PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37179 | Merced PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37180 | Merced PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37181 | Merced PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37184 | Merced PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.22 | 233 | Warning
37187 | Merced PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18830FS-1d |  | 0.2 | 233 | Warning
37190 | Merced PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18834 |  | 0 | 466 | Warning
37191 | Merced PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37193 | Merced PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18837FS+19d | 18839 | 0 | 405 | Warning
37194 | Merced PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18838 |  | 0 | 405 | Warning
37195 | Merced PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37196 | Merced PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18842 | 0 | 363 | Warning
37197 | Merced PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18841 | 18843FS-1d | 0 | 363 | Warning
37198 | Merced PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18842FS-1d |  | 0 | 363 | Warning
37199 | Merced PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37200 | Merced PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37201 | Merced PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
37202 | Merced PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37203 | Merced PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18849SS | 0 | 486 | Warning
37204 | Merced PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18848SS |  | 0 | 424 | Warning
37205 | Merced PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37206 | Merced PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37207 | Merced PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37208 | Merced PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18854SS | 0 | 486 | Warning
37209 | Merced PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18853SS | 18868SS | 0 | 466 | Warning
37210 | Merced PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37211 | Merced PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37212 | Merced PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37213 | Merced PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37214 | Merced PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18860SS | 0 | 345 | Warning
37215 | Merced PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18859SS | 18861SS,18862 | 0 | 345 | Warning
37216 | Merced PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18860SS | 18862 | 0 | 345 | Warning
37217 | Merced PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18860,18861 |  | 0 | 345 | Warning
37218 | Merced PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37219 | Merced PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37220 | Merced PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18866SS | 0 | 486 | Warning
37221 | Merced PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18865SS |  | 0 | 424 | Warning
37222 | Merced PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37223 | Merced PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18854SS |  | 0 | 466 | Warning
37224 | Merced PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37225 | Merced PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18871SS | 0 | 486 | Warning
37226 | Merced PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18870SS |  | 0 | 466 | Warning
37227 | Merced PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37228 | Merced PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18874SS+18d | 0 | 373 | Warning
37229 | Merced PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18873SS+18d |  | 0 | 373 | Warning
37230 | Merced PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37231 | Merced PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18877SS | 0 | 362 | Warning
37232 | Merced PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18876SS |  | 0 | 362 | Warning
37233 | Merced PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18879 | 0 | 345 | Warning
37234 | Merced PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18878 |  | 0 | 345 | Warning
37235 | Merced PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37236 | Merced PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37237 | Merced PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18883SS | 0 | 362 | Warning
37238 | Merced PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18882SS | 18884SS | 0 | 362 | Warning
37239 | Merced PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18883SS | 18885SS | 0 | 362 | Warning
37240 | Merced PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18884SS | 18886SS | 0 | 362 | Warning
37241 | Merced PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18885SS | 18887SS | 0 | 362 | Warning
37242 | Merced PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18886SS | 18888SS | 0 | 362 | Warning
37243 | Merced PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18887SS | 18889SS | 0 | 362 | Warning
37244 | Merced PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18888SS | 18890SS | 0 | 362 | Warning
37245 | Merced PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18889SS | 18891SS | 0 | 362 | Warning
37246 | Merced PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18890SS | 18892SS | 0 | 362 | Warning
37247 | Merced PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18891SS |  | 0 | 362 | Warning
37248 | Merced PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37249 | Merced PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37252 | Merced PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18896SS |  | 0 | 384 | Warning
37253 | Merced PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37254 | Merced PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18907 | 0 | 234 | Warning
37255 | Merced PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18908 | 0 | 234 | Warning
37257 | Merced PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37258 | Merced PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18904SS,18912SS+20d | 0 | 240 | Warning
37259 | Merced PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18903SS | 18905SS,18913SS+20d | 0 | 309 | Warning
37260 | Merced PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18904SS | 18914SS+20d | 0 | 309 | Warning
37261 | Merced PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37262 | Merced PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18899 | 18908SS | 0 | 234 | Warning
37263 | Merced PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18900,18907SS |  | 0 | 234 | Warning
37264 | Merced PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18917FS+12d | 0 | 240 | Warning
37265 | Merced PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18911SS | 0 | 321 | Warning
37266 | Merced PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18910SS |  | 0 | 321 | Warning
37267 | Merced PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18903SS+20d |  | 0 | 240 | Warning
37268 | Merced PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18904SS+20d |  | 0 | 240 | Warning
37269 | Merced PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 18905SS+20d |  | 0 | 240 | Warning
37270 | Merced PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18917SS+44d | 0 | 240 | Warning
37271 | Merced PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37272 | Merced PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 18909FS+12d,18915SS+44d |  | 0 | 240 | Warning
37274 | Modoc PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
37275 | Modoc PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
37280 | Modoc PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37281 | Modoc PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37282 | Modoc PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37283 | Modoc PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37284 | Modoc PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37285 | Modoc PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37286 | Modoc PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37287 | Modoc PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37288 | Modoc PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37289 | Modoc PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37290 | Modoc PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37291 | Modoc PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37300 | Modoc PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
37301 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18947SS | 0 | 414 | Warning
37302 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18946SS |  | 0 | 414 | Warning
37303 | Modoc PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18949SS | 0 | 362 | Warning
37304 | Modoc PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18948SS |  | 0 | 362 | Warning
37305 | Modoc PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37306 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18952SS | 0 | 364 | Warning
37307 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18951SS |  | 0 | 353 | Warning
37308 | Modoc PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37309 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18955SS | 0 | 300 | Warning
37310 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 18954SS |  | 0 | 288 | Warning
37311 | Modoc PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37312 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18958SS | 0 | 279 | Warning
37313 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18957SS |  | 0 | 268 | Warning
37314 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18960SS | 0 | 246 | Warning
37315 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18959SS |  | 0 | 246 | Warning
37316 | Modoc PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37317 | Modoc PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37319 | Modoc PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37320 | Modoc PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37321 | Modoc PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37322 | Modoc PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37325 | Modoc PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.22 | 233 | Warning
37328 | Modoc PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18971FS-1d |  | 0.2 | 233 | Warning
37331 | Modoc PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18975 |  | 0.2 | 466 | Warning
37332 | Modoc PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37333 | Modoc PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18979FS+19d | 0.4 | 405 | Warning
37334 | Modoc PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18978FS+19d | 18980 | 0 | 405 | Warning
37335 | Modoc PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 18979 |  | 0 | 405 | Warning
37336 | Modoc PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37337 | Modoc PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18983 | 0 | 363 | Warning
37338 | Modoc PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18982 | 18984FS-1d | 0 | 363 | Warning
37339 | Modoc PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18983FS-1d |  | 0 | 363 | Warning
37340 | Modoc PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37341 | Modoc PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37342 | Modoc PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
37343 | Modoc PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37344 | Modoc PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18990SS | 0 | 486 | Warning
37345 | Modoc PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18989SS |  | 0 | 424 | Warning
37346 | Modoc PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37347 | Modoc PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37348 | Modoc PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37349 | Modoc PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18995SS | 0 | 486 | Warning
37350 | Modoc PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18994SS | 19009SS | 0 | 466 | Warning
37351 | Modoc PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37352 | Modoc PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37353 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37354 | Modoc PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37355 | Modoc PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19001SS | 0 | 345 | Warning
37356 | Modoc PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19000SS | 19002SS,19003 | 0 | 345 | Warning
37357 | Modoc PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19001SS | 19003 | 0 | 345 | Warning
37358 | Modoc PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19001,19002 |  | 0 | 345 | Warning
37359 | Modoc PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37360 | Modoc PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37361 | Modoc PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19007SS | 0 | 486 | Warning
37362 | Modoc PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19006SS |  | 0 | 424 | Warning
37363 | Modoc PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37364 | Modoc PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18995SS |  | 0 | 466 | Warning
37365 | Modoc PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37366 | Modoc PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19012SS | 0 | 486 | Warning
37367 | Modoc PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19011SS |  | 0 | 466 | Warning
37368 | Modoc PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37369 | Modoc PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19015SS+18d | 0 | 373 | Warning
37370 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19014SS+18d |  | 0 | 373 | Warning
37371 | Modoc PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37372 | Modoc PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19018SS | 0 | 362 | Warning
37373 | Modoc PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19017SS |  | 0 | 362 | Warning
37374 | Modoc PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19020 | 0 | 345 | Warning
37375 | Modoc PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19019 |  | 0 | 345 | Warning
37376 | Modoc PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37377 | Modoc PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37378 | Modoc PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19024SS | 0 | 362 | Warning
37379 | Modoc PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19023SS | 19025SS | 0 | 362 | Warning
37380 | Modoc PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19024SS | 19026SS | 0 | 362 | Warning
37381 | Modoc PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19025SS | 19027SS | 0 | 362 | Warning
37382 | Modoc PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19026SS | 19028SS | 0 | 362 | Warning
37383 | Modoc PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19027SS | 19029SS | 0 | 362 | Warning
37384 | Modoc PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19028SS | 19030SS | 0 | 362 | Warning
37385 | Modoc PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19029SS | 19031SS | 0 | 362 | Warning
37386 | Modoc PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19030SS | 19032SS | 0 | 362 | Warning
37387 | Modoc PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19031SS | 19033SS | 0 | 362 | Warning
37388 | Modoc PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19032SS |  | 0 | 362 | Warning
37389 | Modoc PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37390 | Modoc PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37393 | Modoc PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19037SS |  | 0 | 384 | Warning
37394 | Modoc PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37395 | Modoc PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19048 | 0 | 234 | Warning
37396 | Modoc PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19049 | 0 | 234 | Warning
37398 | Modoc PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37399 | Modoc PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19045SS,19053SS+20d | 0 | 240 | Warning
37400 | Modoc PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19044SS | 19046SS,19054SS+20d | 0 | 309 | Warning
37401 | Modoc PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19045SS | 19055SS+20d | 0 | 309 | Warning
37402 | Modoc PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37403 | Modoc PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19040 | 19049SS | 0 | 234 | Warning
37404 | Modoc PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19041,19048SS |  | 0 | 234 | Warning
37405 | Modoc PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19058FS+12d | 0 | 240 | Warning
37406 | Modoc PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19052SS | 0 | 321 | Warning
37407 | Modoc PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19051SS |  | 0 | 321 | Warning
37408 | Modoc PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19044SS+20d |  | 0 | 240 | Warning
37409 | Modoc PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19045SS+20d |  | 0 | 240 | Warning
37410 | Modoc PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19046SS+20d |  | 0 | 240 | Warning
37411 | Modoc PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19058SS+44d | 0 | 240 | Warning
37412 | Modoc PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37413 | Modoc PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19050FS+12d,19056SS+44d |  | 0 | 240 | Warning
37415 | Mono PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
37416 | Mono PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
37421 | Mono PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37422 | Mono PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37423 | Mono PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37424 | Mono PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37425 | Mono PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37426 | Mono PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37427 | Mono PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37428 | Mono PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37429 | Mono PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37430 | Mono PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37431 | Mono PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37432 | Mono PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37441 | Mono PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
37442 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19088SS | 0 | 414 | Warning
37443 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19087SS |  | 0 | 414 | Warning
37444 | Mono PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19090SS | 0 | 362 | Warning
37445 | Mono PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19089SS |  | 0 | 362 | Warning
37446 | Mono PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37447 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19093SS | 0 | 364 | Warning
37448 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19092SS |  | 0 | 353 | Warning
37449 | Mono PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37450 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19096SS | 0 | 300 | Warning
37451 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19095SS |  | 0 | 288 | Warning
37452 | Mono PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37453 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19099SS | 0 | 279 | Warning
37454 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19098SS |  | 0 | 268 | Warning
37455 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19101SS | 0 | 246 | Warning
37456 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19100SS |  | 0 | 246 | Warning
37457 | Mono PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37458 | Mono PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37460 | Mono PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37461 | Mono PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37462 | Mono PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37463 | Mono PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37466 | Mono PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.21 | 233 | Warning
37469 | Mono PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19112FS-1d |  | 0.2 | 233 | Warning
37472 | Mono PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19116 |  | 0.2 | 466 | Warning
37473 | Mono PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37475 | Mono PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19119FS+19d | 19121 | 0 | 405 | Warning
37476 | Mono PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19120 |  | 0 | 405 | Warning
37477 | Mono PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37478 | Mono PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19124 | 0 | 363 | Warning
37479 | Mono PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19123 | 19125FS-1d | 0 | 363 | Warning
37480 | Mono PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19124FS-1d |  | 0 | 363 | Warning
37481 | Mono PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37482 | Mono PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37483 | Mono PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
37484 | Mono PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37485 | Mono PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19131SS | 0 | 362 | Warning
37486 | Mono PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19130SS | 19132SS | 0 | 362 | Warning
37487 | Mono PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19131SS | 19133SS | 0 | 362 | Warning
37488 | Mono PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19132SS | 19134SS | 0 | 362 | Warning
37489 | Mono PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19133SS | 19135SS | 0 | 362 | Warning
37490 | Mono PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19134SS | 19136SS | 0 | 362 | Warning
37491 | Mono PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19135SS | 19137SS | 0 | 362 | Warning
37492 | Mono PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19136SS | 19138SS | 0 | 362 | Warning
37493 | Mono PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19137SS | 19139SS | 0 | 362 | Warning
37494 | Mono PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19138SS | 19140SS | 0 | 362 | Warning
37495 | Mono PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19139SS |  | 0 | 362 | Warning
37496 | Mono PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37497 | Mono PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37500 | Mono PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19144SS |  | 0 | 384 | Warning
37501 | Mono PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37502 | Mono PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19155 | 0 | 234 | Warning
37503 | Mono PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19156 | 0 | 234 | Warning
37505 | Mono PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37506 | Mono PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19152SS,19160SS+20d | 0 | 240 | Warning
37507 | Mono PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19151SS | 19153SS,19161SS+20d | 0 | 309 | Warning
37508 | Mono PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19152SS | 19162SS+20d | 0 | 309 | Warning
37509 | Mono PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37510 | Mono PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19147 | 19156SS | 0 | 234 | Warning
37511 | Mono PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19148,19155SS |  | 0 | 234 | Warning
37512 | Mono PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19165FS+12d | 0 | 240 | Warning
37513 | Mono PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19159SS | 0 | 321 | Warning
37514 | Mono PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19158SS |  | 0 | 321 | Warning
37515 | Mono PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19151SS+20d |  | 0 | 240 | Warning
37516 | Mono PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19152SS+20d |  | 0 | 240 | Warning
37517 | Mono PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19153SS+20d |  | 0 | 240 | Warning
37518 | Mono PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19165SS+44d | 0 | 240 | Warning
37519 | Mono PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37520 | Mono PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19157FS+12d,19163SS+44d |  | 0 | 240 | Warning
37522 | Monterey PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.26 | 235 | Warning
37523 | Monterey PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
37528 | Monterey PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37529 | Monterey PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37530 | Monterey PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37531 | Monterey PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37532 | Monterey PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37533 | Monterey PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37534 | Monterey PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37535 | Monterey PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37536 | Monterey PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37537 | Monterey PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37538 | Monterey PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37539 | Monterey PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37548 | Monterey PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | 445 | Warning
37549 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19195SS | 0 | 414 | Warning
37550 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19194SS |  | 0 | 414 | Warning
37551 | Monterey PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19197SS | 0 | 362 | Warning
37552 | Monterey PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19196SS |  | 0 | 362 | Warning
37553 | Monterey PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37554 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19200SS | 0 | 364 | Warning
37555 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19199SS |  | 0 | 353 | Warning
37556 | Monterey PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37557 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19203SS | 0 | 300 | Warning
37558 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19202SS |  | 0 | 288 | Warning
37559 | Monterey PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37560 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19206SS | 0 | 279 | Warning
37561 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19205SS |  | 0 | 268 | Warning
37562 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19208SS | 0 | 246 | Warning
37563 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19207SS |  | 0 | 246 | Warning
37564 | Monterey PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37565 | Monterey PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37567 | Monterey PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37568 | Monterey PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37569 | Monterey PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37570 | Monterey PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37573 | Monterey PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.23 | 233 | Warning
37576 | Monterey PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19219FS-1d |  | 0.2 | 233 | Warning
37579 | Monterey PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19223 |  | 0.2 | 466 | Warning
37580 | Monterey PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37582 | Monterey PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19226FS+19d | 19228 | 0 | 405 | Warning
37583 | Monterey PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19227 |  | 0 | 405 | Warning
37584 | Monterey PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37585 | Monterey PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19231 | 0 | 363 | Warning
37586 | Monterey PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19230 | 19232FS-1d | 0 | 363 | Warning
37587 | Monterey PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19231FS-1d |  | 0 | 363 | Warning
37588 | Monterey PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37589 | Monterey PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37590 | Monterey PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
37591 | Monterey PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37592 | Monterey PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19238SS | 0 | 362 | Warning
37593 | Monterey PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19237SS | 19239SS | 0 | 362 | Warning
37594 | Monterey PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19238SS | 19240SS | 0 | 362 | Warning
37595 | Monterey PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19239SS | 19241SS | 0 | 362 | Warning
37596 | Monterey PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19240SS | 19242SS | 0 | 362 | Warning
37597 | Monterey PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19241SS | 19243SS | 0 | 362 | Warning
37598 | Monterey PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19242SS | 19244SS | 0 | 362 | Warning
37599 | Monterey PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19243SS | 19245SS | 0 | 362 | Warning
37600 | Monterey PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19244SS | 19246SS | 0 | 362 | Warning
37601 | Monterey PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19245SS | 19247SS | 0 | 362 | Warning
37602 | Monterey PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19246SS |  | 0 | 362 | Warning
37603 | Monterey PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37604 | Monterey PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37607 | Monterey PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19251SS |  | 0 | 384 | Warning
37608 | Monterey PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37609 | Monterey PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19262 | 0 | 234 | Warning
37610 | Monterey PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19263 | 0 | 234 | Warning
37612 | Monterey PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37613 | Monterey PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19259SS,19267SS+20d | 0 | 240 | Warning
37614 | Monterey PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19258SS | 19260SS,19268SS+20d | 0 | 309 | Warning
37615 | Monterey PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19259SS | 19269SS+20d | 0 | 309 | Warning
37616 | Monterey PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37617 | Monterey PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19254 | 19263SS | 0 | 234 | Warning
37618 | Monterey PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19255,19262SS |  | 0 | 234 | Warning
37619 | Monterey PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19272FS+12d | 0 | 240 | Warning
37620 | Monterey PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19266SS | 0 | 321 | Warning
37621 | Monterey PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19265SS |  | 0 | 321 | Warning
37622 | Monterey PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19258SS+20d |  | 0 | 240 | Warning
37623 | Monterey PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19259SS+20d |  | 0 | 240 | Warning
37624 | Monterey PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19260SS+20d |  | 0 | 240 | Warning
37625 | Monterey PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19272SS+44d | 0 | 240 | Warning
37626 | Monterey PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37627 | Monterey PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19264FS+12d,19270SS+44d |  | 0 | 240 | Warning
37629 | Napa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
37630 | Napa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
37634 | Napa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
37635 | Napa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37636 | Napa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37637 | Napa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37638 | Napa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37639 | Napa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37640 | Napa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37641 | Napa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37642 | Napa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37643 | Napa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37644 | Napa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37645 | Napa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37646 | Napa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37655 | Napa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
37656 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19302SS | 0 | 414 | Warning
37657 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19301SS |  | 0 | 414 | Warning
37658 | Napa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19304SS | 0 | 362 | Warning
37659 | Napa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19303SS |  | 0 | 362 | Warning
37660 | Napa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37661 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19307SS | 0 | 364 | Warning
37662 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19306SS |  | 0 | 353 | Warning
37663 | Napa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37664 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19310SS | 0 | 300 | Warning
37665 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19309SS |  | 0 | 288 | Warning
37666 | Napa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37667 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19313SS | 0 | 279 | Warning
37668 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19312SS |  | 0 | 268 | Warning
37669 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19315SS | 0 | 246 | Warning
37670 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19314SS |  | 0 | 246 | Warning
37671 | Napa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37672 | Napa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37674 | Napa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37675 | Napa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37676 | Napa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37677 | Napa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37680 | Napa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
37683 | Napa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19326FS-1d |  | 0.2 | 233 | Warning
37686 | Napa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19330 |  | 0 | 466 | Warning
37687 | Napa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37688 | Napa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19334FS+19d | 0 | 405 | Warning
37689 | Napa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19333FS+19d | 19335 | 0 | 405 | Warning
37690 | Napa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19334 |  | 0 | 405 | Warning
37691 | Napa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37692 | Napa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19338 | 0 | 363 | Warning
37693 | Napa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19337 | 19339FS-1d | 0 | 363 | Warning
37694 | Napa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19338FS-1d |  | 0 | 363 | Warning
37695 | Napa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37696 | Napa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37697 | Napa PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
37698 | Napa PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37699 | Napa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19345SS | 0 | 486 | Warning
37700 | Napa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19344SS |  | 0 | 424 | Warning
37701 | Napa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37702 | Napa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37703 | Napa PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37704 | Napa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19350SS | 0 | 486 | Warning
37705 | Napa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19349SS | 19364SS | 0 | 466 | Warning
37706 | Napa PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37707 | Napa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37708 | Napa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37709 | Napa PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37710 | Napa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19356SS | 0 | 345 | Warning
37711 | Napa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19355SS | 19357SS,19358 | 0 | 345 | Warning
37712 | Napa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19356SS | 19358 | 0 | 345 | Warning
37713 | Napa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19356,19357 |  | 0 | 345 | Warning
37714 | Napa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37715 | Napa PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37716 | Napa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19362SS | 0 | 486 | Warning
37717 | Napa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19361SS |  | 0 | 424 | Warning
37718 | Napa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37719 | Napa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19350SS |  | 0 | 466 | Warning
37720 | Napa PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37721 | Napa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19367SS | 0 | 486 | Warning
37722 | Napa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19366SS |  | 0 | 466 | Warning
37723 | Napa PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37724 | Napa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19370SS+18d | 0 | 373 | Warning
37725 | Napa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19369SS+18d |  | 0 | 373 | Warning
37726 | Napa PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37727 | Napa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19373SS | 0 | 362 | Warning
37728 | Napa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19372SS |  | 0 | 362 | Warning
37729 | Napa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19375 | 0 | 345 | Warning
37730 | Napa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19374 |  | 0 | 345 | Warning
37731 | Napa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37732 | Napa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37733 | Napa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19379SS | 0 | 362 | Warning
37734 | Napa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19378SS | 19380SS | 0 | 362 | Warning
37735 | Napa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19379SS | 19381SS | 0 | 362 | Warning
37736 | Napa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19380SS | 19382SS | 0 | 362 | Warning
37737 | Napa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19381SS | 19383SS | 0 | 362 | Warning
37738 | Napa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19382SS | 19384SS | 0 | 362 | Warning
37739 | Napa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19383SS | 19385SS | 0 | 362 | Warning
37740 | Napa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19384SS | 19386SS | 0 | 362 | Warning
37741 | Napa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19385SS | 19387SS | 0 | 362 | Warning
37742 | Napa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19386SS | 19388SS | 0 | 362 | Warning
37743 | Napa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19387SS |  | 0 | 362 | Warning
37744 | Napa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37745 | Napa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37748 | Napa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19392SS |  | 0 | 384 | Warning
37749 | Napa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37750 | Napa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19403 | 0 | 234 | Warning
37751 | Napa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19404 | 0 | 234 | Warning
37753 | Napa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37754 | Napa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19400SS,19408SS+20d | 0 | 240 | Warning
37755 | Napa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19399SS | 19401SS,19409SS+20d | 0 | 309 | Warning
37756 | Napa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19400SS | 19410SS+20d | 0 | 309 | Warning
37757 | Napa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37758 | Napa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19395 | 19404SS | 0 | 234 | Warning
37759 | Napa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19396,19403SS |  | 0 | 234 | Warning
37760 | Napa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19413FS+12d | 0 | 240 | Warning
37761 | Napa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19407SS | 0 | 321 | Warning
37762 | Napa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19406SS |  | 0 | 321 | Warning
37763 | Napa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19399SS+20d |  | 0 | 240 | Warning
37764 | Napa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19400SS+20d |  | 0 | 240 | Warning
37765 | Napa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19401SS+20d |  | 0 | 240 | Warning
37766 | Napa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19413SS+44d | 0 | 240 | Warning
37767 | Napa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37768 | Napa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19405FS+12d,19411SS+44d |  | 0 | 240 | Warning
37770 | Nevada PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
37771 | Nevada PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
37775 | Nevada PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
37776 | Nevada PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37777 | Nevada PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37778 | Nevada PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37779 | Nevada PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37780 | Nevada PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37781 | Nevada PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37782 | Nevada PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37783 | Nevada PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37784 | Nevada PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37785 | Nevada PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37786 | Nevada PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37787 | Nevada PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37796 | Nevada PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
37797 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19443SS | 0 | 414 | Warning
37798 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19442SS |  | 0 | 414 | Warning
37799 | Nevada PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19445SS | 0 | 362 | Warning
37800 | Nevada PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19444SS |  | 0 | 362 | Warning
37801 | Nevada PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37802 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19448SS | 0 | 364 | Warning
37803 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19447SS |  | 0 | 353 | Warning
37804 | Nevada PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37805 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19451SS | 0 | 300 | Warning
37806 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19450SS |  | 0 | 288 | Warning
37807 | Nevada PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37808 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19454SS | 0 | 279 | Warning
37809 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19453SS |  | 0 | 268 | Warning
37810 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19456SS | 0 | 246 | Warning
37811 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19455SS |  | 0 | 246 | Warning
37812 | Nevada PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37813 | Nevada PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37815 | Nevada PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37816 | Nevada PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37817 | Nevada PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37818 | Nevada PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37821 | Nevada PR - OCM Activities | July 1, 2025 12:00 AM | July 17, 2026 5:00 PM | 263 | 309d |  |  | 0.24 | 309 | Warning
37826 | Nevada PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19470 |  | 0 | 466 | Warning
37827 | Nevada PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37829 | Nevada PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19473FS+19d | 19475 | 0 | 405 | Warning
37830 | Nevada PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19474 |  | 0 | 405 | Warning
37831 | Nevada PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37832 | Nevada PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19478 | 0 | 363 | Warning
37833 | Nevada PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19477 | 19479FS-1d | 0 | 363 | Warning
37834 | Nevada PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19478FS-1d |  | 0 | 363 | Warning
37835 | Nevada PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37836 | Nevada PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37837 | Nevada PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0.07 | 298 | Warning
37838 | Nevada PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0.6 | 362 | Warning
37841 | Nevada PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0.2 | 362 | Warning
37843 | Nevada PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | 466 | Warning
37844 | Nevada PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19490SS | 0.2 | 486 | Warning
37845 | Nevada PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19489SS | 19504SS | 0.2 | 466 | Warning
37846 | Nevada PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37847 | Nevada PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37848 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37849 | Nevada PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37850 | Nevada PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19496SS | 0 | 345 | Warning
37851 | Nevada PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19495SS | 19497SS,19498 | 0 | 345 | Warning
37852 | Nevada PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19496SS | 19498 | 0 | 345 | Warning
37853 | Nevada PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19496,19497 |  | 0 | 345 | Warning
37854 | Nevada PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37855 | Nevada PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37856 | Nevada PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19502SS | 0 | 486 | Warning
37857 | Nevada PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19501SS |  | 0 | 424 | Warning
37858 | Nevada PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37859 | Nevada PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19490SS |  | 0 | 466 | Warning
37860 | Nevada PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | 466 | Warning
37861 | Nevada PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19507SS | 0.2 | 486 | Warning
37862 | Nevada PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19506SS |  | 0.2 | 466 | Warning
37863 | Nevada PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37864 | Nevada PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19510SS+18d | 0 | 373 | Warning
37865 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19509SS+18d |  | 0 | 373 | Warning
37866 | Nevada PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37867 | Nevada PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19513SS | 0 | 362 | Warning
37868 | Nevada PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19512SS |  | 0 | 362 | Warning
37869 | Nevada PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19515 | 0 | 345 | Warning
37870 | Nevada PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19514 |  | 0 | 345 | Warning
37871 | Nevada PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37872 | Nevada PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
37873 | Nevada PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19519SS | 0 | 362 | Warning
37874 | Nevada PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19518SS | 19520SS | 0 | 362 | Warning
37875 | Nevada PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19519SS | 19521SS | 0 | 362 | Warning
37876 | Nevada PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19520SS | 19522SS | 0 | 362 | Warning
37877 | Nevada PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19521SS | 19523SS | 0 | 362 | Warning
37878 | Nevada PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19522SS | 19524SS | 0 | 362 | Warning
37879 | Nevada PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19523SS | 19525SS | 0 | 362 | Warning
37880 | Nevada PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19524SS | 19526SS | 0 | 362 | Warning
37881 | Nevada PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19525SS | 19527SS | 0 | 362 | Warning
37882 | Nevada PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19526SS | 19528SS | 0 | 362 | Warning
37883 | Nevada PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19527SS |  | 0 | 362 | Warning
37884 | Nevada PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
37885 | Nevada PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
37888 | Nevada PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19532SS |  | 0 | 384 | Warning
37889 | Nevada PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
37890 | Nevada PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19543 | 0 | 234 | Warning
37891 | Nevada PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19544 | 0 | 234 | Warning
37893 | Nevada PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
37894 | Nevada PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19540SS,19548SS+20d | 0 | 240 | Warning
37895 | Nevada PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19539SS | 19541SS,19549SS+20d | 0 | 309 | Warning
37896 | Nevada PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19540SS | 19550SS+20d | 0 | 309 | Warning
37897 | Nevada PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
37898 | Nevada PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19535 | 19544SS | 0 | 234 | Warning
37899 | Nevada PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19536,19543SS |  | 0 | 234 | Warning
37900 | Nevada PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19553FS+12d | 0 | 240 | Warning
37901 | Nevada PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19547SS | 0 | 321 | Warning
37902 | Nevada PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19546SS |  | 0 | 321 | Warning
37903 | Nevada PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19539SS+20d |  | 0 | 240 | Warning
37904 | Nevada PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19540SS+20d |  | 0 | 240 | Warning
37905 | Nevada PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19541SS+20d |  | 0 | 240 | Warning
37906 | Nevada PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19553SS+44d | 0 | 240 | Warning
37907 | Nevada PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
37908 | Nevada PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19545FS+12d,19551SS+44d |  | 0 | 240 | Warning
37910 | Orange PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
37911 | Orange PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
37915 | Orange PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
37916 | Orange PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
37917 | Orange PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
37918 | Orange PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
37919 | Orange PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
37920 | Orange PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
37921 | Orange PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
37922 | Orange PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
37923 | Orange PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
37924 | Orange PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
37925 | Orange PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
37926 | Orange PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37927 | Orange PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
37936 | Orange PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
37937 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19583SS | 0 | 414 | Warning
37938 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19582SS |  | 0 | 414 | Warning
37939 | Orange PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19585SS | 0 | 362 | Warning
37940 | Orange PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19584SS |  | 0 | 362 | Warning
37941 | Orange PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
37942 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19588SS | 0 | 364 | Warning
37943 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19587SS |  | 0 | 353 | Warning
37944 | Orange PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
37945 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19591SS | 0 | 300 | Warning
37946 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19590SS |  | 0 | 288 | Warning
37947 | Orange PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
37948 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19594SS | 0 | 279 | Warning
37949 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19593SS |  | 0 | 268 | Warning
37950 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19596SS | 0 | 246 | Warning
37951 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19595SS |  | 0 | 246 | Warning
37952 | Orange PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
37953 | Orange PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
37955 | Orange PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
37956 | Orange PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
37957 | Orange PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
37958 | Orange PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
37961 | Orange PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
37964 | Orange PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19607FS-1d |  | 0.2 | 233 | Warning
37967 | Orange PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19611 |  | 0 | 466 | Warning
37968 | Orange PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
37969 | Orange PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19615FS+19d | 0 | 405 | Warning
37970 | Orange PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19614FS+19d | 19616 | 0 | 405 | Warning
37971 | Orange PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19615 |  | 0 | 405 | Warning
37972 | Orange PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
37973 | Orange PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19619 | 0 | 363 | Warning
37974 | Orange PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19618 | 19620FS-1d | 0 | 363 | Warning
37975 | Orange PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19619FS-1d |  | 0 | 363 | Warning
37976 | Orange PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
37977 | Orange PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
37978 | Orange PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
37979 | Orange PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37980 | Orange PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19626SS | 0 | 486 | Warning
37981 | Orange PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19625SS |  | 0 | 424 | Warning
37982 | Orange PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
37983 | Orange PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37984 | Orange PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
37985 | Orange PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19631SS | 0 | 486 | Warning
37986 | Orange PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19630SS | 19645SS | 0 | 466 | Warning
37987 | Orange PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
37988 | Orange PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
37989 | Orange PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
37990 | Orange PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
37991 | Orange PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19637SS | 0 | 345 | Warning
37992 | Orange PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19636SS | 19638SS,19639 | 0 | 345 | Warning
37993 | Orange PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19637SS | 19639 | 0 | 345 | Warning
37994 | Orange PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19637,19638 |  | 0 | 345 | Warning
37995 | Orange PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
37996 | Orange PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
37997 | Orange PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19643SS | 0 | 486 | Warning
37998 | Orange PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19642SS |  | 0 | 424 | Warning
37999 | Orange PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38000 | Orange PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19631SS |  | 0 | 466 | Warning
38001 | Orange PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38002 | Orange PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19648SS | 0 | 486 | Warning
38003 | Orange PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19647SS |  | 0 | 466 | Warning
38004 | Orange PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38005 | Orange PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19651SS+18d | 0 | 373 | Warning
38006 | Orange PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19650SS+18d |  | 0 | 373 | Warning
38007 | Orange PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38008 | Orange PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19654SS | 0 | 362 | Warning
38009 | Orange PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19653SS |  | 0 | 362 | Warning
38010 | Orange PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19656 | 0 | 345 | Warning
38011 | Orange PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19655 |  | 0 | 345 | Warning
38012 | Orange PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38013 | Orange PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38014 | Orange PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19660SS | 0 | 362 | Warning
38015 | Orange PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19659SS | 19661SS | 0 | 362 | Warning
38016 | Orange PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19660SS | 19662SS | 0 | 362 | Warning
38017 | Orange PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19661SS | 19663SS | 0 | 362 | Warning
38018 | Orange PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19662SS | 19664SS | 0 | 362 | Warning
38019 | Orange PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19663SS | 19665SS | 0 | 362 | Warning
38020 | Orange PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19664SS | 19666SS | 0 | 362 | Warning
38021 | Orange PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19665SS | 19667SS | 0 | 362 | Warning
38022 | Orange PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19666SS | 19668SS | 0 | 362 | Warning
38023 | Orange PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19667SS | 19669SS | 0 | 362 | Warning
38024 | Orange PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19668SS |  | 0 | 362 | Warning
38025 | Orange PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38026 | Orange PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38029 | Orange PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19673SS |  | 0 | 384 | Warning
38030 | Orange PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38031 | Orange PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19684 | 0 | 234 | Warning
38032 | Orange PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19685 | 0 | 234 | Warning
38034 | Orange PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38035 | Orange PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19681SS,19689SS+20d | 0 | 240 | Warning
38036 | Orange PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19680SS | 19682SS,19690SS+20d | 0 | 309 | Warning
38037 | Orange PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19681SS | 19691SS+20d | 0 | 309 | Warning
38038 | Orange PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38039 | Orange PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19676 | 19685SS | 0 | 234 | Warning
38040 | Orange PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19677,19684SS |  | 0 | 234 | Warning
38041 | Orange PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19694FS+12d | 0 | 240 | Warning
38042 | Orange PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19688SS | 0 | 321 | Warning
38043 | Orange PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19687SS |  | 0 | 321 | Warning
38044 | Orange PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19680SS+20d |  | 0 | 240 | Warning
38045 | Orange PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19681SS+20d |  | 0 | 240 | Warning
38046 | Orange PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19682SS+20d |  | 0 | 240 | Warning
38047 | Orange PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19694SS+44d | 0 | 240 | Warning
38048 | Orange PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38049 | Orange PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19686FS+12d,19692SS+44d |  | 0 | 240 | Warning
38051 | Placer PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38052 | Placer PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38056 | Placer PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38057 | Placer PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38058 | Placer PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38059 | Placer PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38060 | Placer PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38061 | Placer PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38062 | Placer PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38063 | Placer PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38064 | Placer PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38065 | Placer PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38066 | Placer PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38067 | Placer PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38068 | Placer PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38077 | Placer PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38078 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19724SS | 0 | 414 | Warning
38079 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19723SS |  | 0 | 414 | Warning
38080 | Placer PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19726SS | 0 | 362 | Warning
38081 | Placer PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19725SS |  | 0 | 362 | Warning
38082 | Placer PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
38083 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19729SS | 0 | 364 | Warning
38084 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19728SS |  | 0 | 353 | Warning
38085 | Placer PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
38086 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19732SS | 0 | 300 | Warning
38087 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19731SS |  | 0 | 288 | Warning
38088 | Placer PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
38089 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19735SS | 0 | 279 | Warning
38090 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19734SS |  | 0 | 268 | Warning
38091 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19737SS | 0 | 246 | Warning
38092 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19736SS |  | 0 | 246 | Warning
38093 | Placer PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38094 | Placer PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
38096 | Placer PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
38097 | Placer PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38098 | Placer PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38099 | Placer PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
38102 | Placer PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
38105 | Placer PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19748FS-1d |  | 0.2 | 233 | Warning
38108 | Placer PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19752 |  | 0 | 466 | Warning
38109 | Placer PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38110 | Placer PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19756FS+19d | 0.2 | 405 | Warning
38111 | Placer PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19755FS+19d | 19757 | 0 | 405 | Warning
38112 | Placer PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19756 |  | 0 | 405 | Warning
38113 | Placer PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38114 | Placer PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19760 | 0 | 363 | Warning
38115 | Placer PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19759 | 19761FS-1d | 0 | 363 | Warning
38116 | Placer PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19760FS-1d |  | 0 | 363 | Warning
38117 | Placer PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38118 | Placer PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38119 | Placer PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0.04 | 298 | Warning
38120 | Placer PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38121 | Placer PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19767SS | 0 | 486 | Warning
38122 | Placer PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19766SS |  | 0 | 424 | Warning
38123 | Placer PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38124 | Placer PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | 466 | Warning
38126 | Placer PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19772SS | 0 | 486 | Warning
38128 | Placer PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0.3 | 373 | Warning
38130 | Placer PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38131 | Placer PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0.1 | 298 | Warning
38133 | Placer PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19777SS | 19779SS,19780 | 0 | 345 | Warning
38134 | Placer PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19778SS | 19780 | 0 | 345 | Warning
38135 | Placer PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19778,19779 |  | 0 | 345 | Warning
38136 | Placer PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38137 | Placer PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38138 | Placer PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19784SS | 0 | 486 | Warning
38139 | Placer PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19783SS |  | 0 | 424 | Warning
38140 | Placer PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38141 | Placer PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19772SS |  | 0.2 | 466 | Warning
38142 | Placer PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | 466 | Warning
38143 | Placer PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19789SS | 0.2 | 486 | Warning
38144 | Placer PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19788SS |  | 0.2 | 466 | Warning
38145 | Placer PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38146 | Placer PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19792SS+18d | 0 | 373 | Warning
38147 | Placer PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19791SS+18d |  | 0 | 373 | Warning
38148 | Placer PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38149 | Placer PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19795SS | 0 | 362 | Warning
38150 | Placer PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19794SS |  | 0 | 362 | Warning
38151 | Placer PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19797 | 0 | 345 | Warning
38152 | Placer PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19796 |  | 0 | 345 | Warning
38153 | Placer PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38154 | Placer PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38155 | Placer PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19801SS | 0 | 362 | Warning
38156 | Placer PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19800SS | 19802SS | 0 | 362 | Warning
38157 | Placer PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19801SS | 19803SS | 0 | 362 | Warning
38158 | Placer PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19802SS | 19804SS | 0 | 362 | Warning
38159 | Placer PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19803SS | 19805SS | 0 | 362 | Warning
38160 | Placer PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19804SS | 19806SS | 0 | 362 | Warning
38161 | Placer PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19805SS | 19807SS | 0 | 362 | Warning
38162 | Placer PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19806SS | 19808SS | 0 | 362 | Warning
38163 | Placer PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19807SS | 19809SS | 0 | 362 | Warning
38164 | Placer PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19808SS | 19810SS | 0 | 362 | Warning
38165 | Placer PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19809SS |  | 0 | 362 | Warning
38166 | Placer PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38167 | Placer PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38170 | Placer PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19814SS |  | 0 | 384 | Warning
38171 | Placer PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38172 | Placer PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19825 | 0 | 234 | Warning
38173 | Placer PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19826 | 0 | 234 | Warning
38175 | Placer PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38176 | Placer PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19822SS,19830SS+20d | 0 | 240 | Warning
38177 | Placer PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19821SS | 19823SS,19831SS+20d | 0 | 309 | Warning
38178 | Placer PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19822SS | 19832SS+20d | 0 | 309 | Warning
38179 | Placer PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38180 | Placer PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19817 | 19826SS | 0 | 234 | Warning
38181 | Placer PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19818,19825SS |  | 0 | 234 | Warning
38182 | Placer PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19835FS+12d | 0 | 240 | Warning
38183 | Placer PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19829SS | 0 | 321 | Warning
38184 | Placer PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19828SS |  | 0 | 321 | Warning
38185 | Placer PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19821SS+20d |  | 0 | 240 | Warning
38186 | Placer PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19822SS+20d |  | 0 | 240 | Warning
38187 | Placer PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19823SS+20d |  | 0 | 240 | Warning
38188 | Placer PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19835SS+44d | 0 | 240 | Warning
38189 | Placer PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38190 | Placer PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19827FS+12d,19833SS+44d |  | 0 | 240 | Warning
38192 | Plumas PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38193 | Plumas PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38197 | Plumas PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38198 | Plumas PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38199 | Plumas PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38200 | Plumas PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38201 | Plumas PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38202 | Plumas PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38203 | Plumas PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38204 | Plumas PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38205 | Plumas PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38206 | Plumas PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38207 | Plumas PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38208 | Plumas PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38209 | Plumas PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38218 | Plumas PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38219 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19865SS | 0 | 414 | Warning
38220 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19864SS |  | 0 | 414 | Warning
38221 | Plumas PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19867SS | 0 | 362 | Warning
38222 | Plumas PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19866SS |  | 0 | 362 | Warning
38223 | Plumas PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
38224 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19870SS | 0 | 364 | Warning
38225 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19869SS |  | 0 | 353 | Warning
38226 | Plumas PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
38227 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19873SS | 0 | 300 | Warning
38228 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 19872SS |  | 0 | 288 | Warning
38229 | Plumas PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
38230 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19876SS | 0 | 279 | Warning
38231 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19875SS |  | 0 | 268 | Warning
38232 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19878SS | 0 | 246 | Warning
38233 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19877SS |  | 0 | 246 | Warning
38234 | Plumas PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38235 | Plumas PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
38237 | Plumas PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
38238 | Plumas PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38239 | Plumas PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38240 | Plumas PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
38243 | Plumas PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
38246 | Plumas PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19889FS-1d |  | 0.2 | 233 | Warning
38249 | Plumas PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19893 |  | 0 | 466 | Warning
38250 | Plumas PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38251 | Plumas PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19897FS+19d | 0 | 405 | Warning
38252 | Plumas PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19896FS+19d | 19898 | 0 | 405 | Warning
38253 | Plumas PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 19897 |  | 0 | 405 | Warning
38254 | Plumas PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38255 | Plumas PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19901 | 0 | 363 | Warning
38256 | Plumas PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19900 | 19902FS-1d | 0 | 363 | Warning
38257 | Plumas PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19901FS-1d |  | 0 | 363 | Warning
38258 | Plumas PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38259 | Plumas PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38260 | Plumas PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
38261 | Plumas PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38262 | Plumas PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19908SS | 0 | 486 | Warning
38263 | Plumas PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19907SS |  | 0 | 424 | Warning
38264 | Plumas PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38265 | Plumas PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38266 | Plumas PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38267 | Plumas PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19913SS | 0 | 486 | Warning
38268 | Plumas PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19912SS | 19927SS | 0 | 466 | Warning
38269 | Plumas PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38270 | Plumas PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
38271 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38272 | Plumas PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38273 | Plumas PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19919SS | 0 | 345 | Warning
38274 | Plumas PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19918SS | 19920SS,19921 | 0 | 345 | Warning
38275 | Plumas PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19919SS | 19921 | 0 | 345 | Warning
38276 | Plumas PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19919,19920 |  | 0 | 345 | Warning
38277 | Plumas PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38278 | Plumas PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38279 | Plumas PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19925SS | 0 | 486 | Warning
38280 | Plumas PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19924SS |  | 0 | 424 | Warning
38281 | Plumas PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38282 | Plumas PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19913SS |  | 0 | 466 | Warning
38283 | Plumas PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38284 | Plumas PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19930SS | 0 | 486 | Warning
38285 | Plumas PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19929SS |  | 0 | 466 | Warning
38286 | Plumas PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38287 | Plumas PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19933SS+18d | 0 | 373 | Warning
38288 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19932SS+18d |  | 0 | 373 | Warning
38289 | Plumas PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38290 | Plumas PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19936SS | 0 | 362 | Warning
38291 | Plumas PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19935SS |  | 0 | 362 | Warning
38292 | Plumas PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19938 | 0 | 345 | Warning
38293 | Plumas PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19937 |  | 0 | 345 | Warning
38294 | Plumas PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38295 | Plumas PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38296 | Plumas PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19942SS | 0 | 362 | Warning
38297 | Plumas PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19941SS | 19943SS | 0 | 362 | Warning
38298 | Plumas PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19942SS | 19944SS | 0 | 362 | Warning
38299 | Plumas PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19943SS | 19945SS | 0 | 362 | Warning
38300 | Plumas PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19944SS | 19946SS | 0 | 362 | Warning
38301 | Plumas PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19945SS | 19947SS | 0 | 362 | Warning
38302 | Plumas PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19946SS | 19948SS | 0 | 362 | Warning
38303 | Plumas PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19947SS | 19949SS | 0 | 362 | Warning
38304 | Plumas PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19948SS | 19950SS | 0 | 362 | Warning
38305 | Plumas PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19949SS | 19951SS | 0 | 362 | Warning
38306 | Plumas PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19950SS |  | 0 | 362 | Warning
38307 | Plumas PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38308 | Plumas PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38311 | Plumas PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19955SS |  | 0 | 384 | Warning
38312 | Plumas PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38313 | Plumas PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19966 | 0 | 234 | Warning
38314 | Plumas PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19967 | 0 | 234 | Warning
38316 | Plumas PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38317 | Plumas PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19963SS,19971SS+20d | 0 | 240 | Warning
38318 | Plumas PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19962SS | 19964SS,19972SS+20d | 0 | 309 | Warning
38319 | Plumas PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19963SS | 19973SS+20d | 0 | 309 | Warning
38320 | Plumas PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38321 | Plumas PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19958 | 19967SS | 0 | 234 | Warning
38322 | Plumas PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19959,19966SS |  | 0 | 234 | Warning
38323 | Plumas PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19976FS+12d | 0 | 240 | Warning
38324 | Plumas PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19970SS | 0 | 321 | Warning
38325 | Plumas PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19969SS |  | 0 | 321 | Warning
38326 | Plumas PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19962SS+20d |  | 0 | 240 | Warning
38327 | Plumas PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19963SS+20d |  | 0 | 240 | Warning
38328 | Plumas PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 19964SS+20d |  | 0 | 240 | Warning
38329 | Plumas PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19976SS+44d | 0 | 240 | Warning
38330 | Plumas PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38331 | Plumas PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 19968FS+12d,19974SS+44d |  | 0 | 240 | Warning
38333 | Riverside PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38334 | Riverside PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38338 | Riverside PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38339 | Riverside PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38340 | Riverside PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38341 | Riverside PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38342 | Riverside PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38343 | Riverside PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38344 | Riverside PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38345 | Riverside PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38346 | Riverside PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38347 | Riverside PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38348 | Riverside PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38349 | Riverside PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38350 | Riverside PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38359 | Riverside PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38360 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20006SS | 0 | 414 | Warning
38361 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20005SS |  | 0 | 414 | Warning
38362 | Riverside PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20008SS | 0 | 362 | Warning
38363 | Riverside PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20007SS |  | 0 | 362 | Warning
38364 | Riverside PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 20011SS,20010SS | 0 | 342 | Warning
38365 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 20009SS |  | 0 | 385 | Warning
38366 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 20009SS |  | 0 | 371 | Warning
38367 | Riverside PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
38368 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 20014SS | 0 | 332 | Warning
38369 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 20013SS |  | 0 | 332 | Warning
38370 | Riverside PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
38371 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 20017SS | 0 | 311 | Warning
38372 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 20016SS |  | 0 | 311 | Warning
38373 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 20019SS | 0 | 289 | Warning
38374 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 20018SS |  | 0 | 289 | Warning
38375 | Riverside PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
38376 | Riverside PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
38377 | Riverside PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
38378 | Riverside PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
38379 | Riverside PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38380 | Riverside PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38381 | Riverside PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
38382 | Riverside PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
38383 | Riverside PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.2 | 277 | Warning
38386 | Riverside PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 20029FS-1d |  | 0.2 | 277 | Warning
38389 | Riverside PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20033 |  | 0 | 466 | Warning
38390 | Riverside PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38391 | Riverside PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20037FS+19d | 0.2 | 405 | Warning
38392 | Riverside PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20036FS+19d | 20038 | 0 | 405 | Warning
38393 | Riverside PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20037 |  | 0 | 405 | Warning
38394 | Riverside PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38395 | Riverside PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20041 | 0 | 363 | Warning
38396 | Riverside PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20040 | 20042FS-1d | 0 | 363 | Warning
38397 | Riverside PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20041FS-1d |  | 0 | 363 | Warning
38398 | Riverside PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38399 | Riverside PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38400 | Riverside PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
38401 | Riverside PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38402 | Riverside PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20048SS | 0 | 486 | Warning
38403 | Riverside PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20047SS |  | 0 | 424 | Warning
38404 | Riverside PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38405 | Riverside PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38406 | Riverside PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38407 | Riverside PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20053SS | 0 | 486 | Warning
38408 | Riverside PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20052SS | 20067SS | 0 | 466 | Warning
38409 | Riverside PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38410 | Riverside PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
38411 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38412 | Riverside PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38413 | Riverside PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20059SS | 0 | 345 | Warning
38414 | Riverside PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20058SS | 20060SS,20061 | 0 | 345 | Warning
38415 | Riverside PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20059SS | 20061 | 0 | 345 | Warning
38416 | Riverside PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20059,20060 |  | 0 | 345 | Warning
38417 | Riverside PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38418 | Riverside PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38419 | Riverside PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20065SS | 0 | 486 | Warning
38420 | Riverside PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20064SS |  | 0 | 424 | Warning
38421 | Riverside PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38422 | Riverside PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20053SS |  | 0 | 466 | Warning
38423 | Riverside PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38424 | Riverside PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20070SS | 0 | 486 | Warning
38425 | Riverside PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20069SS |  | 0 | 466 | Warning
38426 | Riverside PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38427 | Riverside PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20073SS+18d | 0 | 373 | Warning
38428 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20072SS+18d |  | 0 | 373 | Warning
38429 | Riverside PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38430 | Riverside PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20076SS | 0 | 362 | Warning
38431 | Riverside PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20075SS |  | 0 | 362 | Warning
38432 | Riverside PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20078 | 0 | 345 | Warning
38433 | Riverside PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20077 |  | 0 | 345 | Warning
38434 | Riverside PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38435 | Riverside PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38436 | Riverside PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20082SS | 0 | 362 | Warning
38437 | Riverside PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20081SS | 20083SS | 0 | 362 | Warning
38438 | Riverside PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20082SS | 20084SS | 0 | 362 | Warning
38439 | Riverside PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20083SS | 20085SS | 0 | 362 | Warning
38440 | Riverside PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20084SS | 20086SS | 0 | 362 | Warning
38441 | Riverside PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20085SS | 20087SS | 0 | 362 | Warning
38442 | Riverside PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20086SS | 20088SS | 0 | 362 | Warning
38443 | Riverside PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20087SS | 20089SS | 0 | 362 | Warning
38444 | Riverside PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20088SS | 20090SS | 0 | 362 | Warning
38445 | Riverside PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20089SS | 20091SS | 0 | 362 | Warning
38446 | Riverside PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20090SS |  | 0 | 362 | Warning
38447 | Riverside PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
38448 | Riverside PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
38451 | Riverside PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20095SS |  | 0 | 384 | Warning
38452 | Riverside PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38453 | Riverside PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20106 | 0 | 273 | Warning
38454 | Riverside PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20107 | 0 | 273 | Warning
38456 | Riverside PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38457 | Riverside PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 20103SS,20111SS+20d | 0 | 299 | Warning
38458 | Riverside PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 20102SS | 20104SS,20112SS+20d | 0 | 299 | Warning
38459 | Riverside PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 20103SS | 20113SS+20d | 0 | 299 | Warning
38460 | Riverside PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38461 | Riverside PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20098 | 20107SS | 0 | 273 | Warning
38462 | Riverside PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20099,20106SS |  | 0 | 273 | Warning
38463 | Riverside PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 20116FS+12d | 0 | 279 | Warning
38464 | Riverside PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20110SS | 0 | 321 | Warning
38465 | Riverside PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20109SS |  | 0 | 321 | Warning
38466 | Riverside PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20102SS+20d |  | 0 | 299 | Warning
38467 | Riverside PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20103SS+20d |  | 0 | 299 | Warning
38468 | Riverside PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20104SS+20d |  | 0 | 299 | Warning
38469 | Riverside PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 20116SS+44d | 0 | 279 | Warning
38470 | Riverside PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38471 | Riverside PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 20108FS+12d,20114SS+44d |  | 0 | 279 | Warning
38473 | Sacramento PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38474 | Sacramento PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38478 | Sacramento PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38479 | Sacramento PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38480 | Sacramento PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38481 | Sacramento PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38482 | Sacramento PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38483 | Sacramento PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38484 | Sacramento PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38485 | Sacramento PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38486 | Sacramento PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38487 | Sacramento PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38488 | Sacramento PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38489 | Sacramento PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38490 | Sacramento PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38499 | Sacramento PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38500 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20146SS | 0 | 414 | Warning
38501 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20145SS |  | 0 | 414 | Warning
38502 | Sacramento PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20148SS | 0 | 362 | Warning
38503 | Sacramento PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20147SS |  | 0 | 362 | Warning
38504 | Sacramento PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
38505 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20151SS | 0 | 364 | Warning
38506 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20150SS |  | 0 | 353 | Warning
38507 | Sacramento PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
38508 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20154SS | 0 | 300 | Warning
38509 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20153SS |  | 0 | 288 | Warning
38510 | Sacramento PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
38511 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20157SS | 0 | 279 | Warning
38512 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20156SS |  | 0 | 268 | Warning
38513 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20159SS | 0 | 246 | Warning
38514 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20158SS |  | 0 | 246 | Warning
38515 | Sacramento PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38516 | Sacramento PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
38518 | Sacramento PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
38519 | Sacramento PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38520 | Sacramento PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38521 | Sacramento PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
38524 | Sacramento PR - OCM Activities | July 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.25 | 233 | Warning
38527 | Sacramento PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20170FS-1d |  | 0.2 | 233 | Warning
38531 | Sacramento PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38532 | Sacramento PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20178FS+19d | 0 | 405 | Warning
38533 | Sacramento PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20177FS+19d | 20179 | 0 | 405 | Warning
38534 | Sacramento PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20178 |  | 0 | 405 | Warning
38535 | Sacramento PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38536 | Sacramento PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20182 | 0 | 363 | Warning
38537 | Sacramento PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20181 | 20183FS-1d | 0 | 363 | Warning
38538 | Sacramento PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20182FS-1d |  | 0 | 363 | Warning
38539 | Sacramento PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38540 | Sacramento PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38541 | Sacramento PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
38542 | Sacramento PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38543 | Sacramento PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20189SS | 0 | 486 | Warning
38544 | Sacramento PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20188SS |  | 0 | 424 | Warning
38545 | Sacramento PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38546 | Sacramento PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38547 | Sacramento PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38548 | Sacramento PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20194SS | 0 | 486 | Warning
38549 | Sacramento PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20193SS | 20208SS | 0 | 466 | Warning
38550 | Sacramento PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38551 | Sacramento PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
38552 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38553 | Sacramento PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38554 | Sacramento PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20200SS | 0 | 345 | Warning
38555 | Sacramento PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20199SS | 20201SS,20202 | 0 | 345 | Warning
38556 | Sacramento PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20200SS | 20202 | 0 | 345 | Warning
38557 | Sacramento PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20200,20201 |  | 0 | 345 | Warning
38558 | Sacramento PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38559 | Sacramento PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38560 | Sacramento PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20206SS | 0 | 486 | Warning
38561 | Sacramento PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20205SS |  | 0 | 424 | Warning
38562 | Sacramento PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38563 | Sacramento PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20194SS |  | 0 | 466 | Warning
38564 | Sacramento PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38565 | Sacramento PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20211SS | 0 | 486 | Warning
38566 | Sacramento PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20210SS |  | 0 | 466 | Warning
38567 | Sacramento PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38568 | Sacramento PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20214SS+18d | 0 | 373 | Warning
38569 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20213SS+18d |  | 0 | 373 | Warning
38570 | Sacramento PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38571 | Sacramento PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20217SS | 0 | 362 | Warning
38572 | Sacramento PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20216SS |  | 0 | 362 | Warning
38573 | Sacramento PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20219 | 0 | 345 | Warning
38574 | Sacramento PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20218 |  | 0 | 345 | Warning
38575 | Sacramento PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38576 | Sacramento PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38577 | Sacramento PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20223SS | 0 | 362 | Warning
38578 | Sacramento PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20222SS | 20224SS | 0 | 362 | Warning
38579 | Sacramento PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20223SS | 20225SS | 0 | 362 | Warning
38580 | Sacramento PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20224SS | 20226SS | 0 | 362 | Warning
38581 | Sacramento PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20225SS | 20227SS | 0 | 362 | Warning
38582 | Sacramento PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20226SS | 20228SS | 0 | 362 | Warning
38583 | Sacramento PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20227SS | 20229SS | 0 | 362 | Warning
38584 | Sacramento PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20228SS | 20230SS | 0 | 362 | Warning
38585 | Sacramento PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20229SS | 20231SS | 0 | 362 | Warning
38586 | Sacramento PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20230SS | 20232SS | 0 | 362 | Warning
38587 | Sacramento PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20231SS |  | 0 | 362 | Warning
38588 | Sacramento PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38589 | Sacramento PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38592 | Sacramento PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20236SS |  | 0 | 384 | Warning
38593 | Sacramento PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38594 | Sacramento PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20247 | 0 | 234 | Warning
38595 | Sacramento PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20248 | 0 | 234 | Warning
38597 | Sacramento PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38598 | Sacramento PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20244SS,20252SS+20d | 0 | 240 | Warning
38599 | Sacramento PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20243SS | 20245SS,20253SS+20d | 0 | 309 | Warning
38600 | Sacramento PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20244SS | 20254SS+20d | 0 | 309 | Warning
38601 | Sacramento PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38602 | Sacramento PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20239 | 20248SS | 0 | 234 | Warning
38603 | Sacramento PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20240,20247SS |  | 0 | 234 | Warning
38604 | Sacramento PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20257FS+12d | 0 | 240 | Warning
38605 | Sacramento PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20251SS | 0 | 321 | Warning
38606 | Sacramento PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20250SS |  | 0 | 321 | Warning
38607 | Sacramento PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20243SS+20d |  | 0 | 240 | Warning
38608 | Sacramento PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20244SS+20d |  | 0 | 240 | Warning
38609 | Sacramento PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20245SS+20d |  | 0 | 240 | Warning
38610 | Sacramento PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20257SS+44d | 0 | 240 | Warning
38611 | Sacramento PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38612 | Sacramento PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 20249FS+12d,20255SS+44d |  | 0 | 240 | Warning
38614 | San Benito PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38615 | San Benito PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38619 | San Benito PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38620 | San Benito PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38621 | San Benito PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38622 | San Benito PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38623 | San Benito PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38624 | San Benito PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38625 | San Benito PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38626 | San Benito PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38627 | San Benito PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38628 | San Benito PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38629 | San Benito PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38630 | San Benito PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38631 | San Benito PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38640 | San Benito PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38641 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20287SS | 0 | 414 | Warning
38642 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20286SS |  | 0 | 414 | Warning
38643 | San Benito PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20289SS | 0 | 362 | Warning
38644 | San Benito PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20288SS |  | 0 | 362 | Warning
38645 | San Benito PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
38646 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20292SS | 0 | 364 | Warning
38647 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20291SS |  | 0 | 353 | Warning
38648 | San Benito PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
38649 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20295SS | 0 | 300 | Warning
38650 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20294SS |  | 0 | 288 | Warning
38651 | San Benito PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
38652 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20298SS | 0 | 279 | Warning
38653 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20297SS |  | 0 | 268 | Warning
38654 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20300SS | 0 | 246 | Warning
38655 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20299SS |  | 0 | 246 | Warning
38656 | San Benito PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38657 | San Benito PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
38659 | San Benito PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
38660 | San Benito PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38661 | San Benito PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38662 | San Benito PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
38665 | San Benito PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
38668 | San Benito PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20311FS-1d |  | 0.2 | 233 | Warning
38671 | San Benito PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20315 |  | 0 | 466 | Warning
38672 | San Benito PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38673 | San Benito PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20319FS+19d | 0 | 405 | Warning
38674 | San Benito PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20318FS+19d | 20320 | 0 | 405 | Warning
38675 | San Benito PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20319 |  | 0 | 405 | Warning
38676 | San Benito PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38677 | San Benito PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20323 | 0 | 363 | Warning
38678 | San Benito PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20322 | 20324FS-1d | 0 | 363 | Warning
38679 | San Benito PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20323FS-1d |  | 0 | 363 | Warning
38680 | San Benito PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38681 | San Benito PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38682 | San Benito PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
38683 | San Benito PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38684 | San Benito PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20330SS | 0 | 362 | Warning
38685 | San Benito PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20329SS | 20331SS | 0 | 362 | Warning
38686 | San Benito PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20330SS | 20332SS | 0 | 362 | Warning
38687 | San Benito PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20331SS | 20333SS | 0 | 362 | Warning
38688 | San Benito PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20332SS | 20334SS | 0 | 362 | Warning
38689 | San Benito PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20333SS | 20335SS | 0 | 362 | Warning
38690 | San Benito PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20334SS | 20336SS | 0 | 362 | Warning
38691 | San Benito PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20335SS | 20337SS | 0 | 362 | Warning
38692 | San Benito PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20336SS | 20338SS | 0 | 362 | Warning
38693 | San Benito PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20337SS | 20339SS | 0 | 362 | Warning
38694 | San Benito PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20338SS |  | 0 | 362 | Warning
38695 | San Benito PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38696 | San Benito PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38699 | San Benito PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20343SS |  | 0 | 384 | Warning
38700 | San Benito PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38701 | San Benito PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20354 | 0 | 234 | Warning
38702 | San Benito PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20355 | 0 | 234 | Warning
38704 | San Benito PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38705 | San Benito PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20351SS,20359SS+20d | 0 | 240 | Warning
38706 | San Benito PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20350SS | 20352SS,20360SS+20d | 0 | 309 | Warning
38707 | San Benito PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20351SS | 20361SS+20d | 0 | 309 | Warning
38708 | San Benito PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38709 | San Benito PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20346 | 20355SS | 0 | 234 | Warning
38710 | San Benito PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20347,20354SS |  | 0 | 234 | Warning
38711 | San Benito PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20364FS+12d | 0 | 240 | Warning
38712 | San Benito PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20358SS | 0 | 321 | Warning
38713 | San Benito PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20357SS |  | 0 | 321 | Warning
38714 | San Benito PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20350SS+20d |  | 0 | 240 | Warning
38715 | San Benito PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20351SS+20d |  | 0 | 240 | Warning
38716 | San Benito PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20352SS+20d |  | 0 | 240 | Warning
38717 | San Benito PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20364SS+44d | 0 | 240 | Warning
38718 | San Benito PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38719 | San Benito PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 20356FS+12d,20362SS+44d |  | 0 | 240 | Warning
38721 | San Bernardino PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38722 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38726 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38727 | San Bernardino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38728 | San Bernardino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38729 | San Bernardino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38730 | San Bernardino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38731 | San Bernardino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38732 | San Bernardino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38733 | San Bernardino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38734 | San Bernardino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38735 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38736 | San Bernardino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38737 | San Bernardino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38738 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38747 | San Bernardino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38748 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20394SS | 0 | 414 | Warning
38749 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20393SS |  | 0 | 414 | Warning
38750 | San Bernardino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20396SS | 0 | 362 | Warning
38751 | San Bernardino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20395SS |  | 0 | 362 | Warning
38752 | San Bernardino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
38753 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20399SS | 0 | 364 | Warning
38754 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20398SS |  | 0 | 353 | Warning
38755 | San Bernardino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
38756 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20402SS | 0 | 300 | Warning
38757 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20401SS |  | 0 | 288 | Warning
38758 | San Bernardino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
38759 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20405SS | 0 | 279 | Warning
38760 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20404SS |  | 0 | 268 | Warning
38761 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20407SS | 0 | 246 | Warning
38762 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20406SS |  | 0 | 246 | Warning
38763 | San Bernardino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38764 | San Bernardino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
38766 | San Bernardino PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
38767 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38768 | San Bernardino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38769 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
38772 | San Bernardino PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
38775 | San Bernardino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20418FS-1d |  | 0 | 233 | Warning
38778 | San Bernardino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20422 |  | 0 | 466 | Warning
38779 | San Bernardino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38780 | San Bernardino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if appli | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20426FS+19d | 0 | 405 | Warning
38781 | San Bernardino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20425FS+19d | 20427 | 0 | 405 | Warning
38782 | San Bernardino PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20426 |  | 0 | 405 | Warning
38783 | San Bernardino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38784 | San Bernardino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and op | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20430 | 0 | 363 | Warning
38785 | San Bernardino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20429 | 20431FS-1d | 0 | 363 | Warning
38786 | San Bernardino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20430FS-1d |  | 0 | 363 | Warning
38787 | San Bernardino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38788 | San Bernardino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38789 | San Bernardino PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
38790 | San Bernardino PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38791 | San Bernardino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20437SS | 0 | 486 | Warning
38792 | San Bernardino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20436SS |  | 0 | 424 | Warning
38793 | San Bernardino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38794 | San Bernardino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38795 | San Bernardino PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38796 | San Bernardino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20442SS | 0 | 486 | Warning
38797 | San Bernardino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20441SS | 20456SS | 0 | 466 | Warning
38798 | San Bernardino PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38799 | San Bernardino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
38800 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38801 | San Bernardino PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38802 | San Bernardino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20448SS | 0 | 345 | Warning
38803 | San Bernardino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20447SS | 20449SS,20450 | 0 | 345 | Warning
38804 | San Bernardino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20448SS | 20450 | 0 | 345 | Warning
38805 | San Bernardino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20448,20449 |  | 0 | 345 | Warning
38806 | San Bernardino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38807 | San Bernardino PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38808 | San Bernardino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20454SS | 0 | 486 | Warning
38809 | San Bernardino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20453SS |  | 0 | 424 | Warning
38810 | San Bernardino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38811 | San Bernardino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20442SS |  | 0 | 466 | Warning
38812 | San Bernardino PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38813 | San Bernardino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20459SS | 0 | 486 | Warning
38814 | San Bernardino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20458SS |  | 0 | 466 | Warning
38815 | San Bernardino PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38816 | San Bernardino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20462SS+18d | 0 | 373 | Warning
38817 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20461SS+18d |  | 0 | 373 | Warning
38818 | San Bernardino PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38819 | San Bernardino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20465SS | 0 | 362 | Warning
38820 | San Bernardino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20464SS |  | 0 | 362 | Warning
38821 | San Bernardino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20467 | 0 | 345 | Warning
38822 | San Bernardino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20466 |  | 0 | 345 | Warning
38823 | San Bernardino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38824 | San Bernardino PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38825 | San Bernardino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20471SS | 0 | 362 | Warning
38826 | San Bernardino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20470SS | 20472SS | 0 | 362 | Warning
38827 | San Bernardino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20471SS | 20473SS | 0 | 362 | Warning
38828 | San Bernardino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20472SS | 20474SS | 0 | 362 | Warning
38829 | San Bernardino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20473SS | 20475SS | 0 | 362 | Warning
38830 | San Bernardino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20474SS | 20476SS | 0 | 362 | Warning
38831 | San Bernardino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20475SS | 20477SS | 0 | 362 | Warning
38832 | San Bernardino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Da | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20476SS | 20478SS | 0 | 362 | Warning
38833 | San Bernardino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20477SS | 20479SS | 0 | 362 | Warning
38834 | San Bernardino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20478SS | 20480SS | 0 | 362 | Warning
38835 | San Bernardino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20479SS |  | 0 | 362 | Warning
38836 | San Bernardino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
38837 | San Bernardino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
38840 | San Bernardino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20484SS |  | 0 | 384 | Warning
38841 | San Bernardino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38842 | San Bernardino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20495 | 0 | 234 | Warning
38843 | San Bernardino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20496 | 0 | 234 | Warning
38845 | San Bernardino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38846 | San Bernardino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20492SS,20500SS+20d | 0 | 240 | Warning
38847 | San Bernardino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20491SS | 20493SS,20501SS+20d | 0 | 309 | Warning
38848 | San Bernardino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20492SS | 20502SS+20d | 0 | 309 | Warning
38849 | San Bernardino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38850 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20487 | 20496SS | 0 | 234 | Warning
38851 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20488,20495SS |  | 0 | 234 | Warning
38852 | San Bernardino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20505FS+12d | 0 | 240 | Warning
38853 | San Bernardino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20499SS | 0 | 321 | Warning
38854 | San Bernardino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20498SS |  | 0 | 321 | Warning
38855 | San Bernardino PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20491SS+20d |  | 0 | 240 | Warning
38856 | San Bernardino PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20492SS+20d |  | 0 | 240 | Warning
38857 | San Bernardino PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20493SS+20d |  | 0 | 240 | Warning
38858 | San Bernardino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20505SS+44d | 0 | 240 | Warning
38859 | San Bernardino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
38860 | San Bernardino PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 20497FS+12d,20503SS+44d |  | 0 | 240 | Warning
38862 | San Diego PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
38863 | San Diego PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
38867 | San Diego PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
38868 | San Diego PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
38869 | San Diego PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
38870 | San Diego PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
38871 | San Diego PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
38872 | San Diego PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
38873 | San Diego PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
38874 | San Diego PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
38875 | San Diego PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
38876 | San Diego PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
38877 | San Diego PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
38878 | San Diego PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
38879 | San Diego PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
38888 | San Diego PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
38889 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20535SS | 0 | 414 | Warning
38890 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20534SS |  | 0 | 414 | Warning
38891 | San Diego PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20537SS | 0 | 362 | Warning
38892 | San Diego PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20536SS |  | 0 | 362 | Warning
38893 | San Diego PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 20540SS,20539SS | 0 | 342 | Warning
38894 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 20538SS |  | 0 | 385 | Warning
38895 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 20538SS |  | 0 | 371 | Warning
38896 | San Diego PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
38897 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 20543SS | 0 | 332 | Warning
38898 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 20542SS |  | 0 | 332 | Warning
38899 | San Diego PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
38900 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 20546SS | 0 | 311 | Warning
38901 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 20545SS |  | 0 | 311 | Warning
38902 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 20548SS | 0 | 289 | Warning
38903 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 20547SS |  | 0 | 289 | Warning
38904 | San Diego PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
38905 | San Diego PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
38906 | San Diego PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
38907 | San Diego PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
38908 | San Diego PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
38909 | San Diego PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
38910 | San Diego PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
38911 | San Diego PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
38912 | San Diego PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.2 | 277 | Warning
38915 | San Diego PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 20558FS-1d |  | 0.2 | 277 | Warning
38918 | San Diego PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20562 |  | 0 | 466 | Warning
38919 | San Diego PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
38920 | San Diego PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20566FS+19d | 0 | 405 | Warning
38921 | San Diego PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20565FS+19d | 20567 | 0 | 405 | Warning
38922 | San Diego PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20566 |  | 0 | 405 | Warning
38923 | San Diego PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
38924 | San Diego PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20570 | 0 | 363 | Warning
38925 | San Diego PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20569 | 20571FS-1d | 0 | 363 | Warning
38926 | San Diego PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20570FS-1d |  | 0 | 363 | Warning
38927 | San Diego PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
38928 | San Diego PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
38929 | San Diego PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
38930 | San Diego PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38931 | San Diego PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20577SS | 0 | 486 | Warning
38932 | San Diego PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20576SS |  | 0 | 424 | Warning
38933 | San Diego PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38934 | San Diego PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38935 | San Diego PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38936 | San Diego PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20582SS | 0 | 486 | Warning
38937 | San Diego PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20581SS | 20596SS | 0 | 466 | Warning
38938 | San Diego PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38939 | San Diego PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
38940 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
38941 | San Diego PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38942 | San Diego PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20588SS | 0 | 345 | Warning
38943 | San Diego PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20587SS | 20589SS,20590 | 0 | 345 | Warning
38944 | San Diego PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20588SS | 20590 | 0 | 345 | Warning
38945 | San Diego PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20588,20589 |  | 0 | 345 | Warning
38946 | San Diego PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38947 | San Diego PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
38948 | San Diego PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20594SS | 0 | 486 | Warning
38949 | San Diego PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20593SS |  | 0 | 424 | Warning
38950 | San Diego PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
38951 | San Diego PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20582SS |  | 0 | 466 | Warning
38952 | San Diego PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
38953 | San Diego PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20599SS | 0 | 486 | Warning
38954 | San Diego PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20598SS |  | 0 | 466 | Warning
38955 | San Diego PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
38956 | San Diego PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20602SS+18d | 0 | 373 | Warning
38957 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20601SS+18d |  | 0 | 373 | Warning
38958 | San Diego PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
38959 | San Diego PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20605SS | 0 | 362 | Warning
38960 | San Diego PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20604SS |  | 0 | 362 | Warning
38961 | San Diego PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20607 | 0 | 345 | Warning
38962 | San Diego PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20606 |  | 0 | 345 | Warning
38963 | San Diego PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
38964 | San Diego PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
38965 | San Diego PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20611SS | 0 | 362 | Warning
38966 | San Diego PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20610SS | 20612SS | 0 | 362 | Warning
38967 | San Diego PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20611SS | 20613SS | 0 | 362 | Warning
38968 | San Diego PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20612SS | 20614SS | 0 | 362 | Warning
38969 | San Diego PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20613SS | 20615SS | 0 | 362 | Warning
38970 | San Diego PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20614SS | 20616SS | 0 | 362 | Warning
38971 | San Diego PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20615SS | 20617SS | 0 | 362 | Warning
38972 | San Diego PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20616SS | 20618SS | 0 | 362 | Warning
38973 | San Diego PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20617SS | 20619SS | 0 | 362 | Warning
38974 | San Diego PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20618SS | 20620SS | 0 | 362 | Warning
38975 | San Diego PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20619SS |  | 0 | 362 | Warning
38976 | San Diego PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
38977 | San Diego PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
38980 | San Diego PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20624SS |  | 0 | 384 | Warning
38981 | San Diego PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
38982 | San Diego PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20635 | 0 | 273 | Warning
38983 | San Diego PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20636 | 0 | 273 | Warning
38985 | San Diego PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
38986 | San Diego PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 20632SS,20640SS+20d | 0 | 299 | Warning
38987 | San Diego PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 20631SS | 20633SS,20641SS+20d | 0 | 299 | Warning
38988 | San Diego PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 20632SS | 20642SS+20d | 0 | 299 | Warning
38989 | San Diego PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
38990 | San Diego PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20627 | 20636SS | 0 | 273 | Warning
38991 | San Diego PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20628,20635SS |  | 0 | 273 | Warning
38992 | San Diego PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 20645FS+12d | 0 | 279 | Warning
38993 | San Diego PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20639SS | 0 | 321 | Warning
38994 | San Diego PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20638SS |  | 0 | 321 | Warning
38995 | San Diego PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20631SS+20d |  | 0 | 299 | Warning
38996 | San Diego PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20632SS+20d |  | 0 | 299 | Warning
38997 | San Diego PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 20633SS+20d |  | 0 | 299 | Warning
38998 | San Diego PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 20645SS+44d | 0 | 279 | Warning
38999 | San Diego PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39000 | San Diego PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 20637FS+12d,20643SS+44d |  | 0 | 279 | Warning
39002 | San Francisco PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
39003 | San Francisco PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39007 | San Francisco PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39008 | San Francisco PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39009 | San Francisco PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39010 | San Francisco PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39011 | San Francisco PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39012 | San Francisco PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39013 | San Francisco PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39014 | San Francisco PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39015 | San Francisco PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39016 | San Francisco PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39017 | San Francisco PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39018 | San Francisco PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39019 | San Francisco PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39028 | San Francisco PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39029 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20675SS | 0 | 414 | Warning
39030 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20674SS |  | 0 | 414 | Warning
39031 | San Francisco PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20677SS | 0 | 362 | Warning
39032 | San Francisco PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20676SS |  | 0 | 362 | Warning
39033 | San Francisco PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39034 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20680SS | 0 | 364 | Warning
39035 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20679SS |  | 0 | 353 | Warning
39036 | San Francisco PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39037 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20683SS | 0 | 300 | Warning
39038 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20682SS |  | 0 | 288 | Warning
39039 | San Francisco PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39040 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20686SS | 0 | 279 | Warning
39041 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20685SS |  | 0 | 268 | Warning
39042 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20688SS | 0 | 246 | Warning
39043 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20687SS |  | 0 | 246 | Warning
39044 | San Francisco PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39045 | San Francisco PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39047 | San Francisco PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39048 | San Francisco PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39049 | San Francisco PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39050 | San Francisco PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39053 | San Francisco PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
39056 | San Francisco PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20699FS-1d |  | 0 | 233 | Warning
39059 | San Francisco PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20703 |  | 0 | 466 | Warning
39060 | San Francisco PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39061 | San Francisco PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20707FS+19d | 0 | 405 | Warning
39062 | San Francisco PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20706FS+19d | 20708 | 0 | 405 | Warning
39063 | San Francisco PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20707 |  | 0 | 405 | Warning
39064 | San Francisco PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39065 | San Francisco PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20711 | 0 | 363 | Warning
39066 | San Francisco PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20710 | 20712FS-1d | 0 | 363 | Warning
39067 | San Francisco PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20711FS-1d |  | 0 | 363 | Warning
39068 | San Francisco PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39069 | San Francisco PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39070 | San Francisco PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
39071 | San Francisco PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39072 | San Francisco PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20718SS | 0 | 362 | Warning
39073 | San Francisco PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20717SS | 20719SS | 0 | 362 | Warning
39074 | San Francisco PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20718SS | 20720SS | 0 | 362 | Warning
39075 | San Francisco PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20719SS | 20721SS | 0 | 362 | Warning
39076 | San Francisco PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20720SS | 20722SS | 0 | 362 | Warning
39077 | San Francisco PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20721SS | 20723SS | 0 | 362 | Warning
39078 | San Francisco PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20722SS | 20724SS | 0 | 362 | Warning
39079 | San Francisco PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20723SS | 20725SS | 0 | 362 | Warning
39080 | San Francisco PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20724SS | 20726SS | 0 | 362 | Warning
39081 | San Francisco PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20725SS | 20727SS | 0 | 362 | Warning
39082 | San Francisco PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20726SS |  | 0 | 362 | Warning
39083 | San Francisco PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39084 | San Francisco PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39087 | San Francisco PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20731SS |  | 0 | 384 | Warning
39088 | San Francisco PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39089 | San Francisco PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20742 | 0 | 234 | Warning
39090 | San Francisco PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20743 | 0 | 234 | Warning
39092 | San Francisco PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39093 | San Francisco PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20739SS,20747SS+20d | 0 | 240 | Warning
39094 | San Francisco PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20738SS | 20740SS,20748SS+20d | 0 | 309 | Warning
39095 | San Francisco PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20739SS | 20749SS+20d | 0 | 309 | Warning
39096 | San Francisco PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39097 | San Francisco PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20734 | 20743SS | 0 | 234 | Warning
39098 | San Francisco PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20735,20742SS |  | 0 | 234 | Warning
39099 | San Francisco PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20752FS+12d | 0 | 240 | Warning
39100 | San Francisco PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20746SS | 0 | 321 | Warning
39101 | San Francisco PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20745SS |  | 0 | 321 | Warning
39102 | San Francisco PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20738SS+20d |  | 0 | 240 | Warning
39103 | San Francisco PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20739SS+20d |  | 0 | 240 | Warning
39104 | San Francisco PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20740SS+20d |  | 0 | 240 | Warning
39105 | San Francisco PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20752SS+44d | 0 | 240 | Warning
39106 | San Francisco PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39107 | San Francisco PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 20744FS+12d,20750SS+44d |  | 0 | 240 | Warning
39109 | San Joaquin PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
39110 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39114 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39115 | San Joaquin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39116 | San Joaquin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39117 | San Joaquin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39118 | San Joaquin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39119 | San Joaquin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39120 | San Joaquin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39121 | San Joaquin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39122 | San Joaquin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39123 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39124 | San Joaquin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39125 | San Joaquin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39126 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39135 | San Joaquin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
39136 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20782SS | 0 | 414 | Warning
39137 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20781SS |  | 0 | 414 | Warning
39138 | San Joaquin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20784SS | 0.2 | 362 | Warning
39139 | San Joaquin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20783SS |  | 0 | 362 | Warning
39140 | San Joaquin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39141 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20787SS | 0 | 364 | Warning
39142 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20786SS |  | 0 | 353 | Warning
39143 | San Joaquin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39144 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20790SS | 0 | 300 | Warning
39145 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20789SS |  | 0 | 288 | Warning
39146 | San Joaquin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39147 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20793SS | 0 | 279 | Warning
39148 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20792SS |  | 0 | 268 | Warning
39149 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20795SS | 0 | 246 | Warning
39150 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20794SS |  | 0 | 246 | Warning
39151 | San Joaquin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39152 | San Joaquin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39154 | San Joaquin PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39155 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39156 | San Joaquin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39157 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39160 | San Joaquin PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
39163 | San Joaquin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20806FS-1d |  | 0.2 | 233 | Warning
39166 | San Joaquin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20810 |  | 0 | 466 | Warning
39167 | San Joaquin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39168 | San Joaquin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20814FS+19d | 0 | 405 | Warning
39169 | San Joaquin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20813FS+19d | 20815 | 0 | 405 | Warning
39170 | San Joaquin PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20814 |  | 0 | 405 | Warning
39171 | San Joaquin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39172 | San Joaquin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20818 | 0 | 363 | Warning
39173 | San Joaquin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20817 | 20819FS-1d | 0 | 363 | Warning
39174 | San Joaquin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20818FS-1d |  | 0 | 363 | Warning
39175 | San Joaquin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39176 | San Joaquin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39177 | San Joaquin PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
39178 | San Joaquin PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39179 | San Joaquin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20825SS | 0 | 486 | Warning
39180 | San Joaquin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20824SS |  | 0 | 424 | Warning
39181 | San Joaquin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39182 | San Joaquin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39183 | San Joaquin PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39184 | San Joaquin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20830SS | 0 | 486 | Warning
39185 | San Joaquin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20829SS | 20844SS | 0 | 466 | Warning
39186 | San Joaquin PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39187 | San Joaquin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39188 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39189 | San Joaquin PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39190 | San Joaquin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20836SS | 0 | 345 | Warning
39191 | San Joaquin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20835SS | 20837SS,20838 | 0 | 345 | Warning
39192 | San Joaquin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20836SS | 20838 | 0 | 345 | Warning
39193 | San Joaquin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20836,20837 |  | 0 | 345 | Warning
39194 | San Joaquin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39195 | San Joaquin PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39196 | San Joaquin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20842SS | 0 | 486 | Warning
39197 | San Joaquin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20841SS |  | 0 | 424 | Warning
39198 | San Joaquin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39199 | San Joaquin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20830SS |  | 0 | 466 | Warning
39200 | San Joaquin PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39201 | San Joaquin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20847SS | 0 | 486 | Warning
39202 | San Joaquin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20846SS |  | 0 | 466 | Warning
39203 | San Joaquin PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39204 | San Joaquin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20850SS+18d | 0 | 373 | Warning
39205 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20849SS+18d |  | 0 | 373 | Warning
39206 | San Joaquin PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39207 | San Joaquin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20853SS | 0 | 362 | Warning
39208 | San Joaquin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20852SS |  | 0 | 362 | Warning
39209 | San Joaquin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20855 | 0 | 345 | Warning
39210 | San Joaquin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20854 |  | 0 | 345 | Warning
39211 | San Joaquin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39212 | San Joaquin PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39213 | San Joaquin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20859SS | 0 | 362 | Warning
39214 | San Joaquin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20858SS | 20860SS | 0 | 362 | Warning
39215 | San Joaquin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20859SS | 20861SS | 0 | 362 | Warning
39216 | San Joaquin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20860SS | 20862SS | 0 | 362 | Warning
39217 | San Joaquin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20861SS | 20863SS | 0 | 362 | Warning
39218 | San Joaquin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20862SS | 20864SS | 0 | 362 | Warning
39219 | San Joaquin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20863SS | 20865SS | 0 | 362 | Warning
39220 | San Joaquin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20864SS | 20866SS | 0 | 362 | Warning
39221 | San Joaquin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20865SS | 20867SS | 0 | 362 | Warning
39222 | San Joaquin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20866SS | 20868SS | 0 | 362 | Warning
39223 | San Joaquin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20867SS |  | 0 | 362 | Warning
39224 | San Joaquin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39225 | San Joaquin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39228 | San Joaquin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20872SS |  | 0 | 384 | Warning
39229 | San Joaquin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39230 | San Joaquin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20883 | 0 | 234 | Warning
39231 | San Joaquin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20884 | 0 | 234 | Warning
39233 | San Joaquin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39234 | San Joaquin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20880SS,20888SS+20d | 0 | 240 | Warning
39235 | San Joaquin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20879SS | 20881SS,20889SS+20d | 0 | 309 | Warning
39236 | San Joaquin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20880SS | 20890SS+20d | 0 | 309 | Warning
39237 | San Joaquin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39238 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20875 | 20884SS | 0 | 234 | Warning
39239 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20876,20883SS |  | 0 | 234 | Warning
39240 | San Joaquin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20893FS+12d | 0 | 240 | Warning
39241 | San Joaquin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20887SS | 0 | 321 | Warning
39242 | San Joaquin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20886SS |  | 0 | 321 | Warning
39243 | San Joaquin PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20879SS+20d |  | 0 | 240 | Warning
39244 | San Joaquin PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20880SS+20d |  | 0 | 240 | Warning
39245 | San Joaquin PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 20881SS+20d |  | 0 | 240 | Warning
39246 | San Joaquin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20893SS+44d | 0 | 240 | Warning
39247 | San Joaquin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39248 | San Joaquin PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 20885FS+12d,20891SS+44d |  | 0 | 240 | Warning
39250 | San Luis Obispo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
39251 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39255 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39256 | San Luis Obispo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39257 | San Luis Obispo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39258 | San Luis Obispo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39259 | San Luis Obispo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39260 | San Luis Obispo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39261 | San Luis Obispo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39262 | San Luis Obispo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39263 | San Luis Obispo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39264 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39265 | San Luis Obispo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39266 | San Luis Obispo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39267 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39276 | San Luis Obispo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39277 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20923SS | 0 | 414 | Warning
39278 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20922SS |  | 0 | 414 | Warning
39279 | San Luis Obispo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20925SS | 0 | 362 | Warning
39280 | San Luis Obispo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20924SS |  | 0 | 362 | Warning
39281 | San Luis Obispo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39282 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20928SS | 0 | 364 | Warning
39283 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20927SS |  | 0 | 353 | Warning
39284 | San Luis Obispo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39285 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20931SS | 0 | 300 | Warning
39286 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 20930SS |  | 0 | 288 | Warning
39287 | San Luis Obispo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39288 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20934SS | 0 | 279 | Warning
39289 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20933SS |  | 0 | 268 | Warning
39290 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20936SS | 0 | 246 | Warning
39291 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20935SS |  | 0 | 246 | Warning
39292 | San Luis Obispo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39293 | San Luis Obispo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39295 | San Luis Obispo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39296 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39297 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39298 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39301 | San Luis Obispo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.22 | 233 | Warning
39304 | San Luis Obispo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20947FS-1d |  | 0.2 | 233 | Warning
39307 | San Luis Obispo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20951 |  | 0 | 466 | Warning
39308 | San Luis Obispo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39310 | San Luis Obispo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20954FS+19d | 20956 | 0 | 405 | Warning
39311 | San Luis Obispo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 20955 |  | 0 | 405 | Warning
39312 | San Luis Obispo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39313 | San Luis Obispo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and o | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20959 | 0 | 363 | Warning
39314 | San Luis Obispo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20958 | 20960FS-1d | 0 | 363 | Warning
39315 | San Luis Obispo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20959FS-1d |  | 0 | 363 | Warning
39316 | San Luis Obispo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39317 | San Luis Obispo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39318 | San Luis Obispo PR - Technical Activities | September 30, 2025 8:00 AM | August 3, 2026 5:00 PM | 211 | 298d |  |  | 0 | 298 | Warning
39319 | San Luis Obispo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39320 | San Luis Obispo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20966SS | 0 | 486 | Warning
39321 | San Luis Obispo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20965SS |  | 0 | 424 | Warning
39322 | San Luis Obispo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39323 | San Luis Obispo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39324 | San Luis Obispo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39325 | San Luis Obispo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39326 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39327 | San Luis Obispo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39328 | San Luis Obispo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20974SS | 0 | 345 | Warning
39329 | San Luis Obispo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20973SS | 20975SS,20976 | 0 | 345 | Warning
39330 | San Luis Obispo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20974SS | 20976 | 0 | 345 | Warning
39331 | San Luis Obispo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20974,20975 |  | 0 | 345 | Warning
39332 | San Luis Obispo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39333 | San Luis Obispo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39334 | San Luis Obispo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20980SS | 0 | 486 | Warning
39335 | San Luis Obispo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20979SS |  | 0 | 424 | Warning
39336 | San Luis Obispo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39337 | San Luis Obispo PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM | 42 | 467d |  |  | 0 | 467 | Warning
39338 | San Luis Obispo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39339 | San Luis Obispo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20985SS+18d | 0 | 373 | Warning
39340 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20984SS+18d |  | 0 | 373 | Warning
39341 | San Luis Obispo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39342 | San Luis Obispo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20988SS | 0 | 362 | Warning
39343 | San Luis Obispo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20987SS |  | 0 | 362 | Warning
39344 | San Luis Obispo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20990 | 0 | 345 | Warning
39345 | San Luis Obispo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20989 |  | 0 | 345 | Warning
39346 | San Luis Obispo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39347 | San Luis Obispo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39348 | San Luis Obispo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20994SS | 0 | 362 | Warning
39349 | San Luis Obispo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20993SS | 20995SS | 0 | 362 | Warning
39350 | San Luis Obispo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20994SS | 20996SS | 0 | 362 | Warning
39351 | San Luis Obispo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20995SS | 20997SS | 0 | 362 | Warning
39352 | San Luis Obispo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20996SS | 20998SS | 0 | 362 | Warning
39353 | San Luis Obispo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20997SS | 20999SS | 0 | 362 | Warning
39354 | San Luis Obispo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20998SS | 21000SS | 0 | 362 | Warning
39355 | San Luis Obispo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20999SS | 21001SS | 0 | 362 | Warning
39356 | San Luis Obispo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21000SS | 21002SS | 0 | 362 | Warning
39357 | San Luis Obispo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21001SS | 21003SS | 0 | 362 | Warning
39358 | San Luis Obispo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21002SS |  | 0 | 362 | Warning
39359 | San Luis Obispo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39360 | San Luis Obispo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39363 | San Luis Obispo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21007SS |  | 0 | 384 | Warning
39364 | San Luis Obispo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39365 | San Luis Obispo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21018 | 0 | 234 | Warning
39366 | San Luis Obispo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21019 | 0 | 234 | Warning
39368 | San Luis Obispo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39369 | San Luis Obispo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21015SS,21023SS+20d | 0 | 240 | Warning
39370 | San Luis Obispo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21014SS | 21016SS,21024SS+20d | 0 | 309 | Warning
39371 | San Luis Obispo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21015SS | 21025SS+20d | 0 | 309 | Warning
39372 | San Luis Obispo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39373 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21010 | 21019SS | 0 | 234 | Warning
39374 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21011,21018SS |  | 0 | 234 | Warning
39375 | San Luis Obispo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21028FS+12d | 0 | 240 | Warning
39376 | San Luis Obispo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21022SS | 0 | 321 | Warning
39377 | San Luis Obispo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21021SS |  | 0 | 321 | Warning
39378 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21014SS+20d |  | 0 | 240 | Warning
39379 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21015SS+20d |  | 0 | 240 | Warning
39380 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21016SS+20d |  | 0 | 240 | Warning
39381 | San Luis Obispo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21028SS+44d | 0 | 240 | Warning
39382 | San Luis Obispo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39383 | San Luis Obispo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21020FS+12d,21026SS+44d |  | 0 | 240 | Warning
39385 | San Mateo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
39386 | San Mateo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39390 | San Mateo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39391 | San Mateo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39392 | San Mateo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39393 | San Mateo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39394 | San Mateo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39395 | San Mateo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39396 | San Mateo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39397 | San Mateo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39398 | San Mateo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39399 | San Mateo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39400 | San Mateo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39401 | San Mateo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39402 | San Mateo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39411 | San Mateo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39412 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21058SS | 0 | 414 | Warning
39413 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21057SS |  | 0 | 414 | Warning
39414 | San Mateo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21060SS | 0 | 362 | Warning
39415 | San Mateo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21059SS |  | 0 | 362 | Warning
39416 | San Mateo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 21063SS,21062SS | 0 | 342 | Warning
39417 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 21061SS |  | 0 | 385 | Warning
39418 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 21061SS |  | 0 | 371 | Warning
39419 | San Mateo PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
39420 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 21066SS | 0 | 332 | Warning
39421 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 21065SS |  | 0 | 332 | Warning
39422 | San Mateo PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
39423 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 21069SS | 0 | 311 | Warning
39424 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 21068SS |  | 0 | 311 | Warning
39425 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 21071SS | 0 | 289 | Warning
39426 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 21070SS |  | 0 | 289 | Warning
39427 | San Mateo PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
39428 | San Mateo PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
39429 | San Mateo PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
39430 | San Mateo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
39431 | San Mateo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39432 | San Mateo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39433 | San Mateo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
39434 | San Mateo PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
39435 | San Mateo PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.2 | 277 | Warning
39438 | San Mateo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 21081FS-1d |  | 0.2 | 277 | Warning
39441 | San Mateo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21085 |  | 0 | 466 | Warning
39442 | San Mateo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39443 | San Mateo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21089FS+19d | 0 | 405 | Warning
39444 | San Mateo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21088FS+19d | 21090 | 0 | 405 | Warning
39445 | San Mateo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21089 |  | 0 | 405 | Warning
39446 | San Mateo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39447 | San Mateo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21093 | 0 | 363 | Warning
39448 | San Mateo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21092 | 21094FS-1d | 0 | 363 | Warning
39449 | San Mateo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21093FS-1d |  | 0 | 363 | Warning
39450 | San Mateo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39451 | San Mateo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39452 | San Mateo PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
39453 | San Mateo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39454 | San Mateo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21100SS | 0 | 486 | Warning
39455 | San Mateo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21099SS |  | 0 | 424 | Warning
39456 | San Mateo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39457 | San Mateo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39458 | San Mateo PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39459 | San Mateo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21105SS | 0 | 486 | Warning
39460 | San Mateo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21104SS | 21119SS | 0 | 466 | Warning
39461 | San Mateo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39462 | San Mateo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39463 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39464 | San Mateo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39465 | San Mateo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21111SS | 0 | 345 | Warning
39466 | San Mateo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21110SS | 21112SS,21113 | 0 | 345 | Warning
39467 | San Mateo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21111SS | 21113 | 0 | 345 | Warning
39468 | San Mateo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21111,21112 |  | 0 | 345 | Warning
39469 | San Mateo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39470 | San Mateo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39471 | San Mateo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21117SS | 0 | 486 | Warning
39472 | San Mateo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21116SS |  | 0 | 424 | Warning
39473 | San Mateo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39474 | San Mateo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21105SS |  | 0 | 466 | Warning
39475 | San Mateo PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39476 | San Mateo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21122SS | 0 | 486 | Warning
39477 | San Mateo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21121SS |  | 0 | 466 | Warning
39478 | San Mateo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39479 | San Mateo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21125SS+18d | 0 | 373 | Warning
39480 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21124SS+18d |  | 0 | 373 | Warning
39481 | San Mateo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39482 | San Mateo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21128SS | 0 | 362 | Warning
39483 | San Mateo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21127SS |  | 0 | 362 | Warning
39484 | San Mateo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21130 | 0 | 345 | Warning
39485 | San Mateo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21129 |  | 0 | 345 | Warning
39486 | San Mateo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39487 | San Mateo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39488 | San Mateo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21134SS | 0 | 362 | Warning
39489 | San Mateo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21133SS | 21135SS | 0 | 362 | Warning
39490 | San Mateo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21134SS | 21136SS | 0 | 362 | Warning
39491 | San Mateo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21135SS | 21137SS | 0 | 362 | Warning
39492 | San Mateo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21136SS | 21138SS | 0 | 362 | Warning
39493 | San Mateo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21137SS | 21139SS | 0 | 362 | Warning
39494 | San Mateo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21138SS | 21140SS | 0 | 362 | Warning
39495 | San Mateo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21139SS | 21141SS | 0 | 362 | Warning
39496 | San Mateo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21140SS | 21142SS | 0 | 362 | Warning
39497 | San Mateo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21141SS | 21143SS | 0 | 362 | Warning
39498 | San Mateo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21142SS |  | 0 | 362 | Warning
39499 | San Mateo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
39500 | San Mateo PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
39503 | San Mateo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21147SS |  | 0 | 384 | Warning
39504 | San Mateo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39505 | San Mateo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 21158 | 0 | 273 | Warning
39506 | San Mateo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 21159 | 0 | 273 | Warning
39508 | San Mateo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39509 | San Mateo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 21155SS,21163SS+20d | 0 | 299 | Warning
39510 | San Mateo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 21154SS | 21156SS,21164SS+20d | 0 | 299 | Warning
39511 | San Mateo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 21155SS | 21165SS+20d | 0 | 299 | Warning
39512 | San Mateo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39513 | San Mateo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 21150 | 21159SS | 0 | 273 | Warning
39514 | San Mateo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 21151,21158SS |  | 0 | 273 | Warning
39515 | San Mateo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 21168FS+12d | 0 | 279 | Warning
39516 | San Mateo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21162SS | 0 | 321 | Warning
39517 | San Mateo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21161SS |  | 0 | 321 | Warning
39518 | San Mateo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 21154SS+20d |  | 0 | 299 | Warning
39519 | San Mateo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 21155SS+20d |  | 0 | 299 | Warning
39520 | San Mateo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 21156SS+20d |  | 0 | 299 | Warning
39521 | San Mateo PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 21168SS+44d | 0 | 279 | Warning
39522 | San Mateo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39523 | San Mateo PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 21160FS+12d,21166SS+44d |  | 0 | 279 | Warning
39525 | Santa Barbara PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.2 | 235 | Warning
39526 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39530 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39531 | Santa Barbara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39532 | Santa Barbara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39533 | Santa Barbara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39534 | Santa Barbara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39535 | Santa Barbara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39536 | Santa Barbara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39537 | Santa Barbara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39538 | Santa Barbara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39539 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39540 | Santa Barbara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39541 | Santa Barbara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39542 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39551 | Santa Barbara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
39552 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21198SS | 0 | 414 | Warning
39553 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21197SS |  | 0 | 414 | Warning
39554 | Santa Barbara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21200SS | 0 | 362 | Warning
39555 | Santa Barbara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21199SS |  | 0 | 362 | Warning
39556 | Santa Barbara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39557 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21203SS | 0 | 364 | Warning
39558 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21202SS |  | 0 | 353 | Warning
39559 | Santa Barbara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39560 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21206SS | 0 | 300 | Warning
39561 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21205SS |  | 0 | 288 | Warning
39562 | Santa Barbara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39563 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21209SS | 0 | 279 | Warning
39564 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21208SS |  | 0 | 268 | Warning
39565 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21211SS | 0 | 246 | Warning
39566 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21210SS |  | 0 | 246 | Warning
39567 | Santa Barbara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39568 | Santa Barbara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39570 | Santa Barbara PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39571 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39572 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39573 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39576 | Santa Barbara PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.13 | 233 | Warning
39579 | Santa Barbara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21222FS-1d |  | 0 | 233 | Warning
39582 | Santa Barbara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21226 |  | 0 | 466 | Warning
39583 | Santa Barbara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39584 | Santa Barbara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21230FS+19d | 0 | 405 | Warning
39585 | Santa Barbara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21229FS+19d | 21231 | 0 | 405 | Warning
39586 | Santa Barbara PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21230 |  | 0 | 405 | Warning
39587 | Santa Barbara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39588 | Santa Barbara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21234 | 0 | 363 | Warning
39589 | Santa Barbara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21233 | 21235FS-1d | 0 | 363 | Warning
39590 | Santa Barbara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21234FS-1d |  | 0 | 363 | Warning
39591 | Santa Barbara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39592 | Santa Barbara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39593 | Santa Barbara PR - Technical Activities | September 30, 2025 8:00 AM | August 3, 2026 5:00 PM | 211 | 298d |  |  | 0.02 | 298 | Warning
39594 | Santa Barbara PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39595 | Santa Barbara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21241SS | 0 | 486 | Warning
39596 | Santa Barbara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21240SS |  | 0 | 424 | Warning
39597 | Santa Barbara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39598 | Santa Barbara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39599 | Santa Barbara PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39600 | Santa Barbara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39601 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39602 | Santa Barbara PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0.06 | 298 | Warning
39603 | Santa Barbara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 424d |  | 21249SS | 0.6 | 424 | Warning
39604 | Santa Barbara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21248SS | 21250SS,21251 | 0 | 345 | Warning
39605 | Santa Barbara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21249SS | 21251 | 0 | 345 | Warning
39606 | Santa Barbara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21249,21250 |  | 0 | 345 | Warning
39607 | Santa Barbara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39608 | Santa Barbara PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39609 | Santa Barbara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21255SS | 0 | 486 | Warning
39610 | Santa Barbara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21254SS |  | 0 | 424 | Warning
39611 | Santa Barbara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39612 | Santa Barbara PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM | 42 | 467d |  |  | 0 | 467 | Warning
39613 | Santa Barbara PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39614 | Santa Barbara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21260SS+18d | 0 | 373 | Warning
39615 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21259SS+18d |  | 0 | 373 | Warning
39616 | Santa Barbara PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0.06 | 298 | Warning
39617 | Santa Barbara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 424d |  | 21263SS | 0.6 | 424 | Warning
39618 | Santa Barbara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21262SS |  | 0 | 362 | Warning
39619 | Santa Barbara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21265 | 0 | 345 | Warning
39620 | Santa Barbara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21264 |  | 0 | 345 | Warning
39621 | Santa Barbara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39622 | Santa Barbara PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39623 | Santa Barbara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21269SS | 0 | 362 | Warning
39624 | Santa Barbara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21268SS | 21270SS | 0 | 362 | Warning
39625 | Santa Barbara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21269SS | 21271SS | 0 | 362 | Warning
39626 | Santa Barbara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21270SS | 21272SS | 0 | 362 | Warning
39627 | Santa Barbara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21271SS | 21273SS | 0 | 362 | Warning
39628 | Santa Barbara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21272SS | 21274SS | 0 | 362 | Warning
39629 | Santa Barbara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21273SS | 21275SS | 0 | 362 | Warning
39630 | Santa Barbara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21274SS | 21276SS | 0 | 362 | Warning
39631 | Santa Barbara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21275SS | 21277SS | 0 | 362 | Warning
39632 | Santa Barbara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21276SS | 21278SS | 0 | 362 | Warning
39633 | Santa Barbara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21277SS |  | 0 | 362 | Warning
39634 | Santa Barbara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39635 | Santa Barbara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39638 | Santa Barbara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21282SS |  | 0 | 384 | Warning
39639 | Santa Barbara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39640 | Santa Barbara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21293 | 0 | 234 | Warning
39641 | Santa Barbara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21294 | 0 | 234 | Warning
39643 | Santa Barbara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39644 | Santa Barbara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21290SS,21298SS+20d | 0 | 240 | Warning
39645 | Santa Barbara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21289SS | 21291SS,21299SS+20d | 0 | 309 | Warning
39646 | Santa Barbara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21290SS | 21300SS+20d | 0 | 309 | Warning
39647 | Santa Barbara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39648 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21285 | 21294SS | 0 | 234 | Warning
39649 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21286,21293SS |  | 0 | 234 | Warning
39650 | Santa Barbara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21303FS+12d | 0 | 240 | Warning
39651 | Santa Barbara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21297SS | 0 | 321 | Warning
39652 | Santa Barbara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21296SS |  | 0 | 321 | Warning
39653 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21289SS+20d |  | 0 | 240 | Warning
39654 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21290SS+20d |  | 0 | 240 | Warning
39655 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21291SS+20d |  | 0 | 240 | Warning
39656 | Santa Barbara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21303SS+44d | 0 | 240 | Warning
39657 | Santa Barbara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39658 | Santa Barbara PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21295FS+12d,21301SS+44d |  | 0 | 240 | Warning
39660 | Santa Clara PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
39661 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39665 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39666 | Santa Clara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39667 | Santa Clara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39668 | Santa Clara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39669 | Santa Clara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39670 | Santa Clara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39671 | Santa Clara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39672 | Santa Clara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39673 | Santa Clara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39674 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39675 | Santa Clara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39676 | Santa Clara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39677 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39686 | Santa Clara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39687 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21333SS | 0 | 414 | Warning
39688 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21332SS |  | 0 | 414 | Warning
39689 | Santa Clara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21335SS | 0 | 362 | Warning
39690 | Santa Clara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21334SS |  | 0 | 362 | Warning
39691 | Santa Clara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39692 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21338SS | 0 | 364 | Warning
39693 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21337SS |  | 0 | 353 | Warning
39694 | Santa Clara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39695 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21341SS | 0 | 300 | Warning
39696 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21340SS |  | 0 | 288 | Warning
39697 | Santa Clara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39698 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21344SS | 0 | 279 | Warning
39699 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21343SS |  | 0 | 268 | Warning
39700 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21346SS | 0 | 246 | Warning
39701 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21345SS |  | 0 | 246 | Warning
39702 | Santa Clara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39703 | Santa Clara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39705 | Santa Clara PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39706 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39707 | Santa Clara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39708 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39711 | Santa Clara PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
39714 | Santa Clara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21357FS-1d |  | 0.2 | 233 | Warning
39717 | Santa Clara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21361 |  | 0 | 466 | Warning
39718 | Santa Clara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39719 | Santa Clara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21365FS+19d | 0 | 405 | Warning
39720 | Santa Clara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21364FS+19d | 21366 | 0 | 405 | Warning
39721 | Santa Clara PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21365 |  | 0 | 405 | Warning
39722 | Santa Clara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39723 | Santa Clara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21369 | 0 | 363 | Warning
39724 | Santa Clara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21368 | 21370FS-1d | 0 | 363 | Warning
39725 | Santa Clara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21369FS-1d |  | 0 | 363 | Warning
39726 | Santa Clara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39727 | Santa Clara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39728 | Santa Clara PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
39729 | Santa Clara PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39730 | Santa Clara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21376SS | 0 | 486 | Warning
39731 | Santa Clara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21375SS |  | 0 | 424 | Warning
39732 | Santa Clara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39733 | Santa Clara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39734 | Santa Clara PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39735 | Santa Clara PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21381SS | 0 | 486 | Warning
39736 | Santa Clara PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21380SS | 21395SS | 0 | 466 | Warning
39737 | Santa Clara PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39738 | Santa Clara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39739 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39740 | Santa Clara PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39741 | Santa Clara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21387SS | 0 | 345 | Warning
39742 | Santa Clara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21386SS | 21388SS,21389 | 0 | 345 | Warning
39743 | Santa Clara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21387SS | 21389 | 0 | 345 | Warning
39744 | Santa Clara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21387,21388 |  | 0 | 345 | Warning
39745 | Santa Clara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39746 | Santa Clara PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39747 | Santa Clara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21393SS | 0 | 486 | Warning
39748 | Santa Clara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21392SS |  | 0 | 424 | Warning
39749 | Santa Clara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39750 | Santa Clara PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21381SS |  | 0 | 466 | Warning
39751 | Santa Clara PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39752 | Santa Clara PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21398SS | 0 | 486 | Warning
39753 | Santa Clara PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21397SS |  | 0 | 466 | Warning
39754 | Santa Clara PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39755 | Santa Clara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21401SS+18d | 0 | 373 | Warning
39756 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21400SS+18d |  | 0 | 373 | Warning
39757 | Santa Clara PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39758 | Santa Clara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21404SS | 0 | 362 | Warning
39759 | Santa Clara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21403SS |  | 0 | 362 | Warning
39760 | Santa Clara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21406 | 0 | 345 | Warning
39761 | Santa Clara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21405 |  | 0 | 345 | Warning
39762 | Santa Clara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39763 | Santa Clara PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39764 | Santa Clara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21410SS | 0 | 362 | Warning
39765 | Santa Clara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21409SS | 21411SS | 0 | 362 | Warning
39766 | Santa Clara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21410SS | 21412SS | 0 | 362 | Warning
39767 | Santa Clara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21411SS | 21413SS | 0 | 362 | Warning
39768 | Santa Clara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21412SS | 21414SS | 0 | 362 | Warning
39769 | Santa Clara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21413SS | 21415SS | 0 | 362 | Warning
39770 | Santa Clara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21414SS | 21416SS | 0 | 362 | Warning
39771 | Santa Clara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21415SS | 21417SS | 0 | 362 | Warning
39772 | Santa Clara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21416SS | 21418SS | 0 | 362 | Warning
39773 | Santa Clara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21417SS | 21419SS | 0 | 362 | Warning
39774 | Santa Clara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21418SS |  | 0 | 362 | Warning
39775 | Santa Clara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39776 | Santa Clara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39779 | Santa Clara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21423SS |  | 0 | 384 | Warning
39780 | Santa Clara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39781 | Santa Clara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21434 | 0 | 234 | Warning
39782 | Santa Clara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21435 | 0 | 234 | Warning
39784 | Santa Clara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39785 | Santa Clara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21431SS,21439SS+20d | 0 | 240 | Warning
39786 | Santa Clara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21430SS | 21432SS,21440SS+20d | 0 | 309 | Warning
39787 | Santa Clara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21431SS | 21441SS+20d | 0 | 309 | Warning
39788 | Santa Clara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39789 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21426 | 21435SS | 0 | 234 | Warning
39790 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21427,21434SS |  | 0 | 234 | Warning
39791 | Santa Clara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21444FS+12d | 0 | 240 | Warning
39792 | Santa Clara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21438SS | 0 | 321 | Warning
39793 | Santa Clara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21437SS |  | 0 | 321 | Warning
39794 | Santa Clara PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21430SS+20d |  | 0 | 240 | Warning
39795 | Santa Clara PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21431SS+20d |  | 0 | 240 | Warning
39796 | Santa Clara PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21432SS+20d |  | 0 | 240 | Warning
39797 | Santa Clara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21444SS+44d | 0 | 240 | Warning
39798 | Santa Clara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39799 | Santa Clara PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21436FS+12d,21442SS+44d |  | 0 | 240 | Warning
39801 | Santa Cruz PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
39802 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
39806 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
39807 | Santa Cruz PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39808 | Santa Cruz PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39809 | Santa Cruz PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39810 | Santa Cruz PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39811 | Santa Cruz PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39812 | Santa Cruz PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39813 | Santa Cruz PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39814 | Santa Cruz PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39815 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39816 | Santa Cruz PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39817 | Santa Cruz PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39818 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39827 | Santa Cruz PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39828 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21474SS | 0 | 414 | Warning
39829 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21473SS |  | 0 | 414 | Warning
39830 | Santa Cruz PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21476SS | 0 | 362 | Warning
39831 | Santa Cruz PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21475SS |  | 0 | 362 | Warning
39832 | Santa Cruz PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39833 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21479SS | 0 | 364 | Warning
39834 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21478SS |  | 0 | 353 | Warning
39835 | Santa Cruz PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39836 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21482SS | 0 | 300 | Warning
39837 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21481SS |  | 0 | 288 | Warning
39838 | Santa Cruz PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39839 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21485SS | 0 | 279 | Warning
39840 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21484SS |  | 0 | 268 | Warning
39841 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21487SS | 0 | 246 | Warning
39842 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21486SS |  | 0 | 246 | Warning
39843 | Santa Cruz PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39844 | Santa Cruz PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39846 | Santa Cruz PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39847 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39848 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39849 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39852 | Santa Cruz PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
39855 | Santa Cruz PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21498FS-1d |  | 0.2 | 233 | Warning
39858 | Santa Cruz PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21502 |  | 0 | 466 | Warning
39859 | Santa Cruz PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39860 | Santa Cruz PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21506FS+19d | 0 | 405 | Warning
39861 | Santa Cruz PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21505FS+19d | 21507 | 0 | 405 | Warning
39862 | Santa Cruz PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21506 |  | 0 | 405 | Warning
39863 | Santa Cruz PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39864 | Santa Cruz PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21510 | 0 | 363 | Warning
39865 | Santa Cruz PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21509 | 21511FS-1d | 0 | 363 | Warning
39866 | Santa Cruz PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21510FS-1d |  | 0 | 363 | Warning
39867 | Santa Cruz PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39868 | Santa Cruz PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39869 | Santa Cruz PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
39870 | Santa Cruz PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
39871 | Santa Cruz PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21517SS | 0 | 362 | Warning
39872 | Santa Cruz PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21516SS | 21518SS | 0 | 362 | Warning
39873 | Santa Cruz PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21517SS | 21519SS | 0 | 362 | Warning
39874 | Santa Cruz PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21518SS | 21520SS | 0 | 362 | Warning
39875 | Santa Cruz PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21519SS | 21521SS | 0 | 362 | Warning
39876 | Santa Cruz PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21520SS | 21522SS | 0 | 362 | Warning
39877 | Santa Cruz PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21521SS | 21523SS | 0 | 362 | Warning
39878 | Santa Cruz PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21522SS | 21524SS | 0 | 362 | Warning
39879 | Santa Cruz PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21523SS | 21525SS | 0 | 362 | Warning
39880 | Santa Cruz PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21524SS | 21526SS | 0 | 362 | Warning
39881 | Santa Cruz PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21525SS |  | 0 | 362 | Warning
39882 | Santa Cruz PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
39883 | Santa Cruz PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
39886 | Santa Cruz PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21530SS |  | 0 | 384 | Warning
39887 | Santa Cruz PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
39888 | Santa Cruz PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21541 | 0 | 234 | Warning
39889 | Santa Cruz PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21542 | 0 | 234 | Warning
39891 | Santa Cruz PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
39892 | Santa Cruz PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21538SS,21546SS+20d | 0 | 240 | Warning
39893 | Santa Cruz PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21537SS | 21539SS,21547SS+20d | 0 | 309 | Warning
39894 | Santa Cruz PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21538SS | 21548SS+20d | 0 | 309 | Warning
39895 | Santa Cruz PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
39896 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21533 | 21542SS | 0 | 234 | Warning
39897 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21534,21541SS |  | 0 | 234 | Warning
39898 | Santa Cruz PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21551FS+12d | 0 | 240 | Warning
39899 | Santa Cruz PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21545SS | 0 | 321 | Warning
39900 | Santa Cruz PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21544SS |  | 0 | 321 | Warning
39901 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21537SS+20d |  | 0 | 240 | Warning
39902 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21538SS+20d |  | 0 | 240 | Warning
39903 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21539SS+20d |  | 0 | 240 | Warning
39904 | Santa Cruz PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21551SS+44d | 0 | 240 | Warning
39905 | Santa Cruz PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
39906 | Santa Cruz PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21543FS+12d,21549SS+44d |  | 0 | 240 | Warning
39908 | Shasta PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.21 | 235 | Warning
39909 | Shasta PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
39914 | Shasta PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
39915 | Shasta PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
39916 | Shasta PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
39917 | Shasta PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
39918 | Shasta PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
39919 | Shasta PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
39920 | Shasta PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
39921 | Shasta PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
39922 | Shasta PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
39923 | Shasta PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
39924 | Shasta PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39925 | Shasta PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
39934 | Shasta PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
39935 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21581SS | 0 | 414 | Warning
39936 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21580SS |  | 0 | 414 | Warning
39937 | Shasta PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21583SS | 0 | 362 | Warning
39938 | Shasta PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21582SS |  | 0 | 362 | Warning
39939 | Shasta PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
39940 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21586SS | 0 | 364 | Warning
39941 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21585SS |  | 0 | 353 | Warning
39942 | Shasta PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
39943 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21589SS | 0 | 300 | Warning
39944 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21588SS |  | 0 | 288 | Warning
39945 | Shasta PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
39946 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21592SS | 0 | 279 | Warning
39947 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21591SS |  | 0 | 268 | Warning
39948 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21594SS | 0 | 246 | Warning
39949 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21593SS |  | 0 | 246 | Warning
39950 | Shasta PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
39951 | Shasta PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
39953 | Shasta PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
39954 | Shasta PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
39955 | Shasta PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
39956 | Shasta PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
39959 | Shasta PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.23 | 233 | Warning
39962 | Shasta PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21605FS-1d |  | 0.2 | 233 | Warning
39965 | Shasta PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21609 |  | 0.2 | 466 | Warning
39966 | Shasta PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
39968 | Shasta PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21612FS+19d | 21614 | 0 | 405 | Warning
39969 | Shasta PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21613 |  | 0 | 405 | Warning
39970 | Shasta PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
39971 | Shasta PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21617 | 0 | 363 | Warning
39972 | Shasta PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21616 | 21618FS-1d | 0 | 363 | Warning
39973 | Shasta PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21617FS-1d |  | 0 | 363 | Warning
39974 | Shasta PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
39975 | Shasta PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
39976 | Shasta PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
39977 | Shasta PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39978 | Shasta PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21624SS | 0 | 486 | Warning
39979 | Shasta PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21623SS |  | 0 | 424 | Warning
39980 | Shasta PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39981 | Shasta PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39982 | Shasta PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
39983 | Shasta PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21629SS | 0 | 486 | Warning
39984 | Shasta PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21628SS | 21643SS | 0 | 466 | Warning
39985 | Shasta PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
39986 | Shasta PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
39987 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
39988 | Shasta PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
39989 | Shasta PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21635SS | 0 | 345 | Warning
39990 | Shasta PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21634SS | 21636SS,21637 | 0 | 345 | Warning
39991 | Shasta PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21635SS | 21637 | 0 | 345 | Warning
39992 | Shasta PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21635,21636 |  | 0 | 345 | Warning
39993 | Shasta PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
39994 | Shasta PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
39995 | Shasta PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21641SS | 0 | 486 | Warning
39996 | Shasta PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21640SS |  | 0 | 424 | Warning
39997 | Shasta PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
39998 | Shasta PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21629SS |  | 0 | 466 | Warning
39999 | Shasta PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40000 | Shasta PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21646SS | 0 | 486 | Warning
40001 | Shasta PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21645SS |  | 0 | 466 | Warning
40002 | Shasta PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40003 | Shasta PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21649SS+18d | 0 | 373 | Warning
40004 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21648SS+18d |  | 0 | 373 | Warning
40005 | Shasta PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40006 | Shasta PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21652SS | 0 | 362 | Warning
40007 | Shasta PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21651SS |  | 0 | 362 | Warning
40008 | Shasta PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21654 | 0 | 345 | Warning
40009 | Shasta PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21653 |  | 0 | 345 | Warning
40010 | Shasta PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40011 | Shasta PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40012 | Shasta PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21658SS | 0 | 362 | Warning
40013 | Shasta PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21657SS | 21659SS | 0 | 362 | Warning
40014 | Shasta PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21658SS | 21660SS | 0 | 362 | Warning
40015 | Shasta PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21659SS | 21661SS | 0 | 362 | Warning
40016 | Shasta PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21660SS | 21662SS | 0 | 362 | Warning
40017 | Shasta PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21661SS | 21663SS | 0 | 362 | Warning
40018 | Shasta PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21662SS | 21664SS | 0 | 362 | Warning
40019 | Shasta PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21663SS | 21665SS | 0 | 362 | Warning
40020 | Shasta PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21664SS | 21666SS | 0 | 362 | Warning
40021 | Shasta PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21665SS | 21667SS | 0 | 362 | Warning
40022 | Shasta PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21666SS |  | 0 | 362 | Warning
40023 | Shasta PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40024 | Shasta PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40027 | Shasta PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21671SS |  | 0 | 384 | Warning
40028 | Shasta PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40029 | Shasta PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21682 | 0 | 234 | Warning
40030 | Shasta PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21683 | 0 | 234 | Warning
40032 | Shasta PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40033 | Shasta PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21679SS,21687SS+20d | 0 | 240 | Warning
40034 | Shasta PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21678SS | 21680SS,21688SS+20d | 0 | 309 | Warning
40035 | Shasta PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21679SS | 21689SS+20d | 0 | 309 | Warning
40036 | Shasta PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40037 | Shasta PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21674 | 21683SS | 0 | 234 | Warning
40038 | Shasta PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21675,21682SS |  | 0 | 234 | Warning
40039 | Shasta PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21692FS+12d | 0 | 240 | Warning
40040 | Shasta PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21686SS | 0 | 321 | Warning
40041 | Shasta PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21685SS |  | 0 | 321 | Warning
40042 | Shasta PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21678SS+20d |  | 0 | 240 | Warning
40043 | Shasta PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21679SS+20d |  | 0 | 240 | Warning
40044 | Shasta PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21680SS+20d |  | 0 | 240 | Warning
40045 | Shasta PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21692SS+44d | 0 | 240 | Warning
40046 | Shasta PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40047 | Shasta PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21684FS+12d,21690SS+44d |  | 0 | 240 | Warning
40049 | Sierra PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
40050 | Sierra PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40054 | Sierra PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40055 | Sierra PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40056 | Sierra PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40057 | Sierra PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40058 | Sierra PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40059 | Sierra PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40060 | Sierra PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40061 | Sierra PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40062 | Sierra PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40063 | Sierra PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40064 | Sierra PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40065 | Sierra PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40066 | Sierra PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40075 | Sierra PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
40076 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21722SS | 0 | 414 | Warning
40077 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21721SS |  | 0 | 414 | Warning
40078 | Sierra PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21724SS | 0 | 362 | Warning
40079 | Sierra PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21723SS |  | 0 | 362 | Warning
40080 | Sierra PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40081 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21727SS | 0 | 364 | Warning
40082 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21726SS |  | 0 | 353 | Warning
40083 | Sierra PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40084 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21730SS | 0 | 300 | Warning
40085 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21729SS |  | 0 | 288 | Warning
40086 | Sierra PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40087 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21733SS | 0 | 279 | Warning
40088 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21732SS |  | 0 | 268 | Warning
40089 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21735SS | 0 | 246 | Warning
40090 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21734SS |  | 0 | 246 | Warning
40091 | Sierra PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40092 | Sierra PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40094 | Sierra PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40095 | Sierra PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40096 | Sierra PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40097 | Sierra PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40100 | Sierra PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
40103 | Sierra PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21746FS-1d |  | 0.2 | 233 | Warning
40106 | Sierra PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21750 |  | 0 | 466 | Warning
40107 | Sierra PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40108 | Sierra PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21754FS+19d | 0 | 405 | Warning
40109 | Sierra PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21753FS+19d | 21755 | 0 | 405 | Warning
40110 | Sierra PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21754 |  | 0 | 405 | Warning
40111 | Sierra PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40112 | Sierra PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21758 | 0 | 363 | Warning
40113 | Sierra PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21757 | 21759FS-1d | 0 | 363 | Warning
40114 | Sierra PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21758FS-1d |  | 0 | 363 | Warning
40115 | Sierra PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40116 | Sierra PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40117 | Sierra PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0.01 | 298 | Warning
40118 | Sierra PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40119 | Sierra PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21765SS | 0 | 486 | Warning
40120 | Sierra PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21764SS |  | 0 | 424 | Warning
40121 | Sierra PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40122 | Sierra PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40123 | Sierra PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40124 | Sierra PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21770SS | 0 | 486 | Warning
40125 | Sierra PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21769SS | 21784SS | 0 | 466 | Warning
40126 | Sierra PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40127 | Sierra PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40128 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40129 | Sierra PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40130 | Sierra PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21776SS | 0 | 345 | Warning
40131 | Sierra PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21775SS | 21777SS,21778 | 0 | 345 | Warning
40132 | Sierra PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21776SS | 21778 | 0 | 345 | Warning
40133 | Sierra PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21776,21777 |  | 0 | 345 | Warning
40134 | Sierra PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40135 | Sierra PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40136 | Sierra PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21782SS | 0 | 486 | Warning
40137 | Sierra PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21781SS |  | 0 | 424 | Warning
40138 | Sierra PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40139 | Sierra PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21770SS |  | 0 | 466 | Warning
40140 | Sierra PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40141 | Sierra PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21787SS | 0 | 486 | Warning
40142 | Sierra PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21786SS |  | 0 | 466 | Warning
40143 | Sierra PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0.14 | 373 | Warning
40145 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21789SS+18d |  | 0.2 | 373 | Warning
40146 | Sierra PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0.01 | 298 | Warning
40147 | Sierra PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21793SS | 0 | 362 | Warning
40148 | Sierra PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21792SS |  | 0 | 362 | Warning
40150 | Sierra PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21794 |  | 0.2 | 345 | Warning
40151 | Sierra PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40152 | Sierra PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40153 | Sierra PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21799SS | 0 | 362 | Warning
40154 | Sierra PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21798SS | 21800SS | 0 | 362 | Warning
40155 | Sierra PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21799SS | 21801SS | 0 | 362 | Warning
40156 | Sierra PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21800SS | 21802SS | 0 | 362 | Warning
40157 | Sierra PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21801SS | 21803SS | 0 | 362 | Warning
40158 | Sierra PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21802SS | 21804SS | 0 | 362 | Warning
40159 | Sierra PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21803SS | 21805SS | 0 | 362 | Warning
40160 | Sierra PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21804SS | 21806SS | 0 | 362 | Warning
40161 | Sierra PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21805SS | 21807SS | 0 | 362 | Warning
40162 | Sierra PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21806SS | 21808SS | 0 | 362 | Warning
40163 | Sierra PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21807SS |  | 0 | 362 | Warning
40164 | Sierra PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40165 | Sierra PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40168 | Sierra PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21812SS |  | 0 | 384 | Warning
40169 | Sierra PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40170 | Sierra PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21823 | 0 | 234 | Warning
40171 | Sierra PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21824 | 0 | 234 | Warning
40173 | Sierra PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40174 | Sierra PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21820SS,21828SS+20d | 0 | 240 | Warning
40175 | Sierra PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21819SS | 21821SS,21829SS+20d | 0 | 309 | Warning
40176 | Sierra PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21820SS | 21830SS+20d | 0 | 309 | Warning
40177 | Sierra PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40178 | Sierra PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21815 | 21824SS | 0 | 234 | Warning
40179 | Sierra PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21816,21823SS |  | 0 | 234 | Warning
40180 | Sierra PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21833FS+12d | 0 | 240 | Warning
40181 | Sierra PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21827SS | 0 | 321 | Warning
40182 | Sierra PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21826SS |  | 0 | 321 | Warning
40183 | Sierra PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21819SS+20d |  | 0 | 240 | Warning
40184 | Sierra PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21820SS+20d |  | 0 | 240 | Warning
40185 | Sierra PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21821SS+20d |  | 0 | 240 | Warning
40186 | Sierra PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21833SS+44d | 0 | 240 | Warning
40187 | Sierra PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40188 | Sierra PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21825FS+12d,21831SS+44d |  | 0 | 240 | Warning
40190 | Siskiyou PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
40191 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40195 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40196 | Siskiyou PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40197 | Siskiyou PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40198 | Siskiyou PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40199 | Siskiyou PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40200 | Siskiyou PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40201 | Siskiyou PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40202 | Siskiyou PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40203 | Siskiyou PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40204 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40205 | Siskiyou PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40206 | Siskiyou PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40207 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40216 | Siskiyou PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
40217 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21863SS | 0 | 414 | Warning
40218 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21862SS |  | 0 | 414 | Warning
40219 | Siskiyou PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21865SS | 0 | 362 | Warning
40220 | Siskiyou PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21864SS |  | 0 | 362 | Warning
40221 | Siskiyou PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40222 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21868SS | 0 | 364 | Warning
40223 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21867SS |  | 0 | 353 | Warning
40224 | Siskiyou PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40225 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21871SS | 0 | 300 | Warning
40226 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 21870SS |  | 0 | 288 | Warning
40227 | Siskiyou PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40228 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21874SS | 0 | 279 | Warning
40229 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21873SS |  | 0 | 268 | Warning
40230 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21876SS | 0 | 246 | Warning
40231 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21875SS |  | 0 | 246 | Warning
40232 | Siskiyou PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40233 | Siskiyou PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40235 | Siskiyou PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40236 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40237 | Siskiyou PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40238 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40241 | Siskiyou PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
40244 | Siskiyou PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21887FS-1d |  | 0.2 | 233 | Warning
40247 | Siskiyou PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21891 |  | 0 | 466 | Warning
40248 | Siskiyou PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40249 | Siskiyou PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21895FS+19d | 0 | 405 | Warning
40250 | Siskiyou PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21894FS+19d | 21896 | 0 | 405 | Warning
40251 | Siskiyou PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 21895 |  | 0 | 405 | Warning
40252 | Siskiyou PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40253 | Siskiyou PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21899 | 0 | 363 | Warning
40254 | Siskiyou PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21898 | 21900FS-1d | 0 | 363 | Warning
40255 | Siskiyou PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21899FS-1d |  | 0 | 363 | Warning
40256 | Siskiyou PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40257 | Siskiyou PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40258 | Siskiyou PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
40259 | Siskiyou PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40260 | Siskiyou PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21906SS | 0 | 486 | Warning
40261 | Siskiyou PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21905SS |  | 0 | 424 | Warning
40262 | Siskiyou PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40263 | Siskiyou PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40264 | Siskiyou PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40265 | Siskiyou PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21911SS | 0 | 486 | Warning
40266 | Siskiyou PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21910SS | 21925SS | 0 | 466 | Warning
40267 | Siskiyou PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40268 | Siskiyou PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40269 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40270 | Siskiyou PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40271 | Siskiyou PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21917SS | 0 | 345 | Warning
40272 | Siskiyou PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21916SS | 21918SS,21919 | 0 | 345 | Warning
40273 | Siskiyou PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21917SS | 21919 | 0 | 345 | Warning
40274 | Siskiyou PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21917,21918 |  | 0 | 345 | Warning
40275 | Siskiyou PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40276 | Siskiyou PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40277 | Siskiyou PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21923SS | 0 | 486 | Warning
40278 | Siskiyou PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21922SS |  | 0 | 424 | Warning
40279 | Siskiyou PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40280 | Siskiyou PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21911SS |  | 0 | 466 | Warning
40281 | Siskiyou PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40282 | Siskiyou PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21928SS | 0 | 486 | Warning
40283 | Siskiyou PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21927SS |  | 0 | 466 | Warning
40284 | Siskiyou PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40285 | Siskiyou PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21931SS+18d | 0 | 373 | Warning
40286 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21930SS+18d |  | 0 | 373 | Warning
40287 | Siskiyou PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40288 | Siskiyou PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21934SS | 0 | 362 | Warning
40289 | Siskiyou PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21933SS |  | 0 | 362 | Warning
40290 | Siskiyou PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21936 | 0 | 345 | Warning
40291 | Siskiyou PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21935 |  | 0 | 345 | Warning
40292 | Siskiyou PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40293 | Siskiyou PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40294 | Siskiyou PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21940SS | 0 | 362 | Warning
40295 | Siskiyou PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21939SS | 21941SS | 0 | 362 | Warning
40296 | Siskiyou PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21940SS | 21942SS | 0 | 362 | Warning
40297 | Siskiyou PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21941SS | 21943SS | 0 | 362 | Warning
40298 | Siskiyou PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21942SS | 21944SS | 0 | 362 | Warning
40299 | Siskiyou PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21943SS | 21945SS | 0 | 362 | Warning
40300 | Siskiyou PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21944SS | 21946SS | 0 | 362 | Warning
40301 | Siskiyou PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21945SS | 21947SS | 0 | 362 | Warning
40302 | Siskiyou PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21946SS | 21948SS | 0 | 362 | Warning
40303 | Siskiyou PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21947SS | 21949SS | 0 | 362 | Warning
40304 | Siskiyou PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21948SS |  | 0 | 362 | Warning
40305 | Siskiyou PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40306 | Siskiyou PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40309 | Siskiyou PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21953SS |  | 0 | 384 | Warning
40310 | Siskiyou PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40311 | Siskiyou PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21964 | 0 | 234 | Warning
40312 | Siskiyou PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21965 | 0 | 234 | Warning
40314 | Siskiyou PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40315 | Siskiyou PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21961SS,21969SS+20d | 0 | 240 | Warning
40316 | Siskiyou PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21960SS | 21962SS,21970SS+20d | 0 | 309 | Warning
40317 | Siskiyou PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21961SS | 21971SS+20d | 0 | 309 | Warning
40318 | Siskiyou PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40319 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21956 | 21965SS | 0 | 234 | Warning
40320 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21957,21964SS |  | 0 | 234 | Warning
40321 | Siskiyou PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21974FS+12d | 0 | 240 | Warning
40322 | Siskiyou PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21968SS | 0 | 321 | Warning
40323 | Siskiyou PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21967SS |  | 0 | 321 | Warning
40324 | Siskiyou PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21960SS+20d |  | 0 | 240 | Warning
40325 | Siskiyou PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21961SS+20d |  | 0 | 240 | Warning
40326 | Siskiyou PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 21962SS+20d |  | 0 | 240 | Warning
40327 | Siskiyou PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21974SS+44d | 0 | 240 | Warning
40328 | Siskiyou PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40329 | Siskiyou PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 21966FS+12d,21972SS+44d |  | 0 | 240 | Warning
40331 | Solano PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.2 | 235 | Warning
40332 | Solano PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40336 | Solano PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40337 | Solano PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40338 | Solano PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40339 | Solano PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40340 | Solano PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40341 | Solano PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40342 | Solano PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40343 | Solano PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40344 | Solano PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40345 | Solano PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40346 | Solano PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40347 | Solano PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40348 | Solano PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40357 | Solano PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | 445 | Warning
40358 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22004SS | 0 | 414 | Warning
40359 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22003SS |  | 0 | 414 | Warning
40360 | Solano PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22006SS | 0 | 362 | Warning
40361 | Solano PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22005SS |  | 0 | 362 | Warning
40362 | Solano PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40363 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22009SS | 0 | 364 | Warning
40364 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22008SS |  | 0 | 353 | Warning
40365 | Solano PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40366 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22012SS | 0 | 300 | Warning
40367 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22011SS |  | 0 | 288 | Warning
40368 | Solano PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40369 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22015SS | 0 | 279 | Warning
40370 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22014SS |  | 0 | 268 | Warning
40371 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22017SS | 0 | 246 | Warning
40372 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22016SS |  | 0 | 246 | Warning
40373 | Solano PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40374 | Solano PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40376 | Solano PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40377 | Solano PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40378 | Solano PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40379 | Solano PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40382 | Solano PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.21 | 233 | Warning
40385 | Solano PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22028FS-1d |  | 0.2 | 233 | Warning
40388 | Solano PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22032 |  | 0.2 | 466 | Warning
40389 | Solano PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40390 | Solano PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22036FS+19d | 0 | 405 | Warning
40391 | Solano PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22035FS+19d | 22037 | 0 | 405 | Warning
40392 | Solano PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22036 |  | 0 | 405 | Warning
40393 | Solano PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40394 | Solano PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22040 | 0 | 363 | Warning
40395 | Solano PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22039 | 22041FS-1d | 0 | 363 | Warning
40396 | Solano PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22040FS-1d |  | 0 | 363 | Warning
40397 | Solano PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40398 | Solano PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40399 | Solano PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
40400 | Solano PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40401 | Solano PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22047SS | 0 | 486 | Warning
40402 | Solano PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22046SS |  | 0 | 424 | Warning
40403 | Solano PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40404 | Solano PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40405 | Solano PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40406 | Solano PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22052SS | 0 | 486 | Warning
40407 | Solano PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22051SS | 22066SS | 0 | 466 | Warning
40408 | Solano PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40409 | Solano PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40410 | Solano PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40411 | Solano PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40412 | Solano PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22058SS | 0 | 345 | Warning
40413 | Solano PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22057SS | 22059SS,22060 | 0 | 345 | Warning
40414 | Solano PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22058SS | 22060 | 0 | 345 | Warning
40415 | Solano PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22058,22059 |  | 0 | 345 | Warning
40416 | Solano PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40417 | Solano PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40418 | Solano PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22064SS | 0 | 486 | Warning
40419 | Solano PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22063SS |  | 0 | 424 | Warning
40420 | Solano PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40421 | Solano PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22052SS |  | 0 | 466 | Warning
40422 | Solano PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40423 | Solano PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22069SS | 0 | 486 | Warning
40424 | Solano PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22068SS |  | 0 | 466 | Warning
40425 | Solano PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40426 | Solano PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22072SS+18d | 0 | 373 | Warning
40427 | Solano PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22071SS+18d |  | 0 | 373 | Warning
40428 | Solano PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40429 | Solano PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22075SS | 0 | 362 | Warning
40430 | Solano PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22074SS |  | 0 | 362 | Warning
40431 | Solano PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22077 | 0 | 345 | Warning
40432 | Solano PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22076 |  | 0 | 345 | Warning
40433 | Solano PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40434 | Solano PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40435 | Solano PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22081SS | 0 | 362 | Warning
40436 | Solano PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22080SS | 22082SS | 0 | 362 | Warning
40437 | Solano PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22081SS | 22083SS | 0 | 362 | Warning
40438 | Solano PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22082SS | 22084SS | 0 | 362 | Warning
40439 | Solano PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22083SS | 22085SS | 0 | 362 | Warning
40440 | Solano PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22084SS | 22086SS | 0 | 362 | Warning
40441 | Solano PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22085SS | 22087SS | 0 | 362 | Warning
40442 | Solano PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22086SS | 22088SS | 0 | 362 | Warning
40443 | Solano PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22087SS | 22089SS | 0 | 362 | Warning
40444 | Solano PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22088SS | 22090SS | 0 | 362 | Warning
40445 | Solano PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22089SS |  | 0 | 362 | Warning
40446 | Solano PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40447 | Solano PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40450 | Solano PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22094SS |  | 0 | 384 | Warning
40451 | Solano PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40452 | Solano PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22105 | 0 | 234 | Warning
40453 | Solano PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22106 | 0 | 234 | Warning
40455 | Solano PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40456 | Solano PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22102SS,22110SS+20d | 0 | 240 | Warning
40457 | Solano PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22101SS | 22103SS,22111SS+20d | 0 | 309 | Warning
40458 | Solano PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22102SS | 22112SS+20d | 0 | 309 | Warning
40459 | Solano PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40460 | Solano PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22097 | 22106SS | 0 | 234 | Warning
40461 | Solano PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22098,22105SS |  | 0 | 234 | Warning
40462 | Solano PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22115FS+12d | 0 | 240 | Warning
40463 | Solano PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22109SS | 0 | 321 | Warning
40464 | Solano PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22108SS |  | 0 | 321 | Warning
40465 | Solano PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22101SS+20d |  | 0 | 240 | Warning
40466 | Solano PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22102SS+20d |  | 0 | 240 | Warning
40467 | Solano PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22103SS+20d |  | 0 | 240 | Warning
40468 | Solano PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22115SS+44d | 0 | 240 | Warning
40469 | Solano PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40470 | Solano PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22107FS+12d,22113SS+44d |  | 0 | 240 | Warning
40472 | Sonoma PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
40473 | Sonoma PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40477 | Sonoma PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40478 | Sonoma PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40479 | Sonoma PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40480 | Sonoma PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40481 | Sonoma PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40482 | Sonoma PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40483 | Sonoma PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40484 | Sonoma PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40485 | Sonoma PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40486 | Sonoma PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40487 | Sonoma PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40488 | Sonoma PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40489 | Sonoma PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40498 | Sonoma PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
40499 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22145SS | 0 | 414 | Warning
40500 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22144SS |  | 0 | 414 | Warning
40501 | Sonoma PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22147SS | 0 | 362 | Warning
40502 | Sonoma PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22146SS |  | 0 | 362 | Warning
40503 | Sonoma PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40504 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22150SS | 0 | 364 | Warning
40505 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22149SS |  | 0 | 353 | Warning
40506 | Sonoma PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40507 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22153SS | 0 | 300 | Warning
40508 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22152SS |  | 0 | 288 | Warning
40509 | Sonoma PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40510 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22156SS | 0 | 279 | Warning
40511 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22155SS |  | 0 | 268 | Warning
40512 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22158SS | 0 | 246 | Warning
40513 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22157SS |  | 0 | 246 | Warning
40514 | Sonoma PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40515 | Sonoma PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40517 | Sonoma PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40518 | Sonoma PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40519 | Sonoma PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40520 | Sonoma PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40523 | Sonoma PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.17 | 233 | Warning
40526 | Sonoma PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22169FS-1d |  | 0.2 | 233 | Warning
40528 | Sonoma PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 466d |  | 22174 | 0 | 466 | Warning
40529 | Sonoma PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22173 |  | 0 | 466 | Warning
40530 | Sonoma PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40531 | Sonoma PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22177FS+19d | 0 | 405 | Warning
40532 | Sonoma PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22176FS+19d | 22178 | 0 | 405 | Warning
40533 | Sonoma PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22177 |  | 0 | 405 | Warning
40534 | Sonoma PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40535 | Sonoma PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22181 | 0 | 363 | Warning
40536 | Sonoma PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22180 | 22182FS-1d | 0 | 363 | Warning
40537 | Sonoma PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22181FS-1d |  | 0 | 363 | Warning
40538 | Sonoma PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40539 | Sonoma PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40540 | Sonoma PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
40541 | Sonoma PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40542 | Sonoma PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22188SS | 0 | 486 | Warning
40543 | Sonoma PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22187SS |  | 0 | 424 | Warning
40544 | Sonoma PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40545 | Sonoma PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40546 | Sonoma PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40547 | Sonoma PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22193SS | 0 | 486 | Warning
40548 | Sonoma PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22192SS | 22207SS | 0 | 466 | Warning
40549 | Sonoma PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40550 | Sonoma PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40551 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40552 | Sonoma PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40553 | Sonoma PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22199SS | 0 | 345 | Warning
40554 | Sonoma PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22198SS | 22200SS,22201 | 0 | 345 | Warning
40555 | Sonoma PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22199SS | 22201 | 0 | 345 | Warning
40556 | Sonoma PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22199,22200 |  | 0 | 345 | Warning
40557 | Sonoma PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40558 | Sonoma PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40559 | Sonoma PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22205SS | 0 | 486 | Warning
40560 | Sonoma PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22204SS |  | 0 | 424 | Warning
40561 | Sonoma PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40562 | Sonoma PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22193SS |  | 0 | 466 | Warning
40563 | Sonoma PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40564 | Sonoma PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22210SS | 0 | 486 | Warning
40565 | Sonoma PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22209SS |  | 0 | 466 | Warning
40566 | Sonoma PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40567 | Sonoma PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22213SS+18d | 0 | 373 | Warning
40568 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22212SS+18d |  | 0 | 373 | Warning
40569 | Sonoma PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40570 | Sonoma PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22216SS | 0 | 362 | Warning
40571 | Sonoma PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22215SS |  | 0 | 362 | Warning
40572 | Sonoma PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22218 | 0 | 345 | Warning
40573 | Sonoma PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22217 |  | 0 | 345 | Warning
40574 | Sonoma PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40575 | Sonoma PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40576 | Sonoma PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22222SS | 0 | 362 | Warning
40577 | Sonoma PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22221SS | 22223SS | 0 | 362 | Warning
40578 | Sonoma PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22222SS | 22224SS | 0 | 362 | Warning
40579 | Sonoma PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22223SS | 22225SS | 0 | 362 | Warning
40580 | Sonoma PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22224SS | 22226SS | 0 | 362 | Warning
40581 | Sonoma PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22225SS | 22227SS | 0 | 362 | Warning
40582 | Sonoma PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22226SS | 22228SS | 0 | 362 | Warning
40583 | Sonoma PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22227SS | 22229SS | 0 | 362 | Warning
40584 | Sonoma PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22228SS | 22230SS | 0 | 362 | Warning
40585 | Sonoma PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22229SS | 22231SS | 0 | 362 | Warning
40586 | Sonoma PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22230SS |  | 0 | 362 | Warning
40587 | Sonoma PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40588 | Sonoma PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40591 | Sonoma PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22235SS |  | 0 | 384 | Warning
40592 | Sonoma PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40593 | Sonoma PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22246 | 0 | 234 | Warning
40594 | Sonoma PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22247 | 0 | 234 | Warning
40596 | Sonoma PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40597 | Sonoma PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22243SS,22251SS+20d | 0 | 240 | Warning
40598 | Sonoma PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22242SS | 22244SS,22252SS+20d | 0 | 309 | Warning
40599 | Sonoma PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22243SS | 22253SS+20d | 0 | 309 | Warning
40600 | Sonoma PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40601 | Sonoma PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22238 | 22247SS | 0 | 234 | Warning
40602 | Sonoma PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22239,22246SS |  | 0 | 234 | Warning
40603 | Sonoma PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22256FS+12d | 0 | 240 | Warning
40604 | Sonoma PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22250SS | 0 | 321 | Warning
40605 | Sonoma PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22249SS |  | 0 | 321 | Warning
40606 | Sonoma PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22242SS+20d |  | 0 | 240 | Warning
40607 | Sonoma PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22243SS+20d |  | 0 | 240 | Warning
40608 | Sonoma PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22244SS+20d |  | 0 | 240 | Warning
40609 | Sonoma PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22256SS+44d | 0 | 240 | Warning
40610 | Sonoma PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40611 | Sonoma PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22248FS+12d,22254SS+44d |  | 0 | 240 | Warning
40613 | Stanislaus PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.22 | 235 | Warning
40614 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
40619 | Stanislaus PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40620 | Stanislaus PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40621 | Stanislaus PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40622 | Stanislaus PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40623 | Stanislaus PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40624 | Stanislaus PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40625 | Stanislaus PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40626 | Stanislaus PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40627 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40628 | Stanislaus PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40629 | Stanislaus PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40630 | Stanislaus PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40639 | Stanislaus PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.1 | 445 | Warning
40640 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22286SS | 0 | 414 | Warning
40641 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22285SS |  | 0 | 414 | Warning
40642 | Stanislaus PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22288SS | 0 | 362 | Warning
40643 | Stanislaus PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22287SS |  | 0 | 362 | Warning
40644 | Stanislaus PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40645 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22291SS | 0 | 364 | Warning
40646 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22290SS |  | 0 | 353 | Warning
40647 | Stanislaus PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40648 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22294SS | 0 | 300 | Warning
40649 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22293SS |  | 0 | 288 | Warning
40650 | Stanislaus PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40651 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22297SS | 0 | 279 | Warning
40652 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22296SS |  | 0 | 268 | Warning
40653 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22299SS | 0 | 246 | Warning
40654 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22298SS |  | 0 | 246 | Warning
40655 | Stanislaus PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40656 | Stanislaus PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40658 | Stanislaus PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40659 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40660 | Stanislaus PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40661 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40664 | Stanislaus PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.28 | 233 | Warning
40667 | Stanislaus PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22310FS-1d |  | 0.4 | 233 | Warning
40670 | Stanislaus PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22314 |  | 0.2 | 466 | Warning
40671 | Stanislaus PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40672 | Stanislaus PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22318FS+19d | 0.2 | 405 | Warning
40673 | Stanislaus PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22317FS+19d | 22319 | 0 | 405 | Warning
40674 | Stanislaus PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22318 |  | 0 | 405 | Warning
40675 | Stanislaus PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40676 | Stanislaus PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22322 | 0 | 363 | Warning
40677 | Stanislaus PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22321 | 22323FS-1d | 0 | 363 | Warning
40678 | Stanislaus PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22322FS-1d |  | 0 | 363 | Warning
40679 | Stanislaus PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40680 | Stanislaus PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40681 | Stanislaus PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
40682 | Stanislaus PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40683 | Stanislaus PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22329SS | 0 | 486 | Warning
40684 | Stanislaus PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22328SS |  | 0 | 424 | Warning
40685 | Stanislaus PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40686 | Stanislaus PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40687 | Stanislaus PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40688 | Stanislaus PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22334SS | 0 | 486 | Warning
40689 | Stanislaus PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22333SS | 22348SS | 0 | 466 | Warning
40690 | Stanislaus PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40691 | Stanislaus PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40692 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40693 | Stanislaus PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40694 | Stanislaus PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22340SS | 0 | 345 | Warning
40695 | Stanislaus PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22339SS | 22341SS,22342 | 0 | 345 | Warning
40696 | Stanislaus PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22340SS | 22342 | 0 | 345 | Warning
40697 | Stanislaus PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22340,22341 |  | 0 | 345 | Warning
40698 | Stanislaus PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40699 | Stanislaus PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40700 | Stanislaus PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22346SS | 0 | 486 | Warning
40701 | Stanislaus PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22345SS |  | 0 | 424 | Warning
40702 | Stanislaus PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40703 | Stanislaus PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22334SS |  | 0 | 466 | Warning
40704 | Stanislaus PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40705 | Stanislaus PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22351SS | 0 | 486 | Warning
40706 | Stanislaus PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22350SS |  | 0 | 466 | Warning
40707 | Stanislaus PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40708 | Stanislaus PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22354SS+18d | 0 | 373 | Warning
40709 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22353SS+18d |  | 0 | 373 | Warning
40710 | Stanislaus PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40711 | Stanislaus PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22357SS | 0 | 362 | Warning
40712 | Stanislaus PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22356SS |  | 0 | 362 | Warning
40713 | Stanislaus PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22359 | 0 | 345 | Warning
40714 | Stanislaus PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22358 |  | 0 | 345 | Warning
40715 | Stanislaus PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40716 | Stanislaus PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40717 | Stanislaus PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22363SS | 0 | 362 | Warning
40718 | Stanislaus PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22362SS | 22364SS | 0 | 362 | Warning
40719 | Stanislaus PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22363SS | 22365SS | 0 | 362 | Warning
40720 | Stanislaus PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22364SS | 22366SS | 0 | 362 | Warning
40721 | Stanislaus PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22365SS | 22367SS | 0 | 362 | Warning
40722 | Stanislaus PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22366SS | 22368SS | 0 | 362 | Warning
40723 | Stanislaus PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22367SS | 22369SS | 0 | 362 | Warning
40724 | Stanislaus PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22368SS | 22370SS | 0 | 362 | Warning
40725 | Stanislaus PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22369SS | 22371SS | 0 | 362 | Warning
40726 | Stanislaus PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22370SS | 22372SS | 0 | 362 | Warning
40727 | Stanislaus PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22371SS |  | 0 | 362 | Warning
40728 | Stanislaus PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40729 | Stanislaus PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40732 | Stanislaus PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22376SS |  | 0 | 384 | Warning
40733 | Stanislaus PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40734 | Stanislaus PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22387 | 0 | 234 | Warning
40735 | Stanislaus PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22388 | 0 | 234 | Warning
40737 | Stanislaus PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40738 | Stanislaus PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22384SS,22392SS+20d | 0 | 240 | Warning
40739 | Stanislaus PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22383SS | 22385SS,22393SS+20d | 0 | 309 | Warning
40740 | Stanislaus PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22384SS | 22394SS+20d | 0 | 309 | Warning
40741 | Stanislaus PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40742 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22379 | 22388SS | 0 | 234 | Warning
40743 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22380,22387SS |  | 0 | 234 | Warning
40744 | Stanislaus PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22397FS+12d | 0 | 240 | Warning
40745 | Stanislaus PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22391SS | 0 | 321 | Warning
40746 | Stanislaus PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22390SS |  | 0 | 321 | Warning
40747 | Stanislaus PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22383SS+20d |  | 0 | 240 | Warning
40748 | Stanislaus PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22384SS+20d |  | 0 | 240 | Warning
40749 | Stanislaus PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22385SS+20d |  | 0 | 240 | Warning
40750 | Stanislaus PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22397SS+44d | 0 | 240 | Warning
40751 | Stanislaus PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40752 | Stanislaus PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22389FS+12d,22395SS+44d |  | 0 | 240 | Warning
40754 | Sutter PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
40755 | Sutter PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40759 | Sutter PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40760 | Sutter PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40761 | Sutter PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40762 | Sutter PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40763 | Sutter PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40764 | Sutter PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40765 | Sutter PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40766 | Sutter PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40767 | Sutter PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40768 | Sutter PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40769 | Sutter PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40770 | Sutter PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40771 | Sutter PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40780 | Sutter PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
40781 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22427SS | 0 | 414 | Warning
40782 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22426SS |  | 0 | 414 | Warning
40783 | Sutter PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22429SS | 0 | 362 | Warning
40784 | Sutter PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22428SS |  | 0 | 362 | Warning
40785 | Sutter PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40786 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22432SS | 0 | 364 | Warning
40787 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22431SS |  | 0 | 353 | Warning
40788 | Sutter PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40789 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22435SS | 0 | 300 | Warning
40790 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22434SS |  | 0 | 288 | Warning
40791 | Sutter PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40792 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22438SS | 0 | 279 | Warning
40793 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22437SS |  | 0 | 268 | Warning
40794 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22440SS | 0 | 246 | Warning
40795 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22439SS |  | 0 | 246 | Warning
40796 | Sutter PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40797 | Sutter PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40799 | Sutter PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40800 | Sutter PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40801 | Sutter PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40802 | Sutter PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40805 | Sutter PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.22 | 233 | Warning
40808 | Sutter PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22451FS-1d |  | 0.2 | 233 | Warning
40811 | Sutter PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22455 |  | 0 | 466 | Warning
40812 | Sutter PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40814 | Sutter PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22458FS+19d | 22460 | 0 | 405 | Warning
40815 | Sutter PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22459 |  | 0 | 405 | Warning
40816 | Sutter PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40817 | Sutter PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22463 | 0 | 363 | Warning
40818 | Sutter PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22462 | 22464FS-1d | 0 | 363 | Warning
40819 | Sutter PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22463FS-1d |  | 0 | 363 | Warning
40820 | Sutter PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40821 | Sutter PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40822 | Sutter PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
40823 | Sutter PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40824 | Sutter PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22470SS | 0 | 486 | Warning
40825 | Sutter PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22469SS |  | 0 | 424 | Warning
40826 | Sutter PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40827 | Sutter PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40828 | Sutter PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40829 | Sutter PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22475SS | 0 | 486 | Warning
40830 | Sutter PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22474SS | 22489SS | 0 | 466 | Warning
40831 | Sutter PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40832 | Sutter PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
40833 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
40834 | Sutter PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40835 | Sutter PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22481SS | 0 | 345 | Warning
40836 | Sutter PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22480SS | 22482SS,22483 | 0 | 345 | Warning
40837 | Sutter PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22481SS | 22483 | 0 | 345 | Warning
40838 | Sutter PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22481,22482 |  | 0 | 345 | Warning
40839 | Sutter PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40840 | Sutter PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
40841 | Sutter PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22487SS | 0 | 486 | Warning
40842 | Sutter PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22486SS |  | 0 | 424 | Warning
40843 | Sutter PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
40844 | Sutter PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22475SS |  | 0 | 466 | Warning
40845 | Sutter PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
40846 | Sutter PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22492SS | 0 | 486 | Warning
40847 | Sutter PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22491SS |  | 0 | 466 | Warning
40848 | Sutter PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
40849 | Sutter PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22495SS+18d | 0 | 373 | Warning
40850 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22494SS+18d |  | 0 | 373 | Warning
40851 | Sutter PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
40852 | Sutter PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22498SS | 0 | 362 | Warning
40853 | Sutter PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22497SS |  | 0 | 362 | Warning
40854 | Sutter PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22500 | 0 | 345 | Warning
40855 | Sutter PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22499 |  | 0 | 345 | Warning
40856 | Sutter PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
40857 | Sutter PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40858 | Sutter PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22504SS | 0 | 362 | Warning
40859 | Sutter PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22503SS | 22505SS | 0 | 362 | Warning
40860 | Sutter PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22504SS | 22506SS | 0 | 362 | Warning
40861 | Sutter PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22505SS | 22507SS | 0 | 362 | Warning
40862 | Sutter PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22506SS | 22508SS | 0 | 362 | Warning
40863 | Sutter PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22507SS | 22509SS | 0 | 362 | Warning
40864 | Sutter PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22508SS | 22510SS | 0 | 362 | Warning
40865 | Sutter PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22509SS | 22511SS | 0 | 362 | Warning
40866 | Sutter PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22510SS | 22512SS | 0 | 362 | Warning
40867 | Sutter PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22511SS | 22513SS | 0 | 362 | Warning
40868 | Sutter PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22512SS |  | 0 | 362 | Warning
40869 | Sutter PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40870 | Sutter PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40873 | Sutter PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22517SS |  | 0 | 384 | Warning
40874 | Sutter PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40875 | Sutter PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22528 | 0 | 234 | Warning
40876 | Sutter PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22529 | 0 | 234 | Warning
40878 | Sutter PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40879 | Sutter PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22525SS,22533SS+20d | 0 | 240 | Warning
40880 | Sutter PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22524SS | 22526SS,22534SS+20d | 0 | 309 | Warning
40881 | Sutter PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22525SS | 22535SS+20d | 0 | 309 | Warning
40882 | Sutter PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40883 | Sutter PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22520 | 22529SS | 0 | 234 | Warning
40884 | Sutter PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22521,22528SS |  | 0 | 234 | Warning
40885 | Sutter PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22538FS+12d | 0 | 240 | Warning
40886 | Sutter PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22532SS | 0 | 321 | Warning
40887 | Sutter PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22531SS |  | 0 | 321 | Warning
40888 | Sutter PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22524SS+20d |  | 0 | 240 | Warning
40889 | Sutter PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22525SS+20d |  | 0 | 240 | Warning
40890 | Sutter PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22526SS+20d |  | 0 | 240 | Warning
40891 | Sutter PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22538SS+44d | 0 | 240 | Warning
40892 | Sutter PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
40893 | Sutter PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22530FS+12d,22536SS+44d |  | 0 | 240 | Warning
40895 | Tehama PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
40896 | Tehama PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
40900 | Tehama PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
40901 | Tehama PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
40902 | Tehama PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
40903 | Tehama PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
40904 | Tehama PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
40905 | Tehama PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
40906 | Tehama PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
40907 | Tehama PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
40908 | Tehama PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
40909 | Tehama PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
40910 | Tehama PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
40911 | Tehama PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40912 | Tehama PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
40921 | Tehama PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
40922 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22568SS | 0 | 414 | Warning
40923 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22567SS |  | 0 | 414 | Warning
40924 | Tehama PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22570SS | 0 | 362 | Warning
40925 | Tehama PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22569SS |  | 0 | 362 | Warning
40926 | Tehama PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
40927 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22573SS | 0 | 364 | Warning
40928 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22572SS |  | 0 | 353 | Warning
40929 | Tehama PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
40930 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22576SS | 0 | 300 | Warning
40931 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22575SS |  | 0 | 288 | Warning
40932 | Tehama PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
40933 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22579SS | 0 | 279 | Warning
40934 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22578SS |  | 0 | 268 | Warning
40935 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22581SS | 0 | 246 | Warning
40936 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22580SS |  | 0 | 246 | Warning
40937 | Tehama PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
40938 | Tehama PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
40940 | Tehama PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
40941 | Tehama PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
40942 | Tehama PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
40943 | Tehama PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
40946 | Tehama PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
40949 | Tehama PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22592FS-1d |  | 0.2 | 233 | Warning
40952 | Tehama PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22596 |  | 0 | 466 | Warning
40953 | Tehama PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
40954 | Tehama PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22600FS+19d | 0 | 405 | Warning
40955 | Tehama PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22599FS+19d | 22601 | 0 | 405 | Warning
40956 | Tehama PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22600 |  | 0 | 405 | Warning
40957 | Tehama PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
40958 | Tehama PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22604 | 0 | 363 | Warning
40959 | Tehama PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22603 | 22605FS-1d | 0 | 363 | Warning
40960 | Tehama PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22604FS-1d |  | 0 | 363 | Warning
40961 | Tehama PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
40962 | Tehama PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
40963 | Tehama PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
40964 | Tehama PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
40965 | Tehama PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22611SS | 0 | 362 | Warning
40966 | Tehama PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22610SS | 22612SS | 0 | 362 | Warning
40967 | Tehama PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22611SS | 22613SS | 0 | 362 | Warning
40968 | Tehama PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22612SS | 22614SS | 0 | 362 | Warning
40969 | Tehama PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22613SS | 22615SS | 0 | 362 | Warning
40970 | Tehama PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22614SS | 22616SS | 0 | 362 | Warning
40971 | Tehama PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22615SS | 22617SS | 0 | 362 | Warning
40972 | Tehama PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22616SS | 22618SS | 0 | 362 | Warning
40973 | Tehama PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22617SS | 22619SS | 0 | 362 | Warning
40974 | Tehama PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22618SS | 22620SS | 0 | 362 | Warning
40975 | Tehama PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22619SS |  | 0 | 362 | Warning
40976 | Tehama PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
40977 | Tehama PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
40980 | Tehama PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22624SS |  | 0 | 384 | Warning
40981 | Tehama PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
40982 | Tehama PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22635 | 0 | 234 | Warning
40983 | Tehama PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22636 | 0 | 234 | Warning
40985 | Tehama PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
40986 | Tehama PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22632SS,22640SS+20d | 0 | 240 | Warning
40987 | Tehama PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22631SS | 22633SS,22641SS+20d | 0 | 309 | Warning
40988 | Tehama PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22632SS | 22642SS+20d | 0 | 309 | Warning
40989 | Tehama PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
40990 | Tehama PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22627 | 22636SS | 0 | 234 | Warning
40991 | Tehama PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22628,22635SS |  | 0 | 234 | Warning
40992 | Tehama PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22645FS+12d | 0 | 240 | Warning
40993 | Tehama PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22639SS | 0 | 321 | Warning
40994 | Tehama PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22638SS |  | 0 | 321 | Warning
40995 | Tehama PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22631SS+20d |  | 0 | 240 | Warning
40996 | Tehama PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22632SS+20d |  | 0 | 240 | Warning
40997 | Tehama PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22633SS+20d |  | 0 | 240 | Warning
40998 | Tehama PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22645SS+44d | 0 | 240 | Warning
40999 | Tehama PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41000 | Tehama PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22637FS+12d,22643SS+44d |  | 0 | 240 | Warning
41002 | Trinity PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
41003 | Trinity PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
41007 | Trinity PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41008 | Trinity PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41009 | Trinity PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41010 | Trinity PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41011 | Trinity PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41012 | Trinity PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41013 | Trinity PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41014 | Trinity PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41015 | Trinity PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41016 | Trinity PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41017 | Trinity PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41018 | Trinity PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41019 | Trinity PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41028 | Trinity PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41029 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22675SS | 0 | 414 | Warning
41030 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22674SS |  | 0 | 414 | Warning
41031 | Trinity PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22677SS | 0 | 362 | Warning
41032 | Trinity PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22676SS |  | 0 | 362 | Warning
41033 | Trinity PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
41034 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22680SS | 0 | 364 | Warning
41035 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22679SS |  | 0 | 353 | Warning
41036 | Trinity PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
41037 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22683SS | 0 | 300 | Warning
41038 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22682SS |  | 0 | 288 | Warning
41039 | Trinity PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
41040 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22686SS | 0 | 279 | Warning
41041 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22685SS |  | 0 | 268 | Warning
41042 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22688SS | 0 | 246 | Warning
41043 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22687SS |  | 0 | 246 | Warning
41044 | Trinity PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41045 | Trinity PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
41047 | Trinity PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
41048 | Trinity PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41049 | Trinity PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41050 | Trinity PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
41053 | Trinity PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
41056 | Trinity PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22699FS-1d |  | 0.2 | 233 | Warning
41059 | Trinity PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22703 |  | 0 | 466 | Warning
41060 | Trinity PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41061 | Trinity PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22707FS+19d | 0 | 405 | Warning
41062 | Trinity PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22706FS+19d | 22708 | 0 | 405 | Warning
41063 | Trinity PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22707 |  | 0 | 405 | Warning
41064 | Trinity PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41065 | Trinity PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22711 | 0 | 363 | Warning
41066 | Trinity PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22710 | 22712FS-1d | 0 | 363 | Warning
41067 | Trinity PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22711FS-1d |  | 0 | 363 | Warning
41068 | Trinity PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41069 | Trinity PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41070 | Trinity PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
41071 | Trinity PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41072 | Trinity PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22718SS | 0 | 362 | Warning
41073 | Trinity PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22717SS | 22719SS | 0 | 362 | Warning
41074 | Trinity PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22718SS | 22720SS | 0 | 362 | Warning
41075 | Trinity PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22719SS | 22721SS | 0 | 362 | Warning
41076 | Trinity PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22720SS | 22722SS | 0 | 362 | Warning
41077 | Trinity PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22721SS | 22723SS | 0 | 362 | Warning
41078 | Trinity PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22722SS | 22724SS | 0 | 362 | Warning
41079 | Trinity PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22723SS | 22725SS | 0 | 362 | Warning
41080 | Trinity PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22724SS | 22726SS | 0 | 362 | Warning
41081 | Trinity PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22725SS | 22727SS | 0 | 362 | Warning
41082 | Trinity PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22726SS |  | 0 | 362 | Warning
41083 | Trinity PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
41084 | Trinity PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
41087 | Trinity PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22731SS |  | 0 | 384 | Warning
41088 | Trinity PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41089 | Trinity PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22742 | 0 | 234 | Warning
41090 | Trinity PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22743 | 0 | 234 | Warning
41092 | Trinity PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41093 | Trinity PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22739SS,22747SS+20d | 0 | 240 | Warning
41094 | Trinity PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22738SS | 22740SS,22748SS+20d | 0 | 309 | Warning
41095 | Trinity PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22739SS | 22749SS+20d | 0 | 309 | Warning
41096 | Trinity PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41097 | Trinity PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22734 | 22743SS | 0 | 234 | Warning
41098 | Trinity PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22735,22742SS |  | 0 | 234 | Warning
41099 | Trinity PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22752FS+12d | 0 | 240 | Warning
41100 | Trinity PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22746SS | 0 | 321 | Warning
41101 | Trinity PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22745SS |  | 0 | 321 | Warning
41102 | Trinity PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22738SS+20d |  | 0 | 240 | Warning
41103 | Trinity PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22739SS+20d |  | 0 | 240 | Warning
41104 | Trinity PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22740SS+20d |  | 0 | 240 | Warning
41105 | Trinity PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22752SS+44d | 0 | 240 | Warning
41106 | Trinity PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41107 | Trinity PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22744FS+12d,22750SS+44d |  | 0 | 240 | Warning
41109 | Tulare PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
41110 | Tulare PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
41114 | Tulare PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41115 | Tulare PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41116 | Tulare PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41117 | Tulare PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41118 | Tulare PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41119 | Tulare PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41120 | Tulare PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41121 | Tulare PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41122 | Tulare PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41123 | Tulare PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41124 | Tulare PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41125 | Tulare PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41126 | Tulare PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41135 | Tulare PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41136 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22782SS | 0 | 414 | Warning
41137 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22781SS |  | 0 | 414 | Warning
41138 | Tulare PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22784SS | 0 | 362 | Warning
41139 | Tulare PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22783SS |  | 0 | 362 | Warning
41140 | Tulare PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
41141 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22787SS | 0 | 364 | Warning
41142 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22786SS |  | 0 | 353 | Warning
41143 | Tulare PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
41144 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22790SS | 0 | 300 | Warning
41145 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 22789SS |  | 0 | 288 | Warning
41146 | Tulare PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
41147 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22793SS | 0 | 279 | Warning
41148 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22792SS |  | 0 | 268 | Warning
41149 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22795SS | 0 | 246 | Warning
41150 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22794SS |  | 0 | 246 | Warning
41151 | Tulare PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41152 | Tulare PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
41154 | Tulare PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
41155 | Tulare PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41156 | Tulare PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41157 | Tulare PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
41160 | Tulare PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
41163 | Tulare PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22806FS-1d |  | 0.2 | 233 | Warning
41166 | Tulare PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22810 |  | 0 | 466 | Warning
41167 | Tulare PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41168 | Tulare PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22814FS+19d | 0 | 405 | Warning
41169 | Tulare PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22813FS+19d | 22815 | 0 | 405 | Warning
41170 | Tulare PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22814 |  | 0 | 405 | Warning
41171 | Tulare PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41172 | Tulare PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22818 | 0 | 363 | Warning
41173 | Tulare PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22817 | 22819FS-1d | 0 | 363 | Warning
41174 | Tulare PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22818FS-1d |  | 0 | 363 | Warning
41175 | Tulare PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41176 | Tulare PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41177 | Tulare PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
41178 | Tulare PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41179 | Tulare PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22825SS | 0 | 486 | Warning
41180 | Tulare PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22824SS |  | 0 | 424 | Warning
41181 | Tulare PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41182 | Tulare PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41183 | Tulare PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41184 | Tulare PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22830SS | 0 | 486 | Warning
41185 | Tulare PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22829SS | 22844SS | 0 | 466 | Warning
41186 | Tulare PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41187 | Tulare PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
41188 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
41189 | Tulare PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41190 | Tulare PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22836SS | 0 | 345 | Warning
41191 | Tulare PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22835SS | 22837SS,22838 | 0 | 345 | Warning
41192 | Tulare PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22836SS | 22838 | 0 | 345 | Warning
41193 | Tulare PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22836,22837 |  | 0 | 345 | Warning
41194 | Tulare PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41195 | Tulare PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41196 | Tulare PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22842SS | 0 | 486 | Warning
41197 | Tulare PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22841SS |  | 0 | 424 | Warning
41198 | Tulare PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41199 | Tulare PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22830SS |  | 0 | 466 | Warning
41200 | Tulare PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41201 | Tulare PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22847SS | 0 | 486 | Warning
41202 | Tulare PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22846SS |  | 0 | 466 | Warning
41203 | Tulare PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41204 | Tulare PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22850SS+18d | 0 | 373 | Warning
41205 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22849SS+18d |  | 0 | 373 | Warning
41206 | Tulare PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41207 | Tulare PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22853SS | 0 | 362 | Warning
41208 | Tulare PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22852SS |  | 0 | 362 | Warning
41209 | Tulare PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22855 | 0 | 345 | Warning
41210 | Tulare PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22854 |  | 0 | 345 | Warning
41211 | Tulare PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41212 | Tulare PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41213 | Tulare PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22859SS | 0 | 362 | Warning
41214 | Tulare PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22858SS | 22860SS | 0 | 362 | Warning
41215 | Tulare PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22859SS | 22861SS | 0 | 362 | Warning
41216 | Tulare PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22860SS | 22862SS | 0 | 362 | Warning
41217 | Tulare PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22861SS | 22863SS | 0 | 362 | Warning
41218 | Tulare PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22862SS | 22864SS | 0 | 362 | Warning
41219 | Tulare PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22863SS | 22865SS | 0 | 362 | Warning
41220 | Tulare PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22864SS | 22866SS | 0 | 362 | Warning
41221 | Tulare PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22865SS | 22867SS | 0 | 362 | Warning
41222 | Tulare PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22866SS | 22868SS | 0 | 362 | Warning
41223 | Tulare PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22867SS |  | 0 | 362 | Warning
41224 | Tulare PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
41225 | Tulare PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
41228 | Tulare PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22872SS |  | 0 | 384 | Warning
41229 | Tulare PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41230 | Tulare PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22883 | 0 | 234 | Warning
41231 | Tulare PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22884 | 0 | 234 | Warning
41233 | Tulare PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41234 | Tulare PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22880SS,22888SS+20d | 0 | 240 | Warning
41235 | Tulare PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22879SS | 22881SS,22889SS+20d | 0 | 309 | Warning
41236 | Tulare PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22880SS | 22890SS+20d | 0 | 309 | Warning
41237 | Tulare PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41238 | Tulare PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22875 | 22884SS | 0 | 234 | Warning
41239 | Tulare PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22876,22883SS |  | 0 | 234 | Warning
41240 | Tulare PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22893FS+12d | 0 | 240 | Warning
41241 | Tulare PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22887SS | 0 | 321 | Warning
41242 | Tulare PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22886SS |  | 0 | 321 | Warning
41243 | Tulare PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22879SS+20d |  | 0 | 240 | Warning
41244 | Tulare PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22880SS+20d |  | 0 | 240 | Warning
41245 | Tulare PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 22881SS+20d |  | 0 | 240 | Warning
41246 | Tulare PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22893SS+44d | 0 | 240 | Warning
41247 | Tulare PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41248 | Tulare PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 22885FS+12d,22891SS+44d |  | 0 | 240 | Warning
41250 | Tuolumne PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.21 | 235 | Warning
41251 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.26 | 235 | Warning
41256 | Tuolumne PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41257 | Tuolumne PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41258 | Tuolumne PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41259 | Tuolumne PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41260 | Tuolumne PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41261 | Tuolumne PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41262 | Tuolumne PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41263 | Tuolumne PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41264 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41265 | Tuolumne PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41266 | Tuolumne PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41267 | Tuolumne PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41276 | Tuolumne PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41277 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22923SS | 0 | 414 | Warning
41278 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22922SS |  | 0 | 414 | Warning
41279 | Tuolumne PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22925SS | 0 | 362 | Warning
41280 | Tuolumne PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22924SS |  | 0 | 362 | Warning
41281 | Tuolumne PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 22928SS,22927SS | 0 | 342 | Warning
41282 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 22926SS |  | 0 | 385 | Warning
41283 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 22926SS |  | 0 | 371 | Warning
41284 | Tuolumne PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
41285 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 22931SS | 0 | 332 | Warning
41286 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 22930SS |  | 0 | 332 | Warning
41287 | Tuolumne PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
41288 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 22934SS | 0 | 311 | Warning
41289 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 22933SS |  | 0 | 311 | Warning
41290 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 22936SS | 0 | 289 | Warning
41291 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 22935SS |  | 0 | 289 | Warning
41292 | Tuolumne PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
41293 | Tuolumne PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
41294 | Tuolumne PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
41295 | Tuolumne PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
41296 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41297 | Tuolumne PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41298 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
41299 | Tuolumne PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
41300 | Tuolumne PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.13 | 277 | Warning
41303 | Tuolumne PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 22946FS-1d |  | 0 | 277 | Warning
41306 | Tuolumne PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22950 |  | 0 | 466 | Warning
41307 | Tuolumne PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41308 | Tuolumne PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22954FS+19d | 0 | 405 | Warning
41309 | Tuolumne PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22953FS+19d | 22955 | 0 | 405 | Warning
41310 | Tuolumne PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 22954 |  | 0 | 405 | Warning
41311 | Tuolumne PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41312 | Tuolumne PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22958 | 0 | 363 | Warning
41313 | Tuolumne PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22957 | 22959FS-1d | 0 | 363 | Warning
41314 | Tuolumne PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22958FS-1d |  | 0 | 363 | Warning
41315 | Tuolumne PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41316 | Tuolumne PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41317 | Tuolumne PR - Technical Activities | January 2, 2026 8:00 AM | June 12, 2026 5:00 PM | 112 | 333d |  |  | 0 | 333 | Warning
41318 | Tuolumne PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41319 | Tuolumne PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22965SS | 0 | 362 | Warning
41320 | Tuolumne PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22964SS | 22966SS | 0 | 362 | Warning
41321 | Tuolumne PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22965SS | 22967SS | 0 | 362 | Warning
41322 | Tuolumne PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22966SS | 22968SS | 0 | 362 | Warning
41323 | Tuolumne PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22967SS | 22969SS | 0 | 362 | Warning
41324 | Tuolumne PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22968SS | 22970SS | 0 | 362 | Warning
41325 | Tuolumne PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22969SS | 22971SS | 0 | 362 | Warning
41326 | Tuolumne PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22970SS | 22972SS | 0 | 362 | Warning
41327 | Tuolumne PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22971SS | 22973SS | 0 | 362 | Warning
41328 | Tuolumne PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22972SS | 22974SS | 0 | 362 | Warning
41329 | Tuolumne PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22973SS |  | 0 | 362 | Warning
41330 | Tuolumne PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
41331 | Tuolumne PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
41334 | Tuolumne PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22978SS |  | 0 | 384 | Warning
41335 | Tuolumne PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41336 | Tuolumne PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 22989 | 0 | 273 | Warning
41337 | Tuolumne PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 22990 | 0 | 273 | Warning
41339 | Tuolumne PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41340 | Tuolumne PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 22986SS,22994SS+20d | 0 | 299 | Warning
41341 | Tuolumne PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 22985SS | 22987SS,22995SS+20d | 0 | 299 | Warning
41342 | Tuolumne PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 22986SS | 22996SS+20d | 0 | 299 | Warning
41343 | Tuolumne PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41344 | Tuolumne PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 22981 | 22990SS | 0 | 273 | Warning
41345 | Tuolumne PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 22982,22989SS |  | 0 | 273 | Warning
41346 | Tuolumne PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 22999FS+12d | 0 | 279 | Warning
41347 | Tuolumne PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22993SS | 0 | 321 | Warning
41348 | Tuolumne PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22992SS |  | 0 | 321 | Warning
41349 | Tuolumne PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 22985SS+20d |  | 0 | 299 | Warning
41350 | Tuolumne PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 22986SS+20d |  | 0 | 299 | Warning
41351 | Tuolumne PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 22987SS+20d |  | 0 | 299 | Warning
41352 | Tuolumne PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 22999SS+44d | 0 | 279 | Warning
41353 | Tuolumne PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41354 | Tuolumne PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 22991FS+12d,22997SS+44d |  | 0 | 279 | Warning
41356 | Ventura PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
41357 | Ventura PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
41361 | Ventura PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41362 | Ventura PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41363 | Ventura PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41364 | Ventura PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41365 | Ventura PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41366 | Ventura PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41367 | Ventura PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41368 | Ventura PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41369 | Ventura PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41370 | Ventura PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41371 | Ventura PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41372 | Ventura PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41373 | Ventura PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41382 | Ventura PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41383 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23029SS | 0 | 414 | Warning
41384 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23028SS |  | 0 | 414 | Warning
41385 | Ventura PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23031SS | 0 | 362 | Warning
41386 | Ventura PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23030SS |  | 0 | 362 | Warning
41387 | Ventura PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23034SS,23033SS | 0 | 342 | Warning
41388 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 385d | 23032SS |  | 0 | 385 | Warning
41389 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 23032SS |  | 0 | 371 | Warning
41390 | Ventura PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
41391 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23037SS | 0 | 332 | Warning
41392 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 23036SS |  | 0 | 332 | Warning
41393 | Ventura PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
41394 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23040SS | 0 | 311 | Warning
41395 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 23039SS |  | 0 | 311 | Warning
41396 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23042SS | 0 | 289 | Warning
41397 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 23041SS |  | 0 | 289 | Warning
41398 | Ventura PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
41399 | Ventura PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
41400 | Ventura PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM | 211 | 234d |  |  | 0 | 234 | Warning
41401 | Ventura PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM | 166 | 279d |  |  | 0 | 279 | Warning
41402 | Ventura PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41403 | Ventura PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41404 | Ventura PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | 279 | Warning
41405 | Ventura PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
41406 | Ventura PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM | 295 | 277d |  |  | 0.2 | 277 | Warning
41409 | Ventura PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 23052FS-1d |  | 0.2 | 277 | Warning
41412 | Ventura PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23056 |  | 0 | 466 | Warning
41413 | Ventura PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41414 | Ventura PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23060FS+19d | 0 | 405 | Warning
41415 | Ventura PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23059FS+19d | 23061 | 0 | 405 | Warning
41416 | Ventura PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23060 |  | 0 | 405 | Warning
41417 | Ventura PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41418 | Ventura PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23064 | 0 | 363 | Warning
41419 | Ventura PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23063 | 23065FS-1d | 0 | 363 | Warning
41420 | Ventura PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23064FS-1d |  | 0 | 363 | Warning
41421 | Ventura PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41422 | Ventura PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41423 | Ventura PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | 298 | Warning
41424 | Ventura PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41425 | Ventura PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23071SS | 0 | 486 | Warning
41426 | Ventura PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23070SS |  | 0 | 424 | Warning
41427 | Ventura PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41428 | Ventura PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41429 | Ventura PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41430 | Ventura PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23076SS | 0 | 486 | Warning
41431 | Ventura PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23075SS | 23090SS | 0 | 466 | Warning
41432 | Ventura PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41433 | Ventura PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
41434 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
41435 | Ventura PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41436 | Ventura PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 23082SS | 0 | 345 | Warning
41437 | Ventura PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23081SS | 23083SS,23084 | 0 | 345 | Warning
41438 | Ventura PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23082SS | 23084 | 0 | 345 | Warning
41439 | Ventura PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23082,23083 |  | 0 | 345 | Warning
41440 | Ventura PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41441 | Ventura PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41442 | Ventura PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23088SS | 0 | 486 | Warning
41443 | Ventura PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23087SS |  | 0 | 424 | Warning
41444 | Ventura PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41445 | Ventura PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23076SS |  | 0 | 466 | Warning
41446 | Ventura PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41447 | Ventura PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23093SS | 0 | 486 | Warning
41448 | Ventura PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23092SS |  | 0 | 466 | Warning
41449 | Ventura PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41450 | Ventura PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 23096SS+18d | 0 | 373 | Warning
41451 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 23095SS+18d |  | 0 | 373 | Warning
41452 | Ventura PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41453 | Ventura PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 23099SS | 0 | 362 | Warning
41454 | Ventura PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 23098SS |  | 0 | 362 | Warning
41455 | Ventura PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23101 | 0 | 345 | Warning
41456 | Ventura PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23100 |  | 0 | 345 | Warning
41457 | Ventura PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41458 | Ventura PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41459 | Ventura PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23105SS | 0 | 362 | Warning
41460 | Ventura PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23104SS | 23106SS | 0 | 362 | Warning
41461 | Ventura PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23105SS | 23107SS | 0 | 362 | Warning
41462 | Ventura PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23106SS | 23108SS | 0 | 362 | Warning
41463 | Ventura PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23107SS | 23109SS | 0 | 362 | Warning
41464 | Ventura PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23108SS | 23110SS | 0 | 362 | Warning
41465 | Ventura PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23109SS | 23111SS | 0 | 362 | Warning
41466 | Ventura PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23110SS | 23112SS | 0 | 362 | Warning
41467 | Ventura PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23111SS | 23113SS | 0 | 362 | Warning
41468 | Ventura PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23112SS | 23114SS | 0 | 362 | Warning
41469 | Ventura PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23113SS |  | 0 | 362 | Warning
41470 | Ventura PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
41471 | Ventura PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
41474 | Ventura PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23118SS |  | 0 | 384 | Warning
41475 | Ventura PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41476 | Ventura PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 23129 | 0 | 273 | Warning
41477 | Ventura PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 23130 | 0 | 273 | Warning
41479 | Ventura PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41480 | Ventura PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23126SS,23134SS+20d | 0 | 299 | Warning
41481 | Ventura PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23125SS | 23127SS,23135SS+20d | 0 | 299 | Warning
41482 | Ventura PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23126SS | 23136SS+20d | 0 | 299 | Warning
41483 | Ventura PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41484 | Ventura PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 23121 | 23130SS | 0 | 273 | Warning
41485 | Ventura PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 23122,23129SS |  | 0 | 273 | Warning
41486 | Ventura PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 23139FS+12d | 0 | 279 | Warning
41487 | Ventura PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23133SS | 0 | 321 | Warning
41488 | Ventura PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23132SS |  | 0 | 321 | Warning
41489 | Ventura PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23125SS+20d |  | 0 | 299 | Warning
41490 | Ventura PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23126SS+20d |  | 0 | 299 | Warning
41491 | Ventura PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23127SS+20d |  | 0 | 299 | Warning
41492 | Ventura PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 23139SS+44d | 0 | 279 | Warning
41493 | Ventura PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41494 | Ventura PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 23131FS+12d,23137SS+44d |  | 0 | 279 | Warning
41496 | Yolo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
41497 | Yolo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
41501 | Yolo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41502 | Yolo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41503 | Yolo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41504 | Yolo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41505 | Yolo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41506 | Yolo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41507 | Yolo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41508 | Yolo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41509 | Yolo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41510 | Yolo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41511 | Yolo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41512 | Yolo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41513 | Yolo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41522 | Yolo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41523 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23169SS | 0 | 414 | Warning
41524 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23168SS |  | 0 | 414 | Warning
41525 | Yolo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23171SS | 0 | 362 | Warning
41526 | Yolo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23170SS |  | 0 | 362 | Warning
41527 | Yolo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
41528 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23174SS | 0 | 364 | Warning
41529 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23173SS |  | 0 | 353 | Warning
41530 | Yolo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
41531 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23177SS | 0 | 300 | Warning
41532 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 23176SS |  | 0 | 288 | Warning
41533 | Yolo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
41534 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23180SS | 0 | 279 | Warning
41535 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23179SS |  | 0 | 268 | Warning
41536 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 23182SS | 0 | 246 | Warning
41537 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23181SS |  | 0 | 246 | Warning
41538 | Yolo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41539 | Yolo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
41541 | Yolo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
41542 | Yolo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41543 | Yolo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41544 | Yolo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
41547 | Yolo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.21 | 233 | Warning
41550 | Yolo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 23193FS-1d |  | 0.2 | 233 | Warning
41553 | Yolo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23197 |  | 0.2 | 466 | Warning
41554 | Yolo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41555 | Yolo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23201FS+19d | 0 | 405 | Warning
41556 | Yolo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23200FS+19d | 23202 | 0 | 405 | Warning
41557 | Yolo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23201 |  | 0 | 405 | Warning
41558 | Yolo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41559 | Yolo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23205 | 0 | 363 | Warning
41560 | Yolo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23204 | 23206FS-1d | 0 | 363 | Warning
41561 | Yolo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23205FS-1d |  | 0 | 363 | Warning
41562 | Yolo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41563 | Yolo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41564 | Yolo PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM | 131 | 314d |  |  | 0 | 314 | Warning
41565 | Yolo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41566 | Yolo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23212SS | 0 | 362 | Warning
41567 | Yolo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23211SS | 23213SS | 0 | 362 | Warning
41568 | Yolo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23212SS | 23214SS | 0 | 362 | Warning
41569 | Yolo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23213SS | 23215SS | 0 | 362 | Warning
41570 | Yolo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23214SS | 23216SS | 0 | 362 | Warning
41571 | Yolo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23215SS | 23217SS | 0 | 362 | Warning
41572 | Yolo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23216SS | 23218SS | 0 | 362 | Warning
41573 | Yolo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23217SS | 23219SS | 0 | 362 | Warning
41574 | Yolo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23218SS | 23220SS | 0 | 362 | Warning
41575 | Yolo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23219SS | 23221SS | 0 | 362 | Warning
41576 | Yolo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23220SS |  | 0 | 362 | Warning
41577 | Yolo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
41578 | Yolo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
41581 | Yolo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23225SS |  | 0 | 384 | Warning
41582 | Yolo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41583 | Yolo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23236 | 0 | 234 | Warning
41584 | Yolo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23237 | 0 | 234 | Warning
41586 | Yolo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41587 | Yolo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 23233SS,23241SS+20d | 0 | 240 | Warning
41588 | Yolo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23232SS | 23234SS,23242SS+20d | 0 | 309 | Warning
41589 | Yolo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23233SS | 23243SS+20d | 0 | 309 | Warning
41590 | Yolo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41591 | Yolo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23228 | 23237SS | 0 | 234 | Warning
41592 | Yolo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23229,23236SS |  | 0 | 234 | Warning
41593 | Yolo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 23246FS+12d | 0 | 240 | Warning
41594 | Yolo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23240SS | 0 | 321 | Warning
41595 | Yolo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23239SS |  | 0 | 321 | Warning
41596 | Yolo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23232SS+20d |  | 0 | 240 | Warning
41597 | Yolo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23233SS+20d |  | 0 | 240 | Warning
41598 | Yolo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23234SS+20d |  | 0 | 240 | Warning
41599 | Yolo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 23246SS+44d | 0 | 240 | Warning
41600 | Yolo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41601 | Yolo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 23238FS+12d,23244SS+44d |  | 0 | 240 | Warning
41603 | Yuba PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.19 | 235 | Warning
41604 | Yuba PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM | 337 | 235d |  |  | 0.19 | 235 | Warning
41608 | Yuba PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41609 | Yuba PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41610 | Yuba PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41611 | Yuba PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41612 | Yuba PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41613 | Yuba PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
41614 | Yuba PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41615 | Yuba PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41616 | Yuba PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41617 | Yuba PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41618 | Yuba PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41619 | Yuba PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41620 | Yuba PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41629 | Yuba PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
41630 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23276SS | 0 | 414 | Warning
41631 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23275SS |  | 0 | 414 | Warning
41632 | Yuba PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23278SS | 0 | 362 | Warning
41633 | Yuba PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23277SS |  | 0 | 362 | Warning
41634 | Yuba PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
41635 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23281SS | 0 | 364 | Warning
41636 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23280SS |  | 0 | 353 | Warning
41637 | Yuba PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
41638 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23284SS | 0 | 300 | Warning
41639 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 23283SS |  | 0 | 288 | Warning
41640 | Yuba PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
41641 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23287SS | 0 | 279 | Warning
41642 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23286SS |  | 0 | 268 | Warning
41643 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 23289SS | 0 | 246 | Warning
41644 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23288SS |  | 0 | 246 | Warning
41645 | Yuba PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41646 | Yuba PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
41648 | Yuba PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM | 200 | 245d |  |  | 0 | 245 | Warning
41649 | Yuba PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41650 | Yuba PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
41651 | Yuba PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
41654 | Yuba PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 339 | 233d |  |  | 0.2 | 233 | Warning
41657 | Yuba PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 23300FS-1d |  | 0.2 | 233 | Warning
41660 | Yuba PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23304 |  | 0 | 466 | Warning
41661 | Yuba PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | 357 | Warning
41662 | Yuba PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23308FS+19d | 0.2 | 405 | Warning
41663 | Yuba PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23307FS+19d | 23309 | 0 | 405 | Warning
41664 | Yuba PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23308 |  | 0 | 405 | Warning
41665 | Yuba PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41666 | Yuba PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23312 | 0 | 363 | Warning
41667 | Yuba PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23311 | 23313FS-1d | 0 | 363 | Warning
41668 | Yuba PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23312FS-1d |  | 0 | 363 | Warning
41669 | Yuba PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41670 | Yuba PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41671 | Yuba PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0.02 | 298 | Warning
41672 | Yuba PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41673 | Yuba PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23319SS | 0 | 486 | Warning
41674 | Yuba PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23318SS |  | 0 | 424 | Warning
41675 | Yuba PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41676 | Yuba PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41677 | Yuba PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41678 | Yuba PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23324SS | 0 | 486 | Warning
41679 | Yuba PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23323SS | 23338SS | 0 | 466 | Warning
41680 | Yuba PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41681 | Yuba PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
41682 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | 373 | Warning
41683 | Yuba PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41684 | Yuba PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 23330SS | 0 | 345 | Warning
41685 | Yuba PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23329SS | 23331SS,23332 | 0 | 345 | Warning
41686 | Yuba PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23330SS | 23332 | 0 | 345 | Warning
41687 | Yuba PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23330,23331 |  | 0 | 345 | Warning
41688 | Yuba PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41689 | Yuba PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  |  | 0 | 362 | Warning
41690 | Yuba PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23336SS | 0 | 486 | Warning
41691 | Yuba PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23335SS |  | 0 | 424 | Warning
41692 | Yuba PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | 362 | Warning
41694 | Yuba PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | 466 | Warning
41695 | Yuba PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23341SS | 0 | 486 | Warning
41696 | Yuba PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23340SS |  | 0 | 466 | Warning
41697 | Yuba PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d |  |  | 0 | 373 | Warning
41698 | Yuba PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 23344SS+18d | 0 | 373 | Warning
41699 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 23343SS+18d |  | 0 | 373 | Warning
41700 | Yuba PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 169 | 298d |  |  | 0 | 298 | Warning
41701 | Yuba PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 23347SS | 0 | 362 | Warning
41702 | Yuba PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 23346SS |  | 0 | 362 | Warning
41703 | Yuba PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23349 | 0 | 345 | Warning
41704 | Yuba PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23348 |  | 0 | 345 | Warning
41705 | Yuba PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41706 | Yuba PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41707 | Yuba PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23353SS | 0 | 362 | Warning
41708 | Yuba PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23352SS | 23354SS | 0 | 362 | Warning
41709 | Yuba PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23353SS | 23355SS | 0 | 362 | Warning
41710 | Yuba PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23354SS | 23356SS | 0 | 362 | Warning
41711 | Yuba PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23355SS | 23357SS | 0 | 362 | Warning
41712 | Yuba PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23356SS | 23358SS | 0 | 362 | Warning
41713 | Yuba PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23357SS | 23359SS | 0 | 362 | Warning
41714 | Yuba PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23358SS | 23360SS | 0 | 362 | Warning
41715 | Yuba PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23359SS | 23361SS | 0 | 362 | Warning
41716 | Yuba PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23360SS | 23362SS | 0 | 362 | Warning
41717 | Yuba PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23361SS |  | 0 | 362 | Warning
41718 | Yuba PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
41719 | Yuba PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
41722 | Yuba PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23366SS |  | 0 | 384 | Warning
41723 | Yuba PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
41724 | Yuba PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23377 | 0 | 234 | Warning
41725 | Yuba PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23378 | 0 | 234 | Warning
41727 | Yuba PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41728 | Yuba PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 23374SS,23382SS+20d | 0 | 240 | Warning
41729 | Yuba PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23373SS | 23375SS,23383SS+20d | 0 | 309 | Warning
41730 | Yuba PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23374SS | 23384SS+20d | 0 | 309 | Warning
41731 | Yuba PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41732 | Yuba PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23369 | 23378SS | 0 | 234 | Warning
41733 | Yuba PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23370,23377SS |  | 0 | 234 | Warning
41734 | Yuba PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 23387FS+12d | 0 | 240 | Warning
41735 | Yuba PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23381SS | 0 | 321 | Warning
41736 | Yuba PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23380SS |  | 0 | 321 | Warning
41737 | Yuba PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23373SS+20d |  | 0 | 240 | Warning
41738 | Yuba PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23374SS+20d |  | 0 | 240 | Warning
41739 | Yuba PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 23375SS+20d |  | 0 | 240 | Warning
41740 | Yuba PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 23387SS+44d | 0 | 240 | Warning
41741 | Yuba PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
41742 | Yuba PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d | 23379FS+12d,23385SS+44d |  | 0 | 240 | Warning
41744 | CCLD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.49 | 235 | Warning
41758 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
41759 | CCLD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41760 | CCLD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41761 | CCLD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41762 | CCLD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41763 | CCLD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
41764 | CCLD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41765 | CCLD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41766 | CCLD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41767 | CCLD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41768 | CCLD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41769 | CCLD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41770 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41777 | CCLD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
41778 | CCLD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
41779 | CCLD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
41780 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23427SS | 0 | 424 | Warning
41781 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23426SS |  | 0 | 415 | Warning
41782 | CCLD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
41783 | CCLD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
41784 | CCLD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23431SS | 0 | 342 | Warning
41785 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 23430SS | 23432SS | 0 | 371 | Warning
41786 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 23431SS |  | 0 | 371 | Warning
41787 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23434SS | 0 | 332 | Warning
41788 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 23433SS |  | 0 | 332 | Warning
41789 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23436SS | 0 | 311 | Warning
41790 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 23435SS |  | 0 | 311 | Warning
41791 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23438SS | 0 | 289 | Warning
41792 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 23437SS |  | 0 | 289 | Warning
41793 | CCLD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
41794 | CCLD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
41795 | CCLD CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.35 | 233 | Warning
41798 | CCLD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 380 | 233d | 23442SS+40d |  | 0.4 | 233 | Warning
41801 | CCLD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41805 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41807 | CCLD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23452FS-1d | 23454 | 0 | 405 | Warning
41808 | CCLD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23453 |  | 0 | 405 | Warning
41809 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41810 | CCLD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23457 | 0 | 405 | Warning
41811 | CCLD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23456 | 23458 | 0 | 405 | Warning
41812 | CCLD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23457 |  | 0 | 405 | Warning
41813 | CCLD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41814 | CCLD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23461 | 0 | 364 | Warning
41815 | CCLD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23460 | 23463FS-1d | 0 | 363 | Warning
41816 | CCLD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41817 | CCLD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23461FS-1d |  | 0 | 363 | Warning
41818 | CCLD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
41819 | CCLD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41820 | CCLD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
41821 | CCLD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41822 | CCLD CDSS - Technical Activities | April 1, 2025 12:00 AM | August 3, 2026 5:00 PM | 338 | 298d |  |  | 0.24 | 298 | Warning
41833 | CCLD CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0.21 | 373 | Warning
41834 | CCLD CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d | 23478 | 23481FS+1d | 0.6 | 373 | Warning
41835 | CCLD CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 373d | 23480FS+1d |  | 0 | 373 | Warning
41836 | CCLD CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.07 | 298 | Warning
41838 | CCLD CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23483 | 23485FF | 0 | 345 | Warning
41839 | CCLD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23484FF | 23486 | 0 | 345 | Warning
41840 | CCLD CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23485 |  | 0 | 345 | Warning
41841 | CCLD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
41842 | CCLD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
41843 | CCLD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23490SS | 0 | 362 | Warning
41844 | CCLD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23489SS | 23491SS | 0 | 362 | Warning
41845 | CCLD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23490SS | 23492SS | 0 | 362 | Warning
41846 | CCLD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23491SS | 23493SS | 0 | 362 | Warning
41847 | CCLD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23492SS | 23494SS | 0 | 362 | Warning
41848 | CCLD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23493SS | 23495SS | 0 | 362 | Warning
41849 | CCLD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23494SS | 23496SS | 0 | 362 | Warning
41850 | CCLD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23495SS | 23497SS | 0 | 362 | Warning
41851 | CCLD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23496SS | 23498SS | 0 | 362 | Warning
41852 | CCLD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23497SS | 23499SS | 0 | 362 | Warning
41853 | CCLD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23498SS |  | 0 | 362 | Warning
41854 | CCLD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
41855 | CCLD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
41857 | CCLD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
41859 | CCLD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
41860 | CCLD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41861 | CCLD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
41862 | CCLD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23518 | 0 | 275 | Warning
41863 | CCLD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23519 | 0 | 275 | Warning
41865 | CCLD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
41866 | CCLD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23513SS,23521SS+20d | 0 | 299 | Warning
41867 | CCLD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23512SS | 23514SS,23522SS+20d | 0 | 299 | Warning
41868 | CCLD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23513SS | 23515SS,23523SS+20d | 0 | 299 | Warning
41869 | CCLD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23514SS | 23516SS,23524SS+20d | 0 | 299 | Warning
41870 | CCLD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23515SS | 23525SS+20d | 0 | 299 | Warning
41871 | CCLD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
41872 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23508 |  | 0 | 274 | Warning
41873 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23509 |  | 0 | 274 | Warning
41874 | CCLD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23528FS+13d | 0 | 279 | Warning
41875 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23512SS+20d |  | 0 | 299 | Warning
41876 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23513SS+20d |  | 0 | 299 | Warning
41877 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23514SS+20d |  | 0 | 299 | Warning
41878 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23515SS+20d |  | 0 | 299 | Warning
41879 | CCLD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23516SS+20d |  | 0 | 299 | Warning
41880 | CCLD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23528SS+40d | 0 | 283 | Warning
41881 | CCLD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
41882 | CCLD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 23520FS+13d,23526SS+40d |  | 0 | 279 | Warning
41884 | CFSD_Adoptions CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.44 | 235 | Warning
41898 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
41899 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
41900 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
41901 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41902 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
41903 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
41904 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
41905 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
41906 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
41907 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
41908 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41909 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
41916 | CFSD_Adoptions CDSS - Establish method for keeping interim processes and release notes current (if applicable) | May 30, 2025 8:00 AM | September 15, 2026 12:00 AM | 325 | 269d |  |  | 0 | 269 | Warning
41917 | CFSD_Adoptions CDSS - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 12:00 AM | 54 | 258d |  |  | 0 | 258 | Warning
41918 | CFSD_Adoptions CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0.2 | 446 | Warning
41919 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23566SS | 0 | 424 | Warning
41920 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23565SS |  | 0 | 415 | Warning
41921 | CFSD_Adoptions CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
41922 | CFSD_Adoptions CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
41923 | CFSD_Adoptions CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | 342 | Warning
41924 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23571SS | 0 | 364 | Warning
41925 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23570SS |  | 0 | 353 | Warning
41926 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23573SS | 0 | 300 | Warning
41927 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 23572SS |  | 0 | 288 | Warning
41928 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23575SS | 0 | 279 | Warning
41929 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23574SS |  | 0 | 268 | Warning
41930 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 12:00 AM | 20 | 258d |  | 23577SS | 0 | 258 | Warning
41931 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23576SS |  | 0 | 246 | Warning
41932 | CFSD_Adoptions CDSS - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
41933 | CFSD_Adoptions CDSS - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | 246 | Warning
41934 | CFSD_Adoptions CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.37 | 233 | Warning
41937 | CFSD_Adoptions CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | April 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 402 | 233d | 23581SS+40d |  | 0.4 | 233 | Warning
41940 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41943 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41945 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23590FS-1d | 23592 | 0.2 | 405 | Warning
41946 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23591 |  | 0 | 405 | Warning
41947 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41949 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23594 | 23596 | 0 | 405 | Warning
41950 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23595 |  | 0 | 405 | Warning
41951 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
41952 | CFSD_Adoptions CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23599 | 0 | 364 | Warning
41953 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23598 | 23601FS-1d | 0 | 363 | Warning
41954 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
41955 | CFSD_Adoptions CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23599FS-1d |  | 0 | 363 | Warning
41956 | CFSD_Adoptions CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
41957 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
41958 | CFSD_Adoptions CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
41959 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
41960 | CFSD_Adoptions CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.58 | 293 | Warning
41971 | CFSD_Adoptions CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 23616SS |  | 0.2 | 497 | Warning
41972 | CFSD_Adoptions CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
41973 | CFSD_Adoptions CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 23615 | 23620 | 0 | 298 | Warning
41974 | CFSD_Adoptions CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 23619 |  | 0 | 298 | Warning
41975 | CFSD_Adoptions CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
41976 | CFSD_Adoptions CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23623FS+1d,23625SS | 0 | 373 | Warning
41977 | CFSD_Adoptions CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 23622FS+1d |  | 0 | 373 | Warning
41978 | CFSD_Adoptions CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
41980 | CFSD_Adoptions CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23625 | 23627SS,23628 | 0 | 345 | Warning
41981 | CFSD_Adoptions CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23626SS | 23628 | 0 | 345 | Warning
41982 | CFSD_Adoptions CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23626,23627 |  | 0 | 345 | Warning
41983 | CFSD_Adoptions CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
41995 | CFSD_Adoptions CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.71 | 298 | Warning
42000 | CFSD_Adoptions CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
42001 | CFSD_Adoptions CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42002 | CFSD_Adoptions CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23649SS | 0 | 362 | Warning
42003 | CFSD_Adoptions CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23648SS | 23650SS | 0 | 362 | Warning
42004 | CFSD_Adoptions CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23649SS | 23651SS | 0 | 362 | Warning
42005 | CFSD_Adoptions CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23650SS | 23652SS | 0 | 362 | Warning
42006 | CFSD_Adoptions CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23651SS | 23653SS | 0 | 362 | Warning
42007 | CFSD_Adoptions CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23652SS | 23654SS | 0 | 362 | Warning
42008 | CFSD_Adoptions CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23653SS | 23655SS | 0 | 362 | Warning
42009 | CFSD_Adoptions CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23654SS | 23656SS | 0 | 362 | Warning
42010 | CFSD_Adoptions CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23655SS | 23657SS | 0 | 362 | Warning
42011 | CFSD_Adoptions CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23656SS | 23658SS | 0 | 362 | Warning
42012 | CFSD_Adoptions CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23657SS |  | 0 | 362 | Warning
42013 | CFSD_Adoptions CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 12:00 AM | 38 | 324d |  |  | 0 | 324 | Warning
42014 | CFSD_Adoptions CDSS - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 12:00 AM | 28 | 315d |  |  | 0 | 315 | Warning
42016 | CFSD_Adoptions CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42018 | CFSD_Adoptions CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42019 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42020 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42021 | CFSD_Adoptions CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 236d |  | 23677 | 0 | 236 | Warning
42022 | CFSD_Adoptions CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 236d |  | 23678 | 0 | 236 | Warning
42024 | CFSD_Adoptions CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42025 | CFSD_Adoptions CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d |  | 23672SS,23680SS+21d | 0 | 310 | Warning
42026 | CFSD_Adoptions CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23671SS | 23673SS,23681SS+21d | 0 | 310 | Warning
42027 | CFSD_Adoptions CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23672SS | 23674SS,23682SS+21d | 0 | 310 | Warning
42028 | CFSD_Adoptions CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23673SS | 23675SS,23683SS+21d | 0 | 310 | Warning
42029 | CFSD_Adoptions CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23674SS | 23684SS+21d | 0 | 310 | Warning
42030 | CFSD_Adoptions CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42031 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 23667 |  | 0 | 235 | Warning
42032 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 23668 |  | 0 | 235 | Warning
42033 | CFSD_Adoptions CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 242d |  | 23687FS+12d | 0 | 242 | Warning
42034 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Intake | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 103 | 239d | 23671SS+21d |  | 0 | 239 | Warning
42035 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 103 | 239d | 23672SS+21d |  | 0 | 239 | Warning
42036 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 103 | 239d | 23673SS+21d |  | 0 | 239 | Warning
42037 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 103 | 239d | 23674SS+21d |  | 0 | 239 | Warning
42038 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 103 | 239d | 23675SS+21d |  | 0 | 239 | Warning
42039 | CFSD_Adoptions CDSS - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 12:00 AM | 92 | 251d |  | 23687SS+40d | 0 | 251 | Warning
42040 | CFSD_Adoptions CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42041 | CFSD_Adoptions CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 12:00 AM | 58 | 241d | 23679FS+12d,23685SS+40d |  | 0 | 241 | Warning
42043 | CFSD_CSQMB CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.5 | 235 | Warning
42056 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42057 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42058 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42059 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
42060 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42061 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
42062 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42063 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
42064 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42065 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42066 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42067 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42068 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42075 | CFSD_CSQMB CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42076 | CFSD_CSQMB CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42077 | CFSD_CSQMB CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42078 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23725SS | 0 | 424 | Warning
42079 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23724SS |  | 0 | 415 | Warning
42080 | CFSD_CSQMB CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42081 | CFSD_CSQMB CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42082 | CFSD_CSQMB CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23729SS | 0 | 342 | Warning
42083 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 23728SS | 23730SS | 0 | 371 | Warning
42084 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 23729SS |  | 0 | 371 | Warning
42085 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23732SS | 0 | 332 | Warning
42086 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 23731SS |  | 0 | 332 | Warning
42087 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23734SS | 0 | 311 | Warning
42088 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 23733SS |  | 0 | 311 | Warning
42089 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23736SS | 0 | 289 | Warning
42090 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 23735SS |  | 0 | 289 | Warning
42091 | CFSD_CSQMB CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42092 | CFSD_CSQMB CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42093 | CFSD_CSQMB CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.33 | 233 | Warning
42096 | CFSD_CSQMB CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 380 | 233d | 23740SS+40d |  | 0.4 | 233 | Warning
42099 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42102 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 23747FS-1d |  | 0.4 | 466 | Warning
42103 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42105 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23750FS-1d | 23752 | 0.2 | 405 | Warning
42106 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23751 |  | 0 | 405 | Warning
42107 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42108 | CFSD_CSQMB CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23755 | 0 | 405 | Warning
42109 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23754 | 23756 | 0 | 405 | Warning
42110 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23755 |  | 0 | 405 | Warning
42111 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42112 | CFSD_CSQMB CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23759 | 0 | 364 | Warning
42113 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23758 | 23761FS-1d | 0 | 363 | Warning
42114 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42115 | CFSD_CSQMB CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23759FS-1d |  | 0 | 363 | Warning
42116 | CFSD_CSQMB CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42117 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42118 | CFSD_CSQMB CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42119 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42120 | CFSD_CSQMB CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.41 | 293 | Warning
42121 | CFSD_CSQMB CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
42124 | CFSD_CSQMB CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
42129 | CFSD_CSQMB CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 298d |  | 23776SS,23779 | 0.4 | 298 | Warning
42130 | CFSD_CSQMB CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 23775SS | 23777SS | 0 | 497 | Warning
42131 | CFSD_CSQMB CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 23776SS |  | 0 | 497 | Warning
42132 | CFSD_CSQMB CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42133 | CFSD_CSQMB CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 23775 | 23780 | 0 | 298 | Warning
42134 | CFSD_CSQMB CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 23779 |  | 0 | 298 | Warning
42135 | CFSD_CSQMB CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
42136 | CFSD_CSQMB CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23783FS+1d,23785SS | 0 | 373 | Warning
42137 | CFSD_CSQMB CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 23782FS+1d |  | 0 | 373 | Warning
42138 | CFSD_CSQMB CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
42140 | CFSD_CSQMB CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23785 | 23787SS,23788 | 0 | 345 | Warning
42141 | CFSD_CSQMB CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23786SS | 23788 | 0 | 345 | Warning
42142 | CFSD_CSQMB CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23786,23787 |  | 0 | 345 | Warning
42143 | CFSD_CSQMB CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
42148 | CFSD_CSQMB CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42149 | CFSD_CSQMB CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23796SS | 0 | 362 | Warning
42150 | CFSD_CSQMB CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23795SS | 23797SS | 0 | 362 | Warning
42151 | CFSD_CSQMB CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23796SS | 23798SS | 0 | 362 | Warning
42152 | CFSD_CSQMB CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23797SS | 23799SS | 0 | 362 | Warning
42153 | CFSD_CSQMB CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23798SS | 23800SS | 0 | 362 | Warning
42154 | CFSD_CSQMB CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23799SS | 23801SS | 0 | 362 | Warning
42155 | CFSD_CSQMB CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23800SS | 23802SS | 0 | 362 | Warning
42156 | CFSD_CSQMB CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23801SS | 23803SS | 0 | 362 | Warning
42157 | CFSD_CSQMB CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23802SS | 23804SS | 0 | 362 | Warning
42158 | CFSD_CSQMB CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23803SS | 23805SS | 0 | 362 | Warning
42159 | CFSD_CSQMB CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23804SS |  | 0 | 362 | Warning
42160 | CFSD_CSQMB CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42161 | CFSD_CSQMB CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42163 | CFSD_CSQMB CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42165 | CFSD_CSQMB CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42166 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42167 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42168 | CFSD_CSQMB CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23824 | 0 | 275 | Warning
42169 | CFSD_CSQMB CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23825 | 0 | 275 | Warning
42171 | CFSD_CSQMB CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42172 | CFSD_CSQMB CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23819SS,23827SS+20d | 0 | 299 | Warning
42173 | CFSD_CSQMB CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23818SS | 23820SS,23828SS+20d | 0 | 299 | Warning
42174 | CFSD_CSQMB CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23819SS | 23821SS,23829SS+20d | 0 | 299 | Warning
42175 | CFSD_CSQMB CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23820SS | 23822SS,23830SS+20d | 0 | 299 | Warning
42176 | CFSD_CSQMB CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23821SS | 23831SS+20d | 0 | 299 | Warning
42177 | CFSD_CSQMB CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42178 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23814 |  | 0 | 274 | Warning
42179 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23815 |  | 0 | 274 | Warning
42180 | CFSD_CSQMB CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23834FS+13d | 0 | 279 | Warning
42181 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23818SS+20d |  | 0 | 299 | Warning
42182 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23819SS+20d |  | 0 | 299 | Warning
42183 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23820SS+20d |  | 0 | 299 | Warning
42184 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23821SS+20d |  | 0 | 299 | Warning
42185 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23822SS+20d |  | 0 | 299 | Warning
42186 | CFSD_CSQMB CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23834SS+40d | 0 | 283 | Warning
42187 | CFSD_CSQMB CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42188 | CFSD_CSQMB CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 23826FS+13d,23832SS+40d |  | 0 | 279 | Warning
42190 | CFSD_Permanency CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.47 | 235 | Warning
42204 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42205 | CFSD_Permanency CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42206 | CFSD_Permanency CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42207 | CFSD_Permanency CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
42208 | CFSD_Permanency CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42209 | CFSD_Permanency CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
42210 | CFSD_Permanency CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42211 | CFSD_Permanency CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
42212 | CFSD_Permanency CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42213 | CFSD_Permanency CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42214 | CFSD_Permanency CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42215 | CFSD_Permanency CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42216 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42223 | CFSD_Permanency CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42224 | CFSD_Permanency CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42225 | CFSD_Permanency CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42226 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23873SS | 0 | 424 | Warning
42227 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23872SS |  | 0 | 415 | Warning
42228 | CFSD_Permanency CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42229 | CFSD_Permanency CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42230 | CFSD_Permanency CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23877SS | 0 | 342 | Warning
42231 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 23876SS | 23878SS | 0 | 371 | Warning
42232 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 23877SS |  | 0 | 371 | Warning
42233 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23880SS | 0 | 332 | Warning
42234 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 23879SS |  | 0 | 332 | Warning
42235 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23882SS | 0 | 311 | Warning
42236 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 23881SS |  | 0 | 311 | Warning
42237 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23884SS | 0 | 289 | Warning
42238 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 23883SS |  | 0 | 289 | Warning
42239 | CFSD_Permanency CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42240 | CFSD_Permanency CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42241 | CFSD_Permanency CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.33 | 233 | Warning
42244 | CFSD_Permanency CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 380 | 233d | 23888SS+40d |  | 0.4 | 233 | Warning
42246 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42249 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 23894FS-1d |  | 0.8 | 466 | Warning
42250 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42252 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23897FS-1d | 23899 | 0.2 | 405 | Warning
42253 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23898 |  | 0 | 405 | Warning
42254 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42255 | CFSD_Permanency CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23902 | 0 | 405 | Warning
42256 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23901 | 23903 | 0 | 405 | Warning
42257 | CFSD_Permanency CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23902 |  | 0 | 405 | Warning
42258 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42259 | CFSD_Permanency CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures an | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23906 | 0 | 364 | Warning
42260 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23905 | 23908FS-1d | 0 | 363 | Warning
42261 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42262 | CFSD_Permanency CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23906FS-1d |  | 0 | 363 | Warning
42263 | CFSD_Permanency CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42264 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42265 | CFSD_Permanency CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42266 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42267 | CFSD_Permanency CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.31 | 293 | Warning
42268 | CFSD_Permanency CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
42270 | CFSD_Permanency CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 23915SS |  | 0.2 | 405 | Warning
42271 | CFSD_Permanency CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
42277 | CFSD_Permanency CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 23922SS | 23924SS | 0 | 497 | Warning
42278 | CFSD_Permanency CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 23923SS |  | 0 | 497 | Warning
42279 | CFSD_Permanency CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42280 | CFSD_Permanency CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 23922 | 23927 | 0 | 298 | Warning
42281 | CFSD_Permanency CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 23926 |  | 0 | 298 | Warning
42282 | CFSD_Permanency CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
42283 | CFSD_Permanency CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23930FS+1d,23932SS | 0 | 373 | Warning
42284 | CFSD_Permanency CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 23929FS+1d |  | 0 | 373 | Warning
42285 | CFSD_Permanency CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
42287 | CFSD_Permanency CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23932 | 23934SS,23935 | 0 | 345 | Warning
42288 | CFSD_Permanency CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23933SS | 23935 | 0 | 345 | Warning
42289 | CFSD_Permanency CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23933,23934 |  | 0 | 345 | Warning
42290 | CFSD_Permanency CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
42295 | CFSD_Permanency CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42296 | CFSD_Permanency CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23943SS | 0 | 362 | Warning
42297 | CFSD_Permanency CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23942SS | 23944SS | 0 | 362 | Warning
42298 | CFSD_Permanency CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23943SS | 23945SS | 0 | 362 | Warning
42299 | CFSD_Permanency CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23944SS | 23946SS | 0 | 362 | Warning
42300 | CFSD_Permanency CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23945SS | 23947SS | 0 | 362 | Warning
42301 | CFSD_Permanency CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23946SS | 23948SS | 0 | 362 | Warning
42302 | CFSD_Permanency CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23947SS | 23949SS | 0 | 362 | Warning
42303 | CFSD_Permanency CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alt | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23948SS | 23950SS | 0 | 362 | Warning
42304 | CFSD_Permanency CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23949SS | 23951SS | 0 | 362 | Warning
42305 | CFSD_Permanency CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23950SS | 23952SS | 0 | 362 | Warning
42306 | CFSD_Permanency CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23951SS |  | 0 | 362 | Warning
42307 | CFSD_Permanency CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42308 | CFSD_Permanency CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42310 | CFSD_Permanency CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42312 | CFSD_Permanency CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42313 | CFSD_Permanency CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42314 | CFSD_Permanency CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42315 | CFSD_Permanency CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23971 | 0 | 275 | Warning
42316 | CFSD_Permanency CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23972 | 0 | 275 | Warning
42318 | CFSD_Permanency CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42319 | CFSD_Permanency CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23966SS,23974SS+20d | 0 | 299 | Warning
42320 | CFSD_Permanency CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23965SS | 23967SS,23975SS+20d | 0 | 299 | Warning
42321 | CFSD_Permanency CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23966SS | 23968SS,23976SS+20d | 0 | 299 | Warning
42322 | CFSD_Permanency CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23967SS | 23969SS,23977SS+20d | 0 | 299 | Warning
42323 | CFSD_Permanency CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 23968SS | 23978SS+20d | 0 | 299 | Warning
42324 | CFSD_Permanency CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42325 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23961 |  | 0 | 274 | Warning
42326 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23962 |  | 0 | 274 | Warning
42327 | CFSD_Permanency CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23981FS+13d | 0 | 279 | Warning
42328 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23965SS+20d |  | 0 | 299 | Warning
42329 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23966SS+20d |  | 0 | 299 | Warning
42330 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23967SS+20d |  | 0 | 299 | Warning
42331 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23968SS+20d |  | 0 | 299 | Warning
42332 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 23969SS+20d |  | 0 | 299 | Warning
42333 | CFSD_Permanency CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23981SS+40d | 0 | 283 | Warning
42334 | CFSD_Permanency CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42335 | CFSD_Permanency CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 23973FS+13d,23979SS+40d |  | 0 | 279 | Warning
42337 | CFSD_System of Care CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.47 | 235 | Warning
42350 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42351 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42352 | CFSD_System of Care CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42353 | CFSD_System of Care CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
42354 | CFSD_System of Care CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42355 | CFSD_System of Care CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
42356 | CFSD_System of Care CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42357 | CFSD_System of Care CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
42358 | CFSD_System of Care CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42359 | CFSD_System of Care CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42360 | CFSD_System of Care CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42361 | CFSD_System of Care CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42362 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42369 | CFSD_System of Care CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42370 | CFSD_System of Care CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42371 | CFSD_System of Care CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42372 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24019SS | 0 | 424 | Warning
42373 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24018SS |  | 0 | 415 | Warning
42374 | CFSD_System of Care CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42375 | CFSD_System of Care CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42376 | CFSD_System of Care CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24023SS | 0 | 342 | Warning
42377 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 24022SS | 24024SS | 0 | 371 | Warning
42378 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 24023SS |  | 0 | 371 | Warning
42379 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24026SS | 0 | 332 | Warning
42380 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 24025SS |  | 0 | 332 | Warning
42381 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24028SS | 0 | 311 | Warning
42382 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 24027SS |  | 0 | 311 | Warning
42383 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24030SS | 0 | 289 | Warning
42384 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 24029SS |  | 0 | 289 | Warning
42385 | CFSD_System of Care CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42386 | CFSD_System of Care CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42387 | CFSD_System of Care CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.33 | 233 | Warning
42390 | CFSD_System of Care CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 380 | 233d | 24034SS+40d |  | 0.4 | 233 | Warning
42394 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42397 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24042FS-1d |  | 0 | 466 | Warning
42398 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42400 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24045FS-1d | 24047 | 0.2 | 405 | Warning
42401 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24046 |  | 0 | 405 | Warning
42402 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42403 | CFSD_System of Care CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24050 | 0 | 405 | Warning
42404 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24049 | 24051 | 0 | 405 | Warning
42405 | CFSD_System of Care CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24050 |  | 0 | 405 | Warning
42406 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42407 | CFSD_System of Care CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedure | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24054 | 0 | 364 | Warning
42408 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24053 | 24056FS-1d | 0 | 363 | Warning
42409 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42410 | CFSD_System of Care CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24054FS-1d |  | 0 | 363 | Warning
42411 | CFSD_System of Care CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42412 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42413 | CFSD_System of Care CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42414 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42415 | CFSD_System of Care CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.3 | 293 | Warning
42416 | CFSD_System of Care CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
42419 | CFSD_System of Care CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
42425 | CFSD_System of Care CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24070SS | 24072SS | 0 | 497 | Warning
42426 | CFSD_System of Care CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24071SS |  | 0 | 497 | Warning
42427 | CFSD_System of Care CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42428 | CFSD_System of Care CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 24070 | 24075 | 0 | 298 | Warning
42429 | CFSD_System of Care CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 24074 |  | 0 | 298 | Warning
42430 | CFSD_System of Care CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
42431 | CFSD_System of Care CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24078FS+1d,24080SS | 0 | 373 | Warning
42432 | CFSD_System of Care CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24077FS+1d |  | 0 | 373 | Warning
42433 | CFSD_System of Care CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
42435 | CFSD_System of Care CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24080 | 24082SS,24083 | 0 | 345 | Warning
42436 | CFSD_System of Care CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24081SS | 24083 | 0 | 345 | Warning
42437 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24081,24082 |  | 0 | 345 | Warning
42438 | CFSD_System of Care CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
42439 | CFSD_System of Care CDSS - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | April 30, 2026 12:00 AM | 311 | 364d |  |  | 0 | 364 | Warning
42440 | CFSD_System of Care CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24087SS | 0 | 424 | Warning
42441 | CFSD_System of Care CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d | 24086SS |  | 0 | 424 | Warning
42442 | CFSD_System of Care CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM | 273 | 364d |  |  | 0 | 364 | Warning
42447 | CFSD_System of Care CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
42448 | CFSD_System of Care CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d | 24092 | 24095FS+1d | 0 | 373 | Warning
42449 | CFSD_System of Care CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 373d | 24094FS+1d |  | 0 | 373 | Warning
42450 | CFSD_System of Care CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.07 | 298 | Warning
42452 | CFSD_System of Care CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24097 | 24099FF | 0 | 345 | Warning
42453 | CFSD_System of Care CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24098FF | 24100 | 0 | 345 | Warning
42454 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24099 |  | 0 | 345 | Warning
42455 | CFSD_System of Care CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
42456 | CFSD_System of Care CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42457 | CFSD_System of Care CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24104SS | 0 | 362 | Warning
42458 | CFSD_System of Care CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24103SS | 24105SS | 0 | 362 | Warning
42459 | CFSD_System of Care CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24104SS | 24106SS | 0 | 362 | Warning
42460 | CFSD_System of Care CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24105SS | 24107SS | 0 | 362 | Warning
42461 | CFSD_System of Care CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24106SS | 24108SS | 0 | 362 | Warning
42462 | CFSD_System of Care CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24107SS | 24109SS | 0 | 362 | Warning
42463 | CFSD_System of Care CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24108SS | 24110SS | 0 | 362 | Warning
42464 | CFSD_System of Care CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24109SS | 24111SS | 0 | 362 | Warning
42465 | CFSD_System of Care CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24110SS | 24112SS | 0 | 362 | Warning
42466 | CFSD_System of Care CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24111SS | 24113SS | 0 | 362 | Warning
42467 | CFSD_System of Care CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24112SS |  | 0 | 362 | Warning
42468 | CFSD_System of Care CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42469 | CFSD_System of Care CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42471 | CFSD_System of Care CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42473 | CFSD_System of Care CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42474 | CFSD_System of Care CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42475 | CFSD_System of Care CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42476 | CFSD_System of Care CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24132 | 0 | 275 | Warning
42477 | CFSD_System of Care CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24133 | 0 | 275 | Warning
42479 | CFSD_System of Care CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42480 | CFSD_System of Care CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24127SS,24135SS+20d | 0 | 299 | Warning
42481 | CFSD_System of Care CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24126SS | 24128SS,24136SS+20d | 0 | 299 | Warning
42482 | CFSD_System of Care CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24127SS | 24129SS,24137SS+20d | 0 | 299 | Warning
42483 | CFSD_System of Care CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24128SS | 24130SS,24138SS+20d | 0 | 299 | Warning
42484 | CFSD_System of Care CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24129SS | 24139SS+20d | 0 | 299 | Warning
42485 | CFSD_System of Care CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42486 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24122 |  | 0 | 274 | Warning
42487 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24123 |  | 0 | 274 | Warning
42488 | CFSD_System of Care CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24142FS+13d | 0 | 279 | Warning
42489 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24126SS+20d |  | 0 | 299 | Warning
42490 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24127SS+20d |  | 0 | 299 | Warning
42491 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24128SS+20d |  | 0 | 299 | Warning
42492 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24129SS+20d |  | 0 | 299 | Warning
42493 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24130SS+20d |  | 0 | 299 | Warning
42494 | CFSD_System of Care CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24142SS+40d | 0 | 283 | Warning
42495 | CFSD_System of Care CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42496 | CFSD_System of Care CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 24134FS+13d,24140SS+40d |  | 0 | 279 | Warning
42498 | FAD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.41 | 235 | Warning
42499 | FAD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | October 30, 2026 5:00 PM | 461 | 235d |  |  | 0.41 | 235 | Warning
42509 | FAD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42510 | FAD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42511 | FAD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42512 | FAD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
42513 | FAD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
42514 | FAD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
42515 | FAD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42516 | FAD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
42517 | FAD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42518 | FAD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42519 | FAD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42520 | FAD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42521 | FAD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42528 | FAD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42529 | FAD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42530 | FAD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42531 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24178SS | 0 | 424 | Warning
42532 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24177SS |  | 0 | 415 | Warning
42533 | FAD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42534 | FAD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42535 | FAD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24182SS | 0 | 342 | Warning
42536 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 24181SS | 24183SS | 0 | 371 | Warning
42537 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 24182SS |  | 0 | 371 | Warning
42538 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24185SS | 0 | 332 | Warning
42539 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 24184SS |  | 0 | 332 | Warning
42540 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24187SS | 0 | 311 | Warning
42541 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 24186SS |  | 0 | 311 | Warning
42542 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24189SS | 0 | 289 | Warning
42543 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 24188SS |  | 0 | 289 | Warning
42544 | FAD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42545 | FAD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42546 | FAD CDSS - OCM Activities | March 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 423 | 233d |  |  | 0.3 | 233 | Warning
42549 | FAD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | June 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 360 | 233d | 24193SS+40d |  | 0.2 | 233 | Warning
42550 | FAD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42554 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42556 | FAD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24201FS-1d | 24203 | 0.2 | 405 | Warning
42557 | FAD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24202 |  | 0 | 405 | Warning
42558 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42559 | FAD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24206 | 0 | 405 | Warning
42560 | FAD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24205 | 24207 | 0 | 405 | Warning
42561 | FAD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24206 |  | 0 | 405 | Warning
42562 | FAD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42563 | FAD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24210 | 0 | 364 | Warning
42564 | FAD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24209 | 24212FS-1d | 0 | 363 | Warning
42565 | FAD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42566 | FAD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24210FS-1d |  | 0 | 363 | Warning
42567 | FAD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42568 | FAD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42569 | FAD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42570 | FAD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42571 | FAD CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.32 | 293 | Warning
42572 | FAD CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.5 | 357 | Warning
42574 | FAD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 24219SS |  | 0.2 | 405 | Warning
42575 | FAD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
42580 | FAD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 298d |  | 24227SS,24230 | 0.2 | 298 | Warning
42581 | FAD CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24226SS | 24228SS | 0 | 497 | Warning
42582 | FAD CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24227SS |  | 0 | 497 | Warning
42583 | FAD CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42584 | FAD CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 24226 | 24231 | 0 | 298 | Warning
42585 | FAD CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 24230 |  | 0 | 298 | Warning
42586 | FAD CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
42587 | FAD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24234FS+1d,24236SS | 0 | 373 | Warning
42588 | FAD CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24233FS+1d |  | 0 | 373 | Warning
42589 | FAD CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
42591 | FAD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24236 | 24238SS,24239 | 0 | 345 | Warning
42592 | FAD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24237SS | 24239 | 0 | 345 | Warning
42593 | FAD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24237,24238 |  | 0 | 345 | Warning
42594 | FAD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
42599 | FAD CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.71 | 298 | Warning
42604 | FAD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
42605 | FAD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42606 | FAD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24253SS | 0 | 362 | Warning
42607 | FAD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24252SS | 24254SS | 0 | 362 | Warning
42608 | FAD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24253SS | 24255SS | 0 | 362 | Warning
42609 | FAD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24254SS | 24256SS | 0 | 362 | Warning
42610 | FAD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24255SS | 24257SS | 0 | 362 | Warning
42611 | FAD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24256SS | 24258SS | 0 | 362 | Warning
42612 | FAD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24257SS | 24259SS | 0 | 362 | Warning
42613 | FAD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24258SS | 24260SS | 0 | 362 | Warning
42614 | FAD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24259SS | 24261SS | 0 | 362 | Warning
42615 | FAD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24260SS | 24262SS | 0 | 362 | Warning
42616 | FAD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24261SS |  | 0 | 362 | Warning
42617 | FAD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42618 | FAD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42620 | FAD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42622 | FAD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42623 | FAD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42624 | FAD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42625 | FAD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24281 | 0 | 275 | Warning
42626 | FAD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24282 | 0 | 275 | Warning
42628 | FAD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42629 | FAD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24276SS,24284SS+20d | 0 | 299 | Warning
42630 | FAD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24275SS | 24277SS,24285SS+20d | 0 | 299 | Warning
42631 | FAD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24276SS | 24278SS,24286SS+20d | 0 | 299 | Warning
42632 | FAD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24277SS | 24279SS,24287SS+20d | 0 | 299 | Warning
42633 | FAD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24278SS | 24288SS+20d | 0 | 299 | Warning
42634 | FAD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42635 | FAD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24271 |  | 0 | 274 | Warning
42636 | FAD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24272 |  | 0 | 274 | Warning
42637 | FAD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24291FS+13d | 0 | 279 | Warning
42638 | FAD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24275SS+20d |  | 0 | 299 | Warning
42639 | FAD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24276SS+20d |  | 0 | 299 | Warning
42640 | FAD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24277SS+20d |  | 0 | 299 | Warning
42641 | FAD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24278SS+20d |  | 0 | 299 | Warning
42642 | FAD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24279SS+20d |  | 0 | 299 | Warning
42643 | FAD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24291SS+40d | 0 | 283 | Warning
42644 | FAD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42645 | FAD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 24283FS+13d,24289SS+40d |  | 0 | 279 | Warning
42647 | OOE CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.5 | 235 | Warning
42648 | OOE CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM | 440 | 235d |  |  | 0.38 | 235 | Warning
42657 | OOE CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42658 | OOE CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42659 | OOE CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42660 | OOE CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | 425 | Warning
42661 | OOE CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | 406 | Warning
42662 | OOE CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
42663 | OOE CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42664 | OOE CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | 343 | Warning
42665 | OOE CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42666 | OOE CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42667 | OOE CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42668 | OOE CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42669 | OOE CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42676 | OOE CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42677 | OOE CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42678 | OOE CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42679 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24326SS | 0 | 424 | Warning
42680 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24325SS |  | 0 | 415 | Warning
42681 | OOE CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42682 | OOE CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42683 | OOE CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24330SS | 0 | 342 | Warning
42684 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 24329SS | 24331SS | 0 | 371 | Warning
42685 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 24330SS |  | 0 | 371 | Warning
42686 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24333SS | 0 | 332 | Warning
42687 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 24332SS |  | 0 | 332 | Warning
42688 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24335SS | 0 | 311 | Warning
42689 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 24334SS |  | 0 | 311 | Warning
42690 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24337SS | 0 | 289 | Warning
42691 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 24336SS |  | 0 | 289 | Warning
42692 | OOE CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42693 | OOE CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42694 | OOE CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.3 | 233 | Warning
42697 | OOE CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | June 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 360 | 233d | 24341SS+21d |  | 0.4 | 233 | Warning
42700 | OOE CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42703 | OOE CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24348FS-1d |  | 0 | 466 | Warning
42704 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42706 | OOE CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24351FS-1d | 24353 | 0 | 405 | Warning
42707 | OOE CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24352 |  | 0 | 405 | Warning
42708 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42709 | OOE CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24356 | 0 | 405 | Warning
42710 | OOE CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24355 | 24357 | 0 | 405 | Warning
42711 | OOE CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24356 |  | 0 | 405 | Warning
42712 | OOE CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42713 | OOE CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24360 | 0 | 364 | Warning
42714 | OOE CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24359 | 24362FS-1d | 0 | 363 | Warning
42715 | OOE CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42716 | OOE CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24360FS-1d |  | 0 | 363 | Warning
42717 | OOE CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42718 | OOE CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42719 | OOE CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42720 | OOE CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42721 | OOE CDSS - Technical Activities | May 1, 2025 12:00 AM | August 3, 2026 5:00 PM | 316 | 298d |  |  | 0.05 | 298 | Warning
42724 | OOE CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24369SS | 24371SS | 0 | 497 | Warning
42725 | OOE CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24370SS |  | 0 | 497 | Warning
42726 | OOE CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42727 | OOE CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 24369 | 24374 | 0 | 298 | Warning
42728 | OOE CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 24373 |  | 0 | 298 | Warning
42729 | OOE CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42730 | OOE CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24377SS | 0 | 362 | Warning
42731 | OOE CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24376SS | 24378SS | 0 | 362 | Warning
42732 | OOE CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24377SS | 24379SS | 0 | 362 | Warning
42733 | OOE CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24378SS | 24380SS | 0 | 362 | Warning
42734 | OOE CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24379SS | 24381SS | 0 | 362 | Warning
42735 | OOE CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24380SS | 24382SS | 0 | 362 | Warning
42736 | OOE CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24381SS | 24383SS | 0 | 362 | Warning
42737 | OOE CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24382SS | 24384SS | 0 | 362 | Warning
42738 | OOE CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24383SS | 24385SS | 0 | 362 | Warning
42739 | OOE CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24384SS | 24386SS | 0 | 362 | Warning
42740 | OOE CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24385SS |  | 0 | 362 | Warning
42741 | OOE CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42742 | OOE CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42744 | OOE CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42746 | OOE CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42747 | OOE CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42748 | OOE CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42749 | OOE CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24405 | 0 | 275 | Warning
42750 | OOE CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24406 | 0 | 275 | Warning
42752 | OOE CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42753 | OOE CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24400SS,24408SS+20d | 0 | 299 | Warning
42754 | OOE CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24399SS | 24401SS,24409SS+20d | 0 | 299 | Warning
42755 | OOE CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24400SS | 24402SS,24410SS+20d | 0 | 299 | Warning
42756 | OOE CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24401SS | 24403SS,24411SS+20d | 0 | 299 | Warning
42757 | OOE CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24402SS | 24412SS+20d | 0 | 299 | Warning
42758 | OOE CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42759 | OOE CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24395 |  | 0 | 274 | Warning
42760 | OOE CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24396 |  | 0 | 274 | Warning
42761 | OOE CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24415FS+13d | 0 | 279 | Warning
42762 | OOE CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24399SS+20d |  | 0 | 299 | Warning
42763 | OOE CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24400SS+20d |  | 0 | 299 | Warning
42764 | OOE CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24401SS+20d |  | 0 | 299 | Warning
42765 | OOE CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24402SS+20d |  | 0 | 299 | Warning
42766 | OOE CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24403SS+20d |  | 0 | 299 | Warning
42767 | OOE CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24415SS+40d | 0 | 283 | Warning
42768 | OOE CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42769 | OOE CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 24407FS+13d,24413SS+40d |  | 0 | 279 | Warning
42771 | RADD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM | 828 | 235d |  |  | 0.6 | 235 | Warning
42784 | RADD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42785 | RADD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42786 | RADD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42787 | RADD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
42788 | RADD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42789 | RADD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
42790 | RADD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42791 | RADD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
42792 | RADD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42793 | RADD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42794 | RADD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42795 | RADD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42796 | RADD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42803 | RADD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42804 | RADD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42805 | RADD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42806 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24453SS | 0 | 424 | Warning
42807 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24452SS |  | 0 | 415 | Warning
42808 | RADD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42809 | RADD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42810 | RADD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24457SS | 0 | 342 | Warning
42811 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 24456SS | 24458SS | 0 | 371 | Warning
42812 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 24457SS |  | 0 | 371 | Warning
42813 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24460SS | 0 | 332 | Warning
42814 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 24459SS |  | 0 | 332 | Warning
42815 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24462SS | 0 | 311 | Warning
42816 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 24461SS |  | 0 | 311 | Warning
42817 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24464SS | 0 | 289 | Warning
42818 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 24463SS |  | 0 | 289 | Warning
42819 | RADD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42820 | RADD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42821 | RADD CDSS - OCM Activities | January 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 463 | 233d |  |  | 0.32 | 233 | Warning
42824 | RADD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | March 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 422 | 233d | 24468SS+40d |  | 0.4 | 233 | Warning
42827 | RADD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42830 | RADD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24475FS-1d |  | 0 | 466 | Warning
42831 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42833 | RADD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24478FS-1d | 24480 | 0.2 | 405 | Warning
42834 | RADD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24479 |  | 0 | 405 | Warning
42835 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42836 | RADD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24483 | 0 | 405 | Warning
42837 | RADD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24482 | 24484 | 0 | 405 | Warning
42838 | RADD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24483 |  | 0 | 405 | Warning
42839 | RADD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42840 | RADD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24487 | 0 | 364 | Warning
42841 | RADD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24486 | 24489FS-1d | 0 | 363 | Warning
42842 | RADD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42843 | RADD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24487FS-1d |  | 0 | 363 | Warning
42844 | RADD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42845 | RADD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42846 | RADD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42847 | RADD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42848 | RADD CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.28 | 293 | Warning
42849 | RADD CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.57 | 357 | Warning
42850 | RADD CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 24497SS | 0.6 | 405 | Warning
42851 | RADD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 24496SS |  | 0.6 | 405 | Warning
42852 | RADD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
42858 | RADD CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24503SS | 24505SS | 0 | 497 | Warning
42859 | RADD CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24504SS |  | 0 | 497 | Warning
42860 | RADD CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
42861 | RADD CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 24503 | 24508 | 0 | 298 | Warning
42862 | RADD CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 24507 |  | 0 | 298 | Warning
42863 | RADD CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0.2 | 373 | Warning
42864 | RADD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24511FS+1d,24513SS | 0.6 | 373 | Warning
42865 | RADD CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24510FS+1d |  | 0 | 373 | Warning
42866 | RADD CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
42868 | RADD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24513 | 24515SS,24516 | 0 | 345 | Warning
42869 | RADD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24514SS | 24516 | 0 | 345 | Warning
42870 | RADD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24514,24515 |  | 0 | 345 | Warning
42871 | RADD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
42872 | RADD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
42873 | RADD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24520SS | 0 | 362 | Warning
42874 | RADD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24519SS | 24521SS | 0 | 362 | Warning
42875 | RADD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24520SS | 24522SS | 0 | 362 | Warning
42876 | RADD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24521SS | 24523SS | 0 | 362 | Warning
42877 | RADD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24522SS | 24524SS | 0 | 362 | Warning
42878 | RADD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24523SS | 24525SS | 0 | 362 | Warning
42879 | RADD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24524SS | 24526SS | 0 | 362 | Warning
42880 | RADD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24525SS | 24527SS | 0 | 362 | Warning
42881 | RADD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24526SS | 24528SS | 0 | 362 | Warning
42882 | RADD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24527SS | 24529SS | 0 | 362 | Warning
42883 | RADD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24528SS |  | 0 | 362 | Warning
42884 | RADD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
42885 | RADD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
42887 | RADD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
42889 | RADD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
42890 | RADD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42891 | RADD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
42892 | RADD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24548 | 0 | 275 | Warning
42893 | RADD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24549 | 0 | 275 | Warning
42895 | RADD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
42896 | RADD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24543SS,24551SS+20d | 0 | 299 | Warning
42897 | RADD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24542SS | 24544SS,24552SS+20d | 0 | 299 | Warning
42898 | RADD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24543SS | 24545SS,24553SS+20d | 0 | 299 | Warning
42899 | RADD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24544SS | 24546SS,24554SS+20d | 0 | 299 | Warning
42900 | RADD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24545SS | 24555SS+20d | 0 | 299 | Warning
42901 | RADD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
42902 | RADD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24538 |  | 0 | 274 | Warning
42903 | RADD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24539 |  | 0 | 274 | Warning
42904 | RADD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24558FS+13d | 0 | 279 | Warning
42905 | RADD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24542SS+20d |  | 0 | 299 | Warning
42906 | RADD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24543SS+20d |  | 0 | 299 | Warning
42907 | RADD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24544SS+20d |  | 0 | 299 | Warning
42908 | RADD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24545SS+20d |  | 0 | 299 | Warning
42909 | RADD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24546SS+20d |  | 0 | 299 | Warning
42910 | RADD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24558SS+40d | 0 | 283 | Warning
42911 | RADD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
42912 | RADD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 24550FS+13d,24556SS+40d |  | 0 | 279 | Warning
42914 | SPEI CDSS - Implementation Management | July 17, 2023 12:00 AM | November 2, 2026 5:00 PM | 829 | 234d |  |  | 0.51 | 234 | Warning
42915 | SPEI CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | October 30, 2026 5:00 PM | 482 | 235d |  |  | 0.43 | 235 | Warning
42926 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
42927 | SPEI CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
42928 | SPEI CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
42929 | SPEI CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
42930 | SPEI CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42931 | SPEI CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | 384 | Warning
42932 | SPEI CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
42933 | SPEI CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
42934 | SPEI CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
42935 | SPEI CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
42936 | SPEI CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | 278 | Warning
42937 | SPEI CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
42938 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
42945 | SPEI CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | 307 | Warning
42946 | SPEI CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | 296 | Warning
42947 | SPEI CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | 446 | Warning
42948 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24595SS | 0 | 424 | Warning
42949 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24594SS |  | 0 | 415 | Warning
42950 | SPEI CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42951 | SPEI CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | 364 | Warning
42952 | SPEI CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24599SS | 0 | 342 | Warning
42953 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22 | 371d | 24598SS | 24600SS | 0 | 371 | Warning
42954 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 36 | 371d | 24599SS |  | 0 | 371 | Warning
42955 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24602SS | 0 | 332 | Warning
42956 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 24601SS |  | 0 | 332 | Warning
42957 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24604SS | 0 | 311 | Warning
42958 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 24603SS |  | 0 | 311 | Warning
42959 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24606SS | 0 | 289 | Warning
42960 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 24605SS |  | 0 | 289 | Warning
42961 | SPEI CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | 296 | Warning
42962 | SPEI CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | 284 | Warning
42963 | SPEI CDSS - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | 234 | Warning
42964 | SPEI CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 442 | 233d |  |  | 0.38 | 233 | Warning
42967 | SPEI CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 380 | 233d | 24611SS+40d |  | 0.4 | 233 | Warning
42971 | SPEI CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42975 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42977 | SPEI CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24622FS-1d | 24624 | 0.2 | 405 | Warning
42978 | SPEI CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24623 |  | 0 | 405 | Warning
42979 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42980 | SPEI CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24627 | 0 | 405 | Warning
42981 | SPEI CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24626 | 24628 | 0 | 405 | Warning
42982 | SPEI CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24627 |  | 0 | 405 | Warning
42983 | SPEI CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
42984 | SPEI CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24631 | 0 | 364 | Warning
42985 | SPEI CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24630 | 24633FS-1d | 0 | 363 | Warning
42986 | SPEI CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
42987 | SPEI CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24631FS-1d |  | 0 | 363 | Warning
42988 | SPEI CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | 446 | Warning
42989 | SPEI CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
42990 | SPEI CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | 364 | Warning
42991 | SPEI CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
42992 | SPEI CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM | 602 | 293d |  |  | 0.57 | 293 | Warning
42993 | SPEI CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM | 538 | 357d |  |  | 0.95 | 357 | Warning
42996 | SPEI CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | 357 | Warning
43003 | SPEI CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 32 | 497d | 24648SS |  | 0 | 497 | Warning
43004 | SPEI CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d |  |  | 0 | 298 | Warning
43005 | SPEI CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 52 | 298d | 24647 | 24652 | 0 | 298 | Warning
43006 | SPEI CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 158 | 298d | 24651 |  | 0 | 298 | Warning
43007 | SPEI CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
43008 | SPEI CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24655FS+1d,24657SS | 0 | 373 | Warning
43009 | SPEI CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24654FS+1d |  | 0 | 373 | Warning
43010 | SPEI CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM | 251 | 293d |  |  | 0.07 | 293 | Warning
43012 | SPEI CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24657 | 24659SS,24660 | 0 | 345 | Warning
43013 | SPEI CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24658SS | 24660 | 0 | 345 | Warning
43014 | SPEI CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24658,24659 |  | 0 | 345 | Warning
43015 | SPEI CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | 293 | Warning
43027 | SPEI CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0.71 | 298 | Warning
43032 | SPEI CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
43033 | SPEI CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
43034 | SPEI CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24681SS | 0 | 362 | Warning
43035 | SPEI CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24680SS | 24682SS | 0 | 362 | Warning
43036 | SPEI CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24681SS | 24683SS | 0 | 362 | Warning
43037 | SPEI CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24682SS | 24684SS | 0 | 362 | Warning
43038 | SPEI CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24683SS | 24685SS | 0 | 362 | Warning
43039 | SPEI CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24684SS | 24686SS | 0 | 362 | Warning
43040 | SPEI CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24685SS | 24687SS | 0 | 362 | Warning
43041 | SPEI CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24686SS | 24688SS | 0 | 362 | Warning
43042 | SPEI CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24687SS | 24689SS | 0 | 362 | Warning
43043 | SPEI CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24688SS | 24690SS | 0 | 362 | Warning
43044 | SPEI CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24689SS |  | 0 | 362 | Warning
43045 | SPEI CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | 343 | Warning
43046 | SPEI CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | 333 | Warning
43048 | SPEI CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
43050 | SPEI CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | 322 | Warning
43051 | SPEI CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43052 | SPEI CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43053 | SPEI CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24709 | 0 | 275 | Warning
43054 | SPEI CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24710 | 0 | 275 | Warning
43056 | SPEI CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | 358 | Warning
43057 | SPEI CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24704SS,24712SS+20d | 0 | 299 | Warning
43058 | SPEI CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24703SS | 24705SS,24713SS+20d | 0 | 299 | Warning
43059 | SPEI CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24704SS | 24706SS,24714SS+20d | 0 | 299 | Warning
43060 | SPEI CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24705SS | 24707SS,24715SS+20d | 0 | 299 | Warning
43061 | SPEI CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d | 24706SS | 24716SS+20d | 0 | 299 | Warning
43062 | SPEI CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
43063 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24699 |  | 0 | 274 | Warning
43064 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24700 |  | 0 | 274 | Warning
43065 | SPEI CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24719FS+13d | 0 | 279 | Warning
43066 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24703SS+20d |  | 0 | 299 | Warning
43067 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24704SS+20d |  | 0 | 299 | Warning
43068 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24705SS+20d |  | 0 | 299 | Warning
43069 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24706SS+20d |  | 0 | 299 | Warning
43070 | SPEI CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 24707SS+20d |  | 0 | 299 | Warning
43071 | SPEI CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24719SS+40d | 0 | 283 | Warning
43072 | SPEI CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | 300 | Warning
43073 | SPEI CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 24711FS+13d,24717SS+40d |  | 0 | 279 | Warning
43077 | Karuk TR - Implementation Management | November 1, 2023 8:00 AM | October 30, 2026 5:00 PM | 752 | 235d |  |  | 0.17 | 235 | Warning
43082 | Karuk TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
43083 | Karuk TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
43084 | Karuk TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
43085 | Karuk TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
43086 | Karuk TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
43087 | Karuk TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
43088 | Karuk TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
43089 | Karuk TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
43090 | Karuk TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43091 | Karuk TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
43092 | Karuk TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 22 | 278d |  |  | 0 | 278 | Warning
43093 | Karuk TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
43094 | Karuk TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
43102 | Karuk TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
43103 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM | 21 | 423d |  |  | 0 | 423 | Warning
43104 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d |  |  | 0 | 414 | Warning
43105 | Karuk TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 24751SS | 0 | 362 | Warning
43106 | Karuk TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 24750SS |  | 0 | 362 | Warning
43107 | Karuk TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM | 65 | 341d |  |  | 0 | 341 | Warning
43108 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
43109 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d |  |  | 0 | 352 | Warning
43110 | Karuk TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
43111 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
43112 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d |  |  | 0 | 288 | Warning
43113 | Karuk TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
43114 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM | 22 | 277d |  |  | 0 | 277 | Warning
43115 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d |  |  | 0 | 268 | Warning
43116 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  | 24762SS | 0 | 257 | Warning
43117 | Karuk TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d | 24761SS | 24763SS | 0 | 257 | Warning
43118 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 24762SS |  | 0 | 246 | Warning
43119 | Karuk TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
43121 | Karuk TR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | November 30, 2026 5:00 PM | 228 | 217d |  |  | 0 | 217 | Warning
43122 | Karuk TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43123 | Karuk TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
43124 | Karuk TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
43125 | Karuk TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM | 40 | 217d |  |  | 0 | 217 | Warning
43127 | Karuk TR - OCM Activities | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.18 | 233 | Warning
43128 | Karuk TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.2 | 233 | Warning
43131 | Karuk TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43133 | Karuk TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d |  |  | 0 | 466 | Warning
43134 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43136 | Karuk TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | 485 | Warning
43137 | Karuk TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d |  |  | 0 | 405 | Warning
43138 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43139 | Karuk TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | 485 | Warning
43140 | Karuk TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
43141 | Karuk TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43142 | Karuk TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43143 | Karuk TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
43144 | Karuk TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43145 | Karuk TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
43146 | Karuk TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d |  |  | 0 | 362 | Warning
43147 | Karuk TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
43148 | Karuk TR - Technical Activities | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0 | 298 | Warning
43149 | Karuk TR - Complete Tableau Training | March 19, 2024 8:00 AM | May 11, 2026 5:00 PM | 539 | 356d |  |  | 0 | 356 | Warning
43150 | Karuk TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d |  | 24796SS,24797 | 0 | 356 | Warning
43151 | Karuk TR - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d | 24795SS | 24797 | 0 | 356 | Warning
43152 | Karuk TR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 11, 2026 5:00 PM | 49 | 356d | 24795,24796 |  | 0 | 356 | Warning
43153 | Karuk TR - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
43154 | Karuk TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24800 | 0 | 373 | Warning
43155 | Karuk TR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24799 |  | 0 | 373 | Warning
43156 | Karuk TR - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0 | 298 | Warning
43157 | Karuk TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d |  |  | 0 | 508 | Warning
43158 | Karuk TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  | 24804SS | 0 | 362 | Warning
43159 | Karuk TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d | 24803SS |  | 0 | 362 | Warning
43160 | Karuk TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | 346 | Warning
43161 | Karuk TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
43162 | Karuk TR - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | May 1, 2026 5:00 PM | 313 | 362d |  |  | 0 | 362 | Warning
43163 | Karuk TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24809SS | 0 | 424 | Warning
43164 | Karuk TR - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d | 24808SS |  | 0 | 424 | Warning
43165 | Karuk TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 274 | 362d |  |  | 0 | 362 | Warning
43166 | Karuk TR - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
43167 | Karuk TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24813 | 0 | 373 | Warning
43168 | Karuk TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24812 |  | 0 | 373 | Warning
43169 | Karuk TR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0 | 298 | Warning
43170 | Karuk TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 345d |  | 24816 | 0 | 345 | Warning
43171 | Karuk TR - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24815 | 24817SS,24818 | 0 | 345 | Warning
43172 | Karuk TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24816SS | 24818 | 0 | 345 | Warning
43173 | Karuk TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24816,24817 |  | 0 | 345 | Warning
43174 | Karuk TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
43175 | Karuk TR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
43176 | Karuk TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24822SS | 0 | 362 | Warning
43177 | Karuk TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24821SS | 24823SS | 0 | 362 | Warning
43178 | Karuk TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24822SS | 24824SS | 0 | 362 | Warning
43179 | Karuk TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24823SS | 24825SS | 0 | 362 | Warning
43180 | Karuk TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24824SS | 24826SS | 0 | 362 | Warning
43181 | Karuk TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24825SS | 24827SS | 0 | 362 | Warning
43182 | Karuk TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24826SS | 24828SS | 0 | 362 | Warning
43183 | Karuk TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24827SS | 24829SS | 0 | 362 | Warning
43184 | Karuk TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24828SS | 24830SS | 0 | 362 | Warning
43185 | Karuk TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24829SS | 24831SS | 0 | 362 | Warning
43186 | Karuk TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24830SS |  | 0 | 362 | Warning
43187 | Karuk TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
43188 | Karuk TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
43190 | Karuk TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
43191 | Karuk TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
43192 | Karuk TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
43193 | Karuk TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
43194 | Karuk TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
43196 | Karuk TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
43197 | Karuk TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d |  | 24843SS | 0 | 309 | Warning
43198 | Karuk TR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24842SS | 24844SS | 0 | 309 | Warning
43199 | Karuk TR - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24843SS | 24845SS | 0 | 309 | Warning
43200 | Karuk TR - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24844SS | 24846SS | 0 | 309 | Warning
43201 | Karuk TR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24845SS |  | 0 | 309 | Warning
43202 | Karuk TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d |  | 24848SS | 0 | 235 | Warning
43203 | Karuk TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 24847SS |  | 0 | 235 | Warning
43204 | Karuk TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 311d |  |  | 0 | 311 | Warning
43205 | Karuk TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43206 | Karuk TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43207 | Karuk TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
43208 | Karuk TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 24854SS | 0 | 240 | Warning
43209 | Karuk TR - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24853SS | 24857SS | 0 | 240 | Warning
43210 | Karuk TR - Deliver processes/procedures training (if applicable) for Courts | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24857SS | 24856SS | 0 | 240 | Warning
43211 | Karuk TR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24855SS |  | 0 | 240 | Warning
43212 | Karuk TR - Deliver processes/procedures training (if applicable) for Resource Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24854SS | 24855SS | 0 | 240 | Warning
43213 | Karuk TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  |  | 0 | 250 | Warning
43214 | Karuk TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
43215 | Karuk TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d |  |  | 0 | 240 | Warning
43217 | Yurok TR - Implementation Management | November 1, 2023 8:00 AM | October 30, 2026 5:00 PM | 752 | 235d |  |  | 0.17 | 235 | Warning
43222 | Yurok TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | 485 | Warning
43223 | Yurok TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | 466 | Warning
43224 | Yurok TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | 445 | Warning
43225 | Yurok TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | 424 | Warning
43226 | Yurok TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | 405 | Warning
43227 | Yurok TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | 385 | Warning
43228 | Yurok TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
43229 | Yurok TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | 342 | Warning
43230 | Yurok TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43231 | Yurok TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
43232 | Yurok TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 22 | 278d |  |  | 0 | 278 | Warning
43233 | Yurok TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | 257 | Warning
43234 | Yurok TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | 235 | Warning
43242 | Yurok TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | 445 | Warning
43243 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM | 21 | 423d |  |  | 0 | 423 | Warning
43244 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d |  |  | 0 | 414 | Warning
43245 | Yurok TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 24891SS | 0 | 362 | Warning
43246 | Yurok TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 24890SS |  | 0 | 362 | Warning
43247 | Yurok TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM | 65 | 341d |  |  | 0 | 341 | Warning
43248 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | 363 | Warning
43249 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d |  |  | 0 | 352 | Warning
43250 | Yurok TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | 268 | Warning
43251 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | 299 | Warning
43252 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d |  |  | 0 | 288 | Warning
43253 | Yurok TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | 257 | Warning
43254 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM | 22 | 277d |  |  | 0 | 277 | Warning
43255 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d |  |  | 0 | 268 | Warning
43256 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  | 24902SS | 0 | 257 | Warning
43257 | Yurok TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d | 24901SS | 24903SS | 0 | 257 | Warning
43258 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 24902SS |  | 0 | 246 | Warning
43259 | Yurok TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | 245 | Warning
43261 | Yurok TR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | November 30, 2026 5:00 PM | 228 | 217d |  |  | 0 | 217 | Warning
43262 | Yurok TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43263 | Yurok TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | 342 | Warning
43264 | Yurok TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | 278 | Warning
43265 | Yurok TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM | 40 | 217d |  |  | 0 | 217 | Warning
43267 | Yurok TR - OCM Activities | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.18 | 233 | Warning
43268 | Yurok TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.2 | 233 | Warning
43271 | Yurok TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43273 | Yurok TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d |  |  | 0 | 466 | Warning
43274 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43276 | Yurok TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | 485 | Warning
43277 | Yurok TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d |  |  | 0 | 405 | Warning
43278 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43279 | Yurok TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | 485 | Warning
43280 | Yurok TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
43281 | Yurok TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43282 | Yurok TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | 357 | Warning
43283 | Yurok TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | 445 | Warning
43284 | Yurok TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | 405 | Warning
43285 | Yurok TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | 357 | Warning
43286 | Yurok TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d |  |  | 0 | 362 | Warning
43287 | Yurok TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | 309 | Warning
43288 | Yurok TR - Technical Activities | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM | 597 | 298d |  |  | 0 | 298 | Warning
43289 | Yurok TR - Complete Tableau Training | March 19, 2024 8:00 AM | May 11, 2026 5:00 PM | 539 | 356d |  |  | 0 | 356 | Warning
43290 | Yurok TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d |  | 24936SS,24937 | 0 | 356 | Warning
43291 | Yurok TR - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d | 24935SS | 24937 | 0 | 356 | Warning
43292 | Yurok TR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 11, 2026 5:00 PM | 49 | 356d | 24935,24936 |  | 0 | 356 | Warning
43293 | Yurok TR - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
43294 | Yurok TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24940 | 0 | 373 | Warning
43295 | Yurok TR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24939 |  | 0 | 373 | Warning
43296 | Yurok TR - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0 | 298 | Warning
43297 | Yurok TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d |  |  | 0 | 508 | Warning
43298 | Yurok TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  | 24944SS | 0 | 362 | Warning
43299 | Yurok TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d | 24943SS |  | 0 | 362 | Warning
43300 | Yurok TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | 346 | Warning
43301 | Yurok TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
43302 | Yurok TR - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | May 1, 2026 5:00 PM | 313 | 362d |  |  | 0 | 362 | Warning
43303 | Yurok TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24949SS | 0 | 424 | Warning
43304 | Yurok TR - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d | 24948SS |  | 0 | 424 | Warning
43305 | Yurok TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 274 | 362d |  |  | 0 | 362 | Warning
43306 | Yurok TR - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM | 171 | 373d |  |  | 0 | 373 | Warning
43307 | Yurok TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24953 | 0 | 373 | Warning
43308 | Yurok TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24952 |  | 0 | 373 | Warning
43309 | Yurok TR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM | 246 | 298d |  |  | 0 | 298 | Warning
43310 | Yurok TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 345d |  | 24956 | 0 | 345 | Warning
43311 | Yurok TR - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24955 | 24957SS,24958 | 0 | 345 | Warning
43312 | Yurok TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24956SS | 24958 | 0 | 345 | Warning
43313 | Yurok TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24956,24957 |  | 0 | 345 | Warning
43314 | Yurok TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | 298 | Warning
43315 | Yurok TR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  |  | 0 | 362 | Warning
43316 | Yurok TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24962SS | 0 | 362 | Warning
43317 | Yurok TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24961SS | 24963SS | 0 | 362 | Warning
43318 | Yurok TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24962SS | 24964SS | 0 | 362 | Warning
43319 | Yurok TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24963SS | 24965SS | 0 | 362 | Warning
43320 | Yurok TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24964SS | 24966SS | 0 | 362 | Warning
43321 | Yurok TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24965SS | 24967SS | 0 | 362 | Warning
43322 | Yurok TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24966SS | 24968SS | 0 | 362 | Warning
43323 | Yurok TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24967SS | 24969SS | 0 | 362 | Warning
43324 | Yurok TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24968SS | 24970SS | 0 | 362 | Warning
43325 | Yurok TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24969SS | 24971SS | 0 | 362 | Warning
43326 | Yurok TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24970SS |  | 0 | 362 | Warning
43327 | Yurok TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | 323 | Warning
43328 | Yurok TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | 314 | Warning
43330 | Yurok TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | 384 | Warning
43331 | Yurok TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | 384 | Warning
43332 | Yurok TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | 320 | Warning
43333 | Yurok TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
43334 | Yurok TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | 362 | Warning
43336 | Yurok TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | 357 | Warning
43337 | Yurok TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d |  | 24983SS | 0 | 309 | Warning
43338 | Yurok TR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24982SS | 24984SS | 0 | 309 | Warning
43339 | Yurok TR - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24983SS | 24985SS | 0 | 309 | Warning
43340 | Yurok TR - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24984SS | 24986SS | 0 | 309 | Warning
43341 | Yurok TR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 24985SS |  | 0 | 309 | Warning
43342 | Yurok TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d |  | 24988SS | 0 | 235 | Warning
43343 | Yurok TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 24987SS |  | 0 | 235 | Warning
43344 | Yurok TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 311d |  |  | 0 | 311 | Warning
43345 | Yurok TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43346 | Yurok TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | 321 | Warning
43347 | Yurok TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | 255 | Warning
43348 | Yurok TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 24994SS | 0 | 240 | Warning
43349 | Yurok TR - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24993SS | 24997SS | 0 | 240 | Warning
43350 | Yurok TR - Deliver processes/procedures training (if applicable) for Courts | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24997SS | 24996SS | 0 | 240 | Warning
43351 | Yurok TR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24995SS |  | 0 | 240 | Warning
43352 | Yurok TR - Deliver processes/procedures training (if applicable) for Resource Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d | 24994SS | 24995SS | 0 | 240 | Warning
43353 | Yurok TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  |  | 0 | 250 | Warning
43354 | Yurok TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | 299 | Warning
43355 | Yurok TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d |  |  | 0 | 240 | Warning

## Missing_Preds
Info
No rows for Missing_Preds

## Missing_Succs
Info
No rows for Missing_Succs

## Constraints
UID | Task Name | Start | Finish | Duration | Total Slack | Predecessors | Successors | Percent Complete | Constraint_Type | Severity
11036 | M6.1: RC: Finalize Value Hypothesis | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 | 0d |  | 296SS,297SS,298SS,299SS,300SS,301SS,302SS | 1 | Must Start On | Warning
11300 | M9: RC: Finalize Value Hypothesis | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 | 0d |  | 2520SS,319SS | 1 | Must Start On | Warning
11336 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 | 0d | 351SS | 4490,353SS | 1 | Finish No Earlier Than | Warning
11337 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 | 0d | 352SS | 4490,354SS | 1 | Finish No Earlier Than | Warning
11338 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 | 0d | 353SS | 4490,355SS | 1 | Finish No Earlier Than | Warning
11339 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 | 0d | 354SS | 5426,4490,357FS-84d,627FF | 1 | Finish No Earlier Than | Warning
11261 | M10: RC: Finalize Value Hypothesis | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 | 0d |  | 366SS | 1 | Must Start On | Warning
4558 | M15: RC: Finalize Value Hypothesis | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 | 0d |  | 418SS | 1 | Must Start On | Warning
6881 | M31: B1: 22.04 Build and Share Ad-hoc Queries, Graphs (Visualizations) and Dashboards (CARESV1-28) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 0d | 520SS | 559,2442SS,2421FF,2422SS,2423SS,2424SS | 1 | Must Start On | Warning
7005 | CARESV1-34751 Technical Analytical Training (LOE) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 467d | 559SS | 561SS | 0.57 | Start No Earlier Than | Warning
7006 | CARESV1-34752 Data Architecture (LOE) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 112d | 560SS | 562FF | 0.57 | Start No Earlier Than | Warning
1307 | Case Management - Milestone 08 - Document and Confirm Requirements | May 28, 2024 8:00 AM | July 12, 2024 5:00 PM | 33 | 0d | 570 | 1476FS-19d | 1 | Finish No Earlier Than | Warning
6483 | Case Management - Group 1 - Design Cycle 2 - Prepare Walkthrough | September 2, 2024 8:00 AM | September 10, 2024 5:00 PM | 7 | 0d |  | 578,2514SS,2515SS,2516SS,2554SS,2555SS,2556SS,1386SS-31d | 1 | Must Start On | Warning
11519 | Case Management Group 1 - User Feedback - Identify User Feedback Scenarios | December 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 20 | 0d | 579FS-1d | 582SS | 1 | Start No Earlier Than | Warning
11514 | Case Management Group 1 - User Feedback - Conduct and Gather User Feedback | January 6, 2025 8:00 AM | January 17, 2025 5:00 PM | 10 | 0d | 582FS+3d | 584SS | 1 | Start No Earlier Than | Warning
11515 | Case Management Group 1 - User Feedback - Capture and Document in JIRA | January 6, 2025 8:00 AM | January 24, 2025 5:00 PM | 14 | 0d | 583SS | 585 | 1 | Start No Earlier Than | Warning
2130 | Case Management Group 2 - Finalize Requirements Baseline | September 13, 2024 8:00 AM | September 30, 2024 5:00 PM | 12 | 0d | 674FF-14d,573 | 4393FS+22d,593SS-40d | 1 | Finish No Earlier Than | Warning
4147 | Case Management Group 2 Design Cycle 1 - Prepare Blueprint | July 15, 2024 8:00 AM | October 14, 2024 5:00 PM | 66 | 0d | 588SS-40d | 594SS+10d,2246SS,2258SS,2250SS,2521SS,2522SS,1319SS,1323SS,1335SS,4532,4534 | 1 | Start No Earlier Than | Warning
11477 | Case Management Group 2 Design Cycle 2 - Perform Pre-Build activities | October 28, 2024 8:00 AM | March 7, 2025 5:00 PM | 88 | 0d | 595FS-1d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | 1 | Finish No Earlier Than | Warning
11478 | Case Management Group 2 Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | November 18, 2024 8:00 AM | March 7, 2025 5:00 PM | 74 | 0d | 595FS-1d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | 1 | Finish No Earlier Than | Warning
4153 | Case Management Group 2 Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 | 0d | 595FS+44d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | 1 | Finish No Earlier Than | Warning
6168 | Case Management Group 3 - Finalize Requirements Baseline | October 3, 2024 8:00 AM | November 8, 2024 5:00 PM | 27 | 0d | 661FF,674FS-12d | 608SS+12d,606FS-18d | 1 | Finish No Earlier Than | Warning
6175 | Case Management Group 3 Design Cycle 1 - Prepare Blueprint | October 21, 2024 8:00 AM | February 14, 2025 5:00 PM | 79 | 0d | 603SS+12d | 609SS+10d,2262SS,2270SS,2274SS,1327SS,1339SS,1359SS,1373SS,1351SS,630SS,377SS,689SS,696SS | 1 | Start No Earlier Than | Warning
11482 | Case Management Group 3 Design Cycle 2 - Perform Pre-Build activities | March 3, 2025 8:00 AM | May 9, 2025 5:00 PM | 49 | 0d | 610 | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS,613SS+10d | 1 | Finish No Earlier Than | Warning
11481 | Case Management Group 3 Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | March 17, 2025 8:00 AM | May 9, 2025 5:00 PM | 39 | 0d | 612SS+10d | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS,614SS+10d | 1 | Finish No Earlier Than | Warning
6179 | Case Management Group 3 Design Cycle 2 - Prepare for Walkthrough with Core Constituents | April 1, 2025 8:00 AM | May 9, 2025 5:00 PM | 29 | 0d | 613SS+10d | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS | 1 | Start No Earlier Than | Warning
11408 | M7: RC: Finalize Value Hypothesis | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 | 0d |  | 638SS | 1 | Must Start On | Warning
11417 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | August 12, 2024 8:00 AM | October 11, 2024 5:00 PM | 45 | 0d | 644FS+136d | 647SS-54d | 1 | Start No Earlier Than | Warning
11418 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | May 28, 2024 8:00 AM | June 25, 2024 5:00 PM | 21 | 0d | 646SS-54d |  | 1 | Start No Earlier Than | Warning
11426 | M11: RC: Finalize Value Hypothesis | December 4, 2023 8:00 AM | February 7, 2024 5:00 PM | 45 | 0d |  | 654SS+5d | 1 | Start No Earlier Than | Warning
418 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 97 | 0d | 644 | 664SS | 1 | Must Start On | Warning
425 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 35 | 0d | 651SS-10d | 671SS | 1 | Start No Earlier Than | Warning
426 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 35 | 0d | 670SS | 672SS | 1 | Start No Earlier Than | Warning
428 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 35 | 0d | 671SS | 673SS | 1 | Start No Earlier Than | Warning
429 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 35 | 0d | 672SS | 674SS | 1 | Start No Earlier Than | Warning
430 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 35 | 0d | 673SS | 588FF-14d,679FF,1406SS-500d,603FS-12d,4501SS+22d | 1 | Start No Earlier Than | Warning
432 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 | 0d | 660 | 677SS | 1 | Start No Earlier Than | Warning
433 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 | 0d | 676SS | 678SS | 1 | Start No Earlier Than | Warning
4595 | Courts - M14 - Conduct Walkthrough | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 | 0d |  | 1475,790SS | 1 | Must Start On | Warning
4216 | Courts - Design Cycle 1 - Prepare Blueprint | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 89 | 0d | 790 | 799SS+10d,2282SS,2286SS,2290SS,2294SS,1337SS,1363SS | 1 | Must Start On | Warning
11484 | Courts - Design Cycle 2 - Perform Pre-Build activities | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 | 0d | 800 | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS,803SS+10d | 1 | Start No Earlier Than | Warning
11483 | Courts - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | January 21, 2025 8:00 AM | March 7, 2025 5:00 PM | 33 | 0d | 802SS+10d | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS | 1 | Start No Earlier Than | Warning
4220 | Courts - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 29 | 0d | 800FS+14d | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS | 1 | Start No Earlier Than | Warning
781 | M16: RC: Finalize Value Hypothesis | November 6, 2023 8:00 AM | January 12, 2024 5:00 PM | 45 | 0d |  | 810SS | 1 | Must Start On | Warning
816 | M18: RC: Finalize Value Hypothesis | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 | 0d |  | 828SS | 1 | Must Start On | Warning
851 | M16: B1 09.11 Generate Notices (CARESV1-67) | July 22, 2024 8:00 AM | June 27, 2025 5:00 PM | 234 | 0d | 806FF,849FS-10d | 853SS,867,871,876 | 1 | Must Start On | Warning
873 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 867SS | 869SS,4567 | 0.83 | Start No Earlier Than | Warning
874 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 544d | 868SS | 882SS,4567 | 0.48 | Start No Earlier Than | Warning
877 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 43.74d | 871SS | 873SS,4582 | 0.75 | Start No Earlier Than | Warning
878 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 0d | 872SS | 874SS,4582 | 1 | Start No Earlier Than | Warning
879 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 | 0d | 873SS | 886SS,4582 | 1 | Start No Earlier Than | Warning
925 | M16: B1 09.11 Generate Notices (CARESV1-67) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 899SS | 912SS,2565SS | 0.2 | Start No Earlier Than | Warning
975 | Resource Family Approval - Design Cycle 1 - Prepare Blueprint | September 30, 2024 8:00 AM | December 20, 2024 5:00 PM | 57 | 0d | 933FS+6d | 935SS+10d,2314SS,2318SS,2322SS,1331SS,1343SS,1369SS | 1 | Must Start On | Warning
981 | Resource Family Approval - Design Cycle 2 - Final Review and Design Baseline | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 34 | 636d | 941SS+5d | 992FF,1000FF | 0.97 | Finish No Earlier Than | Warning
993 | M27: RC: Finalize Value Hypothesis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 | 0d |  | 955SS,2605SS+100d | 1 | Must Start On | Warning
1002 | M28: RC: Finalize Value Hypothesis | February 26, 2024 8:00 AM | April 22, 2024 5:00 PM | 40 | 0d |  | 964SS+10d | 1 | Start No Earlier Than | Warning
1035 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 218 | 0d | 961SS-65d | 982SS | 1 | Start No Earlier Than | Warning
2606 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 218 | 0d | 981SS | 983SS | 1 | Start No Earlier Than | Warning
1036 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 218 | 0d | 982SS | 984SS | 1 | Start No Earlier Than | Warning
1012 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 218 | 0d | 983SS | 1000FS+22d | 1 | Start No Earlier Than | Warning
2703 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Application (CARESV1-56) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -13d | 1011SS | 1030SS,1037SS,1042SS+38d,4639FS-19d | 0 | Start No Earlier Than | Warning
2704 | M26: B2: 16.04 Document Resource Family Home Interactions (CARESV1-18) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1029SS | 1031SS | 0 | Start No Earlier Than | Warning
2705 | M26: B3: 16.06 Update Resource Family Home Information (CARESV1-102) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1030SS | 1032SS | 0 | Start No Earlier Than | Warning
2706 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1031SS | 1033SS | 0 | Start No Earlier Than | Warning
2707 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1032SS | 1034SS | 0 | Start No Earlier Than | Warning
2708 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1033SS | 1035SS | 0 | Start No Earlier Than | Warning
2709 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 3.42d | 1034SS | 1047,4643FF | 0 | Start No Earlier Than | Warning
2711 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 59d | 1029SS | 1038SS | 0 | Start No Earlier Than | Warning
2716 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1029SS+38d | 1043SS,1060 | 0 | Start No Earlier Than | Warning
2717 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1042SS | 1044SS | 0 | Start No Earlier Than | Warning
2718 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1043SS | 4665FF | 0 | Start No Earlier Than | Warning
4209 | Financial Management - Scenario Requirements Validation | October 21, 2024 8:00 AM | November 8, 2024 5:00 PM | 15 | 0d | 1130FF+15d | 1090FS-5d | 1 | Finish No Earlier Than | Warning
4202 | Financial Management - Design Cycle 1 - Prepare Blueprint | December 4, 2024 8:00 AM | March 19, 2025 9:17 AM | 71 | 0d | 1091FS+10d | 1093SS+10d,2310SS,2312SS,1355SS,1365SS,1133SS,1138SS | 1 | Must Start On | Warning
11487 | Financial Management - Design Cycle 2 - Perform Pre-Build activities | April 2, 2025 8:00 AM | June 20, 2025 5:00 PM | 57 | 0d | 1094FS-2d | 1099SS+5d,2594SS,1097SS+10d | 1 | Start No Earlier Than | Warning
11488 | Financial Management - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | April 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 47 | 0d | 1096SS+10d | 1099SS+5d,2594SS | 1 | Start No Earlier Than | Warning
4206 | Financial Management - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | May 12, 2025 8:00 AM | June 20, 2025 5:00 PM | 29 | 0d | 1094FS+28d | 1099SS+5d,2594SS | 1 | Start No Earlier Than | Warning
1193 | M23: RC: Finalize Value Hypothesis | March 25, 2024 8:00 AM | May 20, 2024 5:00 PM | 40 | 0d |  | 1104SS+5d | 1 | Must Start On | Warning
1202 | M24: RC: Finalize Value Hypothesis | January 2, 2024 8:00 AM | February 28, 2024 5:00 PM | 40 | 0d |  | 1113SS+15d | 1 | Must Start On | Warning
7535 | Eligibility - Scenario Requirements Validation | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 15 | 0d | 1213FF | 5479SS-10d,5507,5513,1194SS+3d | 1 | Finish No Earlier Than | Warning
7539 | Eligibility - Design Cycle 1 - Prepare Interface Specifications | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 89 | 0d | 1189SS+3d | 1195SS+10d,2306SS | 1 | Start No Earlier Than | Warning
7548 | M21: RC: Finalize Value Hypothesis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d |  | 1206SS | 1 | Finish No Earlier Than | Warning
7549 | M21: RC: Draft Service Maps | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1205SS | 1207SS | 1 | Finish No Earlier Than | Warning
7550 | M21: RC: Complete Legacy Analysis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1206SS | 1208SS | 1 | Finish No Earlier Than | Warning
7551 | M21: RC: Finalize Epics | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1207SS | 1209SS | 1 | Finish No Earlier Than | Warning
7552 | M21: RC: Complete conceptual and epic-level Domain Model diagrams | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1208SS | 1210SS | 1 | Finish No Earlier Than | Warning
7553 | M21: RC: Define User Story titles | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1209SS | 1211SS | 1 | Finish No Earlier Than | Warning
7554 | M21: RC: Complete External Systems pre-analysis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1210SS | 1212SS | 1 | Finish No Earlier Than | Warning
7555 | M21: RC: Facilitate Inception | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 80 | 0d | 1211SS | 1215FS+20d,2587FS+210d | 1 | Finish No Earlier Than | Warning
7578 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 | 0d | 1202FF,1220 | 1225SS,1226SS,1227SS,1224SS | 1 | Finish No Earlier Than | Warning
4677 | Admin Console - Design Cycle 1 - Prepare Blueprint | February 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 39 | 0d | 1261SS+185d | 1267SS+10d | 1 | Must Start On | Warning
11521 | Identify and Prioritize Tech Debt Items | August 12, 2024 8:00 AM | December 31, 2024 5:00 PM | 98 | 0d |  |  | 1 | Finish No Earlier Than | Warning
12683 | Shared Services - RBAC Framework (SalesForce) - Design | May 5, 2025 8:00 AM | August 8, 2025 5:00 PM | 68 | 0d |  | 1380 | 1 | Start No Earlier Than | Warning
7457 | Complete Build/SIT/QA of Walkthrough Findings - EUST 2 | July 15, 2024 8:00 AM | May 2, 2025 5:00 PM | 202 | 0d | 577SS-31d | 1387SS | 1 | Must Start On | Warning
7456 | Complete Build/SIT/QA of Walkthrough Findings - EUST 3 | July 15, 2024 8:00 AM | May 1, 2026 5:00 PM | 452 | 80d | 1386SS | 1855 | 0.68 | Start No Earlier Than | Warning
4275 | Milestone FCED 20.1 - BRC | January 30, 2023 8:00 AM | October 4, 2024 5:00 PM | 425 | 0d | 674SS-500d | 1407 | 1 | Finish No Earlier Than | Warning
4280 | Milestone JNET 15.1 - BRC | May 30, 2023 8:00 AM | July 31, 2024 5:00 PM | 295 | 0d | 426SS-2d | 1414 | 1 | Finish No Earlier Than | Warning
4281 | Milestone JNET 15.1 - Design | January 29, 2024 8:00 AM | August 30, 2024 8:58 AM | 57 | 0d | 1413,431SS+113d | 1415SS+39d | 1 | Finish No Earlier Than | Warning
4283 | Milestone JNET 15.1 - QA and End-to-End Testing | June 17, 2024 8:00 AM | December 6, 2024 5:00 PM | 121 | 0d | 1415SS+58d | 1417FF | 1 | Finish No Earlier Than | Warning
11588 | Milestone JNET 15.1 (CARESV1-45367) Complete | December 6, 2024 8:00 AM | December 6, 2024 5:00 PM | 1 | 0d | 1416FF |  | 1 | Finish No Earlier Than | Warning
4290 | Milestone (LIS/FAS data) 26.1 - BRC | July 15, 2024 8:00 AM | October 25, 2024 5:00 PM | 75 | 0d | 979SS+77d |  | 1 | Finish No Earlier Than | Warning
4291 | Milestone (LIS/FAS data) 26.1 - Design | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 151 | -7d |  | 1427 | 0.86 | Start No Earlier Than | Warning
4292 | Milestone (LIS/FAS data) 26.1 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -7d | 1426 | 1428,4644 | 0 | Finish No Earlier Than | Warning
4293 | Milestone (LIS/FAS data) 26.1 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1427 | 1429FF | 0.08 | Start No Earlier Than | Warning
11590 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1428FF |  | 0 | Start No Earlier Than | Warning
4296 | Milestone CECRIS 23.2 - Design | March 10, 2025 8:00 AM | October 3, 2025 5:00 PM | 146 | 0d | 1136SS,1431 | 1433 | 1 | Finish No Earlier Than | Warning
4297 | Milestone CECRIS 23.2 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 446d | 1432 | 1434,523FF+21d | 0 | Finish No Earlier Than | Warning
4298 | Milestone CECRIS 23.2 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1433 | 1435 | 0 | Finish No Earlier Than | Warning
6816 | M10.1: RC: Finalize Value Hypothesis | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 | 0d |  | 1439SS | 1 | Must Start On | Warning
6457 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 121 | 0d | 1453FS-64d | 1456SS,2268SS | 1 | Must Start On | Warning
4306 | H2 Re-work (Conduct Hardening) | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 137 | 0d | 20,45,234,279,788,790 | 2987,2990,3000 | 1 | Start No Earlier Than | Warning
4312 | H3 Re-work (Conduct Hardening) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | -17d | 345 | 2988,2991,2992,3001,3003,3004,3005 | 0.45 | Start No Earlier Than | Warning
5478 | H3 EUST Backlog (Resolve Prior EUST Findings) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 | 466d | 707FF,735FF,717FF,745FF,713FF,741FF,878FF,893FF | 1481SS | 0.45 | Start No Earlier Than | Warning
2860 | EUST for Milestones 3, 4, and 5 | February 1, 2024 8:00 AM | April 11, 2024 5:00 PM | 49 | 0d | 87FF,133FF,189FF,98,144,204,1473,2483,2490 | 1485SS+30d | 1 | Finish No Earlier Than | Warning
12699 | Send communication to Service Managers, SMEs and interface partners around scenario writing workshops | October 22, 2024 8:00 AM | October 22, 2024 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
12700 | Schedule EUST 2 scenario writing workgroups based on Milestone | October 30, 2024 8:00 AM | November 1, 2024 5:00 PM | 3 | 0d |  | 1500 | 1 | Start No Earlier Than | Warning
12701 | Prepare template for scenarios, includes mapping to specific functionality | November 1, 2024 8:00 AM | November 7, 2024 5:00 PM | 5 | 0d |  |  | 1 | Start No Earlier Than | Warning
12709 | Establish date the communications should be sent to CC SPOC to identify users | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM | 5 | 0d |  | 1510SS | 1 | Start No Earlier Than | Warning
12711 | Draft communication to send to all counties requesting EUST participation | November 8, 2024 8:00 AM | November 15, 2024 5:00 PM | 5 | 0d |  | 1512 | 1 | Start No Earlier Than | Warning
12715 | Hold EUST 2 overview meeting option 1 | December 6, 2024 8:00 AM | December 6, 2024 5:00 PM | 1 | 0d |  | 1516 | 1 | Start No Earlier Than | Warning
12732 | Set up Salesforce EUST environment | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM | 1 | 0d |  | 1529SS | 1 | Start No Earlier Than | Warning
12734 | Mule Integration Setup | November 12, 2024 8:00 AM | November 15, 2024 5:00 PM | 4 | 0d |  | 1539,1531,1532,1533,1535,1537 | 1 | Start No Earlier Than | Warning
12745 | Identify counties participating in EUST 2 | November 12, 2024 8:00 AM | November 18, 2024 5:00 PM | 5 | 0d |  | 1547FS+73d,1548FS+73d | 1 | Start No Earlier Than | Warning
12750 | Final Code Deployment for User Feedback | December 23, 2024 8:00 AM | December 30, 2024 5:00 PM | 5 | 0d |  | 1552 | 1 | Start No Earlier Than | Warning
12752 | Final Code Deployment for EUST2 | February 24, 2025 8:00 AM | February 28, 2025 5:00 PM | 5 | 0d |  | 1555 | 1 | Start No Earlier Than | Warning
12758 | Identify Transactional Data Needs for EUST 2 (including volume) | November 18, 2024 8:00 AM | January 2, 2025 5:00 PM | 30 | 0d |  | 1559 | 1 | Start No Earlier Than | Warning
12762 | Identify Office / Unit Structure Needs for EUST 2 | October 28, 2024 8:00 AM | November 1, 2024 5:00 PM | 5 | 0d |  | 1559 | 1 | Start No Earlier Than | Warning
12757 | Confirm readiness of staging environment | October 23, 2024 8:00 AM | October 29, 2024 5:00 PM | 5 | 0d |  | 1571,1572 | 1 | Start No Earlier Than | Warning
12769 | Confirm interface integration connection | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5 | 0d |  | 1571FS+56d,1572FS+56d | 1 | Start No Earlier Than | Warning
12772 | Develop the Training Materials for EUST 2 | October 28, 2024 8:00 AM | February 14, 2025 5:00 PM | 74 | 0d |  | 1577FS+4d | 1 | Start No Earlier Than | Warning
13069 | Setup EUST Testers in Salesforce Enablement | January 6, 2025 8:00 AM | February 19, 2025 5:00 PM | 31 | 0d |  |  | 1 | Start No Earlier Than | Warning
12771 | EUST Testers complete online training | March 17, 2025 8:00 AM | March 21, 2025 5:00 PM | 5 | 0d |  |  | 1 | Start No Earlier Than | Warning
12785 | Conduct ELT presentation of EUST 2 | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
43570 | Conduct Funcational Analysis | June 2, 2025 8:00 AM | June 6, 2025 5:00 PM | 5 | 0d |  | 1623 | 1 | Start No Earlier Than | Warning
43579 | Conduct Initial Analysis of Planned Build Drop 2 | June 13, 2025 8:00 AM | July 11, 2025 5:00 PM | 20 | 0d |  |  | 1 | Start No Earlier Than | Warning
43580 | Delivery of Build Drop Completed | July 7, 2025 8:00 AM | July 7, 2025 5:00 PM | 1 | 0d |  | 1634SS | 1 | Start No Earlier Than | Warning
43581 | PaaS application demo and walkthrough of developed funcationality | July 11, 2025 8:00 AM | July 11, 2025 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
43584 | Review Draft Scenario Narratives with Service Areas | July 21, 2025 8:00 AM | July 30, 2025 5:00 PM | 8 | 0d |  | 1637FF | 1 | Start No Earlier Than | Warning
43588 | Review and Validate Key Actions/Steps | August 11, 2025 8:00 AM | August 15, 2025 5:00 PM | 5 | 539d |  | 1641FF | 0.9 | Start No Earlier Than | Warning
43591 | Conduct Initial Analysis of Planned Build Drop 3 | July 7, 2025 8:00 AM | August 8, 2025 5:00 PM | 25 | 0d |  |  | 1 | Start No Earlier Than | Warning
43592 | Delivery of Build Drop Completed | August 8, 2025 8:00 AM | August 8, 2025 5:00 PM | 1 | 0d |  | 1645,1646 | 1 | Start No Earlier Than | Warning
43594 | Conduct Funcational Analysis | August 11, 2025 8:00 AM | August 15, 2025 5:00 PM | 5 | 0d | 1644 | 1647SS,1648 | 1 | Finish No Earlier Than | Warning
43595 | Develop Scenario Narratives | August 11, 2025 8:00 AM | August 27, 2025 5:00 PM | 13 | 0d | 1646SS |  | 1 | Finish No Earlier Than | Warning
43596 | Review Draft Scenario Narratives with Service Areas | August 18, 2025 8:00 AM | August 22, 2025 5:00 PM | 5 | 0d | 1646 | 1649FF | 1 | Finish No Earlier Than | Warning
43597 | Submit Scenario Narratives to Technical Testing Team | August 22, 2025 8:00 AM | August 22, 2025 5:00 PM | 1 | 1.2d | 1648FF | 1650 | 0.8 | Start No Earlier Than | Warning
43598 | Conduct Testing and Add Key Actions | August 25, 2025 8:00 AM | September 10, 2025 5:00 PM | 12 | 0.1d | 1649 | 1651,1652 | 0.1 | Finish No Earlier Than | Warning
43599 | Submit completed testing and key Actions and sed to User Feedback Team | September 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 1 | 521d | 1650 |  | 0.1 | Start No Earlier Than | Warning
43600 | Review and Validate Key Actions/Steps | September 11, 2025 8:00 AM | September 12, 2025 5:00 PM | 2 | 0.05d | 1650 | 1653 | 0.05 | Finish No Earlier Than | Warning
43601 | Submit Final Scenarios to Training Team | September 15, 2025 8:00 AM | September 15, 2025 5:00 PM | 1 | 519d | 1652 | 1768 | 0.05 | Start No Earlier Than | Warning
43603 | Conduct Initial Analysis of Planned Build Drop 4 | August 18, 2025 8:00 AM | September 22, 2025 5:00 PM | 25 | 0d |  |  | 1 | Start No Earlier Than | Warning
43604 | Delivery of Build Drop Completed | October 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 1 | 0.99d |  | 1658,1659SS | 0 | Start No Earlier Than | Warning
43605 | PaaS application demo and walkthrough of developed funcationality | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 504d |  |  | 0 | Start No Earlier Than | Warning
43607 | Develop Scenario Narratives | October 3, 2025 8:00 AM | October 17, 2025 5:00 PM | 11 | 495d | 1656SS |  | 0.09 | Finish No Earlier Than | Warning
43609 | Submit Scenario Narratives to Technical Testing Team | October 17, 2025 8:00 AM | October 17, 2025 5:00 PM | 1 | 480d | 1660FF | 1662 | 0 | Start No Earlier Than | Warning
43611 | Submit completed testing and key Actions and sed to User Feedback Team | November 7, 2025 8:00 AM | November 7, 2025 5:00 PM | 1 | 476d |  | 1664 | 0 | Start No Earlier Than | Warning
43613 | Submit Final Scenarios to Training Team | November 14, 2025 8:00 AM | November 14, 2025 5:00 PM | 1 | 439d |  | 1769 | 0 | Start No Earlier Than | Warning
43615 | Conduct Initial Analysis of Planned Build Drop 5 | September 17, 2025 8:00 AM | November 28, 2025 5:00 PM | 51 | 466d |  | 1669 | 0.25 | Start No Earlier Than | Warning
43616 | Delivery of Build Drop Completed | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 1 | 426d |  | 1670 | 0 | Start No Earlier Than | Warning
43619 | Develop Scenario Narratives | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 10 | 457d |  |  | 0 | Start No Earlier Than | Warning
43621 | Submit Scenario Narratives to Technical Testing Team | December 12, 2025 8:00 AM | December 12, 2025 5:00 PM | 1 | 426d | 1672FF | 1674 | 0 | Start No Earlier Than | Warning
43624 | Review and Validate Key Actions/Steps | January 8, 2026 8:00 AM | January 13, 2026 5:00 PM | 4 | 426d | 1675 | 1677 | 0 | Start No Earlier Than | Warning
43829 | Create new MS Teams/SharePoint space for User Feedback (EUST 3 ) | July 14, 2025 8:00 AM | July 18, 2025 5:00 PM | 5 | 0d |  |  | 1 | Start No Earlier Than | Warning
43830 | Identify CC to participate in UF Testing (Must have completed EUST 2) | July 11, 2025 8:00 AM | July 11, 2025 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
43832 | Draft communication User Feedback Effort | September 8, 2025 8:00 AM | September 10, 2025 5:00 PM | 3 | 0d |  | 1683 | 1 | Start No Earlier Than | Warning
43835 | Load users to SharePoint feedback site as needed | October 7, 2025 8:00 AM | November 3, 2025 5:00 PM | 20 | 484d |  |  | 0 | Start No Earlier Than | Warning
43838 | Confirm Staging Environment Readiness | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | 494d |  | 1689SS | 0 | Start No Earlier Than | Warning
43841 | PaaS User Access Testing to Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 490d |  |  | 0 | Start No Earlier Than | Warning
43842 | Complete State QA of code in Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 5 | 489d | 1690 | 1693 | 0 | Start No Earlier Than | Warning
43844 | Schedule M-Th office hours for 2 weeks of testing | October 27, 2025 8:00 AM | October 27, 2025 5:00 PM | 1 | 489d | 1690 |  | 0 | Start No Earlier Than | Warning
43845 | Conduct User Feedback Testing | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM | 10 | 465d |  | 1696SS | 0 | Start No Earlier Than | Warning
43846 | Capture feedback in MS Teams and Document in JIRA | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM | 10 | 465d | 1695SS | 1697 | 0 | Start No Earlier Than | Warning
43847 | Report out on User Feedback | November 10, 2025 8:00 AM | November 20, 2025 5:00 PM | 8 | 465d | 1696 | 1698 | 0 | Finish No Earlier Than | Warning
43848 | Present findings to ELT | November 24, 2025 8:00 AM | November 24, 2025 5:00 PM | 1 | 464d | 1697 | 1699FS+5d | 0 | Start No Earlier Than | Warning
43849 | Present findings to User Feedback participants | December 3, 2025 8:00 AM | December 3, 2025 5:00 PM | 1 | 464d | 1698FS+5d |  | 0 | Start No Earlier Than | Warning
43851 | Confrim User Permission Sets Validated | November 24, 2025 8:00 AM | November 26, 2025 5:00 PM | 3 | 468d |  |  | 0 | Start No Earlier Than | Warning
43852 | Confirm Staging Environment Readiness | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | Start No Earlier Than | Warning
43853 | Complete Build / SIT and data load in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | Start No Earlier Than | Warning
43854 | Data loaded in staging (Day 0 data) | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | Start No Earlier Than | Warning
43855 | Complete State QA of code in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 | 462d |  |  | 0 | Start No Earlier Than | Warning
43856 | Hold User Feedback Kickoff Meeting | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM | 1 | 461d |  |  | 0 | Start No Earlier Than | Warning
43857 | Schedule M-Th office hours for 2 weeks of testing | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM | 1 | 461d |  |  | 0 | Start No Earlier Than | Warning
43858 | Conduct User Feedback Testing | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 | 452d |  |  | 0 | Start No Earlier Than | Warning
43859 | Capture feedback in MS Teams and Document in JIRA | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 | 437d |  | 1710 | 0 | Start No Earlier Than | Warning
43860 | Report out on User Feedback | December 22, 2025 8:00 AM | January 2, 2026 5:00 PM | 8 | 437d | 1709 | 1711 | 0 | Finish No Earlier Than | Warning
43861 | Present findings to ELT | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 437d | 1710 | 1712FS+5d | 0 | Start No Earlier Than | Warning
43862 | Present findings to User Feedback participants | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1 | 437d | 1711FS+5d |  | 0 | Start No Earlier Than | Warning
43648 | Establish date the communications should be sent to CC SPOC to identify users | September 8, 2025 8:00 AM | September 12, 2025 5:00 PM | 5 | 0d |  | 1715 | 1 | Start No Earlier Than | Warning
43653 | Hold EUST 3 overview meeting option 1 | November 6, 2025 8:00 AM | November 6, 2025 5:00 PM | 1 | 480d |  | 1720 | 0 | Finish No Earlier Than | Warning
43655 | Document county participants in EUST 3 | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 454d | 1717SS | 1729FS-1d | 0 | Start No Earlier Than | Warning
43656 | Add new users to spreadsheet: Users by County | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 468d | 1717SS |  | 0 | Start No Earlier Than | Warning
43657 | Add county participants to Microsoft Teams Space for EUST 3 Feedback | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 37 | 468d | 1717SS |  | 0 | Start No Earlier Than | Warning
43658 | Communicate with County teams to test access to EUST 3 | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM | 5 | 425d |  | 1725SS | 0 | Start No Earlier Than | Warning
43662 | Identify Office / Unit Structure Needs for EUST 3 | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 485d |  | 1761 | 0 | Start No Earlier Than | Warning
43664 | Produce Template for Office / Unit Structure | November 26, 2025 8:00 AM | November 26, 2025 5:00 PM | 1 | 434d |  | 1731 | 0 | Start No Earlier Than | Warning
43665 | Distribute the Template to Counties | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 1 | 434d | 1730 | 1732 | 0 | Start No Earlier Than | Warning
43673 | Communicate to end users and confirm access (CC SPOC) or if they need a PW reset | January 16, 2026 8:00 AM | January 16, 2026 5:00 PM | 1 | 434d | 1736 |  | 0 | Start No Earlier Than | Warning
43675 | Set up Salesforce EUST environment | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
43677 | Mule API Updated Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 439d |  | 1742SS | 0 | Start No Earlier Than | Warning
43678 | DocuEdge Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 5 | 439d |  |  | 0 | Start No Earlier Than | Warning
43679 | DocuEdge Mule Endpoint Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 414d |  | 1746 | 0 | Start No Earlier Than | Warning
43681 | AEM Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 442d |  |  | 0 | Start No Earlier Than | Warning
43682 | SOLR API Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 2 | 442d |  |  | 0 | Start No Earlier Than | Warning
43685 | Snowflake Updated Deployment | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d | 1742SS |  | 0 | Start No Earlier Than | Warning
43690 | Final Code Deployment for EUST 3 Admin | January 6, 2026 8:00 AM | January 6, 2026 5:00 PM | 1 | 437d |  | 1758 | 0 | Start No Earlier Than | Warning
43694 | Identify Transactional Data Needs for EUST 3 (including volume) | November 17, 2025 8:00 AM | December 30, 2025 5:00 PM | 30 | 436d |  | 1761 | 0 | Start No Earlier Than | Warning
43696 | Develop steps to manually create Transactional Data | December 8, 2025 8:00 AM | January 6, 2026 5:00 PM | 20 | 437d |  |  | 0 | Start No Earlier Than | Warning
43697 | Deploy EUST 3 Package and Day 0 Data | January 5, 2026 8:00 AM | January 16, 2026 5:00 PM | 10 | 429d |  |  | 0 | Start No Earlier Than | Warning
43705 | Confirm Number of Admin Console Training Attendees (by Course) | December 17, 2025 8:00 AM | December 17, 2025 5:00 PM | 1 | 439d | 1769FF+7d | 1773FS+10d | 0 | Finish No Earlier Than | Warning
43706 | Schedule Training Sessions | December 22, 2025 8:00 AM | December 22, 2025 5:00 PM | 1 | 451d |  |  | 0 | Start No Earlier Than | Warning
43708 | Load Quick Reference Guides and Knowledge Base Articles for Admin | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | Start No Earlier Than | Warning
43710 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | Start No Earlier Than | Warning
43711 | Load Quick Reference Guides and Knowledge Base Articles for EUST3 | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 5 | 434d |  |  | 0 | Start No Earlier Than | Warning
43713 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 30, 2026 5:00 PM | 14 | 425d |  |  | 0 | Start No Earlier Than | Warning
43714 | Load Quick Reference Guides and Knowledge Base Articles for Reporting Training | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 1 | 425d |  |  | 0 | Start No Earlier Than | Warning
43716 | Support Office Hours / Delivery Make-Up Sessions (As needed) | February 23, 2026 8:00 AM | February 26, 2026 5:00 PM | 4 | 407d |  |  | 0 | Start No Earlier Than | Warning
43718 | Confirm readiness of environment | January 6, 2026 8:00 AM | January 12, 2026 5:00 PM | 5 | 428d |  | 1786,1787,1785,1788,1789,1790,1791 | 0 | Start No Earlier Than | Warning
43719 | Confirm interface integration connection | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Start No Earlier Than | Warning
43727 | EUST 3 Admin Go-No-Go | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d |  |  | 0 | Start No Earlier Than | Warning
43728 | EUST 3 Go-No-Go (session 1) | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 443d |  |  | 0 | Start No Earlier Than | Warning
43729 | EUST 3 Final Go-No-Go | January 26, 2026 8:00 AM | January 26, 2026 5:00 PM | 1 | 429d |  |  | 0 | Start No Earlier Than | Warning
43730 | EUST 3 Reporting - Confirm EUST Readiness | February 9, 2026 8:00 AM | February 9, 2026 5:00 PM | 1 | 419d |  |  | 0 | Start No Earlier Than | Warning
43731 | Validation for all scenarios | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 1 | 425d |  |  | 0 | Start No Earlier Than | Warning
43734 | EUST 3 Admin Testing Start | January 20, 2026 8:00 AM | January 20, 2026 5:00 PM | 1 | 433d |  |  | 0 | Start No Earlier Than | Warning
43736 | EUST 3 Testing Start | February 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 1 | 424d |  |  | 0 | Start No Earlier Than | Warning
43740 | EUST 3 Admin Console (Partial M32) | January 20, 2026 8:00 AM | January 30, 2026 5:00 PM | 9 | 382d |  | 1807 | 0 | Start No Earlier Than | Warning
43749 | EUST 3 Reporting | February 23, 2026 8:00 AM | April 3, 2026 5:00 PM | 29 | 382d | 1804SS |  | 0 | Start No Earlier Than | Warning
43753 | Conduct Office Hours | January 16, 2026 8:00 AM | April 3, 2026 5:00 PM | 53 | 382d |  |  | 0 | Start No Earlier Than | Warning
43754 | Schedule prioritization sessions to prioritize feedback | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1 | 437d |  |  | 0 | Start No Earlier Than | Warning
43755 | Upload the spreadsheet w/user feedback to JIRA | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d |  | 1822SS,1823SS,1824SS | 0 | Start No Earlier Than | Warning
43758 | EUST 3 - QA Findings | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 52 | 382d | 1821SS |  | 0 | Start No Earlier Than | Warning
43761 | Coordinate with comms team to prepare mid-point sentiment survey | February 23, 2026 8:00 AM | February 27, 2026 5:00 PM | 5 | 406d |  |  | 0 | Start No Earlier Than | Warning
43762 | Send link to mid-point survey | March 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 1 | 396d |  | 1829SS | 0 | Start No Earlier Than | Warning
43764 | Coordinate with Communications team to prepare the Sentiment Survey for EUST | March 30, 2026 8:00 AM | April 6, 2026 5:00 PM | 5 | 376d |  | 1831SS | 0 | Start No Earlier Than | Warning
43765 | Send link to Sentiment Survey to EUST Participants | April 1, 2026 8:00 AM | April 1, 2026 5:00 PM | 1 | 375d | 1830SS | 1832SS | 0 | Start No Earlier Than | Warning
43768 | Confirm exit criteria for EUST is met | April 13, 2026 8:00 AM | April 13, 2026 5:00 PM | 1 | 350d |  | 1835 | 0 | Start No Earlier Than | Warning
10295 | Schedule Mitigation Checkpoint # 1 | September 20, 2024 8:00 AM | September 20, 2024 5:00 PM | 1 | 0d |  | 1862FS+37d | 1 | Must Start On | Warning
13101 | STRP: Draft new Plan | October 1, 2024 8:00 AM | November 26, 2024 5:00 PM | 40 | 0d |  | 1866FS-20d | 1 | Start No Earlier Than | Warning
13113 | V1CP: Determine CARES V1 Final Cutover Plan | December 31, 2024 8:00 AM | February 18, 2025 5:00 PM | 33 | 0d |  | 1878 | 1 | Start No Earlier Than | Warning
13119 | V2CP: Draft new plan or update existing V1 Cutover Plan | June 1, 2027 8:00 AM | July 27, 2027 5:00 PM | 40 | 0d |  | 1893 | 0 | Start No Earlier Than | Warning
11050 | Training Checkpoint # 1 | December 5, 2025 8:00 AM | December 5, 2025 5:00 PM | 1 | 0d |  | 5618,1905FS+65d | 0 | Must Start On | Warning
2878 | DocuEdge Infrastructure Setup & Configuration | June 1, 2022 8:00 AM | April 11, 2024 5:00 PM | 466 | 0d | 1908 | 1912 | 1 | Start No Earlier Than | Warning
2938 | DocuEdge - Milestone 7 - CARESV1-315 ADM - CM - Redaction | August 30, 2024 8:00 AM | September 15, 2025 5:00 PM | 261 | 0d | 1968SS | 1970FS-285d | 1 | Finish No Earlier Than | Warning
2939 | DocuEdge - Milestone 7 - CARESV1-317 ADM - CM - Versioning | July 30, 2024 8:00 AM | August 29, 2024 5:00 PM | 23 | 0d | 1968SS-1d,1969FS-285d | 1971SS | 1 | Finish No Earlier Than | Warning
2940 | DocuEdge - Milestone 7 - CARESV1-319 ADM - CM - Retrieval | August 12, 2024 8:00 AM | August 22, 2024 5:00 PM | 9 | 0d | 1970SS | 1972SS | 1 | Finish No Earlier Than | Warning
2941 | DocuEdge - Milestone 7 - CARESV1-320 ADM - CM - Upload | August 12, 2024 8:00 AM | August 29, 2024 5:00 PM | 14 | 0d | 1971SS | 1973 | 1 | Finish No Earlier Than | Warning
2942 | DocuEdge - Milestone 7 - CARESV1-322 ADM - CM - Storage | September 3, 2024 8:00 AM | September 24, 2024 5:00 PM | 16 | 0d | 1972 | 1974 | 1 | Finish No Earlier Than | Warning
2943 | DocuEdge - Milestone 7 - CARESV1-323 ADM - CM - Search | October 15, 2024 8:00 AM | January 27, 2025 5:00 PM | 69 | 0d | 1973 | 1976,2088FS+29d | 1 | Finish No Earlier Than | Warning
2961 | DocuEdge - Milestone 10 - CARESV1-313 ADM - CM - File Management and Metadata | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 | 0d | 2302,1990 | 1993SS+7d,2000SS | 1 | Finish No Earlier Than | Warning
2969 | DocuEdge - Milestone 10.1 - CARESV1-313 ADM - CM - File Management and Metadata | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 | 0d | 1992SS | 2001FS-146d,2032SS-5d | 1 | Finish No Earlier Than | Warning
2970 | DocuEdge - Milestone 10.1 - CARESV1-315 ADM - CM - Redaction | January 10, 2025 8:00 AM | February 11, 2025 5:00 PM | 22 | 0d | 2000FS-146d | 2002FS-2d | 1 | Finish No Earlier Than | Warning
2971 | DocuEdge - Milestone 10.1 - CARESV1-317 ADM - CM - Versioning | February 10, 2025 8:00 AM | March 11, 2025 5:00 PM | 21 | 0d | 2001FS-2d | 2003FS-2d | 1 | Finish No Earlier Than | Warning
2972 | DocuEdge - Milestone 10.1 - CARESV1-319 ADM - CM - Retrieval | March 10, 2025 8:00 AM | April 11, 2025 5:00 PM | 24 | 0d | 2002FS-2d | 2004FS-2d | 1 | Finish No Earlier Than | Warning
2973 | DocuEdge - Milestone 10.1 - CARESV1-320 ADM - CM - Upload | April 10, 2025 8:00 AM | May 9, 2025 5:00 PM | 22 | 0d | 2003FS-2d | 2005 | 1 | Finish No Earlier Than | Warning
2974 | DocuEdge - Milestone 10.1 - CARESV1-322 ADM - CM - Storage | June 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 23 | 0d | 2004 | 2006 | 1 | Finish No Earlier Than | Warning
2975 | DocuEdge - Milestone 10.1 - CARESV1-323 ADM - CM - Search | August 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 23 | 0d | 2005 |  | 1 | Finish No Earlier Than | Warning
2977 | DocuEdge - Milestone 11 - CARESV1-313 ADM - CM - File Management and Metadata | July 10, 2024 8:00 AM | August 8, 2025 5:00 PM | 273 | 0d | 1968SS-10d | 2009FS-249d,2016SS-3d | 1 | Finish No Earlier Than | Warning
2985 | DocuEdge - Milestone 13 - CARESV1-313 ADM - CM - File Management and Metadata | July 5, 2024 8:00 AM | August 28, 2024 5:00 PM | 39 | 0d | 2008SS-3d | 2017FS-12d | 1 | Finish No Earlier Than | Warning
3001 | DocuEdge - Milestone 15 - CARESV1-313 ADM - CM - File Management and Metadata | January 1, 2024 8:00 AM | August 7, 2025 5:00 PM | 404 | 0d | 2000SS-5d | 2033,2040SS+105d,2072SS+23d | 1 | Finish No Earlier Than | Warning
3009 | DocuEdge - Milestone 16 - CARESV1-313 ADM - CM - File Management and Metadata | June 11, 2024 8:00 AM | May 15, 2025 5:00 PM | 234 | 0d | 2032SS+105d | 2041SS+14d,2048SS | 1 | Finish No Earlier Than | Warning
3017 | DocuEdge - Milestone 17 - CARESV1-313 ADM - CM - File Management and Metadata | June 11, 2024 8:00 AM | May 14, 2025 5:00 PM | 233 | 0d | 2040SS | 2049SS+20d,2056SS-1d,2104SS-20d | 1 | Finish No Earlier Than | Warning
3025 | DocuEdge - Milestone 18 - CARESV1-313 ADM - CM - File Management and Metadata | June 10, 2024 8:00 AM | August 14, 2024 5:00 PM | 47 | 0d | 2048SS-1d | 2057FS+1d | 1 | Finish No Earlier Than | Warning
3041 | DocuEdge - Milestone 20 - CARESV1-313 ADM - CM - File Management and Metadata | February 5, 2024 8:00 AM | September 6, 2024 5:00 PM | 150 | 0d | 2032SS+23d | 2073,2112 | 1 | Finish No Earlier Than | Warning
3042 | DocuEdge - Milestone 20 - CARESV1-315 ADM - CM - Redaction | March 6, 2024 8:00 AM | April 9, 2024 5:00 PM | 24 | 0d | 2072 | 2074 | 1 | Finish No Earlier Than | Warning
3043 | DocuEdge - Milestone 20 - CARESV1-317 ADM - CM - Versioning | April 8, 2024 8:00 AM | May 9, 2024 5:00 PM | 24 | 0d | 2073 | 2075 | 1 | Finish No Earlier Than | Warning
3044 | DocuEdge - Milestone 20 - CARESV1-319 ADM - CM - Retrieval | March 6, 2024 8:00 AM | May 9, 2024 5:00 PM | 46 | 0d | 2074 | 2076 | 1 | Finish No Earlier Than | Warning
3045 | DocuEdge - Milestone 20 - CARESV1-320 ADM - CM - Upload | March 6, 2024 8:00 AM | December 20, 2024 5:00 PM | 202 | 0d | 2075 | 2077 | 1 | Start No Earlier Than | Warning
3046 | DocuEdge - Milestone 20 - CARESV1-322 ADM - CM - Storage | December 23, 2024 8:00 AM | January 27, 2025 5:00 PM | 23 | 0d | 2076 | 2078FS-23d | 1 | Finish No Earlier Than | Warning
3047 | DocuEdge - Milestone 20 - CARESV1-323 ADM - CM - Search | December 23, 2024 8:00 AM | February 26, 2025 5:00 PM | 44 | 0d | 2077FS-23d |  | 1 | Finish No Earlier Than | Warning
3049 | DocuEdge - Milestone 21 - CARESV1-313 ADM - CM - File Management and Metadata | December 15, 2023 8:00 AM | September 6, 2024 5:00 PM | 183 | 0d | 2070FS+72d | 2081FS-170d | 1 | Finish No Earlier Than | Warning
3050 | DocuEdge - Milestone 21 - CARESV1-315 ADM - CM - Redaction | January 8, 2024 8:00 AM | August 6, 2024 5:00 PM | 147 | 0d | 2080FS-170d | 2082 | 1 | Finish No Earlier Than | Warning
3051 | DocuEdge - Milestone 21 - CARESV1-317 ADM - CM - Versioning | February 22, 2024 8:00 AM | March 29, 2024 5:00 PM | 27 | 0d | 2081 | 2083 | 1 | Finish No Earlier Than | Warning
3052 | DocuEdge - Milestone 21 - CARESV1-319 ADM - CM - Retrieval | April 22, 2024 8:00 AM | June 25, 2024 5:00 PM | 46 | 0d | 2082 | 2084FS-2d | 1 | Finish No Earlier Than | Warning
3053 | DocuEdge - Milestone 21 - CARESV1-320 ADM - CM - Upload | June 24, 2024 8:00 AM | August 23, 2024 5:00 PM | 44 | 0d | 2083FS-2d | 2085FS-25d | 1 | Finish No Earlier Than | Warning
3054 | DocuEdge - Milestone 21 - CARESV1-322 ADM - CM - Storage | July 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 25 | 0d | 2084FS-25d | 2086FS-1d | 1 | Finish No Earlier Than | Warning
3055 | DocuEdge - Milestone 21 - CARESV1-323 ADM - CM - Search | August 23, 2024 8:00 AM | September 6, 2024 5:00 PM | 11 | 0d | 2085FS-1d |  | 1 | Finish No Earlier Than | Warning
3057 | DocuEdge - Milestone 23 - CARESV1-313 ADM - CM - File Management and Metadata | March 11, 2025 8:00 AM | December 2, 2025 5:00 PM | 185 | 127.14d | 1974FS+29d | 2089FS-162d,2096SS-1d | 0.81 | Finish No Earlier Than | Warning
3058 | DocuEdge - Milestone 23 - CARESV1-315 ADM - CM - Redaction | April 14, 2025 8:00 AM | December 3, 2025 5:00 PM | 163 | 105.82d | 2088FS-162d | 2090FS-142d | 0.78 | Finish No Earlier Than | Warning
3059 | DocuEdge - Milestone 23 - CARESV1-317 ADM - CM - Versioning | May 13, 2025 8:00 AM | December 4, 2025 5:00 PM | 143 | 463d | 2089FS-142d | 2091FS-1834d | 0.74 | Finish No Earlier Than | Warning
3060 | DocuEdge - Milestone 23 - CARESV1-319 ADM - CM - Retrieval | March 14, 2025 8:00 AM | December 5, 2025 5:00 PM | 185 | 145.36d | 2090FS-1834d | 2092FS-184d | 0.79 | Finish No Earlier Than | Warning
3063 | DocuEdge - Milestone 23 - CARESV1-323 ADM - CM - Search | March 18, 2025 8:00 AM | December 8, 2025 5:00 PM | 184 | 461d | 2093FS-183d |  | 0.79 | Finish No Earlier Than | Warning
3065 | DocuEdge - Milestone 24 - CARESV1-313 ADM - CM - File Management and Metadata | March 10, 2025 8:00 AM | April 16, 2025 5:00 PM | 27 | 0d | 2088SS-1d | 2097 | 1 | Finish No Earlier Than | Warning
3067 | DocuEdge - Milestone 24 - CARESV1-317 ADM - CM - Versioning | May 27, 2025 8:00 AM | July 1, 2025 5:00 PM | 26 | 0d | 2097 | 2099 | 1 | Finish No Earlier Than | Warning
3068 | DocuEdge - Milestone 24 - CARESV1-319 ADM - CM - Retrieval | July 2, 2025 8:00 AM | August 8, 2025 5:00 PM | 27 | 0d | 2098 | 2100 | 1 | Finish No Earlier Than | Warning
3069 | DocuEdge - Milestone 24 - CARESV1-320 ADM - CM - Upload | August 11, 2025 8:00 AM | September 15, 2025 5:00 PM | 25 | 0d | 2099 | 2101 | 1 | Finish No Earlier Than | Warning
3070 | DocuEdge - Milestone 24 - CARESV1-322 ADM - CM - Storage | September 16, 2025 8:00 AM | October 23, 2025 5:00 PM | 28 | 466d | 2100 | 2102 | 0.68 | Finish No Earlier Than | Warning
3071 | DocuEdge - Milestone 24 - CARESV1-323 ADM - CM - Search | October 27, 2025 8:00 AM | December 2, 2025 5:00 PM | 25 | 465d | 2101 |  | 0 | Finish No Earlier Than | Warning
3073 | DocuEdge - Milestone 26 - CARESV1-313 ADM - CM - File Management and Metadata | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 395 | 465d | 2048SS-20d | 2105SS | 0.91 | Finish No Earlier Than | Warning
3074 | DocuEdge - Milestone 26 - CARESV1-315 ADM - CM - Redaction | June 7, 2024 8:00 AM | September 2, 2025 5:00 PM | 311 | 0d | 2104SS | 2106SS | 1 | Finish No Earlier Than | Warning
3075 | DocuEdge - Milestone 26 - CARESV1-317 ADM - CM - Versioning | January 6, 2025 8:00 AM | May 2, 2025 5:00 PM | 82 | 0d | 2105SS | 2107 | 1 | Finish No Earlier Than | Warning
3076 | DocuEdge - Milestone 26 - CARESV1-319 ADM - CM - Retrieval | June 9, 2025 8:00 AM | September 12, 2025 5:00 PM | 68 | 0d | 2106 | 2108 | 1 | Finish No Earlier Than | Warning
3077 | DocuEdge - Milestone 26 - CARESV1-320 ADM - CM - Upload | October 8, 2025 8:00 AM | November 12, 2025 5:00 PM | 25 | 478d | 2107 | 163,2109SS-45d | 0.12 | Finish No Earlier Than | Warning
3078 | DocuEdge - Milestone 26 - CARESV1-322 ADM - CM - Storage | September 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 58 | 465d | 2108SS-45d | 2110FF | 0.4 | Finish No Earlier Than | Warning
3079 | DocuEdge - Milestone 26 - CARESV1-323 ADM - CM - Search | August 12, 2025 8:00 AM | December 2, 2025 5:00 PM | 78 | 465d | 2109FF |  | 0.55 | Finish No Earlier Than | Warning
3084 | DocuEdge - Milestone 27 - CARESV1-319 ADM - CM - Retrieval | February 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 39 | 0d | 2114 | 2116 | 1 | Finish No Earlier Than | Warning
3085 | DocuEdge - Milestone 27 - CARESV1-320 ADM - CM - Upload | April 21, 2025 8:00 AM | June 13, 2025 5:00 PM | 39 | 0d | 2115 | 2117 | 1 | Finish No Earlier Than | Warning
3086 | DocuEdge - Milestone 27 - CARESV1-322 ADM - CM - Storage | June 16, 2025 8:00 AM | August 8, 2025 5:00 PM | 39 | 0d | 2116 | 2118SS-15d | 1 | Finish No Earlier Than | Warning
3087 | DocuEdge - Milestone 27 - CARESV1-323 ADM - CM - Search | July 21, 2025 8:00 AM | August 7, 2025 5:00 PM | 14 | 0d | 2117SS-15d |  | 1 | Finish No Earlier Than | Warning
3089 | DocuEdge - Milestone 28 - CARESV1-313 ADM - CM - File Management and Metadata | September 9, 2024 8:00 AM | November 1, 2024 5:00 PM | 40 | 0d | 2112SS | 2121,2129SS-145d | 1 | Finish No Earlier Than | Warning
3090 | DocuEdge - Milestone 28 - CARESV1-315 ADM - CM - Redaction | November 4, 2024 8:00 AM | December 25, 2024 5:00 PM | 34 | 0d | 2120 | 2122 | 1 | Finish No Earlier Than | Warning
3091 | DocuEdge - Milestone 28 - CARESV1-317 ADM - CM - Versioning | December 26, 2024 8:00 AM | February 17, 2025 5:00 PM | 35 | 0d | 2121 | 2123 | 1 | Finish No Earlier Than | Warning
3092 | DocuEdge - Milestone 28 - CARESV1-319 ADM - CM - Retrieval | February 18, 2025 8:00 AM | April 11, 2025 5:00 PM | 38 | 0d | 2122 | 2124 | 1 | Finish No Earlier Than | Warning
3093 | DocuEdge - Milestone 28 - CARESV1-320 ADM - CM - Upload | April 14, 2025 8:00 AM | June 6, 2025 5:00 PM | 39 | 0d | 2123 | 2125 | 1 | Finish No Earlier Than | Warning
3094 | DocuEdge - Milestone 28 - CARESV1-322 ADM - CM - Storage | June 9, 2025 8:00 AM | July 31, 2025 5:00 PM | 38 | 0d | 2124 | 2126SS-18d | 1 | Finish No Earlier Than | Warning
3095 | DocuEdge - Milestone 28 - CARESV1-323 ADM - CM - Search | July 8, 2025 8:00 AM | July 11, 2025 5:00 PM | 4 | 0d | 2125SS-18d |  | 1 | Finish No Earlier Than | Warning
3122 | Document Ingestion - DC Baseline | January 30, 2024 8:00 AM | May 22, 2024 5:00 PM | 80 | 0d | 2120SS-145d | 2130 | 1 | Finish No Earlier Than | Warning
3127 | Document Linking - DC Dev | September 10, 2024 8:00 AM | October 21, 2024 5:00 PM | 30 | 0d | 2132 | 2135 | 1 | Finish No Earlier Than | Warning
3128 | Document Linking - DC QA | October 22, 2024 8:00 AM | November 12, 2024 5:00 PM | 15 | 0d | 2134 | 2136 | 1 | Finish No Earlier Than | Warning
3129 | Document Linking - DC VAL | November 13, 2024 8:00 AM | December 5, 2024 5:00 PM | 15 | 0d | 2135 |  | 1 | Finish No Earlier Than | Warning
13046 | Taxonomy Design Update | December 19, 2024 8:00 AM | January 10, 2025 5:00 PM | 15 | 0d |  | 2139 | 1 | Start No Earlier Than | Warning
3133 | Non-Structured Data Conversion - File extracts from CWS-CMS Host to CDI | February 1, 2023 8:00 AM | February 28, 2023 5:00 PM | 20 | 0d |  | 2147 | 1 | Start No Earlier Than | Warning
3135 | Non-Structured Data Conversion - Extract CWS-CMS host documents from PullDOCS vdi to CDI (Phase 1 and 2) | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 64 | 0d | 2145 | 2148,2154SS | 1 | Finish No Earlier Than | Warning
3136 | Non-Structured Data Conversion - Build Metadata generation | April 3, 2023 8:00 AM | May 31, 2023 5:00 PM | 42 | 0d | 2147 | 2149 | 1 | Finish No Earlier Than | Warning
3140 | Non-Structured Data Conversion - Generate document ingestion metadata | June 1, 2026 8:00 AM | June 26, 2026 5:00 PM | 20 | 57d | 2151 | 5628 | 0 | Finish No Earlier Than | Warning
3142 | Generating document linking metadata Foundation framework - Build | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 64 | 0d | 2147SS | 2156 | 1 | Finish No Earlier Than | Warning
3144 | Documents and metadata copy from Baseline DocuEdge to DC env - Analysis | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 | 0d | 2154 | 2157 | 1 | Finish No Earlier Than | Warning
3145 | Documents and metadata copy from Baseline DocuEdge to DC env - Design | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 | 0d | 2156 | 2158 | 1 | Finish No Earlier Than | Warning
3146 | Documents and metadata copy from Baseline DocuEdge to DC env - Build | April 2, 2024 8:00 AM | April 12, 2024 5:00 PM | 9 | 0d | 2157 | 2159 | 1 | Finish No Earlier Than | Warning
3147 | Documents and metadata copy from Baseline DocuEdge to DC env - Execution in DCDEV | April 16, 2024 8:00 AM | May 17, 2024 5:00 PM | 24 | 0d | 2158 | 2160 | 1 | Finish No Earlier Than | Warning
3148 | Documents and metadata copy from Baseline DocuEdge to DC env - Execution in DCVAL | May 20, 2024 8:00 AM | June 21, 2024 5:00 PM | 24 | 0d | 2159 | 2162 | 1 | Finish No Earlier Than | Warning
3150 | Generating document linking metadata - Build doc linking logic DC Cycle1,2,3 service areas | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 10 | 0d | 2162 | 2164 | 1 | Finish No Earlier Than | Warning
3151 | Generating document linking metadata - Build doc linking logic DC Cycle4 service areas | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 10 | 0d | 2163 | 2165 | 1 | Start No Earlier Than | Warning
3152 | Generating document linking metadata - Build doc linking logic DC Cycle5 Service areas | March 24, 2025 8:00 AM | April 4, 2025 5:00 PM | 9 | 0d | 2164 | 2166 | 1 | Start No Earlier Than | Warning
3153 | Generating document linking metadata - Build doc linking logic DC Cycle6 Service areas | September 22, 2025 8:00 AM | October 2, 2025 5:00 PM | 9 | 0d | 2165 |  | 1 | Start No Earlier Than | Warning
3155 | Generating document linking metadata - Build Document Ingestion and Linking Reports | June 26, 2025 8:00 AM | July 2, 2025 5:00 PM | 5 | 0d | 2142 | 2198FS-24d | 1 | Start No Earlier Than | Warning
3157 | Load person search master data entity to Solr - Build | March 1, 2023 8:00 AM | April 28, 2023 5:00 PM | 43 | 0d | 2162 | 2170 | 1 | Finish No Earlier Than | Warning
3158 | Load person search master data entity to Solr - Execution - DC Cycle 1 | June 1, 2023 8:00 AM | June 30, 2023 5:00 PM | 22 | 0d | 2169 | 2171 | 1 | Finish No Earlier Than | Warning
3159 | Load person search master data entity to Solr - Execution - DC Cycle 2 | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 15 | 0d | 2170 | 2173 | 1 | Finish No Earlier Than | Warning
3161 | Provider Search Solr Master data entities foundation - Analysis | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 | 0d | 2171 | 2174 | 1 | Finish No Earlier Than | Warning
3162 | Provider Search Solr Master data entities foundation - Mapping | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 | 0d | 2173 | 2175 | 1 | Finish No Earlier Than | Warning
3163 | Provider Search Solr Master data entities foundation - Build | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 5 | 0d | 2174 | 2176 | 1 | Finish No Earlier Than | Warning
3164 | Provider Search Solr Master data entities foundation - Execution in DCDEV | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 10 | 0d | 2175 | 2178 | 1 | Finish No Earlier Than | Warning
3166 | Micro Conversion foundation framework - Build | May 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 110 | 0d | 2176 | 2179,2214SS+1d | 1 | Finish No Earlier Than | Warning
3167 | Micro Conversion foundation framework - Unit Test | July 10, 2023 8:00 AM | October 27, 2023 5:00 PM | 80 | 0d | 2178 | 2180,2210SS | 1 | Finish No Earlier Than | Warning
3168 | Micro Conversion foundation framework - Execution - DC Cycle2 | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 15 | 0d | 2179 | 2182 | 1 | Finish No Earlier Than | Warning
3170 | Micro Conversion scripts - Build scripts for DC Cycle1,2 Scope objects | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 19 | 0d | 2180 | 2333,2183FS+85d | 1 | Finish No Earlier Than | Warning
3171 | Micro Conversion scripts - Build scripts for DC Cycle3 Scope objects | May 6, 2024 8:00 AM | May 24, 2024 5:00 PM | 15 | 0d | 2182FS+85d | 2343,2184FS+85d | 1 | Finish No Earlier Than | Warning
3172 | Micro Conversion scripts - Build scripts for DC Cycle4 Scope objects | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 15 | 0d | 2183FS+85d | 2353,2185FS+85d | 1 | Finish No Earlier Than | Warning
3173 | Micro Conversion scripts - Build scripts for DC Cycle5 Scope objects | April 7, 2025 8:00 AM | April 25, 2025 5:00 PM | 15 | 0d | 2184FS+85d | 2363,2186FS+85d,2192SS+10d | 1 | Finish No Earlier Than | Warning
3174 | Micro Conversion scripts - Build scripts for DC Cycle6 Scope objects | September 29, 2025 8:00 AM | October 17, 2025 5:00 PM | 15 | 444d | 2185FS+85d | 2373FS-5d,2193SS+5d | 0.67 | Finish No Earlier Than | Warning
3177 | Converted Data Load to Snowflake - Build foundation framework | December 4, 2023 8:00 AM | January 26, 2024 5:00 PM | 37 | 0d | 3348SS | 2189,2201FS-18d | 1 | Finish No Earlier Than | Warning
3178 | Converted Data Load to Snowflake - Build views for DC Cycle1,2 scope objects | January 29, 2024 8:00 AM | February 2, 2024 5:00 PM | 5 | 0d | 2188 | 2333,2190FS+70d,2195FS+60d | 1 | Finish No Earlier Than | Warning
3179 | Converted Data Load to Snowflake - Build views for DC Cycle3 scope objects | May 20, 2024 8:00 AM | June 3, 2024 5:00 PM | 10 | 0d | 2189FS+70d | 2343,2191FS+90d | 1 | Start No Earlier Than | Warning
3180 | Converted Data Load to Snowflake - Build views for DC Cycle4 scope objects | October 21, 2024 8:00 AM | November 1, 2024 5:00 PM | 10 | 0d | 2190FS+90d | 2353 | 1 | Start No Earlier Than | Warning
3181 | Converted Data Load to Snowflake - Build views for DC Cycle5 scope objects | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 10 | 0d | 2185SS+10d | 2363 | 1 | Start No Earlier Than | Warning
3182 | Converted Data Load to Snowflake - Build views for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 444d | 2186SS+5d | 2373FS-5d,2199SS | 0.5 | Finish No Earlier Than | Warning
5570 | Trigger analysis for data conversion - Analysis for DC Cycle1,2 scope objects | May 6, 2024 8:00 AM | June 28, 2024 5:00 PM | 39 | 0d | 2189FS+60d | 2333,2196 | 1 | Start No Later Than | Warning
5571 | Trigger analysis for data conversion - Analysis for DC Cycle3 scope objects | July 1, 2024 8:00 AM | August 23, 2024 5:00 PM | 39 | 0d | 2195 | 2343FS-44d,2197 | 1 | Start No Earlier Than | Warning
5572 | Trigger analysis for data conversion - Analysis for DC Cycle4 scope objects | August 26, 2024 8:00 AM | October 17, 2024 5:00 PM | 39 | 0d | 2196 | 2353 | 1 | Start No Earlier Than | Warning
5573 | Trigger analysis for data conversion - Analysis for DC Cycle5 scope objects | January 6, 2025 8:00 AM | July 10, 2025 9:07 AM | 42 | 0d | 2167FS-24d | 2363 | 1 | Start No Earlier Than | Warning
5574 | Trigger analysis for data conversion - Analysis for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 444d | 2193SS | 2373FS-5d | 0.5 | Start No Earlier Than | Warning
5577 | Legacy User loads - Legacy user Initial Load to DCDEV | April 1, 2024 8:00 AM | May 10, 2024 5:00 PM | 29 | 0d | 2201FS-1d | 2203SS | 1 | Start No Earlier Than | Warning
5578 | Legacy User loads - Address Legacy User data quality | April 1, 2024 8:00 AM | December 26, 2024 5:00 PM | 187 | 0d | 2202SS | 2204FS+135d | 1 | Finish No Earlier Than | Warning
5579 | Legacy User loads - Build revision with the Legacy vs CARES Persona finalized mapping | July 14, 2025 8:00 AM | September 5, 2025 5:00 PM | 39 | 0d | 2203FS+135d | 2205SS-150d,2212SS+8d | 1 | Start No Earlier Than | Warning
5580 | Legacy User loads - Link Legacy converted data created by, updated by to the legacy users | May 20, 2024 8:00 AM | July 19, 2024 5:00 PM | 43 | 0d | 2204SS-150d |  | 1 | Start No Earlier Than | Warning
5583 | Legacy data Owner Id mapping - Mapping for each category | April 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 107 | 0d | 2207 |  | 1 | Finish No Earlier Than | Warning
3185 | Infected, Unsupported file extensions Report - Iteration 1 | July 10, 2023 8:00 AM | October 6, 2023 5:00 PM | 65 | 0d | 2179SS | 2211 | 1 | Finish No Earlier Than | Warning
3186 | Infected, Unsupported file extensions Report - Iteration 2 | January 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 60 | 0d | 2210 |  | 1 | Start No Earlier Than | Warning
3187 | Micro Conversion Delta Merge to Stage daily schedule job | January 15, 2024 8:00 AM | February 2, 2024 5:00 PM | 15 | 0d | 2204SS+8d | 2373FS-5d | 1 | Start No Earlier Than | Warning
3189 | Address Standardization using Smarty foundation framework - Build | May 2, 2023 8:00 AM | June 26, 2023 5:00 PM | 40 | 0d | 2178SS+1d | 2373FS-5d | 1 | Start No Earlier Than | Warning
3192 | Data Conversion - Milestone 01 - Pre-Analysis | June 20, 2022 8:00 AM | August 15, 2022 5:00 PM | 40 | 0d | 16 | 2223 | 1 | Start No Earlier Than | Warning
3200 | Data Conversion - Milestone 03 - Pre-Analysis | September 12, 2022 8:00 AM | January 30, 2023 5:00 PM | 95 | 0d | 72 | 2231FS-20d | 1 | Start No Earlier Than | Warning
3204 | Data Conversion - Milestone 04 - Pre-Analysis | August 15, 2022 8:00 AM | December 8, 2022 5:00 PM | 80 | 0d | 118 | 2235FS-20d | 1 | Start No Earlier Than | Warning
3212 | Data Conversion - Milestone 06 - Pre-Analysis | December 5, 2022 8:00 AM | May 26, 2023 5:00 PM | 120 | 0d | 224 | 2243FS-40d | 1 | Start No Earlier Than | Warning
3216 | Data Conversion - Milestone 6.1 - Pre-Analysis | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 | 0d | 593SS | 2247 | 1 | Finish No Earlier Than | Warning
3217 | Data Conversion - Milestone 6.1 - Analysis and Mapping | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 | 0d | 599SS,597SS,598SS,2246 | 2248 | 1 | Finish No Earlier Than | Warning
3218 | Data Conversion - Milestone 6.1 - Build | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 188 | 103d | 702SS,2247 | 2379 | 0.72 | Finish No Earlier Than | Warning
3222 | Data Conversion - Milestone 07 - Build | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 188 | 103d | 702SS,2251 | 2379 | 0.72 | Finish No Earlier Than | Warning
3224 | Data Conversion - Milestone 08 - Pre-Analysis | April 7, 2023 8:00 AM | July 14, 2023 5:00 PM | 69 | 0d | 267SS | 2255SS+40d,2327SS+4d,2399SS+15d | 1 | Finish No Earlier Than | Warning
3225 | Data Conversion - Milestone 08 - Analysis and Mapping | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 | 0d | 2254SS+40d | 2256SS+20d | 1 | Finish No Earlier Than | Warning
3226 | Data Conversion - Milestone 08 - Build and SIT | July 19, 2023 8:00 AM | August 14, 2023 5:00 PM | 19 | 0d | 2255SS+20d | 2216FS+103d | 1 | Finish No Earlier Than | Warning
3228 | Data Conversion - Milestone 09 - Pre-Analysis | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 | 0d | 593SS | 2259 | 1 | Finish No Earlier Than | Warning
3229 | Data Conversion - Milestone 09 - Analysis and Mapping | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 | 0d | 599SS,597SS,598SS,2258 | 2260 | 1 | Finish No Earlier Than | Warning
3230 | Data Conversion - Milestone 09 - Build and SIT | August 14, 2023 8:00 AM | May 15, 2024 5:00 PM | 189 | 0d | 339SS,2259 | 2344 | 1 | Finish No Earlier Than | Warning
3234 | Data Conversion - Milestone 10 - Build and SIT | August 11, 2025 8:00 AM | December 29, 2025 1:58 PM | 52 | 103.38d | 380SS,2263 | 2379 | 0.46 | Start No Earlier Than | Warning
3242 | Data Conversion - Milestone 11 - Build and SIT | June 2, 2025 8:00 AM | December 29, 2025 1:58 PM | 101 | 103.38d | 715SS,2271 | 2379 | 0.64 | Finish No Earlier Than | Warning
3246 | Data Conversion - Milestone 13 - Build and SIT | June 2, 2025 8:00 AM | December 29, 2025 1:58 PM | 101 | 103.38d | 709SS,2275 | 2379 | 0.64 | Finish No Earlier Than | Warning
3258 | Data Conversion - Milestone 16 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 173 | 103.25d | 867SS,2287 | 2379 | 0.72 | Finish No Earlier Than | Warning
3260 | Data Conversion - Milestone 17 - Pre-Analysis | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 97 | 0d | 798SS | 2291FS-29d | 1 | Finish No Earlier Than | Warning
3261 | Data Conversion - Milestone 17 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 | 0d | 804SS,803SS,802SS,2290FS-29d | 2292FS-29d | 1 | Start No Earlier Than | Warning
3262 | Data Conversion - Milestone 17 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 173 | 103.25d | 871SS,2291FS-29d | 2379 | 0.72 | Finish No Earlier Than | Warning
3264 | Data Conversion - Milestone 18 - Pre-Analysis | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 97 | 0d | 798SS | 2295FS-30d | 1 | Finish No Earlier Than | Warning
3266 | Data Conversion - Milestone 18 - Build and SIT | April 2, 2025 8:00 AM | January 22, 2026 3:00 PM | 189 | 87.25d | 876SS,2295FS-29d | 2379 | 0.66 | Finish No Earlier Than | Warning
3276 | Data Conversion - Milestone 21 - Pre-Analysis | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 | 0d | 1194SS | 2307 | 1 | Finish No Earlier Than | Warning
3277 | Data Conversion - Milestone 21 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 | 0d | 1200SS,1199SS,1198SS,2306 | 2308 | 1 | Finish No Earlier Than | Warning
3278 | Data Conversion - Milestone 21 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 173 | 103.25d | 867SS,2307 | 2379 | 0.72 | Finish No Earlier Than | Warning
3313 | Conversion Cycle 1 - ETL | April 3, 2023 8:00 AM | April 28, 2023 5:00 PM | 20 | 0d | 2254SS+4d | 2328SS | 1 | Start No Earlier Than | Warning
3319 | Conversion Cycle 2 - ETL | September 11, 2023 8:00 AM | October 6, 2023 5:00 PM | 20 | 0d | 2331FS+42d,2182,2189,2195 | 2334 | 1 | Start No Earlier Than | Warning
3325 | Conversion Cycle 3 - ETL | April 22, 2024 8:00 AM | June 3, 2024 5:00 PM | 30 | 0d | 2337 | 2340 | 1 | Finish No Earlier Than | Warning
5607 | Conversion Cycle 4 - ETL | September 23, 2024 8:00 AM | November 1, 2024 5:00 PM | 30 | 0d | 2347 | 2350 | 1 | Start No Earlier Than | Warning
5621 | Conversion Cycle 5 - ETL | March 24, 2025 8:00 AM | May 2, 2025 5:00 PM | 29 | 0d | 2357 | 2360 | 1 | Start No Earlier Than | Warning
5622 | Conversion Cycle 5 - Link Documents | May 5, 2025 8:00 AM | May 23, 2025 5:00 PM | 15 | 0d | 2359 | 2361FS-50d | 1 | Start No Earlier Than | Warning
5623 | Conversion Cycle 5 - Solr Load | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 10 | 0d | 2360FS-50d | 2362FS-10d | 1 | Start No Earlier Than | Warning
5624 | Conversion Cycle 5 - Snowflake Load | April 21, 2025 8:00 AM | May 9, 2025 5:00 PM | 15 | 0d | 2361FS-10d | 2363 | 1 | Start No Earlier Than | Warning
5625 | Conversion Cycle 5 - Micro Conversion Execution | July 10, 2025 9:07 AM | September 12, 2025 9:07 AM | 45 | 0d | 2185,2192,2198,2362 | 2364FS-55d | 1 | Start No Earlier Than | Warning
5626 | Conversion Cycle 5 - SIT | June 25, 2025 9:07 AM | July 9, 2025 9:07 AM | 9 | 0d | 2363FS-55d | 2365 | 1 | Start No Earlier Than | Warning
5627 | Conversion Cycle 5 - QA | July 9, 2025 9:07 AM | July 22, 2025 9:07 AM | 9 | 0d | 2364 | 2366 | 1 | Start No Earlier Than | Warning
5628 | Conversion Cycle 5 - County Validation | July 22, 2025 9:07 AM | August 5, 2025 9:07 AM | 10 | 0d | 2365 | 2367 | 1 | Start No Earlier Than | Warning
5629 | Conversion Cycle 5 - Review & Closure | August 5, 2025 9:07 AM | August 19, 2025 9:07 AM | 10 | 0d | 2366 | 2369 | 1 | Start No Earlier Than | Warning
5631 | Conversion Cycle 6 - ETL | September 8, 2025 8:00 AM | October 17, 2025 5:00 PM | 30 | 439d | 2367 | 2370 | 0.83 | Start No Earlier Than | Warning
5632 | Conversion Cycle 6 - Link Documents | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 15 | 439d | 2369 | 2371FS-25d | 0 | Start No Earlier Than | Warning
5633 | Conversion Cycle 6 - Solr Load | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 439d | 2370FS-25d | 2372FS-10d | 0 | Start No Earlier Than | Warning
5634 | Conversion Cycle 6 - Snowflake Load | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 15 | 439d | 2371FS-10d | 2373FS-5d | 0 | Start No Earlier Than | Warning
5635 | Conversion Cycle 6 - Micro Conversion Execution | October 20, 2025 8:00 AM | December 23, 2025 5:00 PM | 45 | 439d | 2186FS-5d,2193FS-5d,2199FS-5d,2212FS-5d,2214FS-5d,2372FS-5d | 2374FS-55d | 0 | Start No Earlier Than | Warning
5636 | Conversion Cycle 6 - SIT | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 20 | 439d | 2373FS-55d | 2375 | 0 | Start No Earlier Than | Warning
5637 | Conversion Cycle 6 - QA | November 3, 2025 8:00 AM | December 2, 2025 5:00 PM | 20 | 439d | 2374 | 2376FS-2d | 0 | Start No Earlier Than | Warning
5638 | Conversion Cycle 6 - County Validation | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 439d | 2375FS-2d | 2377 | 0 | Start No Earlier Than | Warning
5639 | Conversion Cycle 6 - Review & Closure | December 29, 2025 8:00 AM | January 9, 2026 5:00 PM | 9 | 439d | 2376 |  | 0 | Start No Earlier Than | Warning
5641 | Conversion Full Mock Cycle 1 - ETL & SIT | May 8, 2026 3:24 PM | June 8, 2026 3:24 PM | 20 | 13.2d | 2264,2268,2272,2276,2280,2284,2288,2292,2296,2300,2304,2308,2316,2320,2324,2248,2252 | 2380 | 0 | Start No Earlier Than | Warning
5642 | Conversion Full Mock Cycle 1 - QA | June 8, 2026 3:24 PM | June 15, 2026 3:24 PM | 5 | 13.2d | 2379 | 2381 | 0 | Start No Earlier Than | Warning
5643 | Conversion Full Mock Cycle 1 - County Testing | June 15, 2026 3:24 PM | June 22, 2026 3:24 PM | 5 | 13.2d | 2380 | 2382 | 0 | Start No Earlier Than | Warning
5644 | Conversion Full Mock Cycle 1 - Review & Closure | June 22, 2026 3:24 PM | June 29, 2026 3:24 PM | 5 | 13.2d | 2381 | 2384 | 0 | Start No Earlier Than | Warning
5646 | Conversion Full Mock Cycle 2 - ETL & SIT | June 29, 2026 3:24 PM | July 28, 2026 3:24 PM | 20 | 13.2d | 2382 | 2385 | 0 | Start No Earlier Than | Warning
5647 | Conversion Full Mock Cycle 2 - QA | July 28, 2026 3:24 PM | August 4, 2026 3:24 PM | 5 | 13.2d | 2384 | 2386 | 0 | Start No Earlier Than | Warning
5648 | Conversion Full Mock Cycle 2 - County Testing | August 4, 2026 3:24 PM | August 11, 2026 3:24 PM | 5 | 13.2d | 2385 | 2387 | 0 | Start No Earlier Than | Warning
5649 | Conversion Full Mock Cycle 2 - Review & Closure | August 11, 2026 3:24 PM | August 18, 2026 3:24 PM | 5 | 13.2d | 2386 | 2389 | 0 | Start No Earlier Than | Warning
5651 | Conversion Full Mock Cycle 3 - ETL & SIT | August 18, 2026 3:24 PM | September 16, 2026 3:24 PM | 20 | 13.2d | 2219,2387 | 2390 | 0 | Start No Earlier Than | Warning
5652 | Conversion Full Mock Cycle 3 - QA | September 16, 2026 3:24 PM | September 23, 2026 3:24 PM | 5 | 13.2d | 2389 | 2391 | 0 | Start No Earlier Than | Warning
5653 | Conversion Full Mock Cycle 3 - County Testing | September 23, 2026 3:24 PM | September 30, 2026 3:24 PM | 5 | 13.2d | 2390 | 2392 | 0 | Start No Earlier Than | Warning
5654 | Conversion Full Mock Cycle 3 - Review & Closure | September 30, 2026 3:24 PM | October 7, 2026 3:24 PM | 5 | 13.2d | 2391 | 5630,2394FS-1d | 0 | Start No Earlier Than | Warning
6974 | CWS/CMS - Research and Document Current Functionality | May 1, 2023 8:00 AM | October 30, 2024 5:00 PM | 380 | 0d | 2254SS+15d | 2400SS,2401SS,2402SS,2416SS | 1 | Must Start On | Warning
6977 | Future State Requirements - Requirement Elaboration | May 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 167 | 0d | 2399SS | 2404 | 1 | Start No Earlier Than | Warning
6979 | Design Extracts - Perform Initial Design | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 168 | 0d | 2400SS,2402 | 2411 | 1 | Must Start On | Warning
6980 | Design Extracts - Conduct Detailed Design of Extracts | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 379 | 0d | 2400SS | 2415 | 0.96 | Must Start On | Warning
6982 | Security Controls and Capacity Management - Perform Initial Design | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 168 | 0d | 2400SS | 2408,2411 | 1 | Must Start On | Warning
6986 | Perform Validation - POC 1 | June 3, 2024 8:00 AM | September 27, 2024 5:00 PM | 84 | 0d | 2407,2404 | 2412FS+1d | 1 | Must Start On | Warning
6929 | Build Core Extract Capabilities | June 3, 2024 8:00 AM | November 28, 2025 5:00 PM | 376 | 0d | 2408SS | 2415 | 0.91 | Must Start On | Warning
6990 | Forms Training - Organize AEM Training Pilot Cohort | May 2, 2024 8:00 AM | August 8, 2025 5:00 PM | 320 | 0d | 557FF | 2422FS-29d | 0.48 | Must Start On | Warning
6935 | Training Cohort - Cycle 1 | May 1, 2023 8:00 AM | June 7, 2024 5:00 PM | 278 | 0d | 2416SS | 2436,2443FS+144d,2441SS,2983 | 1 | Must Start On | Warning
3371 | DocGen Research and Proof of Concept - County Specific - Forms | July 13, 2023 8:00 AM | June 26, 2024 5:00 PM | 250 | 0d |  | 2450SS,2461SS-18d | 1 | Must Start On | Warning
3422 | DocGen - Milestone 6.1 - Form Identification | January 2, 2024 8:00 AM | January 23, 2024 5:00 PM | 15 | 0d | 2458 | 2500,2617SS+1d | 1 | Start No Earlier Than | Warning
3443 | DocGen - Milestone 9 - Form Identification | June 20, 2023 8:00 AM | July 11, 2023 5:00 PM | 15 | 0d | 318SS | 2521 | 1 | Start No Earlier Than | Warning
3444 | DocGen - Milestone 9 - Analysis and Template Design | July 12, 2023 8:00 AM | July 25, 2023 5:00 PM | 10 | 0d | 593SS,2520 | 2522 | 1 | Start No Earlier Than | Warning
3445 | DocGen - Milestone 9 - Template Design Review and Approval | July 26, 2023 8:00 AM | August 22, 2023 5:00 PM | 20 | 0d | 593SS,2521 | 2523 | 1 | Start No Earlier Than | Warning
3446 | DocGen - Milestone 9 - AEM Design, Review & Approval | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 | 0d | 599SS,597SS,598SS,2522 | 2524 | 1 | Start No Earlier Than | Warning
3447 | DocGen - Milestone 9 - AEM Integration (Build/SIT) | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 | 0d | 343SS,2523 | 2525 | 1 | Start No Earlier Than | Warning
3448 | DocGen - Milestone 9 - QA/Joint Review | March 22, 2024 8:00 AM | April 22, 2024 5:00 PM | 21 | 0d | 351SS,2524 |  | 1 | Start No Earlier Than | Warning
3492 | DocGen - Milestone 16 - Form Identification | March 8, 2024 8:00 AM | January 3, 2025 5:00 PM | 208 | 0d | 816SS |  | 1 | Finish No Earlier Than | Warning
3506 | DocGen - Milestone 18 - Form Identification | May 22, 2023 8:00 AM | January 3, 2025 5:00 PM | 407 | 0d | 834SS |  | 1 | Finish No Earlier Than | Warning
3534 | DocGen - Milestone 23 - Form Identification | April 26, 2024 8:00 AM | April 1, 2025 5:00 PM | 233 | 0d | 1119SS |  | 1 | Finish No Earlier Than | Warning
3537 | DocGen - Milestone 23 - AEM Design, Review & Approval | May 12, 2025 8:00 AM | July 11, 2025 5:00 PM | 43 | 0d | 1098SS,1096SS,1097SS | 2595FS+20d | 1 | Finish No Earlier Than | Warning
3538 | DocGen - Milestone 23 - AEM Integration (Build/SIT) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 | 3d | 2594FS+20d | 2596FS-36d | 0.57 | Finish No Earlier Than | Warning
3548 | DocGen - Milestone 26 - Form Identification | March 29, 2024 8:00 AM | January 3, 2025 5:00 PM | 193 | 0d | 952SS |  | 1 | Finish No Earlier Than | Warning
7526 | Design, Deploy, and Manage Form Templates | January 6, 2025 8:00 AM | January 31, 2025 5:00 PM | 19 | 0d | 2617 | 2620 | 1 | Finish No Earlier Than | Warning
7527 | CARES Doc Gen Features, Data model | February 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 20 | 0d | 2619 | 2621 | 1 | Start No Earlier Than | Warning
7528 | Customizing State Templates to County-Specific Needs | March 4, 2025 8:00 AM | April 1, 2025 5:00 PM | 20 | 0d | 2620 | 2623 | 1 | Start No Earlier Than | Warning
7529 | KX Sessions - Session 1 | May 5, 2025 8:00 AM | June 23, 2025 5:00 PM | 35 | 0d | 2621 | 2624 | 1 | Start No Earlier Than | Warning
7530 | KX Sessions - Session 2 | June 24, 2025 8:00 AM | August 12, 2025 5:00 PM | 35 | 0d | 2623 | 2625 | 1 | Start No Earlier Than | Warning
7531 | KX Sessions - Session 3 | August 13, 2025 8:00 AM | September 29, 2025 5:00 PM | 33 | 0d | 2624 |  | 1 | Start No Earlier Than | Warning
3620 | Setup ADA Validation Infra/ Tools (CARESV1-5420) | April 4, 2022 8:00 AM | May 13, 2022 5:00 PM | 30 | 0d |  | 2629FS+420d | 1 | Start No Earlier Than | Warning
3622 | M1: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2627FS+420d | 2630SS,2631SS,2632SS,2633SS,2634SS,2638SS,2645SS,2649SS,2651SS | 1 | Finish No Earlier Than | Warning
3623 | M2: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3624 | M3: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3625 | M4: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3626 | M5: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3627 | M6: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS | 2635FS-40d,2636FS-40d,2637FS-40d,2639FS-40d,2640FS-40d,2641FS-40d,2642FS-40d,2643FS-40d,2644FS-40d,2646FS-40d,2647FS-40d,2648FS-40d,2650FS-40d,2652FS-40d,2653FS-40d,2654FS-40d,2655FS-40d,2656FS-40d,2657FS-40d,2658FS-40d,2659FS-40d,2660FS-40d,2661FS-40d... | 1 | Finish No Earlier Than | Warning
3628 | M6.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3629 | M7: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3630 | M7.1 ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3631 | M8: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3632 | M9: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3633 | M10: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3634 | M10.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3635 | M11: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3636 | M13: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3637 | M14: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3638 | M15: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3640 | M16: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3641 | M17: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3642 | M18: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3643 | M19: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3644 | M21: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3645 | M20: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | Finish No Earlier Than | Warning
3646 | M20.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3647 | M23: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3648 | M23.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3649 | M23.2: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3650 | M24: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3651 | M26: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3652 | M26.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3653 | M27: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3654 | M28: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3655 | M29: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
5536 | M30: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
5537 | M31: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
5538 | M32: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | Finish No Earlier Than | Warning
3658 | M1: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d |  | 2668SS,2676SS,2704FS+4d,2744SS,2745SS,2746SS,2747SS,2748SS,2752SS,2780FS+4d,2743SS | 1 | Start No Earlier Than | Warning
3659 | M2: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS | 2674SS+8d,2678SS+4d,2685SS+4d,2686SS+4d,2750SS+8d,2754SS+4d,2760SS+4d,2761SS+4d,2762SS+4d,2669SS | 1 | Finish No Earlier Than | Warning
3660 | M3: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2668SS | 2670SS | 1 | Finish No Earlier Than | Warning
3661 | M4: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2669SS | 2671SS | 1 | Finish No Earlier Than | Warning
3662 | M5: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2670SS | 2672SS | 1 | Finish No Earlier Than | Warning
3663 | M6: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2671SS | 2673,2749 | 1 | Finish No Earlier Than | Warning
3664 | M6.1: Create Automation scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 425d | 2672 | 2688SS-10d,2710FS+6d,2711FS+6d,2712FS+6d,2714FS+6d,2715FS+6d,2716FS+6d,2717FS+6d,2718FS+6d,2719FS+6d,2721FS+6d,2722FS+6d,2723FS+6d,2725FS+6d,2727FS+6d,2728FS+6d,2729FS+6d,2730FS+6d,2731FS+6d,2732FS+6d,2733FS+6d,2734FS+6d,2735FS+6d,2736FS+6d,2737FS+6d,2... | 0 | Finish No Earlier Than | Warning
3665 | M7: Create Automation scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 59 | 452d | 2668SS+8d | 2675SS-92d,2751SS-92d | 0.1 | Finish No Earlier Than | Warning
3666 | M7.1 Create Automation scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d | 2677SS-20d,2679SS-20d,2682SS-20d,2753SS-20d,2755SS-20d,2758SS-20d | 0.83 | Finish No Earlier Than | Warning
3667 | M8: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS | 2683SS,2687SS,2689SS,2759SS,2763SS,2765SS | 1 | Finish No Earlier Than | Warning
3668 | M9: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
3669 | M10: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d | 2680SS-23d,2681SS-23d,2756SS-23d,2757SS-23d | 0.23 | Finish No Earlier Than | Warning
3670 | M10.1: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
3671 | M11: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | Finish No Earlier Than | Warning
3672 | M13: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | Finish No Earlier Than | Warning
3673 | M14: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
3674 | M15: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS | 2684FS+154d | 1 | Finish No Earlier Than | Warning
3677 | M17: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
3678 | M18: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
3679 | M19: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | Finish No Earlier Than | Warning
3680 | M21: Create Automation scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 49 | 450d | 2673SS-10d |  | 0 | Finish No Earlier Than | Warning
3681 | M20: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | Finish No Earlier Than | Warning
3682 | M20.1: Create Automation scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 68 | 450d | 2684SS+3d | 2691SS-7d,2692SS-7d,2693SS-7d,2699SS-7d,2700SS-7d,2701SS-7d,2767SS-7d,2768SS-7d,2769SS-7d,2775SS-7d,2776SS-7d,2777SS-7d | 0.19 | Finish No Earlier Than | Warning
3683 | M23: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
3684 | M23.1: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
3685 | M23.2: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2694SS-33d,2695SS-33d,2696SS-33d,2697SS-33d,2698SS-33d,2770SS-33d,2771SS-33d,2772SS-33d,2773SS-33d,2774SS-33d | 0.27 | Finish No Earlier Than | Warning
3686 | M24: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
3687 | M26: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
3688 | M26.1: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
3689 | M27: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
3690 | M28: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
3691 | M29: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
3692 | M30: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
3693 | M31: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2702SS-1d,2778SS-1d | 0.27 | Finish No Earlier Than | Warning
3694 | M32: Create Automation scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | Finish No Earlier Than | Warning
3705 | M1: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2667FS+4d | 2705SS,2706SS,2707SS,2708SS,2709SS+5d | 1 | Finish No Earlier Than | Warning
3706 | M2: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS | 2713SS+5d,2789SS+5d | 1 | Start No Earlier Than | Warning
3707 | M3: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | Finish No Earlier Than | Warning
3708 | M4: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | Start No Earlier Than | Warning
3709 | M5: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | Finish No Earlier Than | Warning
3710 | M6: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2704SS+5d | 2720SS | 1 | Finish No Earlier Than | Warning
3711 | M6.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3712 | M7: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3713 | M7.1 Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3714 | M8: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2705SS+5d |  | 1 | Start No Earlier Than | Warning
3715 | M9: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3716 | M10: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3717 | M10.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3718 | M11: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3719 | M13: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3720 | M14: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3721 | M15: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2709SS | 2724SS,2726SS | 1 | Finish No Earlier Than | Warning
3723 | M16: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3724 | M17: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3725 | M18: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3726 | M19: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2720SS |  | 1 | Start No Earlier Than | Warning
3727 | M21: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3728 | M20: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2720SS |  | 1 | Finish No Earlier Than | Warning
3729 | M20.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3730 | M23: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3731 | M23.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3732 | M23.2: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3733 | M24: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3734 | M26: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3735 | M26.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3736 | M27: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3737 | M28: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3738 | M29: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3739 | M30: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3740 | M31: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3741 | M32: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
3778 | Performance Test Plan | September 1, 2022 8:00 AM | March 1, 2023 5:00 PM | 130 | 0d |  |  | 1 | Finish No Earlier Than | Warning
5480 | M1: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5481 | M2: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5482 | M3: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5483 | M4: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5484 | M5: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5485 | M6: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5655 | M6.1: Create Performance Testing scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 450d | 2672 |  | 0 | Finish No Earlier Than | Warning
5656 | M7: Create Performance Testing scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 59 | 452d | 2668SS+8d |  | 0.1 | Finish No Earlier Than | Warning
5486 | M7.1 Create Performance Testing scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d |  | 0.83 | Finish No Earlier Than | Warning
5487 | M8: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS |  | 1 | Finish No Earlier Than | Warning
5488 | M9: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
5489 | M10: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
5490 | M10.1: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
5491 | M11: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | Finish No Earlier Than | Warning
5492 | M13: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | Finish No Earlier Than | Warning
5493 | M14: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | Finish No Earlier Than | Warning
5494 | M15: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | Finish No Earlier Than | Warning
5496 | M16: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
5497 | M17: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
5498 | M18: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | Finish No Earlier Than | Warning
5499 | M19: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | Finish No Earlier Than | Warning
5500 | M21: Create Performance Testing scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 49 | 450d | 2673SS-10d |  | 0 | Finish No Earlier Than | Warning
5501 | M20: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | Finish No Earlier Than | Warning
5502 | M20.1: Create Performance Testing scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 68 | 450d | 2684SS+3d |  | 0.19 | Finish No Earlier Than | Warning
5503 | M23: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
5504 | M23.1: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
3791 | M23.2: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Start No Earlier Than | Warning
5509 | M24: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
5510 | M26: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
5511 | M26.1: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
5512 | M27: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
5513 | M28: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | Finish No Earlier Than | Warning
5514 | M29: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
5657 | M30: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
5658 | M31: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | Finish No Earlier Than | Warning
5515 | M32: Create Performance Testing scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | Finish No Earlier Than | Warning
5516 | M1: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2667FS+4d | 2781SS,2782SS,2783SS,2784SS,2785SS+5d | 1 | Finish No Earlier Than | Warning
5517 | M2: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2780SS |  | 1 | Finish No Earlier Than | Warning
5518 | M3: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2780SS |  | 1 | Finish No Earlier Than | Warning
5519 | M4: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2780SS |  | 1 | Finish No Earlier Than | Warning
5520 | M5: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2780SS |  | 1 | Finish No Earlier Than | Warning
5521 | M6: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2780SS+5d |  | 1 | Finish No Earlier Than | Warning
5522 | M6.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5523 | M7: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5524 | M7.1 Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5525 | M8: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2705SS+5d | 2796SS | 1 | Finish No Earlier Than | Warning
5526 | M9: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5527 | M10: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5528 | M10.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5529 | M11: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5530 | M13: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5531 | M14: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | Finish No Earlier Than | Warning
5532 | M15: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2789SS | 2800SS | 1 | Finish No Earlier Than | Warning
3806 | Quality Management (CARESV1-14448) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2817SS | 1855,2819SS | 0.91 | Finish No Earlier Than | Warning
3807 | Product Strategy (CARESV1-14458) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2818SS | 1855,2820SS | 0.91 | Finish No Earlier Than | Warning
3808 | SDLC Advisory (CARESV1-14459) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2819SS | 1855,2822SS | 0.91 | Finish No Earlier Than | Warning
3810 | Risk identification and tracking (CARESV1-14439) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2820SS | 1855,2823SS | 0.91 | Finish No Earlier Than | Warning
3811 | Risk analysis (CARESV1-14440) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2822SS | 1855,2824SS | 0.91 | Finish No Earlier Than | Warning
3812 | Risk mitigation (CARESV1-14441) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2823SS | 1855,2825SS | 0.91 | Finish No Earlier Than | Warning
3813 | Risk reporting (CARESV1-14442) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 | 104d | 2824SS | 1855,2827SS | 0.91 | Finish No Earlier Than | Warning
3815 | CCWIS Self-Assessments (Checklist) (CARESV1-14449) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2825SS | 1855,2828SS | 0.99 | Finish No Earlier Than | Warning
3816 | CARESV1-19070 CCWIS Self-Assessments (Checklist) - Implementation | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2827SS | 1855,2829SS | 0.99 | Finish No Earlier Than | Warning
3817 | California CCWIS Monitoring Review (CARESV1-14450) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2828SS | 1855,2830SS | 0.99 | Finish No Earlier Than | Warning
3818 | Governance (CARESV1-14456) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2829SS | 1855,2831SS | 0.99 | Finish No Earlier Than | Warning
3819 | Expectation Management (CARESV1-14446) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2830SS | 1855,2832SS | 0.99 | Finish No Earlier Than | Warning
3820 | Conflict Management (CARESV1-14447) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 | 203d | 2831SS | 1855,2976SS | 0.99 | Finish No Earlier Than | Warning
5660 | County IAM Integration - Alameda | December 5, 2022 8:00 AM | April 14, 2023 5:00 PM | 90 | 0d |  | 1855,2837FS-35d,2838SS-5d,2839SS-120d,2843SS-41d,2852SS | 1 | Finish No Earlier Than | Warning
3824 | Security - Privileged Access Management (PAM) | November 4, 2024 8:00 AM | April 18, 2025 5:00 PM | 112 | 0d | 2869FS-4d | 1855,2880SS-37d | 1 | Start No Earlier Than | Warning
5877 | SAST-4/22/2024 | April 8, 2024 8:00 AM | April 11, 2024 5:00 PM | 4 | 0d | 2876SS-37d | 2881 | 1 | Start No Earlier Than | Warning
5878 | SAST-4/22/2024 | April 22, 2024 8:00 AM | April 29, 2024 5:00 PM | 6 | 0d | 2880 | 2882 | 1 | Start No Earlier Than | Warning
5879 | SAST-4/22/2024 | May 6, 2024 8:00 AM | May 13, 2024 5:00 PM | 6 | 0d | 2881 | 2883 | 1 | Start No Earlier Than | Warning
5880 | SAST-4/22/2024 | May 20, 2024 8:00 AM | May 27, 2024 5:00 PM | 5 | 0d | 2882 | 2884 | 1 | Start No Earlier Than | Warning
5881 | SAST-4/22/2024 | June 3, 2024 8:00 AM | June 10, 2024 5:00 PM | 6 | 0d | 2883 | 2885 | 1 | Start No Earlier Than | Warning
5882 | SAST-4/22/2024 | June 17, 2024 8:00 AM | June 24, 2024 5:00 PM | 6 | 0d | 2884 | 2886 | 1 | Start No Earlier Than | Warning
5883 | SAST-4/22/2024 | July 1, 2024 8:00 AM | July 9, 2024 5:00 PM | 6 | 0d | 2885 | 2887 | 1 | Start No Earlier Than | Warning
5884 | SAST-4/22/2024 | July 15, 2024 8:00 AM | July 22, 2024 5:00 PM | 6 | 0d | 2886 | 2888 | 1 | Start No Earlier Than | Warning
5885 | SAST-4/22/2024 | July 29, 2024 8:00 AM | August 5, 2024 5:00 PM | 6 | 0d | 2887 | 2889 | 1 | Start No Earlier Than | Warning
5886 | SAST-4/22/2024 | August 12, 2024 8:00 AM | August 19, 2024 5:00 PM | 6 | 0d | 2888 | 2890 | 1 | Start No Earlier Than | Warning
5887 | SAST-4/22/2024 | August 26, 2024 8:00 AM | September 3, 2024 5:00 PM | 7 | 0d | 2889 | 2891 | 1 | Start No Earlier Than | Warning
5888 | SAST-4/22/2024 | September 9, 2024 8:00 AM | September 16, 2024 5:00 PM | 6 | 0d | 2890 | 2892 | 1 | Start No Earlier Than | Warning
5889 | SAST-4/22/2024 | September 23, 2024 8:00 AM | September 23, 2024 5:00 PM | 1 | 0d | 2891 | 2893 | 1 | Start No Earlier Than | Warning
5890 | SAST-4/22/2024 | October 7, 2024 8:00 AM | October 14, 2024 5:00 PM | 6 | 0d | 2892 | 2894 | 1 | Start No Earlier Than | Warning
5891 | DevSecOps Security - Conduct SAST-4/22/2024 | October 21, 2024 8:00 AM | October 25, 2024 5:00 PM | 5 | 0d | 2893 | 2896FS-85d | 1 | Finish No Earlier Than | Warning
3833 | Okta FedRAMP Transition | February 3, 2025 8:00 AM | September 22, 2025 5:00 PM | 161 | 0d | 2902 |  | 1 | Finish No Earlier Than | Warning
13698 | Okta Dev Migration | June 23, 2025 8:00 AM | August 4, 2025 5:00 PM | 30 | 0d |  | 2906SS,2907FS+3d | 1 | Start No Earlier Than | Warning
13178 | Develop Data templates for Drop 1 | November 15, 2024 8:00 AM | March 10, 2025 5:00 PM | 76 | 0d |  | 2916FS-1d | 1 | Start No Earlier Than | Warning
13195 | SFTP Server Set up | February 3, 2025 8:00 AM | March 18, 2025 5:00 PM | 31 | 0d |  | 2933FS-1d | 1 | Start No Earlier Than | Warning
13199 | Environment Set up - V1DCDEV2, Mulesoft | February 24, 2025 8:00 AM | April 11, 2025 5:00 PM | 34 | 0d |  |  | 1 | Start No Earlier Than | Warning
13200 | Workspace Seup and access provisioning | February 24, 2025 8:00 AM | April 25, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
13202 | ETL code development and unit testing for Drop 1 | June 2, 2025 8:00 AM | October 17, 2025 5:00 PM | 98 | 495d |  |  | 0.24 | Start No Earlier Than | Warning
13203 | ETL code development and unit testing for Drop 2 | June 2, 2025 8:00 AM | November 21, 2025 5:00 PM | 122 | 471d |  |  | 0.2 | Start No Earlier Than | Warning
13204 | ETL code development and unit testing for Drop 3 | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 | 445d |  |  | 0.16 | Start No Earlier Than | Warning
13205 | Receive Data template for Dry Run 1 | June 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 108 | 485d |  |  | 0 | Start No Earlier Than | Warning
13207 | Data Conversion & Issue remediation | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 434d |  | 2945 | 0 | Start No Earlier Than | Warning
13163 | Receive Data template for Dry Run 2 | December 22, 2025 8:00 AM | January 16, 2026 5:00 PM | 18 | 434d |  |  | 0 | Start No Earlier Than | Warning
13165 | Data Conversion & Issue remediation | January 20, 2026 8:00 AM | February 6, 2026 5:00 PM | 14 | 391d |  | 2951 | 0 | Start No Earlier Than | Warning
13171 | Data Conversion & Issue remediation | March 23, 2026 8:00 AM | April 17, 2026 5:00 PM | 19 | 343d |  | 2957,2960 | 0 | Start No Earlier Than | Warning
13153 | Data Conversion & Issue remediation | June 1, 2026 8:00 AM | June 19, 2026 5:00 PM | 15 | 295d |  | 2963 | 0 | Start No Earlier Than | Warning
13158 | Data load support | February 6, 2026 8:00 AM | July 31, 2026 5:00 PM | 122 | 295d |  | 2968SS+5d | 0 | Start No Earlier Than | Warning
13149 | Pre-Production activities and CutOver Support, Receive Data Templates for Prod load | August 3, 2026 8:00 AM | August 14, 2026 5:00 PM | 10 | 235d |  | 2971 | 0 | Start No Earlier Than | Warning
3975 | CDI: Centralized Business Rules (CARESV1-5231) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2832SS | 1848,2977SS | 1 | Start No Earlier Than | Warning
3976 | CDI: Event Framework (CARESV1-5238) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2976SS | 1848,2978SS | 1 | Start No Earlier Than | Warning
3977 | CDI: Query Composer and Graph Builder Controls (CARESV1-5197) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2977SS | 1848,2979SS | 1 | Start No Earlier Than | Warning
3978 | CDI: Curated Metric Feed/View (CARESV1-5198) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2978SS | 1848,2980SS | 1 | Start No Earlier Than | Warning
3979 | CDI: Notifications (CARESV1-5199) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2979SS | 1848,2981SS | 1 | Start No Earlier Than | Warning
3980 | CDI: Timers (CARESV1-5191) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2980SS | 1848,2982SS | 1 | Start No Earlier Than | Warning
3981 | CDI: Validations (CARESV1-5192) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 | 0d | 2981SS | 1848 | 1 | Start No Earlier Than | Warning
3985 | CARESV1-18894 Reporting & Analytics: M5 (LOE) | July 24, 2023 8:00 AM | December 27, 2024 5:00 PM | 360 | 0d | 169 | 1843 | 1 | Start No Earlier Than | Warning
4006 | CARESV1-34755 Data Pipeline (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 2985FS-80d | 1843,3008SS,3009SS,3010SS,3011SS,3012SS,3013SS,3014SS | 0.97 | Start No Earlier Than | Warning
4007 | CARESV1-34757 State & Federal Report Mapping (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4008 | CARESV1-34759 Data Architecture Layer (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4009 | CARESV1-34760 Data Extract (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4010 | CARESV1-34762 Analytical Authorization Layer (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4011 | CARESV1-34763 Product Metrics (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4012 | CARESV1-34764 Functional Training Material Support (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
4013 | CARESV1-34765 Data Generation | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 | 44d | 3007SS | 1843 | 0.97 | Finish No Earlier Than | Warning
6134 | CWDS Staff Newsletter, Volume 1 Issue 1 | June 17, 2024 8:00 AM | August 30, 2024 5:00 PM | 54 | 0d |  | 3018FS+10d | 1 | Must Start On | Warning
6143 | CARES Compass, Volume 1 Issue 1 | January 5, 2023 8:00 AM | April 2, 2024 5:00 PM | 310 | 0d |  | 3027 | 1 | Must Start On | Warning
6155 | CWS-CARES Public Library for existing project materials accessible by CWDS website | February 3, 2025 8:00 AM | February 12, 2027 5:00 PM | 509 | 0d | 3037 | 3040 | 1 | Finish No Earlier Than | Warning
6158 | Establish a CWS-CARES Branded Merchandise Store | October 1, 2024 8:00 AM | January 30, 2025 5:00 PM | 82 | 0d | 3040,3035FS-76d | 3043 | 1 | Start No Earlier Than | Warning
6160 | External Baseline Communication Survey | December 15, 2023 8:00 AM | February 29, 2024 5:00 PM | 51 | 0d | 3041 | 3044 | 1 | Start No Earlier Than | Warning
13245 | Initiate Q1 ACF reporting of C-SA to all Stakeholders | January 2, 2025 8:00 AM | January 2, 2025 5:00 PM | 1 | 0d |  | 3054 | 1 | Start No Earlier Than | Warning
13307 | Initiate Q3 ACF reporting of C-SA with all resources | July 16, 2025 8:00 AM | July 16, 2025 5:00 PM | 1 | 0d |  | 3071 | 1 | Start No Earlier Than | Warning
13276 | Initiate Q4 ACF reporting of C-SA with all resources | October 14, 2025 8:00 AM | October 14, 2025 5:00 PM | 1 | 456d |  | 3091 | 0 | Start No Earlier Than | Warning
13250 | Initiate Q1 ACF reporting of C-SA with all resources | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1 | 206d |  | 3112 | 0 | Start No Earlier Than | Warning
7643 | Create IL Onboarding Toolkit/Playbook | November 7, 2022 8:00 AM | February 14, 2023 5:00 PM | 66 | 0d | 3192 | 3196SS,3228SS,3197SS,3198SS,3199SS,3200SS | 1 | Start No Earlier Than | Warning
7752 | Conduct Environment Analysis for CARES V1 and Create a Summary Report (DMF) | August 1, 2023 8:00 AM | October 2, 2023 5:00 PM | 44 | 0d | 3192 | 5260FS+33d,5265 | 1 | Start No Earlier Than | Warning
7755 | Initiate and facilitate working group discussions related to rollout contingency planning, in support of Contingency Plan being completed by May 31, 2023 | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 | 0d | 3196SS | 3326FS-19d | 1 | Must Start On | Warning
8101 | Review ToolKit list | March 13, 2023 8:00 AM | April 19, 2023 5:00 PM | 27 | 0d | 3192 | 3452,3457 | 1 | Start No Earlier Than | Warning
8126 | Develop Executive Briefing presentation | November 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 24 | 0d | 3192 | 3473,3477SS,3478SS | 1 | Must Start On | Warning
11664 | Conduct discovery sessions with RADD | October 2, 2023 8:00 AM | March 29, 2024 5:00 PM | 123 | 0d | 3192 | 3528FS+21d,3529FS+21d | 1 | Start No Earlier Than | Warning
11808 | Schedule Executive Briefing | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 | 0d | 3192 | 3538,3546SS | 1 | Start No Earlier Than | Warning
8341 | Review August Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | September 24, 2024 8:00 AM | September 30, 2024 5:00 PM | 5 | 0d | 3757,3751FS-6d | 3765 | 1 | Start No Earlier Than | Warning
13721 | Prepare and Support Sandbox for Cohort 1 Group 1 Users (EUST 2 code) | May 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 128 | 486d |  | 3895SS | 0.89 | Start No Earlier Than | Warning
13722 | Sandbox Launch for Cohort 1 Group 1 Users (EUST 2 code) | July 31, 2025 8:00 AM | July 31, 2025 5:00 PM | 1 | 0d |  |  | 1 | Start No Earlier Than | Warning
13724 | Draft, review, and distribute email communications to Cohort 1 Group 2 Organizations to determine Cohort 1 Group 2 Sandbox Users | August 11, 2025 8:00 AM | August 20, 2025 5:00 PM | 8 | 0d |  | 3919,3920 | 1 | Start No Earlier Than | Warning
13715 | Verify County Connection to CWS-CARES and Whitelisting for Cohort 1 Group 3. | August 21, 2025 8:00 AM | October 20, 2025 5:00 PM | 42 | 0d |  |  | 1 | Start No Earlier Than | Warning
13716 | Draft, review, and distribute email communications to Cohort 1 Group 3 Organizations to determine Cohort 1 Group 3 Sandbox Users | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM | 5 | 0d |  | 3933,3934 | 1 | Start No Earlier Than | Warning
13743 | Draft, review, and distribute email communications to Cohort 2 Organizations to determine Cohort 2 Sandbox Users | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM | 5 | 0d |  | 3954 | 1 | Start No Earlier Than | Warning
13710 | Expand Sandbox schedule tasks until October 2026, with input from PaaS SI, CDI, and State - including EUST, Tech, and PMO | August 25, 2025 8:00 AM | September 12, 2025 5:00 PM | 14 | 0d |  | 3969FS-1d | 1 | Start No Earlier Than | Warning
43926 | Draft, review, and distribute email communications to Cohort 3 Organizations to determine Cohort 3 Sandbox Users | November 17, 2025 8:00 AM | November 21, 2025 5:00 PM | 5 | 372d |  | 3980 | 0 | Start No Earlier Than | Warning
43912 | Draft, review, and distribute email communications to Cohort 4 Organizations to determine Cohort 4 Sandbox Users | February 17, 2026 8:00 AM | February 25, 2026 5:00 PM | 7 | 289d |  | 4005 | 0 | Start No Earlier Than | Warning
8662 | Screening Discovery | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 | 0d | 3192 | 4321,4322 | 1 | Start No Earlier Than | Warning
8674 | Screening Safely Surrender Baby Module | July 31, 2023 8:00 AM | September 28, 2023 5:00 PM | 43 | 0d | 4331 | 4333SS | 1 | Finish No Earlier Than | Warning
8676 | Screening Assignments Module | July 31, 2023 8:00 AM | August 11, 2023 5:00 PM | 10 | 0d | 4331,4332SS | 4334FS-2d | 1 | Finish No Earlier Than | Warning
8677 | Screening Worker Submission Module | August 10, 2023 8:00 AM | September 13, 2023 5:00 PM | 24 | 0d | 4333FS-2d | 4336 | 1 | Finish No Earlier Than | Warning
8680 | Provide review of all CARESV1 Training Material for approval | December 26, 2023 8:00 AM | January 18, 2024 5:00 PM | 16 | 0d | 4334 | 4337 | 1 | Start No Earlier Than | Warning
8681 | Provide completed feedback forms according to timelines | January 19, 2024 8:00 AM | January 19, 2024 5:00 PM | 1 | 0d | 4336 | 4338 | 1 | Start No Earlier Than | Warning
8682 | State Team Final Course Review | January 22, 2024 8:00 AM | February 20, 2024 5:00 PM | 21 | 0d | 4337 | 4339 | 1 | Start No Earlier Than | Warning
8683 | State Team Final Sign-Off of Course Material | February 21, 2024 8:00 AM | March 6, 2024 5:00 PM | 11 | 0d | 4338 | 4340 | 1 | Start No Earlier Than | Warning
8684 | Milestone Complete | March 7, 2024 8:00 AM | March 7, 2024 5:00 PM | 1 | 0d | 4339 | 4341 | 1 | Start No Earlier Than | Warning
8692 | Development Training Materials: Screening Completed | March 7, 2024 5:00 PM | March 7, 2024 5:00 PM | 0 | 0d | 4340 | 4925 | 1 | Finish No Earlier Than | Warning
10634 | MS 07/7.1 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4477,4468,4469FS-76d | 4538,5611,5612,4782,4783,4904 | 0 | Start No Earlier Than | Warning
10823 | MS 21 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4628,4619,4620FS-3d | 4630,5611,5612,4800,4801,4904 | 0 | Start No Earlier Than | Warning
10824 | Eligibility Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4629 | 4925 | 0 | Start No Earlier Than | Warning
9647 | Start Hardening Activities | April 8, 2024 8:00 AM | April 8, 2024 8:00 AM | 0 | 0d | 3192 | 4742,4743,4744,4745,4746,4747,4756,4757,4758,4759,4760,4769,4770 | 1 | Start No Earlier Than | Warning
9678 | Develop ILT Strategy Document | August 14, 2023 8:00 AM | December 6, 2023 5:00 PM | 79 | 0d | 3192 | 4820 | 1 | Must Start On | Warning
13780 | Configure Enablement for Staging Evnironment | November 3, 2025 8:00 AM | November 14, 2025 5:00 PM | 9 | 457d |  | 4893 | 0 | Start No Earlier Than | Warning
9705 | Training Advisory Workgroup Engagement 1 | April 2, 2024 8:00 AM | May 31, 2024 5:00 PM | 43 | 0d | 3192 | 4928 | 1 | Start No Earlier Than | Warning
9706 | Training Advisory Workgroup Engagement 2 | June 3, 2024 8:00 AM | July 31, 2024 5:00 PM | 42 | 0d | 4927 | 4929 | 1 | Start No Earlier Than | Warning
9707 | Training Advisory Workgroup Engagement 3 | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 | 0d | 4928 | 4930 | 1 | Start No Earlier Than | Warning
11680 | Training Advisory Workgroup Engagement 4 | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 21 | 0d | 4929 | 4931 | 1 | Start No Earlier Than | Warning
11681 | Training Advisory Workgroup Engagement 5 | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 23 | 0d | 4930 | 4932 | 1 | Start No Earlier Than | Warning
11682 | Training Advisory Workgroup Engagement 6 | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 18 | 0d | 4931 | 4933 | 1 | Start No Earlier Than | Warning
11683 | Training Advisory Workgroup Engagement 7 | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d | 4932 | 4934 | 1 | Start No Earlier Than | Warning
11684 | Training Advisory Workgroup Engagement 8 | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d | 4933 | 4935 | 1 | Start No Earlier Than | Warning
11685 | Training Advisory Workgroup Engagement 9 | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d | 4934 | 4936 | 1 | Start No Earlier Than | Warning
11686 | Training Advisory Workgroup Engagement 10 | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 20 | 0d | 4935 | 4937 | 1 | Start No Earlier Than | Warning
11687 | Training Advisory Workgroup Engagement 11 | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d | 4936 | 4938 | 1 | Start No Earlier Than | Warning
11688 | Training Advisory Workgroup Engagement 12 | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 21 | 0d | 4937 | 4939 | 1 | Start No Earlier Than | Warning
11689 | Training Advisory Workgroup Engagement 13 | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d | 4938 | 4940 | 1 | Start No Earlier Than | Warning
11690 | Training Advisory Workgroup Engagement 14 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d | 4939 | 4941 | 1 | Start No Earlier Than | Warning
11691 | Training Advisory Workgroup Engagement 15 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d | 4940 | 4942 | 1 | Start No Earlier Than | Warning
11692 | Training Advisory Workgroup Engagement 16 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d | 4941 | 4943 | 1 | Start No Earlier Than | Warning
11693 | Training Advisory Workgroup Engagement 17 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 18d | 4942 | 4944 | 0.35 | Start No Earlier Than | Warning
11694 | Training Advisory Workgroup Engagement 18 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 18d | 4943 | 4945 | 0 | Start No Earlier Than | Warning
11695 | Training Advisory Workgroup Engagement 19 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 18d | 4944 | 4946 | 0 | Start No Earlier Than | Warning
11696 | Training Advisory Workgroup Engagement 20 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 18d | 4945 | 4947 | 0 | Start No Earlier Than | Warning
11697 | Training Advisory Workgroup Engagement 21 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 18d | 4946 | 4948 | 0 | Start No Earlier Than | Warning
11698 | Training Advisory Workgroup Engagement 22 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 21 | 18d | 4947 | 4949 | 0 | Start No Earlier Than | Warning
11699 | Training Advisory Workgroup Engagement 23 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 18d | 4948 | 4950 | 0 | Start No Earlier Than | Warning
11700 | Training Advisory Workgroup Engagement 24 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 18d | 4949 | 4951 | 0 | Start No Earlier Than | Warning
11701 | Training Advisory Workgroup Engagement 25 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 18d | 4950 | 4952 | 0 | Start No Earlier Than | Warning
11702 | Training Advisory Workgroup Engagement 26 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 18d | 4951 | 4953 | 0 | Start No Earlier Than | Warning
11703 | Training Advisory Workgroup Engagement 27 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 18d | 4952 | 4954 | 0 | Start No Earlier Than | Warning
11704 | Training Advisory Workgroup Engagement 28 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 18d | 4953 | 5630 | 0 | Start No Earlier Than | Warning
10022 | Create First Draft of the Sandbox Strategy and Provide to State Leadership for Review | October 3, 2023 8:00 AM | February 23, 2024 5:00 PM | 97 | 0d | 3322 | 5267 | 1 | Start No Earlier Than | Warning
10390 | MS 21: Review To-Be Business Flows/Processes with VPODs | August 26, 2024 8:00 AM | September 5, 2024 5:00 PM | 9 | 0d | 5479FS+5d | 5481FF+3d | 1 | Finish No Earlier Than | Warning
10100 | Deliverable Task 5.5 Completed | February 23, 2026 5:00 PM | February 23, 2026 5:00 PM | 0 | 171d | 5517,5525,5503,5420,5449,5457,5414,5491,5497 | 5630 | 0 | Start No Earlier Than | Warning
10164 | Draft and distribute monthly communications products 1 | July 3, 2023 8:00 AM | July 31, 2023 5:00 PM | 20 | 0d | 3192 | 5570 | 1 | Start No Earlier Than | Warning
10165 | Draft and distribute monthly communications products 2 | August 1, 2023 8:00 AM | August 31, 2023 5:00 PM | 23 | 0d | 5569 | 5571 | 1 | Start No Earlier Than | Warning
10166 | Draft and distribute monthly communications products 3 | September 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 20 | 0d | 5570 | 5572 | 1 | Start No Earlier Than | Warning
10167 | Draft and distribute monthly communications products 4 | October 2, 2023 8:00 AM | October 31, 2023 5:00 PM | 22 | 0d | 5571 | 5573 | 1 | Start No Earlier Than | Warning
10168 | Draft and distribute monthly communications products 5 | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 19 | 0d | 5572 | 5574 | 1 | Start No Earlier Than | Warning
10169 | Draft and distribute monthly communications products 6 | December 1, 2023 8:00 AM | December 29, 2023 5:00 PM | 20 | 0d | 5573 | 5575 | 1 | Start No Earlier Than | Warning
10170 | Draft and distribute monthly communications products 7 | January 2, 2024 8:00 AM | January 31, 2024 5:00 PM | 21 | 0d | 5574 | 5576 | 1 | Start No Earlier Than | Warning
10171 | Draft and distribute monthly communications products 8 | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 20 | 0d | 5575 | 5577 | 1 | Start No Earlier Than | Warning
10172 | Draft and distribute monthly communications products 9 | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 21 | 0d | 5576 | 5578 | 1 | Start No Earlier Than | Warning
10173 | Draft and distribute monthly communications products 10 | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 21 | 0d | 5577 | 5579 | 1 | Start No Earlier Than | Warning
10174 | Draft and distribute monthly communications products 11 | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 | 0d | 5578 | 5580 | 1 | Start No Earlier Than | Warning
10175 | Draft and distribute monthly communications products 12 | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 20 | 0d | 5579 | 5581 | 1 | Start No Earlier Than | Warning
10176 | Draft and distribute monthly communications products 13 | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 22 | 0d | 5580 | 5609,5582 | 1 | Start No Earlier Than | Warning
12228 | Draft and distribute monthly communications products 14 | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 | 0d | 5581 | 5583 | 1 | Start No Earlier Than | Warning
12229 | Draft and distribute monthly communications products 15 | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 21 | 0d | 5582 | 5584 | 1 | Start No Earlier Than | Warning
12230 | Draft and distribute monthly communications products 16 | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 23 | 0d | 5583 | 5585 | 1 | Start No Earlier Than | Warning
12231 | Draft and distribute monthly communications products 17 | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 18 | 0d | 5584 | 5586 | 1 | Start No Earlier Than | Warning
12232 | Draft and distribute monthly communications products 18 | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d | 5585 | 5587 | 1 | Start No Earlier Than | Warning
12233 | Draft and distribute monthly communications products 19 | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d | 5586 | 5588 | 1 | Start No Earlier Than | Warning
12234 | Draft and distribute monthly communications products 20 | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d | 5587 | 5589 | 1 | Start No Earlier Than | Warning
12235 | Draft and distribute monthly communications products 21 | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 20 | 0d | 5588 | 5590 | 1 | Start No Earlier Than | Warning
12236 | Draft and distribute monthly communications products 22 | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d | 5589 | 5591 | 1 | Start No Earlier Than | Warning
12237 | Draft and distribute monthly communications products 23 | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 21 | 0d | 5590 | 5592 | 1 | Start No Earlier Than | Warning
12238 | Draft and distribute monthly communications products 24 | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d | 5591 | 5593 | 1 | Start No Earlier Than | Warning
12239 | Draft and distribute monthly communications products 25 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d | 5592 | 5594 | 1 | Start No Earlier Than | Warning
12240 | Draft and distribute monthly communications products 26 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d | 5593 | 5595 | 1 | Start No Earlier Than | Warning
12241 | Draft and distribute monthly communications products 27 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d | 5594 | 5596 | 1 | Start No Earlier Than | Warning
12242 | Draft and distribute monthly communications products 28 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 239d | 5595 | 5597 | 0.35 | Start No Earlier Than | Warning
12243 | Draft and distribute monthly communications products 29 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 239d | 5596 | 5598 | 0 | Start No Earlier Than | Warning
12244 | Draft and distribute monthly communications products 30 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 239d | 5597 | 5599 | 0 | Start No Earlier Than | Warning
12245 | Draft and distribute monthly communications products 31 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 239d | 5598 | 5600 | 0 | Start No Earlier Than | Warning
12246 | Draft and distribute monthly communications products 32 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 239d | 5599 | 5601 | 0 | Start No Earlier Than | Warning
12247 | Draft and distribute monthly communications products 33 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 21 | 239d | 5600 | 5602 | 0 | Start No Earlier Than | Warning
12248 | Draft and distribute monthly communications products 34 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 239d | 5601 | 5603 | 0 | Start No Earlier Than | Warning
12249 | Draft and distribute monthly communications products 35 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 239d | 5602 | 5604 | 0 | Start No Earlier Than | Warning
12250 | Draft and distribute monthly communications products 36 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 239d | 5603 | 5605 | 0 | Start No Earlier Than | Warning
12251 | Draft and distribute monthly communications products 37 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 239d | 5604 | 5606 | 0 | Start No Earlier Than | Warning
12252 | Draft and distribute monthly communications products 38 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 239d | 5605 | 5607 | 0 | Start No Earlier Than | Warning
12253 | Draft and distribute monthly communications products 39 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 239d | 5606 | 5608 | 0 | Start No Earlier Than | Warning
12254 | Draft and distribute monthly communications products 40 | October 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17 | 239d | 5607 | 5621 | 0 | Start No Earlier Than | Warning
6686 | Go-Live CWS-CARES V1 | October 26, 2026 5:00 PM | October 26, 2026 5:00 PM | 0 | -33d | 5629,5628,5620,2392,1855,4840,4841,4874,5306,5549,4883,4954,5372,5373,5026,5146,5215,5276,5330,5526,5539,5566,5642 | 5643FS+4d | 0 | Must Finish On | Warning
23988 | Alameda CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 5637 | 5639 | 1 | Start No Earlier Than | Warning
23989 | Alameda CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 68d | 5638 | 5640 | 0 | Start No Earlier Than | Warning
23990 | Alameda CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 48d | 5639 | 5641 | 0 | Start No Earlier Than | Warning
23991 | Alameda CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 27d | 5640 | 5642 | 0 | Start No Earlier Than | Warning
23992 | Alameda CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 6d | 5641 | 5630 | 0 | Start No Earlier Than | Warning
24015 | Alameda CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24016 | Alameda CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24017 | Alameda CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
24018 | Alameda CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24019 | Alameda CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24020 | Alameda CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24021 | Alameda CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24022 | Alameda CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24023 | Alameda CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24024 | Alameda CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24025 | Alameda CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24026 | Alameda CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24027 | Alameda CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24028 | Alameda CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24029 | Alameda CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24036 | Alameda CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
24037 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 5688SS | 0 | Start No Earlier Than | Warning
24041 | Alameda CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24042 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 5693SS | 0 | Start No Earlier Than | Warning
24044 | Alameda CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24045 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 5696SS | 0 | Start No Earlier Than | Warning
24046 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 5695SS |  | 0 | Start No Earlier Than | Warning
24047 | Alameda CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24048 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 5699SS | 0 | Start No Earlier Than | Warning
24050 | Alameda CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24051 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 5702SS | 0 | Start No Earlier Than | Warning
24053 | Alameda CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24061 | Alameda CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24065 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24066 | Alameda CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 5717 | 1 | Start No Earlier Than | Warning
24069 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24070 | Alameda CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 5721 | 0.2 | Start No Earlier Than | Warning
24073 | Alameda CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24074 | Alameda CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 5725 | 0 | Start No Earlier Than | Warning
24077 | Alameda CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24078 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24095 | Alameda CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5743SF+30d |  | 0 | Start No Earlier Than | Warning
24096 | Alameda CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24110 | Alameda CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 5754,5761SS | 1 | Start No Earlier Than | Warning
24113 | Alameda CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
24114 | Alameda CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24128 | Alameda CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24131 | Alameda CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
24132 | Alameda CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24133 | Alameda CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24134 | Alameda CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24135 | Alameda CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5794 | 0 | Start No Earlier Than | Warning
24136 | Alameda CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5795 | 0 | Start No Earlier Than | Warning
24138 | Alameda CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24139 | Alameda CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5800SF+30d |  | 0 | Start No Earlier Than | Warning
24140 | Alameda CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5801SF+30d |  | 0 | Start No Earlier Than | Warning
24141 | Alameda CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5802SF+30d |  | 0 | Start No Earlier Than | Warning
24142 | Alameda CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5803SF+30d |  | 0 | Start No Earlier Than | Warning
24143 | Alameda CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5804SF+30d |  | 0 | Start No Earlier Than | Warning
24146 | Alameda CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24147 | Alameda CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 5806FS+12d | 0 | Start No Earlier Than | Warning
24148 | Alameda CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
24149 | Alameda CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 5806SF+60d | 0 | Start No Earlier Than | Warning
24150 | Alameda CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5789SF+30d | 0 | Start No Earlier Than | Warning
24151 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5790SF+30d | 0 | Start No Earlier Than | Warning
24152 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5791SF+30d | 0 | Start No Earlier Than | Warning
24153 | Alameda CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5792SF+30d | 0 | Start No Earlier Than | Warning
24154 | Alameda CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5793SF+30d | 0 | Start No Earlier Than | Warning
24155 | Alameda CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
24163 | Alpine CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
24164 | Alpine CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
24165 | Alpine CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
24166 | Alpine CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
24167 | Alpine CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
24168 | Alpine CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
24190 | Alpine CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24191 | Alpine CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24192 | Alpine CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
24193 | Alpine CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24194 | Alpine CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24195 | Alpine CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24196 | Alpine CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24197 | Alpine CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24198 | Alpine CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24199 | Alpine CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24200 | Alpine CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24201 | Alpine CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24202 | Alpine CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24203 | Alpine CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24204 | Alpine CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24211 | Alpine CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
24212 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 5863SS | 0 | Start No Earlier Than | Warning
24216 | Alpine CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24217 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 5868SS | 0 | Start No Earlier Than | Warning
24219 | Alpine CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24220 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 5871SS | 0 | Start No Earlier Than | Warning
24221 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 5870SS |  | 0 | Start No Earlier Than | Warning
24222 | Alpine CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24223 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 5874SS | 0 | Start No Earlier Than | Warning
24225 | Alpine CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24226 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 5877SS | 0 | Start No Earlier Than | Warning
24228 | Alpine CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24236 | Alpine CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24240 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24241 | Alpine CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 5892 | 1 | Start No Earlier Than | Warning
24244 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24245 | Alpine CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 5896 | 0.6 | Start No Earlier Than | Warning
24248 | Alpine CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24249 | Alpine CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 5900 | 0 | Start No Earlier Than | Warning
24252 | Alpine CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24253 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24270 | Alpine CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5918SF+30d |  | 0 | Start No Earlier Than | Warning
24271 | Alpine CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24285 | Alpine CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 5929,5936SS | 1 | Start No Earlier Than | Warning
24288 | Alpine CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
24289 | Alpine CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24303 | Alpine CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24305 | Alpine CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 5962 | 0.6 | Start No Earlier Than | Warning
24306 | Alpine CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
24307 | Alpine CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24308 | Alpine CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24309 | Alpine CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24310 | Alpine CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5969 | 0 | Start No Earlier Than | Warning
24311 | Alpine CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 5970 | 0 | Start No Earlier Than | Warning
24313 | Alpine CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24314 | Alpine CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5975SF+30d |  | 0 | Start No Earlier Than | Warning
24315 | Alpine CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5976SF+30d |  | 0 | Start No Earlier Than | Warning
24316 | Alpine CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5977SF+30d |  | 0 | Start No Earlier Than | Warning
24317 | Alpine CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5978SF+30d |  | 0 | Start No Earlier Than | Warning
24318 | Alpine CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 5979SF+30d |  | 0 | Start No Earlier Than | Warning
24321 | Alpine CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24322 | Alpine CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 5981FS+12d | 0 | Start No Earlier Than | Warning
24323 | Alpine CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
24324 | Alpine CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 5981SF+60d | 0 | Start No Earlier Than | Warning
24325 | Alpine CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5964SF+30d | 0 | Start No Earlier Than | Warning
24326 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5965SF+30d | 0 | Start No Earlier Than | Warning
24327 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5966SF+30d | 0 | Start No Earlier Than | Warning
24328 | Alpine CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5967SF+30d | 0 | Start No Earlier Than | Warning
24329 | Alpine CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 5968SF+30d | 0 | Start No Earlier Than | Warning
24330 | Alpine CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
24338 | Amador CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
24339 | Amador CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
24340 | Amador CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
24341 | Amador CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
24342 | Amador CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
24343 | Amador CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
24365 | Amador CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24366 | Amador CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24367 | Amador CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
24368 | Amador CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24369 | Amador CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24370 | Amador CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24371 | Amador CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24372 | Amador CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24373 | Amador CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24374 | Amador CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24375 | Amador CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24376 | Amador CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24377 | Amador CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24378 | Amador CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24379 | Amador CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24386 | Amador CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
24387 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6038SS | 0 | Start No Earlier Than | Warning
24391 | Amador CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24392 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6043SS | 0 | Start No Earlier Than | Warning
24394 | Amador CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24395 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6046SS | 0 | Start No Earlier Than | Warning
24396 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6045SS |  | 0 | Start No Earlier Than | Warning
24397 | Amador CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24398 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6049SS | 0 | Start No Earlier Than | Warning
24400 | Amador CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24401 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6052SS | 0 | Start No Earlier Than | Warning
24403 | Amador CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24411 | Amador CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24415 | Amador CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24416 | Amador CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6067 | 1 | Start No Earlier Than | Warning
24419 | Amador CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24420 | Amador CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6071 | 0 | Start No Earlier Than | Warning
24423 | Amador CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24424 | Amador CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6075 | 0 | Start No Earlier Than | Warning
24427 | Amador CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24428 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24431 | Amador CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 6082SS | 0.6 | Start No Earlier Than | Warning
24445 | Amador CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6093SF+30d |  | 0 | Start No Earlier Than | Warning
24446 | Amador CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24449 | Amador CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 6100SS | 0.4 | Start No Earlier Than | Warning
24460 | Amador CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 6104,6111SS | 1 | Start No Earlier Than | Warning
24463 | Amador CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
24464 | Amador CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24478 | Amador CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24480 | Amador CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 6137 | 0.6 | Start No Earlier Than | Warning
24481 | Amador CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
24482 | Amador CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24483 | Amador CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24484 | Amador CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24485 | Amador CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6144 | 0 | Start No Earlier Than | Warning
24486 | Amador CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6145 | 0 | Start No Earlier Than | Warning
24488 | Amador CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24489 | Amador CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6150SF+30d |  | 0 | Start No Earlier Than | Warning
24490 | Amador CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6151SF+30d |  | 0 | Start No Earlier Than | Warning
24491 | Amador CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6152SF+30d |  | 0 | Start No Earlier Than | Warning
24492 | Amador CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6153SF+30d |  | 0 | Start No Earlier Than | Warning
24493 | Amador CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6154SF+30d |  | 0 | Start No Earlier Than | Warning
24496 | Amador CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24497 | Amador CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6156FS+12d | 0 | Start No Earlier Than | Warning
24498 | Amador CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
24499 | Amador CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6156SF+60d | 0 | Start No Earlier Than | Warning
24500 | Amador CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6139SF+30d | 0 | Start No Earlier Than | Warning
24501 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6140SF+30d | 0 | Start No Earlier Than | Warning
24502 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6141SF+30d | 0 | Start No Earlier Than | Warning
24503 | Amador CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6142SF+30d | 0 | Start No Earlier Than | Warning
24504 | Amador CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6143SF+30d | 0 | Start No Earlier Than | Warning
24505 | Amador CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
24513 | Colusa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
24514 | Colusa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
24515 | Colusa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
24516 | Colusa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
24517 | Colusa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
24518 | Colusa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
24540 | Colusa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24541 | Colusa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24542 | Colusa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
24543 | Colusa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24544 | Colusa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24545 | Colusa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24546 | Colusa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24547 | Colusa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24548 | Colusa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24549 | Colusa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24550 | Colusa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24551 | Colusa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24552 | Colusa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24553 | Colusa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24554 | Colusa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24561 | Colusa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
24562 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6213SS | 0 | Start No Earlier Than | Warning
24566 | Colusa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24567 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6218SS | 0 | Start No Earlier Than | Warning
24569 | Colusa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24570 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6221SS | 0 | Start No Earlier Than | Warning
24571 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6220SS |  | 0 | Start No Earlier Than | Warning
24572 | Colusa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24573 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6224SS | 0 | Start No Earlier Than | Warning
24575 | Colusa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24576 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6227SS | 0 | Start No Earlier Than | Warning
24578 | Colusa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24586 | Colusa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24590 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24591 | Colusa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6242 | 1 | Start No Earlier Than | Warning
24594 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24595 | Colusa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 6246 | 1 | Start No Earlier Than | Warning
24598 | Colusa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24599 | Colusa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6250 | 0 | Start No Earlier Than | Warning
24602 | Colusa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24603 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24631 | Colusa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24634 | Colusa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
24635 | Colusa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24636 | Colusa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24637 | Colusa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24638 | Colusa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6297 | 0 | Start No Earlier Than | Warning
24639 | Colusa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6298 | 0 | Start No Earlier Than | Warning
24641 | Colusa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24642 | Colusa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6303SF+30d |  | 0 | Start No Earlier Than | Warning
24643 | Colusa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6304SF+30d |  | 0 | Start No Earlier Than | Warning
24644 | Colusa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6305SF+30d |  | 0 | Start No Earlier Than | Warning
24645 | Colusa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6306SF+30d |  | 0 | Start No Earlier Than | Warning
24646 | Colusa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6307SF+30d |  | 0 | Start No Earlier Than | Warning
24649 | Colusa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24650 | Colusa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6309FS+12d | 0 | Start No Earlier Than | Warning
24651 | Colusa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
24652 | Colusa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6309SF+60d | 0 | Start No Earlier Than | Warning
24653 | Colusa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6292SF+30d | 0 | Start No Earlier Than | Warning
24654 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6293SF+30d | 0 | Start No Earlier Than | Warning
24655 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6294SF+30d | 0 | Start No Earlier Than | Warning
24656 | Colusa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6295SF+30d | 0 | Start No Earlier Than | Warning
24657 | Colusa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6296SF+30d | 0 | Start No Earlier Than | Warning
24658 | Colusa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
24666 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
24667 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
24668 | Contra Costa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
24669 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
24670 | Contra Costa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
24671 | Contra Costa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
24693 | Contra Costa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24694 | Contra Costa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24695 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
24696 | Contra Costa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24697 | Contra Costa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24698 | Contra Costa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24699 | Contra Costa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24700 | Contra Costa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24701 | Contra Costa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24702 | Contra Costa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24703 | Contra Costa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24704 | Contra Costa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24705 | Contra Costa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24706 | Contra Costa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24707 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24714 | Contra Costa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
24715 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6366SS | 0 | Start No Earlier Than | Warning
24719 | Contra Costa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24720 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6371SS | 0 | Start No Earlier Than | Warning
24722 | Contra Costa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24723 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6374SS | 0 | Start No Earlier Than | Warning
24724 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6373SS |  | 0 | Start No Earlier Than | Warning
24725 | Contra Costa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24726 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6377SS | 0 | Start No Earlier Than | Warning
24728 | Contra Costa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24729 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6380SS | 0 | Start No Earlier Than | Warning
24731 | Contra Costa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24739 | Contra Costa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24743 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24744 | Contra Costa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6395 | 1 | Start No Earlier Than | Warning
24747 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24748 | Contra Costa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6399 | 0.2 | Start No Earlier Than | Warning
24751 | Contra Costa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24752 | Contra Costa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6403 | 0 | Start No Earlier Than | Warning
24755 | Contra Costa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24756 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24773 | Contra Costa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6421SF+30d |  | 0 | Start No Earlier Than | Warning
24774 | Contra Costa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24777 | Contra Costa CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 6428SS | 1 | Start No Earlier Than | Warning
24788 | Contra Costa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 6432,6439SS | 1 | Start No Earlier Than | Warning
24791 | Contra Costa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
24792 | Contra Costa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24806 | Contra Costa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24808 | Contra Costa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 6465 | 0.2 | Start No Earlier Than | Warning
24809 | Contra Costa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
24810 | Contra Costa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24811 | Contra Costa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24812 | Contra Costa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24813 | Contra Costa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6472 | 0 | Start No Earlier Than | Warning
24814 | Contra Costa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6473 | 0 | Start No Earlier Than | Warning
24816 | Contra Costa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24817 | Contra Costa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6478SF+30d |  | 0 | Start No Earlier Than | Warning
24818 | Contra Costa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6479SF+30d |  | 0 | Start No Earlier Than | Warning
24819 | Contra Costa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6480SF+30d |  | 0 | Start No Earlier Than | Warning
24820 | Contra Costa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6481SF+30d |  | 0 | Start No Earlier Than | Warning
24821 | Contra Costa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6482SF+30d |  | 0 | Start No Earlier Than | Warning
24824 | Contra Costa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24825 | Contra Costa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6484FS+12d | 0 | Start No Earlier Than | Warning
24826 | Contra Costa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
24827 | Contra Costa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6484SF+60d | 0 | Start No Earlier Than | Warning
24828 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6467SF+30d | 0 | Start No Earlier Than | Warning
24829 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6468SF+30d | 0 | Start No Earlier Than | Warning
24830 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6469SF+30d | 0 | Start No Earlier Than | Warning
24831 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6470SF+30d | 0 | Start No Earlier Than | Warning
24832 | Contra Costa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6471SF+30d | 0 | Start No Earlier Than | Warning
24833 | Contra Costa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
24841 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
24842 | Del Norte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
24843 | Del Norte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
24844 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
24845 | Del Norte CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
24846 | Del Norte CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
24868 | Del Norte CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24869 | Del Norte CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
24870 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
24871 | Del Norte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
24872 | Del Norte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
24873 | Del Norte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
24874 | Del Norte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
24875 | Del Norte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
24876 | Del Norte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
24877 | Del Norte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
24878 | Del Norte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
24879 | Del Norte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
24880 | Del Norte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
24881 | Del Norte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24882 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
24889 | Del Norte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | Start No Earlier Than | Warning
24890 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6541SS | 0 | Start No Earlier Than | Warning
24894 | Del Norte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
24895 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6546SS | 0 | Start No Earlier Than | Warning
24897 | Del Norte CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
24898 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6549SS | 0 | Start No Earlier Than | Warning
24899 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6548SS |  | 0 | Start No Earlier Than | Warning
24900 | Del Norte CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
24901 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6552SS | 0 | Start No Earlier Than | Warning
24903 | Del Norte CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
24904 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6555SS | 0 | Start No Earlier Than | Warning
24906 | Del Norte CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
24914 | Del Norte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24918 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24919 | Del Norte CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6570 | 1 | Start No Earlier Than | Warning
24922 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24923 | Del Norte CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 6574 | 1 | Start No Earlier Than | Warning
24926 | Del Norte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24927 | Del Norte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6578 | 0 | Start No Earlier Than | Warning
24930 | Del Norte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
24931 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
24934 | Del Norte CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d |  | 6585SS | 0 | Start No Earlier Than | Warning
24941 | Del Norte CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d |  | 6592,6594SS | 1 | Start No Earlier Than | Warning
24947 | Del Norte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6595SF+30d |  | 0 | Start No Earlier Than | Warning
24948 | Del Norte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24951 | Del Norte CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 6602SS | 1 | Start No Earlier Than | Warning
24962 | Del Norte CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 6606,6613SS | 1 | Start No Earlier Than | Warning
24965 | Del Norte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
24966 | Del Norte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
24980 | Del Norte CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
24982 | Del Norte CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 6639 | 0.2 | Start No Earlier Than | Warning
24983 | Del Norte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
24984 | Del Norte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
24985 | Del Norte CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
24986 | Del Norte CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
24987 | Del Norte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6646 | 0 | Start No Earlier Than | Warning
24988 | Del Norte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6647 | 0 | Start No Earlier Than | Warning
24990 | Del Norte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
24991 | Del Norte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6652SF+30d |  | 0 | Start No Earlier Than | Warning
24992 | Del Norte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6653SF+30d |  | 0 | Start No Earlier Than | Warning
24993 | Del Norte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6654SF+30d |  | 0 | Start No Earlier Than | Warning
24994 | Del Norte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6655SF+30d |  | 0 | Start No Earlier Than | Warning
24995 | Del Norte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6656SF+30d |  | 0 | Start No Earlier Than | Warning
24998 | Del Norte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
24999 | Del Norte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6658FS+12d | 0 | Start No Earlier Than | Warning
25000 | Del Norte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25001 | Del Norte CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6658SF+60d | 0 | Start No Earlier Than | Warning
25002 | Del Norte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6641SF+30d | 0 | Start No Earlier Than | Warning
25003 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6642SF+30d | 0 | Start No Earlier Than | Warning
25004 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6643SF+30d | 0 | Start No Earlier Than | Warning
25005 | Del Norte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6644SF+30d | 0 | Start No Earlier Than | Warning
25006 | Del Norte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6645SF+30d | 0 | Start No Earlier Than | Warning
25007 | Del Norte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25015 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25016 | El Dorado CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25017 | El Dorado CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25018 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25019 | El Dorado CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25020 | El Dorado CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25042 | El Dorado CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25043 | El Dorado CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25044 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25045 | El Dorado CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25046 | El Dorado CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25047 | El Dorado CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25048 | El Dorado CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25049 | El Dorado CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25050 | El Dorado CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25051 | El Dorado CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25052 | El Dorado CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25053 | El Dorado CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25054 | El Dorado CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25055 | El Dorado CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25056 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25063 | El Dorado CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
25064 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6715SS | 0 | Start No Earlier Than | Warning
25068 | El Dorado CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25069 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6720SS | 0 | Start No Earlier Than | Warning
25071 | El Dorado CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25072 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6723SS | 0 | Start No Earlier Than | Warning
25073 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6722SS |  | 0 | Start No Earlier Than | Warning
25074 | El Dorado CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25075 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6726SS | 0 | Start No Earlier Than | Warning
25077 | El Dorado CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25078 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6729SS | 0 | Start No Earlier Than | Warning
25080 | El Dorado CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25088 | El Dorado CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25092 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25093 | El Dorado CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6744 | 1 | Start No Earlier Than | Warning
25096 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25097 | El Dorado CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6748 | 0 | Start No Earlier Than | Warning
25100 | El Dorado CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25101 | El Dorado CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6752 | 0 | Start No Earlier Than | Warning
25104 | El Dorado CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25105 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25122 | El Dorado CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6770SF+30d |  | 0 | Start No Earlier Than | Warning
25123 | El Dorado CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25126 | El Dorado CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 114d |  | 6777SS | 0 | Start No Earlier Than | Warning
25137 | El Dorado CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 6781,6788SS | 1 | Start No Earlier Than | Warning
25140 | El Dorado CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
25141 | El Dorado CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25155 | El Dorado CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25157 | El Dorado CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 6814 | 0.6 | Start No Earlier Than | Warning
25158 | El Dorado CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25159 | El Dorado CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25160 | El Dorado CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
25161 | El Dorado CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
25162 | El Dorado CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6821 | 0 | Start No Earlier Than | Warning
25163 | El Dorado CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6822 | 0 | Start No Earlier Than | Warning
25165 | El Dorado CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
25166 | El Dorado CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6827SF+30d |  | 0 | Start No Earlier Than | Warning
25167 | El Dorado CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6828SF+30d |  | 0 | Start No Earlier Than | Warning
25168 | El Dorado CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6829SF+30d |  | 0 | Start No Earlier Than | Warning
25169 | El Dorado CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6830SF+30d |  | 0 | Start No Earlier Than | Warning
25170 | El Dorado CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 6831SF+30d |  | 0 | Start No Earlier Than | Warning
25173 | El Dorado CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
25174 | El Dorado CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 6833FS+12d | 0 | Start No Earlier Than | Warning
25175 | El Dorado CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25176 | El Dorado CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 6833SF+60d | 0 | Start No Earlier Than | Warning
25177 | El Dorado CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6816SF+30d | 0 | Start No Earlier Than | Warning
25178 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6817SF+30d | 0 | Start No Earlier Than | Warning
25179 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6818SF+30d | 0 | Start No Earlier Than | Warning
25180 | El Dorado CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6819SF+30d | 0 | Start No Earlier Than | Warning
25181 | El Dorado CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6820SF+30d | 0 | Start No Earlier Than | Warning
25182 | El Dorado CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25190 | Glenn CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25191 | Glenn CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25192 | Glenn CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25193 | Glenn CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25194 | Glenn CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25195 | Glenn CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25217 | Glenn CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25218 | Glenn CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25219 | Glenn CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25220 | Glenn CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25221 | Glenn CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25222 | Glenn CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25223 | Glenn CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25224 | Glenn CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25225 | Glenn CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25226 | Glenn CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25227 | Glenn CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25228 | Glenn CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25229 | Glenn CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25230 | Glenn CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25231 | Glenn CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25238 | Glenn CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
25239 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 6890SS | 0 | Start No Earlier Than | Warning
25243 | Glenn CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25244 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 6895SS | 0 | Start No Earlier Than | Warning
25246 | Glenn CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25247 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 6898SS | 0 | Start No Earlier Than | Warning
25248 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 6897SS |  | 0 | Start No Earlier Than | Warning
25249 | Glenn CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25250 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 6901SS | 0 | Start No Earlier Than | Warning
25252 | Glenn CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25253 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 6904SS | 0 | Start No Earlier Than | Warning
25255 | Glenn CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25263 | Glenn CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25267 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25268 | Glenn CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 6919 | 1 | Start No Earlier Than | Warning
25271 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25272 | Glenn CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 6923 | 0 | Start No Earlier Than | Warning
25275 | Glenn CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25276 | Glenn CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 6927 | 0 | Start No Earlier Than | Warning
25279 | Glenn CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25280 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25297 | Glenn CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6945SF+30d |  | 0 | Start No Earlier Than | Warning
25298 | Glenn CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25312 | Glenn CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 6956,6963SS | 1 | Start No Earlier Than | Warning
25315 | Glenn CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
25316 | Glenn CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25330 | Glenn CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25333 | Glenn CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25334 | Glenn CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25335 | Glenn CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
25336 | Glenn CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
25337 | Glenn CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6996 | 0 | Start No Earlier Than | Warning
25338 | Glenn CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 6997 | 0 | Start No Earlier Than | Warning
25340 | Glenn CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
25341 | Glenn CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7002SF+30d |  | 0 | Start No Earlier Than | Warning
25342 | Glenn CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7003SF+30d |  | 0 | Start No Earlier Than | Warning
25343 | Glenn CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7004SF+30d |  | 0 | Start No Earlier Than | Warning
25344 | Glenn CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7005SF+30d |  | 0 | Start No Earlier Than | Warning
25345 | Glenn CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7006SF+30d |  | 0 | Start No Earlier Than | Warning
25348 | Glenn CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
25349 | Glenn CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7008FS+12d | 0 | Start No Earlier Than | Warning
25350 | Glenn CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25351 | Glenn CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7008SF+60d | 0 | Start No Earlier Than | Warning
25352 | Glenn CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6991SF+30d | 0 | Start No Earlier Than | Warning
25353 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6992SF+30d | 0 | Start No Earlier Than | Warning
25354 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6993SF+30d | 0 | Start No Earlier Than | Warning
25355 | Glenn CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6994SF+30d | 0 | Start No Earlier Than | Warning
25356 | Glenn CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 6995SF+30d | 0 | Start No Earlier Than | Warning
25357 | Glenn CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25365 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25366 | Humboldt CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25367 | Humboldt CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25368 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25369 | Humboldt CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25370 | Humboldt CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25392 | Humboldt CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25393 | Humboldt CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25394 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25395 | Humboldt CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25396 | Humboldt CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25397 | Humboldt CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25398 | Humboldt CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25399 | Humboldt CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25400 | Humboldt CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25401 | Humboldt CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25402 | Humboldt CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25403 | Humboldt CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25404 | Humboldt CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25405 | Humboldt CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25406 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25413 | Humboldt CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
25414 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7065SS | 0 | Start No Earlier Than | Warning
25418 | Humboldt CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25419 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7070SS | 0 | Start No Earlier Than | Warning
25421 | Humboldt CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25422 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7073SS | 0 | Start No Earlier Than | Warning
25423 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7072SS |  | 0 | Start No Earlier Than | Warning
25424 | Humboldt CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25425 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7076SS | 0 | Start No Earlier Than | Warning
25427 | Humboldt CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25428 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7079SS | 0 | Start No Earlier Than | Warning
25430 | Humboldt CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25438 | Humboldt CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25442 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25443 | Humboldt CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7094 | 1 | Start No Earlier Than | Warning
25446 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25447 | Humboldt CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7098 | 0.6 | Start No Earlier Than | Warning
25450 | Humboldt CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25451 | Humboldt CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7102 | 0 | Start No Earlier Than | Warning
25454 | Humboldt CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25455 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25458 | Humboldt CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 7109SS | 1 | Start No Earlier Than | Warning
25472 | Humboldt CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7120SF+30d |  | 0 | Start No Earlier Than | Warning
25473 | Humboldt CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25476 | Humboldt CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 7127SS | 1 | Start No Earlier Than | Warning
25487 | Humboldt CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 7131,7138SS | 1 | Start No Earlier Than | Warning
25490 | Humboldt CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
25491 | Humboldt CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25505 | Humboldt CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25507 | Humboldt CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 7164 | 0.2 | Start No Earlier Than | Warning
25508 | Humboldt CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25509 | Humboldt CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25510 | Humboldt CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
25511 | Humboldt CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
25512 | Humboldt CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7171 | 0 | Start No Earlier Than | Warning
25513 | Humboldt CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7172 | 0 | Start No Earlier Than | Warning
25515 | Humboldt CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
25516 | Humboldt CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7177SF+30d |  | 0 | Start No Earlier Than | Warning
25517 | Humboldt CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7178SF+30d |  | 0 | Start No Earlier Than | Warning
25518 | Humboldt CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7179SF+30d |  | 0 | Start No Earlier Than | Warning
25519 | Humboldt CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7180SF+30d |  | 0 | Start No Earlier Than | Warning
25520 | Humboldt CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7181SF+30d |  | 0 | Start No Earlier Than | Warning
25523 | Humboldt CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
25524 | Humboldt CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7183FS+12d | 0 | Start No Earlier Than | Warning
25525 | Humboldt CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25526 | Humboldt CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7183SF+60d | 0 | Start No Earlier Than | Warning
25527 | Humboldt CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7166SF+30d | 0 | Start No Earlier Than | Warning
25528 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7167SF+30d | 0 | Start No Earlier Than | Warning
25529 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7168SF+30d | 0 | Start No Earlier Than | Warning
25530 | Humboldt CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7169SF+30d | 0 | Start No Earlier Than | Warning
25531 | Humboldt CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7170SF+30d | 0 | Start No Earlier Than | Warning
25532 | Humboldt CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25540 | Imperial CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25541 | Imperial CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25542 | Imperial CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25543 | Imperial CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25544 | Imperial CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25545 | Imperial CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25567 | Imperial CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25568 | Imperial CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25569 | Imperial CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25570 | Imperial CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25571 | Imperial CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25572 | Imperial CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25573 | Imperial CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25574 | Imperial CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25575 | Imperial CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25576 | Imperial CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25577 | Imperial CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25578 | Imperial CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25579 | Imperial CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25580 | Imperial CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25581 | Imperial CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25588 | Imperial CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
25589 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7240SS | 0 | Start No Earlier Than | Warning
25593 | Imperial CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25594 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7245SS | 0 | Start No Earlier Than | Warning
25596 | Imperial CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25597 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7248SS | 0 | Start No Earlier Than | Warning
25598 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7247SS |  | 0 | Start No Earlier Than | Warning
25599 | Imperial CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25600 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7251SS | 0 | Start No Earlier Than | Warning
25602 | Imperial CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25603 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7254SS | 0 | Start No Earlier Than | Warning
25605 | Imperial CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25613 | Imperial CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25617 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25618 | Imperial CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7269 | 1 | Start No Earlier Than | Warning
25621 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25622 | Imperial CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7273 | 0.2 | Start No Earlier Than | Warning
25625 | Imperial CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25626 | Imperial CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7277 | 0 | Start No Earlier Than | Warning
25629 | Imperial CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25630 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25644 | Imperial CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 7288,7295SS | 1 | Start No Earlier Than | Warning
25647 | Imperial CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
25648 | Imperial CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25662 | Imperial CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25665 | Imperial CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25666 | Imperial CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25667 | Imperial CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
25668 | Imperial CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
25669 | Imperial CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7328 | 0 | Start No Earlier Than | Warning
25670 | Imperial CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7329 | 0 | Start No Earlier Than | Warning
25672 | Imperial CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
25673 | Imperial CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7334SF+30d |  | 0 | Start No Earlier Than | Warning
25674 | Imperial CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7335SF+30d |  | 0 | Start No Earlier Than | Warning
25675 | Imperial CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7336SF+30d |  | 0 | Start No Earlier Than | Warning
25676 | Imperial CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7337SF+30d |  | 0 | Start No Earlier Than | Warning
25677 | Imperial CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7338SF+30d |  | 0 | Start No Earlier Than | Warning
25680 | Imperial CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
25681 | Imperial CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7340FS+12d | 0 | Start No Earlier Than | Warning
25682 | Imperial CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25683 | Imperial CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7340SF+60d | 0 | Start No Earlier Than | Warning
25684 | Imperial CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7323SF+30d | 0 | Start No Earlier Than | Warning
25685 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7324SF+30d | 0 | Start No Earlier Than | Warning
25686 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7325SF+30d | 0 | Start No Earlier Than | Warning
25687 | Imperial CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7326SF+30d | 0 | Start No Earlier Than | Warning
25688 | Imperial CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7327SF+30d | 0 | Start No Earlier Than | Warning
25689 | Imperial CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25697 | Inyo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25698 | Inyo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25699 | Inyo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25700 | Inyo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25701 | Inyo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25702 | Inyo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25724 | Inyo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25725 | Inyo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25726 | Inyo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25727 | Inyo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25728 | Inyo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25729 | Inyo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25730 | Inyo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25731 | Inyo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25732 | Inyo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25733 | Inyo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25734 | Inyo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25735 | Inyo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25736 | Inyo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25737 | Inyo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25738 | Inyo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25745 | Inyo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
25746 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7397SS | 0 | Start No Earlier Than | Warning
25750 | Inyo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25751 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7402SS | 0 | Start No Earlier Than | Warning
25753 | Inyo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25754 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7405SS | 0 | Start No Earlier Than | Warning
25755 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7404SS |  | 0 | Start No Earlier Than | Warning
25756 | Inyo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25757 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7408SS | 0 | Start No Earlier Than | Warning
25759 | Inyo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25760 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7411SS | 0 | Start No Earlier Than | Warning
25762 | Inyo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25770 | Inyo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25774 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25775 | Inyo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7426 | 1 | Start No Earlier Than | Warning
25778 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25779 | Inyo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7430 | 0.2 | Start No Earlier Than | Warning
25782 | Inyo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25783 | Inyo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7434 | 0 | Start No Earlier Than | Warning
25786 | Inyo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25787 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25801 | Inyo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 7445,7452SS | 1 | Start No Earlier Than | Warning
25804 | Inyo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
25805 | Inyo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25819 | Inyo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25822 | Inyo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25823 | Inyo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25824 | Inyo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
25825 | Inyo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
25826 | Inyo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7485 | 0 | Start No Earlier Than | Warning
25827 | Inyo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7486 | 0 | Start No Earlier Than | Warning
25829 | Inyo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
25830 | Inyo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7491SF+30d |  | 0 | Start No Earlier Than | Warning
25831 | Inyo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7492SF+30d |  | 0 | Start No Earlier Than | Warning
25832 | Inyo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7493SF+30d |  | 0 | Start No Earlier Than | Warning
25833 | Inyo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7494SF+30d |  | 0 | Start No Earlier Than | Warning
25834 | Inyo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7495SF+30d |  | 0 | Start No Earlier Than | Warning
25837 | Inyo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
25838 | Inyo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7497FS+12d | 0 | Start No Earlier Than | Warning
25839 | Inyo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
25840 | Inyo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7497SF+60d | 0 | Start No Earlier Than | Warning
25841 | Inyo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7480SF+30d | 0 | Start No Earlier Than | Warning
25842 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7481SF+30d | 0 | Start No Earlier Than | Warning
25843 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7482SF+30d | 0 | Start No Earlier Than | Warning
25844 | Inyo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7483SF+30d | 0 | Start No Earlier Than | Warning
25845 | Inyo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7484SF+30d | 0 | Start No Earlier Than | Warning
25846 | Inyo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
25854 | Kern CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
25855 | Kern CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
25856 | Kern CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
25857 | Kern CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
25858 | Kern CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
25859 | Kern CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
25881 | Kern CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25882 | Kern CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
25883 | Kern CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
25884 | Kern CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
25885 | Kern CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
25886 | Kern CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
25887 | Kern CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
25888 | Kern CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
25889 | Kern CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
25890 | Kern CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
25891 | Kern CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
25892 | Kern CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
25893 | Kern CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
25894 | Kern CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25895 | Kern CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
25902 | Kern CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
25903 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7554SS | 0 | Start No Earlier Than | Warning
25907 | Kern CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
25908 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7559SS | 0 | Start No Earlier Than | Warning
25910 | Kern CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
25911 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7562SS | 0 | Start No Earlier Than | Warning
25912 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7561SS |  | 0 | Start No Earlier Than | Warning
25913 | Kern CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
25914 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7565SS | 0 | Start No Earlier Than | Warning
25916 | Kern CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
25917 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7568SS | 0 | Start No Earlier Than | Warning
25919 | Kern CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
25927 | Kern CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25931 | Kern CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25932 | Kern CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7583 | 1 | Start No Earlier Than | Warning
25935 | Kern CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25936 | Kern CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7587 | 0.2 | Start No Earlier Than | Warning
25939 | Kern CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25940 | Kern CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7591 | 0 | Start No Earlier Than | Warning
25943 | Kern CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
25944 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
25961 | Kern CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7609SF+30d |  | 0 | Start No Earlier Than | Warning
25962 | Kern CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25976 | Kern CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 7620,7627SS | 1 | Start No Earlier Than | Warning
25979 | Kern CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
25980 | Kern CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
25994 | Kern CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
25997 | Kern CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
25998 | Kern CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
25999 | Kern CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26000 | Kern CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26001 | Kern CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7660 | 0 | Start No Earlier Than | Warning
26002 | Kern CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7661 | 0 | Start No Earlier Than | Warning
26004 | Kern CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26005 | Kern CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7666SF+30d |  | 0 | Start No Earlier Than | Warning
26006 | Kern CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7667SF+30d |  | 0 | Start No Earlier Than | Warning
26007 | Kern CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7668SF+30d |  | 0 | Start No Earlier Than | Warning
26008 | Kern CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7669SF+30d |  | 0 | Start No Earlier Than | Warning
26009 | Kern CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7670SF+30d |  | 0 | Start No Earlier Than | Warning
26012 | Kern CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26013 | Kern CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7672FS+12d | 0 | Start No Earlier Than | Warning
26014 | Kern CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26015 | Kern CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7672SF+60d | 0 | Start No Earlier Than | Warning
26016 | Kern CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7655SF+30d | 0 | Start No Earlier Than | Warning
26017 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7656SF+30d | 0 | Start No Earlier Than | Warning
26018 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7657SF+30d | 0 | Start No Earlier Than | Warning
26019 | Kern CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7658SF+30d | 0 | Start No Earlier Than | Warning
26020 | Kern CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7659SF+30d | 0 | Start No Earlier Than | Warning
26021 | Kern CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26029 | Lake CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26030 | Lake CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.4 | Start No Earlier Than | Warning
26031 | Lake CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26032 | Lake CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26033 | Lake CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26034 | Lake CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26056 | Lake CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26057 | Lake CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26058 | Lake CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26059 | Lake CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26060 | Lake CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26061 | Lake CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26062 | Lake CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26063 | Lake CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26064 | Lake CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26065 | Lake CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26066 | Lake CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26067 | Lake CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26068 | Lake CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26069 | Lake CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26070 | Lake CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26077 | Lake CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
26078 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7729SS | 0 | Start No Earlier Than | Warning
26082 | Lake CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26083 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7734SS | 0 | Start No Earlier Than | Warning
26085 | Lake CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26086 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7737SS | 0 | Start No Earlier Than | Warning
26087 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7736SS |  | 0 | Start No Earlier Than | Warning
26088 | Lake CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26089 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7740SS | 0 | Start No Earlier Than | Warning
26091 | Lake CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26092 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7743SS | 0 | Start No Earlier Than | Warning
26094 | Lake CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26102 | Lake CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26106 | Lake CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26107 | Lake CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7758 | 1 | Start No Earlier Than | Warning
26110 | Lake CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26111 | Lake CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7762 | 0 | Start No Earlier Than | Warning
26114 | Lake CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26115 | Lake CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7766 | 0 | Start No Earlier Than | Warning
26118 | Lake CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26119 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
26122 | Lake CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 7773SS | 1 | Start No Earlier Than | Warning
26136 | Lake CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7784SF+30d |  | 0 | Start No Earlier Than | Warning
26137 | Lake CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26140 | Lake CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 7791SS | 1 | Start No Earlier Than | Warning
26151 | Lake CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 7795,7802SS | 0.6 | Start No Earlier Than | Warning
26154 | Lake CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
26155 | Lake CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26169 | Lake CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
26172 | Lake CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
26173 | Lake CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
26174 | Lake CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26175 | Lake CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26176 | Lake CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7835 | 0 | Start No Earlier Than | Warning
26177 | Lake CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 7836 | 0 | Start No Earlier Than | Warning
26179 | Lake CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26180 | Lake CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7841SF+30d |  | 0 | Start No Earlier Than | Warning
26181 | Lake CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7842SF+30d |  | 0 | Start No Earlier Than | Warning
26182 | Lake CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7843SF+30d |  | 0 | Start No Earlier Than | Warning
26183 | Lake CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7844SF+30d |  | 0 | Start No Earlier Than | Warning
26184 | Lake CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 7845SF+30d |  | 0 | Start No Earlier Than | Warning
26187 | Lake CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26188 | Lake CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 7847FS+12d | 0 | Start No Earlier Than | Warning
26189 | Lake CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26190 | Lake CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 7847SF+60d | 0 | Start No Earlier Than | Warning
26191 | Lake CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7830SF+30d | 0 | Start No Earlier Than | Warning
26192 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7831SF+30d | 0 | Start No Earlier Than | Warning
26193 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7832SF+30d | 0 | Start No Earlier Than | Warning
26194 | Lake CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7833SF+30d | 0 | Start No Earlier Than | Warning
26195 | Lake CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7834SF+30d | 0 | Start No Earlier Than | Warning
26196 | Lake CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26204 | Lassen CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26205 | Lassen CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
26206 | Lassen CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26207 | Lassen CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26208 | Lassen CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26209 | Lassen CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26231 | Lassen CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26232 | Lassen CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26233 | Lassen CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26234 | Lassen CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26235 | Lassen CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26236 | Lassen CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26237 | Lassen CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26238 | Lassen CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26239 | Lassen CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26240 | Lassen CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26241 | Lassen CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26242 | Lassen CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26243 | Lassen CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26244 | Lassen CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26245 | Lassen CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26252 | Lassen CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
26253 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 7904SS | 0 | Start No Earlier Than | Warning
26257 | Lassen CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26258 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 7909SS | 0 | Start No Earlier Than | Warning
26260 | Lassen CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26261 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 7912SS | 0 | Start No Earlier Than | Warning
26262 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 7911SS |  | 0 | Start No Earlier Than | Warning
26263 | Lassen CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26264 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 7915SS | 0 | Start No Earlier Than | Warning
26266 | Lassen CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26267 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 7918SS | 0 | Start No Earlier Than | Warning
26269 | Lassen CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26277 | Lassen CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26281 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26282 | Lassen CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 7933 | 1 | Start No Earlier Than | Warning
26285 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26286 | Lassen CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 7937 | 0.95 | Start No Earlier Than | Warning
26289 | Lassen CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26290 | Lassen CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 7941 | 0 | Start No Earlier Than | Warning
26293 | Lassen CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26294 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
26311 | Lassen CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7959SF+30d |  | 0 | Start No Earlier Than | Warning
26312 | Lassen CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26337 | Lassen CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
26340 | Lassen CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
26341 | Lassen CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
26342 | Lassen CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26343 | Lassen CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26344 | Lassen CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8003 | 0 | Start No Earlier Than | Warning
26345 | Lassen CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8004 | 0 | Start No Earlier Than | Warning
26347 | Lassen CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26348 | Lassen CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8009SF+30d |  | 0 | Start No Earlier Than | Warning
26349 | Lassen CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8010SF+30d |  | 0 | Start No Earlier Than | Warning
26350 | Lassen CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8011SF+30d |  | 0 | Start No Earlier Than | Warning
26351 | Lassen CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8012SF+30d |  | 0 | Start No Earlier Than | Warning
26352 | Lassen CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8013SF+30d |  | 0 | Start No Earlier Than | Warning
26355 | Lassen CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26356 | Lassen CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8015FS+12d | 0 | Start No Earlier Than | Warning
26357 | Lassen CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26358 | Lassen CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8015SF+60d | 0 | Start No Earlier Than | Warning
26359 | Lassen CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7998SF+30d | 0 | Start No Earlier Than | Warning
26360 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 7999SF+30d | 0 | Start No Earlier Than | Warning
26361 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8000SF+30d | 0 | Start No Earlier Than | Warning
26362 | Lassen CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8001SF+30d | 0 | Start No Earlier Than | Warning
26363 | Lassen CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8002SF+30d | 0 | Start No Earlier Than | Warning
26364 | Lassen CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26372 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26373 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
26374 | Los Angeles CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26375 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26376 | Los Angeles CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26377 | Los Angeles CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26399 | Los Angeles CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26400 | Los Angeles CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26401 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26402 | Los Angeles CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26403 | Los Angeles CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26404 | Los Angeles CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26405 | Los Angeles CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26406 | Los Angeles CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26407 | Los Angeles CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26408 | Los Angeles CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26409 | Los Angeles CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26410 | Los Angeles CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26411 | Los Angeles CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26412 | Los Angeles CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26413 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26420 | Los Angeles CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
26421 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8072SS | 0 | Start No Earlier Than | Warning
26425 | Los Angeles CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26426 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8077SS | 0 | Start No Earlier Than | Warning
26428 | Los Angeles CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26429 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8080SS | 0 | Start No Earlier Than | Warning
26430 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8079SS |  | 0 | Start No Earlier Than | Warning
26431 | Los Angeles CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26432 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8083SS | 0 | Start No Earlier Than | Warning
26434 | Los Angeles CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26435 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8086SS | 0 | Start No Earlier Than | Warning
26437 | Los Angeles CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26445 | Los Angeles CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26449 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26450 | Los Angeles CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8101 | 1 | Start No Earlier Than | Warning
26453 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26454 | Los Angeles CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8105 | 0 | Start No Earlier Than | Warning
26457 | Los Angeles CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26458 | Los Angeles CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8109 | 0 | Start No Earlier Than | Warning
26461 | Los Angeles CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26462 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
26479 | Los Angeles CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8127SF+30d |  | 0 | Start No Earlier Than | Warning
26480 | Los Angeles CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26494 | Los Angeles CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 8138,8145SS | 0.6 | Start No Earlier Than | Warning
26497 | Los Angeles CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
26498 | Los Angeles CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26512 | Los Angeles CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
26515 | Los Angeles CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
26516 | Los Angeles CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
26517 | Los Angeles CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26518 | Los Angeles CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26519 | Los Angeles CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8178 | 0 | Start No Earlier Than | Warning
26520 | Los Angeles CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8179 | 0 | Start No Earlier Than | Warning
26522 | Los Angeles CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26523 | Los Angeles CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8184SF+30d |  | 0 | Start No Earlier Than | Warning
26524 | Los Angeles CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8185SF+30d |  | 0 | Start No Earlier Than | Warning
26525 | Los Angeles CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8186SF+30d |  | 0 | Start No Earlier Than | Warning
26526 | Los Angeles CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8187SF+30d |  | 0 | Start No Earlier Than | Warning
26527 | Los Angeles CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8188SF+30d |  | 0 | Start No Earlier Than | Warning
26530 | Los Angeles CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26531 | Los Angeles CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8190FS+12d | 0 | Start No Earlier Than | Warning
26532 | Los Angeles CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26533 | Los Angeles CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8190SF+60d | 0 | Start No Earlier Than | Warning
26534 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8173SF+30d | 0 | Start No Earlier Than | Warning
26535 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8174SF+30d | 0 | Start No Earlier Than | Warning
26536 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8175SF+30d | 0 | Start No Earlier Than | Warning
26537 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8176SF+30d | 0 | Start No Earlier Than | Warning
26538 | Los Angeles CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8177SF+30d | 0 | Start No Earlier Than | Warning
26539 | Los Angeles CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26547 | Madera CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26548 | Madera CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
26549 | Madera CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26550 | Madera CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26551 | Madera CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26552 | Madera CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26574 | Madera CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26575 | Madera CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26576 | Madera CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26577 | Madera CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26578 | Madera CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26579 | Madera CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26580 | Madera CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26581 | Madera CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26582 | Madera CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26583 | Madera CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26584 | Madera CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26585 | Madera CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26586 | Madera CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26587 | Madera CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26588 | Madera CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26595 | Madera CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
26596 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8247SS | 0 | Start No Earlier Than | Warning
26600 | Madera CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26601 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8252SS | 0 | Start No Earlier Than | Warning
26603 | Madera CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26604 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8255SS | 0 | Start No Earlier Than | Warning
26605 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8254SS |  | 0 | Start No Earlier Than | Warning
26606 | Madera CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26607 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8258SS | 0 | Start No Earlier Than | Warning
26609 | Madera CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26610 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8261SS | 0 | Start No Earlier Than | Warning
26612 | Madera CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26620 | Madera CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26624 | Madera CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26625 | Madera CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8276 | 1 | Start No Earlier Than | Warning
26628 | Madera CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26629 | Madera CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8280 | 0.2 | Start No Earlier Than | Warning
26632 | Madera CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26633 | Madera CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8284 | 0 | Start No Earlier Than | Warning
26636 | Madera CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26637 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
26647 | Madera CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d |  | 8298,8300SS | 1 | Start No Earlier Than | Warning
26653 | Madera CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8301SF+30d |  | 0 | Start No Earlier Than | Warning
26654 | Madera CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26668 | Madera CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 8312,8319SS | 1 | Start No Earlier Than | Warning
26671 | Madera CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
26672 | Madera CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26686 | Madera CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
26688 | Madera CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 8345 | 0.2 | Start No Earlier Than | Warning
26689 | Madera CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
26690 | Madera CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
26691 | Madera CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26692 | Madera CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26693 | Madera CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8352 | 0 | Start No Earlier Than | Warning
26694 | Madera CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8353 | 0 | Start No Earlier Than | Warning
26696 | Madera CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26697 | Madera CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8358SF+30d |  | 0 | Start No Earlier Than | Warning
26698 | Madera CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8359SF+30d |  | 0 | Start No Earlier Than | Warning
26699 | Madera CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8360SF+30d |  | 0 | Start No Earlier Than | Warning
26700 | Madera CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8361SF+30d |  | 0 | Start No Earlier Than | Warning
26701 | Madera CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8362SF+30d |  | 0 | Start No Earlier Than | Warning
26704 | Madera CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26705 | Madera CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8364FS+12d | 0 | Start No Earlier Than | Warning
26706 | Madera CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26707 | Madera CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8364SF+60d | 0 | Start No Earlier Than | Warning
26708 | Madera CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8347SF+30d | 0 | Start No Earlier Than | Warning
26709 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8348SF+30d | 0 | Start No Earlier Than | Warning
26710 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8349SF+30d | 0 | Start No Earlier Than | Warning
26711 | Madera CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8350SF+30d | 0 | Start No Earlier Than | Warning
26712 | Madera CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8351SF+30d | 0 | Start No Earlier Than | Warning
26713 | Madera CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26721 | Marin CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26722 | Marin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
26723 | Marin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26724 | Marin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26725 | Marin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26726 | Marin CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26748 | Marin CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26749 | Marin CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26750 | Marin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26751 | Marin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26752 | Marin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26753 | Marin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26754 | Marin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26755 | Marin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26756 | Marin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26757 | Marin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26758 | Marin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26759 | Marin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26760 | Marin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26761 | Marin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26762 | Marin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26769 | Marin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
26770 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8421SS | 0 | Start No Earlier Than | Warning
26774 | Marin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26775 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8426SS | 0 | Start No Earlier Than | Warning
26777 | Marin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26778 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8429SS | 0 | Start No Earlier Than | Warning
26779 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8428SS |  | 0 | Start No Earlier Than | Warning
26780 | Marin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26781 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8432SS | 0 | Start No Earlier Than | Warning
26783 | Marin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26784 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8435SS | 0 | Start No Earlier Than | Warning
26786 | Marin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26794 | Marin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26798 | Marin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26799 | Marin CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8450 | 1 | Start No Earlier Than | Warning
26802 | Marin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26803 | Marin CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 8454 | 1 | Start No Earlier Than | Warning
26806 | Marin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26807 | Marin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8458 | 0 | Start No Earlier Than | Warning
26810 | Marin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26811 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
26828 | Marin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8476SF+30d |  | 0 | Start No Earlier Than | Warning
26829 | Marin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26843 | Marin CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 8487,8494SS | 1 | Start No Earlier Than | Warning
26846 | Marin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
26847 | Marin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
26861 | Marin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
26863 | Marin CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 8520 | 0.2 | Start No Earlier Than | Warning
26864 | Marin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
26865 | Marin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0.2 | Start No Earlier Than | Warning
26866 | Marin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
26867 | Marin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
26868 | Marin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8527 | 0 | Start No Earlier Than | Warning
26869 | Marin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8528 | 0 | Start No Earlier Than | Warning
26871 | Marin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
26872 | Marin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8533SF+30d |  | 0 | Start No Earlier Than | Warning
26873 | Marin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8534SF+30d |  | 0 | Start No Earlier Than | Warning
26874 | Marin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8535SF+30d |  | 0 | Start No Earlier Than | Warning
26875 | Marin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8536SF+30d |  | 0 | Start No Earlier Than | Warning
26876 | Marin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8537SF+30d |  | 0 | Start No Earlier Than | Warning
26879 | Marin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
26880 | Marin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8539FS+12d | 0 | Start No Earlier Than | Warning
26881 | Marin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
26882 | Marin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8539SF+60d | 0 | Start No Earlier Than | Warning
26883 | Marin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8522SF+30d | 0 | Start No Earlier Than | Warning
26884 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8523SF+30d | 0 | Start No Earlier Than | Warning
26885 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8524SF+30d | 0 | Start No Earlier Than | Warning
26886 | Marin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8525SF+30d | 0 | Start No Earlier Than | Warning
26887 | Marin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8526SF+30d | 0 | Start No Earlier Than | Warning
26888 | Marin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
26896 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
26897 | Mariposa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
26898 | Mariposa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
26899 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
26900 | Mariposa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
26901 | Mariposa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
26923 | Mariposa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26924 | Mariposa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
26925 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
26926 | Mariposa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
26927 | Mariposa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
26928 | Mariposa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
26929 | Mariposa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
26930 | Mariposa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
26931 | Mariposa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
26932 | Mariposa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
26933 | Mariposa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
26934 | Mariposa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
26935 | Mariposa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
26936 | Mariposa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26937 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
26944 | Mariposa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
26945 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8596SS | 0 | Start No Earlier Than | Warning
26949 | Mariposa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
26950 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8601SS | 0 | Start No Earlier Than | Warning
26952 | Mariposa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
26953 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8604SS | 0 | Start No Earlier Than | Warning
26954 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8603SS |  | 0 | Start No Earlier Than | Warning
26955 | Mariposa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
26956 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8607SS | 0 | Start No Earlier Than | Warning
26958 | Mariposa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
26959 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8610SS | 0 | Start No Earlier Than | Warning
26961 | Mariposa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
26969 | Mariposa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26973 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26974 | Mariposa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8625 | 1 | Start No Earlier Than | Warning
26977 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26978 | Mariposa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 8629 | 1 | Start No Earlier Than | Warning
26981 | Mariposa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26982 | Mariposa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8633 | 0 | Start No Earlier Than | Warning
26985 | Mariposa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
26986 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27003 | Mariposa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8651SF+30d |  | 0 | Start No Earlier Than | Warning
27004 | Mariposa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27018 | Mariposa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 8662,8669SS | 1 | Start No Earlier Than | Warning
27021 | Mariposa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
27022 | Mariposa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27036 | Mariposa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27038 | Mariposa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 8695 | 0.2 | Start No Earlier Than | Warning
27039 | Mariposa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
27040 | Mariposa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27041 | Mariposa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27042 | Mariposa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27043 | Mariposa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8702 | 0 | Start No Earlier Than | Warning
27044 | Mariposa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8703 | 0 | Start No Earlier Than | Warning
27046 | Mariposa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27047 | Mariposa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8708SF+30d |  | 0 | Start No Earlier Than | Warning
27048 | Mariposa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8709SF+30d |  | 0 | Start No Earlier Than | Warning
27049 | Mariposa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8710SF+30d |  | 0 | Start No Earlier Than | Warning
27050 | Mariposa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8711SF+30d |  | 0 | Start No Earlier Than | Warning
27051 | Mariposa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8712SF+30d |  | 0 | Start No Earlier Than | Warning
27054 | Mariposa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27055 | Mariposa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8714FS+12d | 0 | Start No Earlier Than | Warning
27056 | Mariposa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27057 | Mariposa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8714SF+60d | 0 | Start No Earlier Than | Warning
27058 | Mariposa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8697SF+30d | 0 | Start No Earlier Than | Warning
27059 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8698SF+30d | 0 | Start No Earlier Than | Warning
27060 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8699SF+30d | 0 | Start No Earlier Than | Warning
27061 | Mariposa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8700SF+30d | 0 | Start No Earlier Than | Warning
27062 | Mariposa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8701SF+30d | 0 | Start No Earlier Than | Warning
27063 | Mariposa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27071 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27072 | Mendocino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
27073 | Mendocino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27074 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27075 | Mendocino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27076 | Mendocino CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27098 | Mendocino CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27099 | Mendocino CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27100 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
27101 | Mendocino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27102 | Mendocino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27103 | Mendocino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27104 | Mendocino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27105 | Mendocino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27106 | Mendocino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27107 | Mendocino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27108 | Mendocino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27109 | Mendocino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27110 | Mendocino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27111 | Mendocino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27112 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27119 | Mendocino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
27120 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8771SS | 0 | Start No Earlier Than | Warning
27124 | Mendocino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27125 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8776SS | 0 | Start No Earlier Than | Warning
27127 | Mendocino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27128 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8779SS | 0 | Start No Earlier Than | Warning
27129 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8778SS |  | 0 | Start No Earlier Than | Warning
27130 | Mendocino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27131 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8782SS | 0 | Start No Earlier Than | Warning
27133 | Mendocino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27134 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8785SS | 0 | Start No Earlier Than | Warning
27136 | Mendocino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27144 | Mendocino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27148 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27149 | Mendocino CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8800 | 1 | Start No Earlier Than | Warning
27152 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27153 | Mendocino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 8804 | 0 | Start No Earlier Than | Warning
27156 | Mendocino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27157 | Mendocino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 8808 | 0 | Start No Earlier Than | Warning
27160 | Mendocino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27161 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27164 | Mendocino CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 357d |  | 8815SS | 0 | Start No Earlier Than | Warning
27178 | Mendocino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8826SF+30d |  | 0 | Start No Earlier Than | Warning
27179 | Mendocino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27182 | Mendocino CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 445d |  | 8833SS | 0 | Start No Earlier Than | Warning
27193 | Mendocino CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 298d |  | 8837,8844SS | 0 | Start No Earlier Than | Warning
27196 | Mendocino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
27197 | Mendocino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27211 | Mendocino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27213 | Mendocino CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 8870 | 0.2 | Start No Earlier Than | Warning
27214 | Mendocino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
27215 | Mendocino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27216 | Mendocino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27217 | Mendocino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27218 | Mendocino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8877 | 0 | Start No Earlier Than | Warning
27219 | Mendocino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 8878 | 0 | Start No Earlier Than | Warning
27221 | Mendocino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27222 | Mendocino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8883SF+30d |  | 0 | Start No Earlier Than | Warning
27223 | Mendocino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8884SF+30d |  | 0 | Start No Earlier Than | Warning
27224 | Mendocino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8885SF+30d |  | 0 | Start No Earlier Than | Warning
27225 | Mendocino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8886SF+30d |  | 0 | Start No Earlier Than | Warning
27226 | Mendocino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 8887SF+30d |  | 0 | Start No Earlier Than | Warning
27229 | Mendocino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27230 | Mendocino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 8889FS+12d | 0 | Start No Earlier Than | Warning
27231 | Mendocino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27232 | Mendocino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 8889SF+60d | 0 | Start No Earlier Than | Warning
27233 | Mendocino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8872SF+30d | 0 | Start No Earlier Than | Warning
27234 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8873SF+30d | 0 | Start No Earlier Than | Warning
27235 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8874SF+30d | 0 | Start No Earlier Than | Warning
27236 | Mendocino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8875SF+30d | 0 | Start No Earlier Than | Warning
27237 | Mendocino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 8876SF+30d | 0 | Start No Earlier Than | Warning
27238 | Mendocino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27246 | Merced CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27247 | Merced CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
27248 | Merced CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27249 | Merced CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27250 | Merced CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27251 | Merced CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27273 | Merced CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27274 | Merced CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27275 | Merced CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
27276 | Merced CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27277 | Merced CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27278 | Merced CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27279 | Merced CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27280 | Merced CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27281 | Merced CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27282 | Merced CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27283 | Merced CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27284 | Merced CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27285 | Merced CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27286 | Merced CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27287 | Merced CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27294 | Merced CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
27295 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 8946SS | 0 | Start No Earlier Than | Warning
27299 | Merced CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27300 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 8951SS | 0 | Start No Earlier Than | Warning
27302 | Merced CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27303 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 8954SS | 0 | Start No Earlier Than | Warning
27304 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 8953SS |  | 0 | Start No Earlier Than | Warning
27305 | Merced CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27306 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 8957SS | 0 | Start No Earlier Than | Warning
27308 | Merced CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27309 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 8960SS | 0 | Start No Earlier Than | Warning
27311 | Merced CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27319 | Merced CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27323 | Merced CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27324 | Merced CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 8975 | 1 | Start No Earlier Than | Warning
27327 | Merced CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27328 | Merced CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 8979 | 1 | Start No Earlier Than | Warning
27331 | Merced CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27332 | Merced CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 0d |  | 8983 | 1 | Start No Earlier Than | Warning
27335 | Merced CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27336 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27353 | Merced CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9001SF+30d |  | 0 | Start No Earlier Than | Warning
27354 | Merced CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27368 | Merced CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 9012,9019SS | 1 | Start No Earlier Than | Warning
27371 | Merced CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
27372 | Merced CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27386 | Merced CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27388 | Merced CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 9045 | 0.2 | Start No Earlier Than | Warning
27389 | Merced CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
27390 | Merced CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27391 | Merced CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27392 | Merced CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27393 | Merced CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9052 | 0 | Start No Earlier Than | Warning
27394 | Merced CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9053 | 0 | Start No Earlier Than | Warning
27396 | Merced CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27397 | Merced CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9058SF+30d |  | 0 | Start No Earlier Than | Warning
27398 | Merced CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9059SF+30d |  | 0 | Start No Earlier Than | Warning
27399 | Merced CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9060SF+30d |  | 0 | Start No Earlier Than | Warning
27400 | Merced CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9061SF+30d |  | 0 | Start No Earlier Than | Warning
27401 | Merced CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9062SF+30d |  | 0 | Start No Earlier Than | Warning
27404 | Merced CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27405 | Merced CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9064FS+12d | 0 | Start No Earlier Than | Warning
27406 | Merced CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27407 | Merced CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9064SF+60d | 0 | Start No Earlier Than | Warning
27408 | Merced CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9047SF+30d | 0 | Start No Earlier Than | Warning
27409 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9048SF+30d | 0 | Start No Earlier Than | Warning
27410 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9049SF+30d | 0 | Start No Earlier Than | Warning
27411 | Merced CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9050SF+30d | 0 | Start No Earlier Than | Warning
27412 | Merced CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9051SF+30d | 0 | Start No Earlier Than | Warning
27413 | Merced CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27421 | Modoc CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27422 | Modoc CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
27423 | Modoc CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27424 | Modoc CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27425 | Modoc CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27426 | Modoc CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27448 | Modoc CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27449 | Modoc CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27450 | Modoc CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
27451 | Modoc CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27452 | Modoc CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27453 | Modoc CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27454 | Modoc CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27455 | Modoc CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27456 | Modoc CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27457 | Modoc CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27458 | Modoc CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27459 | Modoc CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27460 | Modoc CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27461 | Modoc CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27462 | Modoc CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27469 | Modoc CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
27470 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9121SS | 0 | Start No Earlier Than | Warning
27474 | Modoc CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27475 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9126SS | 0 | Start No Earlier Than | Warning
27477 | Modoc CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27478 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9129SS | 0 | Start No Earlier Than | Warning
27479 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9128SS |  | 0 | Start No Earlier Than | Warning
27480 | Modoc CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27481 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9132SS | 0 | Start No Earlier Than | Warning
27483 | Modoc CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27484 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9135SS | 0 | Start No Earlier Than | Warning
27486 | Modoc CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27494 | Modoc CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27498 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27499 | Modoc CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 9150 | 1 | Start No Earlier Than | Warning
27502 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27503 | Modoc CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9154 | 0.8 | Start No Earlier Than | Warning
27506 | Modoc CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27507 | Modoc CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9158 | 0 | Start No Earlier Than | Warning
27510 | Modoc CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27511 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27520 | Modoc CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 64 | 299d |  |  | 0 | Start No Earlier Than | Warning
27521 | Modoc CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | Start No Earlier Than | Warning
27522 | Modoc CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27523 | Modoc CW-POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0.8 | Start No Earlier Than | Warning
27542 | Modoc CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27545 | Modoc CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
27546 | Modoc CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27547 | Modoc CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27548 | Modoc CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27549 | Modoc CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9208 | 0 | Start No Earlier Than | Warning
27550 | Modoc CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9209 | 0 | Start No Earlier Than | Warning
27552 | Modoc CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27553 | Modoc CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9214SF+30d |  | 0 | Start No Earlier Than | Warning
27554 | Modoc CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9215SF+30d |  | 0 | Start No Earlier Than | Warning
27555 | Modoc CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9216SF+30d |  | 0 | Start No Earlier Than | Warning
27556 | Modoc CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9217SF+30d |  | 0 | Start No Earlier Than | Warning
27557 | Modoc CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9218SF+30d |  | 0 | Start No Earlier Than | Warning
27560 | Modoc CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27561 | Modoc CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9220FS+12d | 0 | Start No Earlier Than | Warning
27562 | Modoc CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27563 | Modoc CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9220SF+60d | 0 | Start No Earlier Than | Warning
27564 | Modoc CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9203SF+30d | 0 | Start No Earlier Than | Warning
27565 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9204SF+30d | 0 | Start No Earlier Than | Warning
27566 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9205SF+30d | 0 | Start No Earlier Than | Warning
27567 | Modoc CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9206SF+30d | 0 | Start No Earlier Than | Warning
27568 | Modoc CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9207SF+30d | 0 | Start No Earlier Than | Warning
27569 | Modoc CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27577 | Mono CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27578 | Mono CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
27579 | Mono CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27580 | Mono CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27581 | Mono CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27582 | Mono CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27604 | Mono CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27605 | Mono CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27606 | Mono CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
27607 | Mono CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27608 | Mono CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27609 | Mono CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27610 | Mono CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27611 | Mono CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27612 | Mono CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27613 | Mono CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27614 | Mono CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27615 | Mono CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27616 | Mono CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27617 | Mono CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27618 | Mono CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27625 | Mono CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
27626 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9277SS | 0 | Start No Earlier Than | Warning
27630 | Mono CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27631 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9282SS | 0 | Start No Earlier Than | Warning
27633 | Mono CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27634 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9285SS | 0 | Start No Earlier Than | Warning
27635 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9284SS |  | 0 | Start No Earlier Than | Warning
27636 | Mono CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27637 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9288SS | 0 | Start No Earlier Than | Warning
27639 | Mono CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27640 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9291SS | 0 | Start No Earlier Than | Warning
27642 | Mono CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27650 | Mono CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27654 | Mono CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27655 | Mono CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 9306 | 1 | Start No Earlier Than | Warning
27658 | Mono CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27659 | Mono CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 9310 | 1 | Start No Earlier Than | Warning
27662 | Mono CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27663 | Mono CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9314 | 0 | Start No Earlier Than | Warning
27666 | Mono CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27667 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27684 | Mono CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9332SF+30d |  | 0 | Start No Earlier Than | Warning
27685 | Mono CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27695 | Mono CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 9339,9346SS | 1 | Start No Earlier Than | Warning
27698 | Mono CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
27699 | Mono CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27713 | Mono CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27715 | Mono CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 9372 | 0.2 | Start No Earlier Than | Warning
27716 | Mono CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
27717 | Mono CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27718 | Mono CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27719 | Mono CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27720 | Mono CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9379 | 0 | Start No Earlier Than | Warning
27721 | Mono CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9380 | 0 | Start No Earlier Than | Warning
27723 | Mono CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27724 | Mono CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9385SF+30d |  | 0 | Start No Earlier Than | Warning
27725 | Mono CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9386SF+30d |  | 0 | Start No Earlier Than | Warning
27726 | Mono CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9387SF+30d |  | 0 | Start No Earlier Than | Warning
27727 | Mono CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9388SF+30d |  | 0 | Start No Earlier Than | Warning
27728 | Mono CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9389SF+30d |  | 0 | Start No Earlier Than | Warning
27731 | Mono CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27732 | Mono CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9391FS+12d | 0 | Start No Earlier Than | Warning
27733 | Mono CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27734 | Mono CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9391SF+60d | 0 | Start No Earlier Than | Warning
27735 | Mono CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9374SF+30d | 0 | Start No Earlier Than | Warning
27736 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9375SF+30d | 0 | Start No Earlier Than | Warning
27737 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9376SF+30d | 0 | Start No Earlier Than | Warning
27738 | Mono CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9377SF+30d | 0 | Start No Earlier Than | Warning
27739 | Mono CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9378SF+30d | 0 | Start No Earlier Than | Warning
27740 | Mono CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27748 | Monterey CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27749 | Monterey CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
27750 | Monterey CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27751 | Monterey CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27752 | Monterey CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27753 | Monterey CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27775 | Monterey CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27776 | Monterey CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27777 | Monterey CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
27778 | Monterey CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27779 | Monterey CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27780 | Monterey CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27781 | Monterey CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27782 | Monterey CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27783 | Monterey CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27784 | Monterey CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27785 | Monterey CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27786 | Monterey CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27787 | Monterey CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27788 | Monterey CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27789 | Monterey CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27796 | Monterey CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | Start No Earlier Than | Warning
27797 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9448SS | 0 | Start No Earlier Than | Warning
27801 | Monterey CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27802 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9453SS | 0 | Start No Earlier Than | Warning
27804 | Monterey CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27805 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9456SS | 0 | Start No Earlier Than | Warning
27806 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9455SS |  | 0 | Start No Earlier Than | Warning
27807 | Monterey CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27808 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9459SS | 0 | Start No Earlier Than | Warning
27810 | Monterey CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27811 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9462SS | 0 | Start No Earlier Than | Warning
27813 | Monterey CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27821 | Monterey CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27825 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27826 | Monterey CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 9477 | 1 | Start No Earlier Than | Warning
27829 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27830 | Monterey CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 9481 | 1 | Start No Earlier Than | Warning
27833 | Monterey CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27834 | Monterey CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9485 | 0 | Start No Earlier Than | Warning
27837 | Monterey CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
27838 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
27855 | Monterey CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9503SF+30d |  | 0 | Start No Earlier Than | Warning
27856 | Monterey CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27870 | Monterey CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 9514,9521SS | 1 | Start No Earlier Than | Warning
27873 | Monterey CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
27874 | Monterey CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
27888 | Monterey CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
27891 | Monterey CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
27892 | Monterey CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
27893 | Monterey CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
27894 | Monterey CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
27895 | Monterey CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9554 | 0 | Start No Earlier Than | Warning
27896 | Monterey CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9555 | 0 | Start No Earlier Than | Warning
27898 | Monterey CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
27899 | Monterey CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9560SF+30d |  | 0 | Start No Earlier Than | Warning
27900 | Monterey CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9561SF+30d |  | 0 | Start No Earlier Than | Warning
27901 | Monterey CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9562SF+30d |  | 0 | Start No Earlier Than | Warning
27902 | Monterey CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9563SF+30d |  | 0 | Start No Earlier Than | Warning
27903 | Monterey CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9564SF+30d |  | 0 | Start No Earlier Than | Warning
27906 | Monterey CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
27907 | Monterey CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9566FS+12d | 0 | Start No Earlier Than | Warning
27908 | Monterey CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
27909 | Monterey CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9566SF+60d | 0 | Start No Earlier Than | Warning
27910 | Monterey CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9549SF+30d | 0 | Start No Earlier Than | Warning
27911 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9550SF+30d | 0 | Start No Earlier Than | Warning
27912 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9551SF+30d | 0 | Start No Earlier Than | Warning
27913 | Monterey CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9552SF+30d | 0 | Start No Earlier Than | Warning
27914 | Monterey CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9553SF+30d | 0 | Start No Earlier Than | Warning
27915 | Monterey CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
27923 | Napa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
27924 | Napa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.6 | Start No Earlier Than | Warning
27925 | Napa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
27926 | Napa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
27927 | Napa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
27928 | Napa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
27950 | Napa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27951 | Napa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
27952 | Napa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
27953 | Napa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
27954 | Napa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
27955 | Napa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
27956 | Napa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
27957 | Napa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
27958 | Napa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
27959 | Napa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
27960 | Napa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
27961 | Napa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
27962 | Napa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
27963 | Napa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27964 | Napa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
27971 | Napa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
27972 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9623SS | 0 | Start No Earlier Than | Warning
27976 | Napa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
27977 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9628SS | 0 | Start No Earlier Than | Warning
27979 | Napa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
27980 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9631SS | 0 | Start No Earlier Than | Warning
27981 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9630SS |  | 0 | Start No Earlier Than | Warning
27982 | Napa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
27983 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9634SS | 0 | Start No Earlier Than | Warning
27985 | Napa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
27986 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9637SS | 0 | Start No Earlier Than | Warning
27988 | Napa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
27996 | Napa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28000 | Napa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28001 | Napa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 9652 | 1 | Start No Earlier Than | Warning
28004 | Napa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28005 | Napa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9656 | 0 | Start No Earlier Than | Warning
28008 | Napa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28009 | Napa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9660 | 0 | Start No Earlier Than | Warning
28012 | Napa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28013 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28016 | Napa CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 9667SS | 1 | Start No Earlier Than | Warning
28030 | Napa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9678SF+30d |  | 0 | Start No Earlier Than | Warning
28031 | Napa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28034 | Napa CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 9685SS | 1 | Start No Earlier Than | Warning
28045 | Napa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 9689,9696SS | 1 | Start No Earlier Than | Warning
28048 | Napa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
28049 | Napa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28063 | Napa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28066 | Napa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28067 | Napa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28068 | Napa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28069 | Napa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28070 | Napa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9729 | 0 | Start No Earlier Than | Warning
28071 | Napa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9730 | 0 | Start No Earlier Than | Warning
28073 | Napa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28074 | Napa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9735SF+30d |  | 0 | Start No Earlier Than | Warning
28075 | Napa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9736SF+30d |  | 0 | Start No Earlier Than | Warning
28076 | Napa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9737SF+30d |  | 0 | Start No Earlier Than | Warning
28077 | Napa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9738SF+30d |  | 0 | Start No Earlier Than | Warning
28078 | Napa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9739SF+30d |  | 0 | Start No Earlier Than | Warning
28081 | Napa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28082 | Napa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9741FS+12d | 0 | Start No Earlier Than | Warning
28083 | Napa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28084 | Napa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9741SF+60d | 0 | Start No Earlier Than | Warning
28085 | Napa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9724SF+30d | 0 | Start No Earlier Than | Warning
28086 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9725SF+30d | 0 | Start No Earlier Than | Warning
28087 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9726SF+30d | 0 | Start No Earlier Than | Warning
28088 | Napa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9727SF+30d | 0 | Start No Earlier Than | Warning
28089 | Napa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9728SF+30d | 0 | Start No Earlier Than | Warning
28090 | Napa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28098 | Nevada CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28099 | Nevada CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28100 | Nevada CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28101 | Nevada CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28102 | Nevada CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28103 | Nevada CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
28125 | Nevada CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28126 | Nevada CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28127 | Nevada CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
28128 | Nevada CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
28129 | Nevada CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
28130 | Nevada CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
28131 | Nevada CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
28132 | Nevada CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
28133 | Nevada CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
28134 | Nevada CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
28135 | Nevada CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
28136 | Nevada CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
28137 | Nevada CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
28138 | Nevada CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28139 | Nevada CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
28146 | Nevada CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
28147 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9798SS | 0 | Start No Earlier Than | Warning
28151 | Nevada CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
28152 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9803SS | 0 | Start No Earlier Than | Warning
28154 | Nevada CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
28155 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9806SS | 0 | Start No Earlier Than | Warning
28156 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9805SS |  | 0 | Start No Earlier Than | Warning
28157 | Nevada CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
28158 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9809SS | 0 | Start No Earlier Than | Warning
28160 | Nevada CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28161 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9812SS | 0 | Start No Earlier Than | Warning
28163 | Nevada CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
28171 | Nevada CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28175 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28176 | Nevada CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 9827 | 1 | Start No Earlier Than | Warning
28179 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28180 | Nevada CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 9831 | 0.2 | Start No Earlier Than | Warning
28183 | Nevada CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28184 | Nevada CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 9835 | 0 | Start No Earlier Than | Warning
28187 | Nevada CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28188 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28191 | Nevada CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 9842SS | 1 | Start No Earlier Than | Warning
28205 | Nevada CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9853SF+30d |  | 0 | Start No Earlier Than | Warning
28206 | Nevada CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28220 | Nevada CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 9864,9871SS | 1 | Start No Earlier Than | Warning
28223 | Nevada CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
28224 | Nevada CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28238 | Nevada CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28241 | Nevada CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28242 | Nevada CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28243 | Nevada CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28244 | Nevada CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28245 | Nevada CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9904 | 0 | Start No Earlier Than | Warning
28246 | Nevada CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 9905 | 0 | Start No Earlier Than | Warning
28248 | Nevada CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28249 | Nevada CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9910SF+30d |  | 0 | Start No Earlier Than | Warning
28250 | Nevada CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9911SF+30d |  | 0 | Start No Earlier Than | Warning
28251 | Nevada CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9912SF+30d |  | 0 | Start No Earlier Than | Warning
28252 | Nevada CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9913SF+30d |  | 0 | Start No Earlier Than | Warning
28253 | Nevada CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 9914SF+30d |  | 0 | Start No Earlier Than | Warning
28256 | Nevada CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28257 | Nevada CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 9916FS+12d | 0 | Start No Earlier Than | Warning
28258 | Nevada CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28259 | Nevada CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 9916SF+60d | 0 | Start No Earlier Than | Warning
28260 | Nevada CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9899SF+30d | 0 | Start No Earlier Than | Warning
28261 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9900SF+30d | 0 | Start No Earlier Than | Warning
28262 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9901SF+30d | 0 | Start No Earlier Than | Warning
28263 | Nevada CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9902SF+30d | 0 | Start No Earlier Than | Warning
28264 | Nevada CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 9903SF+30d | 0 | Start No Earlier Than | Warning
28265 | Nevada CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28273 | Orange CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28274 | Orange CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28275 | Orange CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28276 | Orange CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28277 | Orange CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28278 | Orange CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
28300 | Orange CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28301 | Orange CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28302 | Orange CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
28303 | Orange CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
28304 | Orange CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
28305 | Orange CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
28306 | Orange CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
28307 | Orange CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
28308 | Orange CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
28309 | Orange CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
28310 | Orange CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
28311 | Orange CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
28312 | Orange CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
28313 | Orange CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28314 | Orange CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
28321 | Orange CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
28322 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 9973SS | 0 | Start No Earlier Than | Warning
28326 | Orange CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
28327 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 9978SS | 0 | Start No Earlier Than | Warning
28329 | Orange CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
28330 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 9981SS | 0 | Start No Earlier Than | Warning
28331 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 9980SS |  | 0 | Start No Earlier Than | Warning
28332 | Orange CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
28333 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 9984SS | 0 | Start No Earlier Than | Warning
28335 | Orange CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28336 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 9987SS | 0 | Start No Earlier Than | Warning
28338 | Orange CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
28346 | Orange CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28350 | Orange CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28351 | Orange CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10002 | 1 | Start No Earlier Than | Warning
28354 | Orange CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28355 | Orange CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10006 | 0.2 | Start No Earlier Than | Warning
28358 | Orange CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28359 | Orange CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10010 | 0 | Start No Earlier Than | Warning
28362 | Orange CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28363 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28380 | Orange CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10028SF+30d |  | 0 | Start No Earlier Than | Warning
28381 | Orange CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28395 | Orange CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 10039,10046SS | 1 | Start No Earlier Than | Warning
28398 | Orange CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
28399 | Orange CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28413 | Orange CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28416 | Orange CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28417 | Orange CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28418 | Orange CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28419 | Orange CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28420 | Orange CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10079 | 0 | Start No Earlier Than | Warning
28421 | Orange CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10080 | 0 | Start No Earlier Than | Warning
28423 | Orange CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28424 | Orange CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10085SF+30d |  | 0 | Start No Earlier Than | Warning
28425 | Orange CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10086SF+30d |  | 0 | Start No Earlier Than | Warning
28426 | Orange CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10087SF+30d |  | 0 | Start No Earlier Than | Warning
28427 | Orange CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10088SF+30d |  | 0 | Start No Earlier Than | Warning
28428 | Orange CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10089SF+30d |  | 0 | Start No Earlier Than | Warning
28431 | Orange CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28432 | Orange CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10091FS+12d | 0 | Start No Earlier Than | Warning
28433 | Orange CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28434 | Orange CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10091SF+60d | 0 | Start No Earlier Than | Warning
28435 | Orange CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10074SF+30d | 0 | Start No Earlier Than | Warning
28436 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10075SF+30d | 0 | Start No Earlier Than | Warning
28437 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10076SF+30d | 0 | Start No Earlier Than | Warning
28438 | Orange CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10077SF+30d | 0 | Start No Earlier Than | Warning
28439 | Orange CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10078SF+30d | 0 | Start No Earlier Than | Warning
28440 | Orange CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28448 | Placer CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28449 | Placer CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28450 | Placer CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28451 | Placer CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28452 | Placer CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28453 | Placer CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
28475 | Placer CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28476 | Placer CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28477 | Placer CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
28478 | Placer CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
28479 | Placer CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
28480 | Placer CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
28481 | Placer CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
28482 | Placer CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
28483 | Placer CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
28484 | Placer CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
28485 | Placer CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
28486 | Placer CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
28487 | Placer CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
28488 | Placer CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28489 | Placer CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
28496 | Placer CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
28497 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10148SS | 0 | Start No Earlier Than | Warning
28501 | Placer CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
28502 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10153SS | 0 | Start No Earlier Than | Warning
28504 | Placer CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
28505 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10156SS | 0 | Start No Earlier Than | Warning
28506 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10155SS |  | 0 | Start No Earlier Than | Warning
28507 | Placer CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
28508 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10159SS | 0 | Start No Earlier Than | Warning
28510 | Placer CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28511 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10162SS | 0 | Start No Earlier Than | Warning
28513 | Placer CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
28521 | Placer CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28525 | Placer CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28526 | Placer CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10177 | 1 | Start No Earlier Than | Warning
28529 | Placer CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28530 | Placer CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10181 | 0.2 | Start No Earlier Than | Warning
28533 | Placer CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28534 | Placer CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10185 | 0 | Start No Earlier Than | Warning
28537 | Placer CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28538 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28555 | Placer CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10203SF+30d |  | 0 | Start No Earlier Than | Warning
28556 | Placer CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28570 | Placer CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 10214,10221SS | 1 | Start No Earlier Than | Warning
28573 | Placer CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
28574 | Placer CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28588 | Placer CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28591 | Placer CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28592 | Placer CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28593 | Placer CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28594 | Placer CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28595 | Placer CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10254 | 0 | Start No Earlier Than | Warning
28596 | Placer CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10255 | 0 | Start No Earlier Than | Warning
28598 | Placer CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28599 | Placer CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10260SF+30d |  | 0 | Start No Earlier Than | Warning
28600 | Placer CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10261SF+30d |  | 0 | Start No Earlier Than | Warning
28601 | Placer CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10262SF+30d |  | 0 | Start No Earlier Than | Warning
28602 | Placer CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10263SF+30d |  | 0 | Start No Earlier Than | Warning
28603 | Placer CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10264SF+30d |  | 0 | Start No Earlier Than | Warning
28606 | Placer CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28607 | Placer CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10266FS+12d | 0 | Start No Earlier Than | Warning
28608 | Placer CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28609 | Placer CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10266SF+60d | 0 | Start No Earlier Than | Warning
28610 | Placer CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10249SF+30d | 0 | Start No Earlier Than | Warning
28611 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10250SF+30d | 0 | Start No Earlier Than | Warning
28612 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10251SF+30d | 0 | Start No Earlier Than | Warning
28613 | Placer CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10252SF+30d | 0 | Start No Earlier Than | Warning
28614 | Placer CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10253SF+30d | 0 | Start No Earlier Than | Warning
28615 | Placer CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28623 | Plumas CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28624 | Plumas CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28625 | Plumas CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28626 | Plumas CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28627 | Plumas CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28628 | Plumas CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
28650 | Plumas CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28651 | Plumas CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28652 | Plumas CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
28653 | Plumas CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
28654 | Plumas CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
28655 | Plumas CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
28656 | Plumas CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
28657 | Plumas CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
28658 | Plumas CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
28659 | Plumas CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
28660 | Plumas CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
28661 | Plumas CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
28662 | Plumas CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
28663 | Plumas CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28664 | Plumas CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
28671 | Plumas CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
28672 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10323SS | 0 | Start No Earlier Than | Warning
28676 | Plumas CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
28677 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10328SS | 0 | Start No Earlier Than | Warning
28679 | Plumas CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
28680 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10331SS | 0 | Start No Earlier Than | Warning
28681 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10330SS |  | 0 | Start No Earlier Than | Warning
28682 | Plumas CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
28683 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10334SS | 0 | Start No Earlier Than | Warning
28685 | Plumas CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28686 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10337SS | 0 | Start No Earlier Than | Warning
28688 | Plumas CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
28696 | Plumas CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28700 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28701 | Plumas CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10352 | 1 | Start No Earlier Than | Warning
28704 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28705 | Plumas CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 10356 | 1 | Start No Earlier Than | Warning
28708 | Plumas CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28709 | Plumas CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10360 | 0 | Start No Earlier Than | Warning
28712 | Plumas CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28713 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28730 | Plumas CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10378SF+30d |  | 0 | Start No Earlier Than | Warning
28731 | Plumas CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28745 | Plumas CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 10389,10396SS | 1 | Start No Earlier Than | Warning
28748 | Plumas CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
28749 | Plumas CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28763 | Plumas CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28765 | Plumas CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 10422 | 0.2 | Start No Earlier Than | Warning
28766 | Plumas CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28767 | Plumas CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28768 | Plumas CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28769 | Plumas CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28770 | Plumas CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10429 | 0 | Start No Earlier Than | Warning
28771 | Plumas CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10430 | 0 | Start No Earlier Than | Warning
28773 | Plumas CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28774 | Plumas CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10435SF+30d |  | 0 | Start No Earlier Than | Warning
28775 | Plumas CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10436SF+30d |  | 0 | Start No Earlier Than | Warning
28776 | Plumas CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10437SF+30d |  | 0 | Start No Earlier Than | Warning
28777 | Plumas CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10438SF+30d |  | 0 | Start No Earlier Than | Warning
28778 | Plumas CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10439SF+30d |  | 0 | Start No Earlier Than | Warning
28781 | Plumas CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28782 | Plumas CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10441FS+12d | 0 | Start No Earlier Than | Warning
28783 | Plumas CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28784 | Plumas CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10441SF+60d | 0 | Start No Earlier Than | Warning
28785 | Plumas CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10424SF+30d | 0 | Start No Earlier Than | Warning
28786 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10425SF+30d | 0 | Start No Earlier Than | Warning
28787 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10426SF+30d | 0 | Start No Earlier Than | Warning
28788 | Plumas CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10427SF+30d | 0 | Start No Earlier Than | Warning
28789 | Plumas CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10428SF+30d | 0 | Start No Earlier Than | Warning
28790 | Plumas CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28798 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28799 | Sacramento CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28800 | Sacramento CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28801 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28802 | Sacramento CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28803 | Sacramento CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
28825 | Sacramento CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28826 | Sacramento CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
28827 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
28828 | Sacramento CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
28829 | Sacramento CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
28830 | Sacramento CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
28831 | Sacramento CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
28832 | Sacramento CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
28833 | Sacramento CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
28834 | Sacramento CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
28835 | Sacramento CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
28836 | Sacramento CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
28837 | Sacramento CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
28838 | Sacramento CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28839 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
28846 | Sacramento CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
28847 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10498SS | 0 | Start No Earlier Than | Warning
28851 | Sacramento CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
28852 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10503SS | 0 | Start No Earlier Than | Warning
28854 | Sacramento CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
28855 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10506SS | 0 | Start No Earlier Than | Warning
28856 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10505SS |  | 0 | Start No Earlier Than | Warning
28857 | Sacramento CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
28858 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10509SS | 0 | Start No Earlier Than | Warning
28860 | Sacramento CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
28861 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10512SS | 0 | Start No Earlier Than | Warning
28863 | Sacramento CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
28871 | Sacramento CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28875 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28876 | Sacramento CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10527 | 1 | Start No Earlier Than | Warning
28879 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28880 | Sacramento CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 10531 | 1 | Start No Earlier Than | Warning
28883 | Sacramento CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28884 | Sacramento CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10535 | 0 | Start No Earlier Than | Warning
28887 | Sacramento CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
28888 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
28891 | Sacramento CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 10542SS | 1 | Start No Earlier Than | Warning
28905 | Sacramento CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10553SF+30d |  | 0 | Start No Earlier Than | Warning
28906 | Sacramento CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28920 | Sacramento CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 10564,10571SS | 1 | Start No Earlier Than | Warning
28923 | Sacramento CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
28924 | Sacramento CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
28938 | Sacramento CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
28941 | Sacramento CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
28942 | Sacramento CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
28943 | Sacramento CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
28944 | Sacramento CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
28945 | Sacramento CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10604 | 0 | Start No Earlier Than | Warning
28946 | Sacramento CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10605 | 0 | Start No Earlier Than | Warning
28948 | Sacramento CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
28949 | Sacramento CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10610SF+30d |  | 0 | Start No Earlier Than | Warning
28950 | Sacramento CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10611SF+30d |  | 0 | Start No Earlier Than | Warning
28951 | Sacramento CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10612SF+30d |  | 0 | Start No Earlier Than | Warning
28952 | Sacramento CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10613SF+30d |  | 0 | Start No Earlier Than | Warning
28953 | Sacramento CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10614SF+30d |  | 0 | Start No Earlier Than | Warning
28956 | Sacramento CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
28957 | Sacramento CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10616FS+12d | 0 | Start No Earlier Than | Warning
28958 | Sacramento CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
28959 | Sacramento CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10616SF+60d | 0 | Start No Earlier Than | Warning
28960 | Sacramento CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10599SF+30d | 0 | Start No Earlier Than | Warning
28961 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10600SF+30d | 0 | Start No Earlier Than | Warning
28962 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10601SF+30d | 0 | Start No Earlier Than | Warning
28963 | Sacramento CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10602SF+30d | 0 | Start No Earlier Than | Warning
28964 | Sacramento CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10603SF+30d | 0 | Start No Earlier Than | Warning
28965 | Sacramento CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
28973 | San Benito CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
28974 | San Benito CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
28975 | San Benito CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
28976 | San Benito CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
28977 | San Benito CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
28978 | San Benito CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29000 | San Benito CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29001 | San Benito CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29002 | San Benito CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29003 | San Benito CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29004 | San Benito CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29005 | San Benito CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29006 | San Benito CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29007 | San Benito CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29008 | San Benito CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29009 | San Benito CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29010 | San Benito CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29011 | San Benito CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29012 | San Benito CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29013 | San Benito CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29014 | San Benito CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29021 | San Benito CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29022 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10673SS | 0 | Start No Earlier Than | Warning
29026 | San Benito CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29027 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10678SS | 0 | Start No Earlier Than | Warning
29029 | San Benito CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29030 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10681SS | 0 | Start No Earlier Than | Warning
29031 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10680SS |  | 0 | Start No Earlier Than | Warning
29032 | San Benito CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29033 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10684SS | 0 | Start No Earlier Than | Warning
29035 | San Benito CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29036 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10687SS | 0 | Start No Earlier Than | Warning
29038 | San Benito CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29046 | San Benito CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29050 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29051 | San Benito CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10702 | 1 | Start No Earlier Than | Warning
29054 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29055 | San Benito CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 10706 | 1 | Start No Earlier Than | Warning
29058 | San Benito CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29059 | San Benito CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10710 | 0 | Start No Earlier Than | Warning
29062 | San Benito CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29063 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29080 | San Benito CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 0d | 10728SF+30d |  | 1 | Start No Earlier Than | Warning
29081 | San Benito CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29095 | San Benito CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 10739,10746SS | 0.2 | Start No Earlier Than | Warning
29098 | San Benito CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
29099 | San Benito CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29113 | San Benito CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29116 | San Benito CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29117 | San Benito CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29118 | San Benito CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29119 | San Benito CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29120 | San Benito CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10779 | 0 | Start No Earlier Than | Warning
29121 | San Benito CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10780 | 0 | Start No Earlier Than | Warning
29123 | San Benito CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29124 | San Benito CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10785SF+30d |  | 0 | Start No Earlier Than | Warning
29125 | San Benito CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10786SF+30d |  | 0 | Start No Earlier Than | Warning
29126 | San Benito CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10787SF+30d |  | 0 | Start No Earlier Than | Warning
29127 | San Benito CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10788SF+30d |  | 0 | Start No Earlier Than | Warning
29128 | San Benito CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10789SF+30d |  | 0 | Start No Earlier Than | Warning
29131 | San Benito CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
29132 | San Benito CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10791FS+12d | 0 | Start No Earlier Than | Warning
29133 | San Benito CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
29134 | San Benito CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10791SF+60d | 0 | Start No Earlier Than | Warning
29135 | San Benito CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10774SF+30d | 0 | Start No Earlier Than | Warning
29136 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10775SF+30d | 0 | Start No Earlier Than | Warning
29137 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10776SF+30d | 0 | Start No Earlier Than | Warning
29138 | San Benito CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10777SF+30d | 0 | Start No Earlier Than | Warning
29139 | San Benito CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10778SF+30d | 0 | Start No Earlier Than | Warning
29140 | San Benito CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
29148 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
29149 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
29150 | San Bernardino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
29151 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
29152 | San Bernardino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
29153 | San Bernardino CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29175 | San Bernardino CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29176 | San Bernardino CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29177 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29178 | San Bernardino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29179 | San Bernardino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29180 | San Bernardino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29181 | San Bernardino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29182 | San Bernardino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29183 | San Bernardino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29184 | San Bernardino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29185 | San Bernardino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29186 | San Bernardino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29187 | San Bernardino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29188 | San Bernardino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29189 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29196 | San Bernardino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29197 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 10848SS | 0 | Start No Earlier Than | Warning
29201 | San Bernardino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29202 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 10853SS | 0 | Start No Earlier Than | Warning
29204 | San Bernardino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29205 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 10856SS | 0 | Start No Earlier Than | Warning
29206 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 10855SS |  | 0 | Start No Earlier Than | Warning
29207 | San Bernardino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29208 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 10859SS | 0 | Start No Earlier Than | Warning
29210 | San Bernardino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29211 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 10862SS | 0 | Start No Earlier Than | Warning
29213 | San Bernardino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29221 | San Bernardino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29225 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29226 | San Bernardino CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 10877 | 1 | Start No Earlier Than | Warning
29229 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29230 | San Bernardino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 10881 | 0.2 | Start No Earlier Than | Warning
29233 | San Bernardino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29234 | San Bernardino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 10885 | 0 | Start No Earlier Than | Warning
29237 | San Bernardino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29238 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29255 | San Bernardino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10903SF+30d |  | 0 | Start No Earlier Than | Warning
29256 | San Bernardino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29270 | San Bernardino CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 10914,10921SS | 1 | Start No Earlier Than | Warning
29273 | San Bernardino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
29274 | San Bernardino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29288 | San Bernardino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29291 | San Bernardino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29292 | San Bernardino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29293 | San Bernardino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29294 | San Bernardino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29295 | San Bernardino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10954 | 0 | Start No Earlier Than | Warning
29296 | San Bernardino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 10955 | 0 | Start No Earlier Than | Warning
29298 | San Bernardino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29299 | San Bernardino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10960SF+30d |  | 0 | Start No Earlier Than | Warning
29300 | San Bernardino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10961SF+30d |  | 0 | Start No Earlier Than | Warning
29301 | San Bernardino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10962SF+30d |  | 0 | Start No Earlier Than | Warning
29302 | San Bernardino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10963SF+30d |  | 0 | Start No Earlier Than | Warning
29303 | San Bernardino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 10964SF+30d |  | 0 | Start No Earlier Than | Warning
29306 | San Bernardino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
29307 | San Bernardino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 10966FS+12d | 0 | Start No Earlier Than | Warning
29308 | San Bernardino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
29309 | San Bernardino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 10966SF+60d | 0 | Start No Earlier Than | Warning
29310 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10949SF+30d | 0 | Start No Earlier Than | Warning
29311 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10950SF+30d | 0 | Start No Earlier Than | Warning
29312 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10951SF+30d | 0 | Start No Earlier Than | Warning
29313 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10952SF+30d | 0 | Start No Earlier Than | Warning
29314 | San Bernardino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 10953SF+30d | 0 | Start No Earlier Than | Warning
29315 | San Bernardino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
29323 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
29324 | San Francisco CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
29325 | San Francisco CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
29326 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
29327 | San Francisco CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
29328 | San Francisco CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29350 | San Francisco CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29351 | San Francisco CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29352 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29353 | San Francisco CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29354 | San Francisco CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29355 | San Francisco CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29356 | San Francisco CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29357 | San Francisco CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29358 | San Francisco CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29359 | San Francisco CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29360 | San Francisco CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29361 | San Francisco CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29362 | San Francisco CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29363 | San Francisco CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29364 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29371 | San Francisco CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29372 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11023SS | 0 | Start No Earlier Than | Warning
29376 | San Francisco CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29377 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11028SS | 0 | Start No Earlier Than | Warning
29379 | San Francisco CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29380 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11031SS | 0 | Start No Earlier Than | Warning
29381 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11030SS |  | 0 | Start No Earlier Than | Warning
29382 | San Francisco CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29383 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11034SS | 0 | Start No Earlier Than | Warning
29385 | San Francisco CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29386 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11037SS | 0 | Start No Earlier Than | Warning
29388 | San Francisco CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29396 | San Francisco CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29400 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29401 | San Francisco CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11052 | 1 | Start No Earlier Than | Warning
29404 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29405 | San Francisco CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11056 | 0.8 | Start No Earlier Than | Warning
29408 | San Francisco CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29409 | San Francisco CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11060 | 0 | Start No Earlier Than | Warning
29412 | San Francisco CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29413 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29430 | San Francisco CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11078SF+30d |  | 0 | Start No Earlier Than | Warning
29431 | San Francisco CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29445 | San Francisco CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 11089,11096SS | 1 | Start No Earlier Than | Warning
29448 | San Francisco CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
29449 | San Francisco CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29463 | San Francisco CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29466 | San Francisco CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29467 | San Francisco CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29468 | San Francisco CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29469 | San Francisco CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29470 | San Francisco CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11129 | 0 | Start No Earlier Than | Warning
29471 | San Francisco CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11130 | 0 | Start No Earlier Than | Warning
29473 | San Francisco CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29474 | San Francisco CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11135SF+30d |  | 0 | Start No Earlier Than | Warning
29475 | San Francisco CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11136SF+30d |  | 0 | Start No Earlier Than | Warning
29476 | San Francisco CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11137SF+30d |  | 0 | Start No Earlier Than | Warning
29477 | San Francisco CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11138SF+30d |  | 0 | Start No Earlier Than | Warning
29478 | San Francisco CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11139SF+30d |  | 0 | Start No Earlier Than | Warning
29481 | San Francisco CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
29482 | San Francisco CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11141FS+12d | 0 | Start No Earlier Than | Warning
29483 | San Francisco CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
29484 | San Francisco CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11141SF+60d | 0 | Start No Earlier Than | Warning
29485 | San Francisco CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11124SF+30d | 0 | Start No Earlier Than | Warning
29486 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11125SF+30d | 0 | Start No Earlier Than | Warning
29487 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11126SF+30d | 0 | Start No Earlier Than | Warning
29488 | San Francisco CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11127SF+30d | 0 | Start No Earlier Than | Warning
29489 | San Francisco CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11128SF+30d | 0 | Start No Earlier Than | Warning
29490 | San Francisco CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
29498 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
29499 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
29500 | San Joaquin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
29501 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
29502 | San Joaquin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
29503 | San Joaquin CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29525 | San Joaquin CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29526 | San Joaquin CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29527 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29528 | San Joaquin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29529 | San Joaquin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29530 | San Joaquin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29531 | San Joaquin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29532 | San Joaquin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29533 | San Joaquin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29534 | San Joaquin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29535 | San Joaquin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29536 | San Joaquin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29537 | San Joaquin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29538 | San Joaquin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29539 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29546 | San Joaquin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29547 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11198SS | 0 | Start No Earlier Than | Warning
29549 | San Joaquin CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 299d | 3885FS+29d | 11200 | 0 | Start No Earlier Than | Warning
29551 | San Joaquin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29552 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11203SS | 0 | Start No Earlier Than | Warning
29554 | San Joaquin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29555 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11206SS | 0 | Start No Earlier Than | Warning
29556 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11205SS |  | 0 | Start No Earlier Than | Warning
29557 | San Joaquin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29558 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11209SS | 0 | Start No Earlier Than | Warning
29560 | San Joaquin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29561 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11212SS | 0 | Start No Earlier Than | Warning
29563 | San Joaquin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29571 | San Joaquin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29575 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29576 | San Joaquin CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11227 | 1 | Start No Earlier Than | Warning
29579 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29580 | San Joaquin CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 11231 | 1 | Start No Earlier Than | Warning
29583 | San Joaquin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29584 | San Joaquin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11235 | 0 | Start No Earlier Than | Warning
29587 | San Joaquin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29588 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29605 | San Joaquin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11253SF+30d |  | 0 | Start No Earlier Than | Warning
29606 | San Joaquin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29620 | San Joaquin CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 11264,11271SS | 1 | Start No Earlier Than | Warning
29623 | San Joaquin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.6 | Start No Earlier Than | Warning
29624 | San Joaquin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29638 | San Joaquin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29641 | San Joaquin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29642 | San Joaquin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29643 | San Joaquin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29644 | San Joaquin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29645 | San Joaquin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11304 | 0 | Start No Earlier Than | Warning
29646 | San Joaquin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11305 | 0 | Start No Earlier Than | Warning
29648 | San Joaquin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29649 | San Joaquin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11310SF+30d |  | 0 | Start No Earlier Than | Warning
29650 | San Joaquin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11311SF+30d |  | 0 | Start No Earlier Than | Warning
29651 | San Joaquin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11312SF+30d |  | 0 | Start No Earlier Than | Warning
29652 | San Joaquin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11313SF+30d |  | 0 | Start No Earlier Than | Warning
29653 | San Joaquin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11314SF+30d |  | 0 | Start No Earlier Than | Warning
29656 | San Joaquin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
29657 | San Joaquin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11316FS+12d | 0 | Start No Earlier Than | Warning
29658 | San Joaquin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
29659 | San Joaquin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11316SF+60d | 0 | Start No Earlier Than | Warning
29660 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11299SF+30d | 0 | Start No Earlier Than | Warning
29661 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11300SF+30d | 0 | Start No Earlier Than | Warning
29662 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11301SF+30d | 0 | Start No Earlier Than | Warning
29663 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11302SF+30d | 0 | Start No Earlier Than | Warning
29664 | San Joaquin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11303SF+30d | 0 | Start No Earlier Than | Warning
29665 | San Joaquin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
29673 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
29674 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
29675 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
29676 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
29677 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
29678 | San Luis Obispo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29700 | San Luis Obispo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29701 | San Luis Obispo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29702 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29703 | San Luis Obispo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29704 | San Luis Obispo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29705 | San Luis Obispo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29706 | San Luis Obispo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29707 | San Luis Obispo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29708 | San Luis Obispo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29709 | San Luis Obispo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29710 | San Luis Obispo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29711 | San Luis Obispo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29712 | San Luis Obispo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29713 | San Luis Obispo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29714 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29721 | San Luis Obispo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29722 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11373SS | 0 | Start No Earlier Than | Warning
29726 | San Luis Obispo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29727 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11378SS | 0 | Start No Earlier Than | Warning
29729 | San Luis Obispo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29730 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11381SS | 0 | Start No Earlier Than | Warning
29731 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11380SS |  | 0 | Start No Earlier Than | Warning
29732 | San Luis Obispo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29733 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11384SS | 0 | Start No Earlier Than | Warning
29735 | San Luis Obispo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29736 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11387SS | 0 | Start No Earlier Than | Warning
29738 | San Luis Obispo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29746 | San Luis Obispo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29750 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29751 | San Luis Obispo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11402 | 1 | Start No Earlier Than | Warning
29754 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29755 | San Luis Obispo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11406 | 0.2 | Start No Earlier Than | Warning
29758 | San Luis Obispo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29759 | San Luis Obispo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11410 | 0 | Start No Earlier Than | Warning
29762 | San Luis Obispo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29763 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29780 | San Luis Obispo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11428SF+30d |  | 0 | Start No Earlier Than | Warning
29781 | San Luis Obispo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29795 | San Luis Obispo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 11439,11446SS | 1 | Start No Earlier Than | Warning
29798 | San Luis Obispo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
29799 | San Luis Obispo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29813 | San Luis Obispo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29816 | San Luis Obispo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29817 | San Luis Obispo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29818 | San Luis Obispo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29819 | San Luis Obispo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29820 | San Luis Obispo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11479 | 0 | Start No Earlier Than | Warning
29821 | San Luis Obispo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11480 | 0 | Start No Earlier Than | Warning
29823 | San Luis Obispo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29824 | San Luis Obispo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11485SF+30d |  | 0 | Start No Earlier Than | Warning
29825 | San Luis Obispo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11486SF+30d |  | 0 | Start No Earlier Than | Warning
29826 | San Luis Obispo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11487SF+30d |  | 0 | Start No Earlier Than | Warning
29827 | San Luis Obispo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11488SF+30d |  | 0 | Start No Earlier Than | Warning
29828 | San Luis Obispo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11489SF+30d |  | 0 | Start No Earlier Than | Warning
29831 | San Luis Obispo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
29832 | San Luis Obispo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11491FS+12d | 0 | Start No Earlier Than | Warning
29833 | San Luis Obispo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
29834 | San Luis Obispo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11491SF+60d | 0 | Start No Earlier Than | Warning
29835 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11474SF+30d | 0 | Start No Earlier Than | Warning
29836 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11475SF+30d | 0 | Start No Earlier Than | Warning
29837 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11476SF+30d | 0 | Start No Earlier Than | Warning
29838 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11477SF+30d | 0 | Start No Earlier Than | Warning
29839 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11478SF+30d | 0 | Start No Earlier Than | Warning
29840 | San Luis Obispo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
29848 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
29849 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
29850 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
29851 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
29852 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
29853 | Santa Barbara CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
29875 | Santa Barbara CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29876 | Santa Barbara CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
29877 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
29878 | Santa Barbara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
29879 | Santa Barbara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
29880 | Santa Barbara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
29881 | Santa Barbara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
29882 | Santa Barbara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
29883 | Santa Barbara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
29884 | Santa Barbara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
29885 | Santa Barbara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
29886 | Santa Barbara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
29887 | Santa Barbara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
29888 | Santa Barbara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29889 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
29896 | Santa Barbara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
29897 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11548SS | 0 | Start No Earlier Than | Warning
29901 | Santa Barbara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
29902 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11553SS | 0 | Start No Earlier Than | Warning
29904 | Santa Barbara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
29905 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11556SS | 0 | Start No Earlier Than | Warning
29906 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11555SS |  | 0 | Start No Earlier Than | Warning
29907 | Santa Barbara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
29908 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11559SS | 0 | Start No Earlier Than | Warning
29910 | Santa Barbara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
29911 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11562SS | 0 | Start No Earlier Than | Warning
29913 | Santa Barbara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
29921 | Santa Barbara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29925 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29926 | Santa Barbara CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11577 | 1 | Start No Earlier Than | Warning
29929 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29930 | Santa Barbara CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11581 | 0.2 | Start No Earlier Than | Warning
29933 | Santa Barbara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29934 | Santa Barbara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11585 | 0 | Start No Earlier Than | Warning
29937 | Santa Barbara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
29938 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
29955 | Santa Barbara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11603SF+30d |  | 0 | Start No Earlier Than | Warning
29956 | Santa Barbara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29970 | Santa Barbara CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 11614,11621SS | 0.6 | Start No Earlier Than | Warning
29973 | Santa Barbara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
29974 | Santa Barbara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
29988 | Santa Barbara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
29991 | Santa Barbara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
29992 | Santa Barbara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
29993 | Santa Barbara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
29994 | Santa Barbara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
29995 | Santa Barbara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11654 | 0 | Start No Earlier Than | Warning
29996 | Santa Barbara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11655 | 0 | Start No Earlier Than | Warning
29998 | Santa Barbara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
29999 | Santa Barbara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11660SF+30d |  | 0 | Start No Earlier Than | Warning
30000 | Santa Barbara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11661SF+30d |  | 0 | Start No Earlier Than | Warning
30001 | Santa Barbara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11662SF+30d |  | 0 | Start No Earlier Than | Warning
30002 | Santa Barbara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11663SF+30d |  | 0 | Start No Earlier Than | Warning
30003 | Santa Barbara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11664SF+30d |  | 0 | Start No Earlier Than | Warning
30006 | Santa Barbara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30007 | Santa Barbara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11666FS+12d | 0 | Start No Earlier Than | Warning
30008 | Santa Barbara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30009 | Santa Barbara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11666SF+60d | 0 | Start No Earlier Than | Warning
30010 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11649SF+30d | 0 | Start No Earlier Than | Warning
30011 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11650SF+30d | 0 | Start No Earlier Than | Warning
30012 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11651SF+30d | 0 | Start No Earlier Than | Warning
30013 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11652SF+30d | 0 | Start No Earlier Than | Warning
30014 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11653SF+30d | 0 | Start No Earlier Than | Warning
30015 | Santa Barbara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30023 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30024 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30025 | Santa Clara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30026 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30027 | Santa Clara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30028 | Santa Clara CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30050 | Santa Clara CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30051 | Santa Clara CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30052 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
30053 | Santa Clara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30054 | Santa Clara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30055 | Santa Clara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30056 | Santa Clara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30057 | Santa Clara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30058 | Santa Clara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30059 | Santa Clara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30060 | Santa Clara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30061 | Santa Clara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30062 | Santa Clara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30063 | Santa Clara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30064 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30071 | Santa Clara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
30072 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11723SS | 0 | Start No Earlier Than | Warning
30076 | Santa Clara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30077 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11728SS | 0 | Start No Earlier Than | Warning
30079 | Santa Clara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30080 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11731SS | 0 | Start No Earlier Than | Warning
30081 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11730SS |  | 0 | Start No Earlier Than | Warning
30082 | Santa Clara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30083 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11734SS | 0 | Start No Earlier Than | Warning
30085 | Santa Clara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30086 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11737SS | 0 | Start No Earlier Than | Warning
30088 | Santa Clara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30096 | Santa Clara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30100 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30101 | Santa Clara CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11752 | 1 | Start No Earlier Than | Warning
30104 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30105 | Santa Clara CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 11756 | 1 | Start No Earlier Than | Warning
30108 | Santa Clara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30109 | Santa Clara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11760 | 0 | Start No Earlier Than | Warning
30112 | Santa Clara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30113 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30130 | Santa Clara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11778SF+30d |  | 0 | Start No Earlier Than | Warning
30131 | Santa Clara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30145 | Santa Clara CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 11789,11796SS | 1 | Start No Earlier Than | Warning
30148 | Santa Clara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
30149 | Santa Clara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30163 | Santa Clara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
30165 | Santa Clara CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 11822 | 0.2 | Start No Earlier Than | Warning
30166 | Santa Clara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
30167 | Santa Clara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
30168 | Santa Clara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
30169 | Santa Clara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
30170 | Santa Clara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11829 | 0 | Start No Earlier Than | Warning
30171 | Santa Clara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 11830 | 0 | Start No Earlier Than | Warning
30173 | Santa Clara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
30174 | Santa Clara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11835SF+30d |  | 0 | Start No Earlier Than | Warning
30175 | Santa Clara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11836SF+30d |  | 0 | Start No Earlier Than | Warning
30176 | Santa Clara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11837SF+30d |  | 0 | Start No Earlier Than | Warning
30177 | Santa Clara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11838SF+30d |  | 0 | Start No Earlier Than | Warning
30178 | Santa Clara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 11839SF+30d |  | 0 | Start No Earlier Than | Warning
30181 | Santa Clara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30182 | Santa Clara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 11841FS+12d | 0 | Start No Earlier Than | Warning
30183 | Santa Clara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30184 | Santa Clara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 11841SF+60d | 0 | Start No Earlier Than | Warning
30185 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11824SF+30d | 0 | Start No Earlier Than | Warning
30186 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11825SF+30d | 0 | Start No Earlier Than | Warning
30187 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11826SF+30d | 0 | Start No Earlier Than | Warning
30188 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11827SF+30d | 0 | Start No Earlier Than | Warning
30189 | Santa Clara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11828SF+30d | 0 | Start No Earlier Than | Warning
30190 | Santa Clara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30198 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30199 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30200 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30201 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30202 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30203 | Santa Cruz CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30225 | Santa Cruz CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30226 | Santa Cruz CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30227 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
30228 | Santa Cruz CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30229 | Santa Cruz CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30230 | Santa Cruz CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30231 | Santa Cruz CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30232 | Santa Cruz CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30233 | Santa Cruz CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30234 | Santa Cruz CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30235 | Santa Cruz CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30236 | Santa Cruz CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30237 | Santa Cruz CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30238 | Santa Cruz CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30239 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30246 | Santa Cruz CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
30247 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 11898SS | 0 | Start No Earlier Than | Warning
30251 | Santa Cruz CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30252 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 11903SS | 0 | Start No Earlier Than | Warning
30254 | Santa Cruz CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30255 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 11906SS | 0 | Start No Earlier Than | Warning
30256 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 11905SS |  | 0 | Start No Earlier Than | Warning
30257 | Santa Cruz CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30258 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 11909SS | 0 | Start No Earlier Than | Warning
30260 | Santa Cruz CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30261 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 11912SS | 0 | Start No Earlier Than | Warning
30263 | Santa Cruz CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30271 | Santa Cruz CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30275 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30276 | Santa Cruz CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 11927 | 1 | Start No Earlier Than | Warning
30279 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30280 | Santa Cruz CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 11931 | 0.2 | Start No Earlier Than | Warning
30283 | Santa Cruz CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30284 | Santa Cruz CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 11935 | 0 | Start No Earlier Than | Warning
30287 | Santa Cruz CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30288 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30305 | Santa Cruz CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11953SF+30d |  | 0 | Start No Earlier Than | Warning
30306 | Santa Cruz CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30320 | Santa Cruz CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 11964,11971SS | 0.2 | Start No Earlier Than | Warning
30323 | Santa Cruz CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
30324 | Santa Cruz CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30338 | Santa Cruz CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
30341 | Santa Cruz CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
30342 | Santa Cruz CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
30343 | Santa Cruz CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
30344 | Santa Cruz CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
30345 | Santa Cruz CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12004 | 0 | Start No Earlier Than | Warning
30346 | Santa Cruz CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12005 | 0 | Start No Earlier Than | Warning
30348 | Santa Cruz CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
30349 | Santa Cruz CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12010SF+30d |  | 0 | Start No Earlier Than | Warning
30350 | Santa Cruz CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12011SF+30d |  | 0 | Start No Earlier Than | Warning
30351 | Santa Cruz CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12012SF+30d |  | 0 | Start No Earlier Than | Warning
30352 | Santa Cruz CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12013SF+30d |  | 0 | Start No Earlier Than | Warning
30353 | Santa Cruz CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12014SF+30d |  | 0 | Start No Earlier Than | Warning
30356 | Santa Cruz CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30357 | Santa Cruz CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12016FS+12d | 0 | Start No Earlier Than | Warning
30358 | Santa Cruz CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30359 | Santa Cruz CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12016SF+60d | 0 | Start No Earlier Than | Warning
30360 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 11999SF+30d | 0 | Start No Earlier Than | Warning
30361 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12000SF+30d | 0 | Start No Earlier Than | Warning
30362 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12001SF+30d | 0 | Start No Earlier Than | Warning
30363 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12002SF+30d | 0 | Start No Earlier Than | Warning
30364 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12003SF+30d | 0 | Start No Earlier Than | Warning
30365 | Santa Cruz CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30373 | Shasta CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30374 | Shasta CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30375 | Shasta CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30376 | Shasta CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30377 | Shasta CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30378 | Shasta CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30400 | Shasta CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30401 | Shasta CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30402 | Shasta CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
30403 | Shasta CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30404 | Shasta CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30405 | Shasta CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30406 | Shasta CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30407 | Shasta CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30408 | Shasta CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30409 | Shasta CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30410 | Shasta CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30411 | Shasta CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30412 | Shasta CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30413 | Shasta CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30414 | Shasta CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30421 | Shasta CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
30422 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12073SS | 0 | Start No Earlier Than | Warning
30426 | Shasta CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30427 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12078SS | 0 | Start No Earlier Than | Warning
30429 | Shasta CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30430 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12081SS | 0 | Start No Earlier Than | Warning
30431 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12080SS |  | 0 | Start No Earlier Than | Warning
30432 | Shasta CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30433 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12084SS | 0 | Start No Earlier Than | Warning
30435 | Shasta CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30436 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12087SS | 0 | Start No Earlier Than | Warning
30438 | Shasta CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30446 | Shasta CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30450 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30451 | Shasta CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12102 | 1 | Start No Earlier Than | Warning
30454 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30455 | Shasta CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12106 | 0 | Start No Earlier Than | Warning
30458 | Shasta CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30459 | Shasta CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12110 | 0 | Start No Earlier Than | Warning
30462 | Shasta CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30463 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30480 | Shasta CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12128SF+30d |  | 0 | Start No Earlier Than | Warning
30481 | Shasta CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30495 | Shasta CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 12139,12146SS | 1 | Start No Earlier Than | Warning
30498 | Shasta CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
30499 | Shasta CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30513 | Shasta CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
30516 | Shasta CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
30517 | Shasta CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
30518 | Shasta CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
30519 | Shasta CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
30520 | Shasta CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12179 | 0 | Start No Earlier Than | Warning
30521 | Shasta CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12180 | 0 | Start No Earlier Than | Warning
30523 | Shasta CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
30524 | Shasta CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12185SF+30d |  | 0 | Start No Earlier Than | Warning
30525 | Shasta CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12186SF+30d |  | 0 | Start No Earlier Than | Warning
30526 | Shasta CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12187SF+30d |  | 0 | Start No Earlier Than | Warning
30527 | Shasta CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12188SF+30d |  | 0 | Start No Earlier Than | Warning
30528 | Shasta CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12189SF+30d |  | 0 | Start No Earlier Than | Warning
30531 | Shasta CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30532 | Shasta CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12191FS+12d | 0 | Start No Earlier Than | Warning
30533 | Shasta CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30534 | Shasta CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12191SF+60d | 0 | Start No Earlier Than | Warning
30535 | Shasta CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12174SF+30d | 0 | Start No Earlier Than | Warning
30536 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12175SF+30d | 0 | Start No Earlier Than | Warning
30537 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12176SF+30d | 0 | Start No Earlier Than | Warning
30538 | Shasta CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12177SF+30d | 0 | Start No Earlier Than | Warning
30539 | Shasta CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12178SF+30d | 0 | Start No Earlier Than | Warning
30540 | Shasta CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30548 | Sierra CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30549 | Sierra CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30550 | Sierra CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30551 | Sierra CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30552 | Sierra CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30553 | Sierra CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30575 | Sierra CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30576 | Sierra CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30577 | Sierra CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
30578 | Sierra CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30579 | Sierra CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30580 | Sierra CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30581 | Sierra CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30582 | Sierra CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30583 | Sierra CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30584 | Sierra CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30585 | Sierra CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30586 | Sierra CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30587 | Sierra CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30588 | Sierra CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30589 | Sierra CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30596 | Sierra CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
30597 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12248SS | 0 | Start No Earlier Than | Warning
30601 | Sierra CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30602 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12253SS | 0 | Start No Earlier Than | Warning
30604 | Sierra CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30605 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12256SS | 0 | Start No Earlier Than | Warning
30606 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12255SS |  | 0 | Start No Earlier Than | Warning
30607 | Sierra CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30608 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12259SS | 0 | Start No Earlier Than | Warning
30610 | Sierra CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30611 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12262SS | 0 | Start No Earlier Than | Warning
30613 | Sierra CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30621 | Sierra CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30625 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30626 | Sierra CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12277 | 1 | Start No Earlier Than | Warning
30629 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30630 | Sierra CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 12281 | 1 | Start No Earlier Than | Warning
30633 | Sierra CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30634 | Sierra CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12285 | 0 | Start No Earlier Than | Warning
30637 | Sierra CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30638 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30642 | Sierra CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d |  | 12293,12295SS | 1 | Start No Earlier Than | Warning
30648 | Sierra CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12296SF+30d |  | 0 | Start No Earlier Than | Warning
30649 | Sierra CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30658 | Sierra CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 508d |  |  | 0.6 | Start No Earlier Than | Warning
30660 | Sierra CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 64 | 299d |  |  | 0 | Start No Earlier Than | Warning
30661 | Sierra CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
30662 | Sierra CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30663 | Sierra CW-POC or Organization Leadership to sign off on form completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | Start No Earlier Than | Warning
30676 | Sierra CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
30679 | Sierra CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
30680 | Sierra CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
30681 | Sierra CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
30682 | Sierra CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
30683 | Sierra CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12342 | 0 | Start No Earlier Than | Warning
30684 | Sierra CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12343 | 0 | Start No Earlier Than | Warning
30686 | Sierra CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
30687 | Sierra CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12348SF+30d |  | 0 | Start No Earlier Than | Warning
30688 | Sierra CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12349SF+30d |  | 0 | Start No Earlier Than | Warning
30689 | Sierra CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12350SF+30d |  | 0 | Start No Earlier Than | Warning
30690 | Sierra CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12351SF+30d |  | 0 | Start No Earlier Than | Warning
30691 | Sierra CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12352SF+30d |  | 0 | Start No Earlier Than | Warning
30694 | Sierra CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30695 | Sierra CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12354FS+12d | 0 | Start No Earlier Than | Warning
30696 | Sierra CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30697 | Sierra CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12354SF+60d | 0 | Start No Earlier Than | Warning
30698 | Sierra CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12337SF+30d | 0 | Start No Earlier Than | Warning
30699 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12338SF+30d | 0 | Start No Earlier Than | Warning
30700 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12339SF+30d | 0 | Start No Earlier Than | Warning
30701 | Sierra CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12340SF+30d | 0 | Start No Earlier Than | Warning
30702 | Sierra CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12341SF+30d | 0 | Start No Earlier Than | Warning
30703 | Sierra CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30711 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30712 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30713 | Siskiyou CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30714 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30715 | Siskiyou CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30716 | Siskiyou CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30738 | Siskiyou CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30739 | Siskiyou CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30740 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
30741 | Siskiyou CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30742 | Siskiyou CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30743 | Siskiyou CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30744 | Siskiyou CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30745 | Siskiyou CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30746 | Siskiyou CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30747 | Siskiyou CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30748 | Siskiyou CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30749 | Siskiyou CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30750 | Siskiyou CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30751 | Siskiyou CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30752 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30759 | Siskiyou CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
30760 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12411SS | 0 | Start No Earlier Than | Warning
30762 | Siskiyou CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
30763 | Siskiyou CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
30764 | Siskiyou CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30765 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12416SS | 0 | Start No Earlier Than | Warning
30767 | Siskiyou CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30768 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12419SS | 0 | Start No Earlier Than | Warning
30769 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12418SS |  | 0 | Start No Earlier Than | Warning
30770 | Siskiyou CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30771 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12422SS | 0 | Start No Earlier Than | Warning
30773 | Siskiyou CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30774 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12425SS | 0 | Start No Earlier Than | Warning
30776 | Siskiyou CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30784 | Siskiyou CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30788 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30789 | Siskiyou CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12440 | 1 | Start No Earlier Than | Warning
30792 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30793 | Siskiyou CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12444 | 0.2 | Start No Earlier Than | Warning
30796 | Siskiyou CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30797 | Siskiyou CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12448 | 0 | Start No Earlier Than | Warning
30800 | Siskiyou CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30801 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30804 | Siskiyou CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 12455SS | 1 | Start No Earlier Than | Warning
30818 | Siskiyou CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12466SF+30d |  | 0 | Start No Earlier Than | Warning
30819 | Siskiyou CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30833 | Siskiyou CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 12477,12484SS | 1 | Start No Earlier Than | Warning
30836 | Siskiyou CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
30837 | Siskiyou CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30851 | Siskiyou CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
30854 | Siskiyou CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
30855 | Siskiyou CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
30856 | Siskiyou CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
30857 | Siskiyou CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
30858 | Siskiyou CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12517 | 0 | Start No Earlier Than | Warning
30859 | Siskiyou CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12518 | 0 | Start No Earlier Than | Warning
30861 | Siskiyou CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
30862 | Siskiyou CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12523SF+30d |  | 0 | Start No Earlier Than | Warning
30863 | Siskiyou CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12524SF+30d |  | 0 | Start No Earlier Than | Warning
30864 | Siskiyou CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12525SF+30d |  | 0 | Start No Earlier Than | Warning
30865 | Siskiyou CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12526SF+30d |  | 0 | Start No Earlier Than | Warning
30866 | Siskiyou CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12527SF+30d |  | 0 | Start No Earlier Than | Warning
30869 | Siskiyou CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
30870 | Siskiyou CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12529FS+12d | 0 | Start No Earlier Than | Warning
30871 | Siskiyou CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
30872 | Siskiyou CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12529SF+60d | 0 | Start No Earlier Than | Warning
30873 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12512SF+30d | 0 | Start No Earlier Than | Warning
30874 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12513SF+30d | 0 | Start No Earlier Than | Warning
30875 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12514SF+30d | 0 | Start No Earlier Than | Warning
30876 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12515SF+30d | 0 | Start No Earlier Than | Warning
30877 | Siskiyou CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12516SF+30d | 0 | Start No Earlier Than | Warning
30878 | Siskiyou CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
30886 | Solano CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
30887 | Solano CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
30888 | Solano CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
30889 | Solano CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
30890 | Solano CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
30891 | Solano CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
30913 | Solano CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30914 | Solano CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
30915 | Solano CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
30916 | Solano CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
30917 | Solano CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
30918 | Solano CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
30919 | Solano CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
30920 | Solano CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
30921 | Solano CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
30922 | Solano CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
30923 | Solano CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
30924 | Solano CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
30925 | Solano CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
30926 | Solano CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30927 | Solano CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
30934 | Solano CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
30935 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 12586SS | 0.2 | Start No Earlier Than | Warning
30937 | Solano CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
30938 | Solano CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
30939 | Solano CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
30940 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12591SS | 0 | Start No Earlier Than | Warning
30942 | Solano CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
30943 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12594SS | 0 | Start No Earlier Than | Warning
30944 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12593SS |  | 0 | Start No Earlier Than | Warning
30945 | Solano CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
30946 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12597SS | 0 | Start No Earlier Than | Warning
30948 | Solano CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
30949 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12600SS | 0 | Start No Earlier Than | Warning
30951 | Solano CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
30959 | Solano CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30963 | Solano CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30964 | Solano CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12615 | 1 | Start No Earlier Than | Warning
30967 | Solano CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30968 | Solano CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 12619 | 1 | Start No Earlier Than | Warning
30971 | Solano CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30972 | Solano CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12623 | 0 | Start No Earlier Than | Warning
30975 | Solano CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
30976 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
30993 | Solano CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12641SF+30d |  | 0.2 | Start No Earlier Than | Warning
30994 | Solano CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
30997 | Solano CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 12648SS | 1 | Start No Earlier Than | Warning
31008 | Solano CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 12652,12659SS | 1 | Start No Earlier Than | Warning
31011 | Solano CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
31012 | Solano CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31026 | Solano CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31028 | Solano CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 12685 | 0.2 | Start No Earlier Than | Warning
31029 | Solano CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
31030 | Solano CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0.2 | Start No Earlier Than | Warning
31031 | Solano CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31032 | Solano CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31033 | Solano CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12692 | 0 | Start No Earlier Than | Warning
31034 | Solano CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12693 | 0 | Start No Earlier Than | Warning
31036 | Solano CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31037 | Solano CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12698SF+30d |  | 0 | Start No Earlier Than | Warning
31038 | Solano CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12699SF+30d |  | 0 | Start No Earlier Than | Warning
31039 | Solano CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12700SF+30d |  | 0 | Start No Earlier Than | Warning
31040 | Solano CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12701SF+30d |  | 0 | Start No Earlier Than | Warning
31041 | Solano CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12702SF+30d |  | 0 | Start No Earlier Than | Warning
31044 | Solano CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31045 | Solano CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12704FS+12d | 0 | Start No Earlier Than | Warning
31046 | Solano CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31047 | Solano CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12704SF+60d | 0 | Start No Earlier Than | Warning
31048 | Solano CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12687SF+30d | 0 | Start No Earlier Than | Warning
31049 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12688SF+30d | 0 | Start No Earlier Than | Warning
31050 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12689SF+30d | 0 | Start No Earlier Than | Warning
31051 | Solano CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12690SF+30d | 0 | Start No Earlier Than | Warning
31052 | Solano CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12691SF+30d | 0 | Start No Earlier Than | Warning
31053 | Solano CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31061 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31062 | Sonoma CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31063 | Sonoma CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31064 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31065 | Sonoma CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31066 | Sonoma CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31088 | Sonoma CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31089 | Sonoma CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31090 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31091 | Sonoma CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31092 | Sonoma CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31093 | Sonoma CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31094 | Sonoma CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31095 | Sonoma CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31096 | Sonoma CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31097 | Sonoma CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31098 | Sonoma CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31099 | Sonoma CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31100 | Sonoma CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31101 | Sonoma CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31102 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31109 | Sonoma CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
31110 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12761SS | 0 | Start No Earlier Than | Warning
31112 | Sonoma CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31113 | Sonoma CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31114 | Sonoma CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31115 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12766SS | 0 | Start No Earlier Than | Warning
31117 | Sonoma CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31118 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12769SS | 0 | Start No Earlier Than | Warning
31119 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12768SS |  | 0 | Start No Earlier Than | Warning
31120 | Sonoma CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31121 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12772SS | 0 | Start No Earlier Than | Warning
31123 | Sonoma CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31124 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12775SS | 0 | Start No Earlier Than | Warning
31126 | Sonoma CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
31134 | Sonoma CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31138 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31139 | Sonoma CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12790 | 1 | Start No Earlier Than | Warning
31142 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31143 | Sonoma CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 12794 | 0 | Start No Earlier Than | Warning
31146 | Sonoma CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31147 | Sonoma CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 0d |  | 12798 | 1 | Start No Earlier Than | Warning
31150 | Sonoma CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31151 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
31154 | Sonoma CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 12805SS | 1 | Start No Earlier Than | Warning
31168 | Sonoma CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12816SF+30d |  | 0 | Start No Earlier Than | Warning
31169 | Sonoma CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31172 | Sonoma CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 12823SS | 1 | Start No Earlier Than | Warning
31183 | Sonoma CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 12827,12834SS | 0.2 | Start No Earlier Than | Warning
31186 | Sonoma CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
31187 | Sonoma CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31201 | Sonoma CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31204 | Sonoma CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
31205 | Sonoma CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
31206 | Sonoma CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31207 | Sonoma CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31208 | Sonoma CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12867 | 0 | Start No Earlier Than | Warning
31209 | Sonoma CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 12868 | 0 | Start No Earlier Than | Warning
31211 | Sonoma CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31212 | Sonoma CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12873SF+30d |  | 0 | Start No Earlier Than | Warning
31213 | Sonoma CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12874SF+30d |  | 0 | Start No Earlier Than | Warning
31214 | Sonoma CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12875SF+30d |  | 0 | Start No Earlier Than | Warning
31215 | Sonoma CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12876SF+30d |  | 0 | Start No Earlier Than | Warning
31216 | Sonoma CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 12877SF+30d |  | 0 | Start No Earlier Than | Warning
31219 | Sonoma CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31220 | Sonoma CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 12879FS+12d | 0 | Start No Earlier Than | Warning
31221 | Sonoma CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31222 | Sonoma CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 12879SF+60d | 0 | Start No Earlier Than | Warning
31223 | Sonoma CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12862SF+30d | 0 | Start No Earlier Than | Warning
31224 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12863SF+30d | 0 | Start No Earlier Than | Warning
31225 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12864SF+30d | 0 | Start No Earlier Than | Warning
31226 | Sonoma CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12865SF+30d | 0 | Start No Earlier Than | Warning
31227 | Sonoma CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 12866SF+30d | 0 | Start No Earlier Than | Warning
31228 | Sonoma CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31236 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31237 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31238 | Stanislaus CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31239 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31240 | Stanislaus CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31241 | Stanislaus CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31263 | Stanislaus CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31264 | Stanislaus CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31265 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31266 | Stanislaus CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31267 | Stanislaus CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31268 | Stanislaus CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31269 | Stanislaus CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31270 | Stanislaus CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31271 | Stanislaus CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31272 | Stanislaus CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31273 | Stanislaus CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31274 | Stanislaus CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31275 | Stanislaus CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31276 | Stanislaus CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31277 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31284 | Stanislaus CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
31285 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 12936SS | 0 | Start No Earlier Than | Warning
31287 | Stanislaus CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31288 | Stanislaus CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31289 | Stanislaus CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31290 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 12941SS | 0 | Start No Earlier Than | Warning
31292 | Stanislaus CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31293 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 12944SS | 0 | Start No Earlier Than | Warning
31294 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 12943SS |  | 0 | Start No Earlier Than | Warning
31295 | Stanislaus CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31296 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 12947SS | 0 | Start No Earlier Than | Warning
31298 | Stanislaus CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31299 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 12950SS | 0 | Start No Earlier Than | Warning
31301 | Stanislaus CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
31309 | Stanislaus CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31313 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31314 | Stanislaus CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 12965 | 1 | Start No Earlier Than | Warning
31317 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31318 | Stanislaus CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 12969 | 1 | Start No Earlier Than | Warning
31321 | Stanislaus CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31322 | Stanislaus CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 12973 | 0.95 | Start No Earlier Than | Warning
31325 | Stanislaus CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31326 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
31343 | Stanislaus CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12991SF+30d |  | 0 | Start No Earlier Than | Warning
31344 | Stanislaus CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31347 | Stanislaus CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 12998SS | 1 | Start No Earlier Than | Warning
31358 | Stanislaus CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 13002,13009SS | 1 | Start No Earlier Than | Warning
31361 | Stanislaus CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
31362 | Stanislaus CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31376 | Stanislaus CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31379 | Stanislaus CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
31380 | Stanislaus CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
31381 | Stanislaus CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31382 | Stanislaus CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31383 | Stanislaus CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13042 | 0 | Start No Earlier Than | Warning
31384 | Stanislaus CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13043 | 0 | Start No Earlier Than | Warning
31386 | Stanislaus CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31387 | Stanislaus CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13048SF+30d |  | 0 | Start No Earlier Than | Warning
31388 | Stanislaus CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13049SF+30d |  | 0 | Start No Earlier Than | Warning
31389 | Stanislaus CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13050SF+30d |  | 0 | Start No Earlier Than | Warning
31390 | Stanislaus CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13051SF+30d |  | 0 | Start No Earlier Than | Warning
31391 | Stanislaus CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13052SF+30d |  | 0 | Start No Earlier Than | Warning
31394 | Stanislaus CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31395 | Stanislaus CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13054FS+12d | 0 | Start No Earlier Than | Warning
31396 | Stanislaus CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31397 | Stanislaus CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13054SF+60d | 0 | Start No Earlier Than | Warning
31398 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13037SF+30d | 0 | Start No Earlier Than | Warning
31399 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13038SF+30d | 0 | Start No Earlier Than | Warning
31400 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13039SF+30d | 0 | Start No Earlier Than | Warning
31401 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13040SF+30d | 0 | Start No Earlier Than | Warning
31402 | Stanislaus CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13041SF+30d | 0 | Start No Earlier Than | Warning
31403 | Stanislaus CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31411 | Sutter CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31412 | Sutter CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31413 | Sutter CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31414 | Sutter CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31415 | Sutter CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31416 | Sutter CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31438 | Sutter CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31439 | Sutter CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31440 | Sutter CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31441 | Sutter CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31442 | Sutter CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31443 | Sutter CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31444 | Sutter CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31445 | Sutter CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31446 | Sutter CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31447 | Sutter CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31448 | Sutter CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31449 | Sutter CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31450 | Sutter CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31451 | Sutter CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31452 | Sutter CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31459 | Sutter CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
31460 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13111SS | 0 | Start No Earlier Than | Warning
31462 | Sutter CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31463 | Sutter CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31464 | Sutter CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31465 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13116SS | 0 | Start No Earlier Than | Warning
31467 | Sutter CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31468 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13119SS | 0 | Start No Earlier Than | Warning
31469 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13118SS |  | 0 | Start No Earlier Than | Warning
31470 | Sutter CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31471 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13122SS | 0 | Start No Earlier Than | Warning
31473 | Sutter CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31474 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13125SS | 0 | Start No Earlier Than | Warning
31476 | Sutter CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
31484 | Sutter CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31488 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31489 | Sutter CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 13140 | 1 | Start No Earlier Than | Warning
31492 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31493 | Sutter CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13144 | 0.2 | Start No Earlier Than | Warning
31496 | Sutter CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31497 | Sutter CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13148 | 0 | Start No Earlier Than | Warning
31500 | Sutter CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31501 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
31518 | Sutter CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13166SF+30d |  | 0 | Start No Earlier Than | Warning
31519 | Sutter CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31533 | Sutter CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 13177,13184SS | 1 | Start No Earlier Than | Warning
31536 | Sutter CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
31537 | Sutter CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31551 | Sutter CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31554 | Sutter CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
31555 | Sutter CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
31556 | Sutter CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31557 | Sutter CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31558 | Sutter CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13217 | 0 | Start No Earlier Than | Warning
31559 | Sutter CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13218 | 0 | Start No Earlier Than | Warning
31561 | Sutter CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31562 | Sutter CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13223SF+30d |  | 0 | Start No Earlier Than | Warning
31563 | Sutter CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13224SF+30d |  | 0 | Start No Earlier Than | Warning
31564 | Sutter CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13225SF+30d |  | 0 | Start No Earlier Than | Warning
31565 | Sutter CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13226SF+30d |  | 0 | Start No Earlier Than | Warning
31566 | Sutter CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13227SF+30d |  | 0 | Start No Earlier Than | Warning
31569 | Sutter CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31570 | Sutter CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13229FS+12d | 0 | Start No Earlier Than | Warning
31571 | Sutter CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31572 | Sutter CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13229SF+60d | 0 | Start No Earlier Than | Warning
31573 | Sutter CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13212SF+30d | 0 | Start No Earlier Than | Warning
31574 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13213SF+30d | 0 | Start No Earlier Than | Warning
31575 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13214SF+30d | 0 | Start No Earlier Than | Warning
31576 | Sutter CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13215SF+30d | 0 | Start No Earlier Than | Warning
31577 | Sutter CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13216SF+30d | 0 | Start No Earlier Than | Warning
31578 | Sutter CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31586 | Tehama CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31587 | Tehama CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31588 | Tehama CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31589 | Tehama CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31590 | Tehama CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31591 | Tehama CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31613 | Tehama CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31614 | Tehama CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31615 | Tehama CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31616 | Tehama CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31617 | Tehama CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31618 | Tehama CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31619 | Tehama CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31620 | Tehama CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31621 | Tehama CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31622 | Tehama CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31623 | Tehama CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31624 | Tehama CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31625 | Tehama CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31626 | Tehama CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31627 | Tehama CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31634 | Tehama CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
31635 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13286SS | 0 | Start No Earlier Than | Warning
31637 | Tehama CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31638 | Tehama CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31639 | Tehama CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31640 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13291SS | 0 | Start No Earlier Than | Warning
31642 | Tehama CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31643 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13294SS | 0 | Start No Earlier Than | Warning
31644 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13293SS |  | 0 | Start No Earlier Than | Warning
31645 | Tehama CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31646 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13297SS | 0 | Start No Earlier Than | Warning
31648 | Tehama CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31649 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13300SS | 0 | Start No Earlier Than | Warning
31651 | Tehama CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
31659 | Tehama CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31663 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31664 | Tehama CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 13315 | 1 | Start No Earlier Than | Warning
31667 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31668 | Tehama CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13319 | 0 | Start No Earlier Than | Warning
31671 | Tehama CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31672 | Tehama CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13323 | 0 | Start No Earlier Than | Warning
31675 | Tehama CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31676 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
31693 | Tehama CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13341SF+30d |  | 0 | Start No Earlier Than | Warning
31694 | Tehama CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31708 | Tehama CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 13352,13359SS | 1 | Start No Earlier Than | Warning
31711 | Tehama CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 0d |  |  | 1 | Start No Earlier Than | Warning
31712 | Tehama CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31726 | Tehama CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31729 | Tehama CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
31730 | Tehama CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
31731 | Tehama CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31732 | Tehama CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31733 | Tehama CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13392 | 0 | Start No Earlier Than | Warning
31734 | Tehama CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13393 | 0 | Start No Earlier Than | Warning
31736 | Tehama CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31737 | Tehama CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13398SF+30d |  | 0 | Start No Earlier Than | Warning
31738 | Tehama CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13399SF+30d |  | 0 | Start No Earlier Than | Warning
31739 | Tehama CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13400SF+30d |  | 0 | Start No Earlier Than | Warning
31740 | Tehama CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13401SF+30d |  | 0 | Start No Earlier Than | Warning
31741 | Tehama CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13402SF+30d |  | 0 | Start No Earlier Than | Warning
31744 | Tehama CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31745 | Tehama CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13404FS+12d | 0 | Start No Earlier Than | Warning
31746 | Tehama CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31747 | Tehama CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13404SF+60d | 0 | Start No Earlier Than | Warning
31748 | Tehama CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13387SF+30d | 0 | Start No Earlier Than | Warning
31749 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13388SF+30d | 0 | Start No Earlier Than | Warning
31750 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13389SF+30d | 0 | Start No Earlier Than | Warning
31751 | Tehama CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13390SF+30d | 0 | Start No Earlier Than | Warning
31752 | Tehama CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13391SF+30d | 0 | Start No Earlier Than | Warning
31753 | Tehama CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31761 | Trinity CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31762 | Trinity CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31763 | Trinity CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31764 | Trinity CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31765 | Trinity CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31766 | Trinity CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31788 | Trinity CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31789 | Trinity CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31790 | Trinity CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31791 | Trinity CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31792 | Trinity CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31793 | Trinity CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31794 | Trinity CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31795 | Trinity CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31796 | Trinity CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31797 | Trinity CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31798 | Trinity CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31799 | Trinity CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31800 | Trinity CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31801 | Trinity CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31802 | Trinity CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31809 | Trinity CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
31810 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13461SS | 0 | Start No Earlier Than | Warning
31812 | Trinity CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31813 | Trinity CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31814 | Trinity CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31815 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13466SS | 0 | Start No Earlier Than | Warning
31817 | Trinity CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31818 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13469SS | 0 | Start No Earlier Than | Warning
31819 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13468SS |  | 0 | Start No Earlier Than | Warning
31820 | Trinity CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31821 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13472SS | 0 | Start No Earlier Than | Warning
31823 | Trinity CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31824 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13475SS | 0 | Start No Earlier Than | Warning
31826 | Trinity CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
31834 | Trinity CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31838 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31839 | Trinity CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 13490 | 1 | Start No Earlier Than | Warning
31842 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31843 | Trinity CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 13494 | 1 | Start No Earlier Than | Warning
31846 | Trinity CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31847 | Trinity CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13498 | 0 | Start No Earlier Than | Warning
31850 | Trinity CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
31851 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
31854 | Trinity CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 13505SS | 0.2 | Start No Earlier Than | Warning
31868 | Trinity CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13516SF+30d |  | 0 | Start No Earlier Than | Warning
31869 | Trinity CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31872 | Trinity CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 13523SS | 0.2 | Start No Earlier Than | Warning
31883 | Trinity CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 13527,13534SS | 1 | Start No Earlier Than | Warning
31886 | Trinity CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
31887 | Trinity CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
31901 | Trinity CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
31904 | Trinity CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
31905 | Trinity CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
31906 | Trinity CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
31907 | Trinity CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
31908 | Trinity CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13567 | 0 | Start No Earlier Than | Warning
31909 | Trinity CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13568 | 0 | Start No Earlier Than | Warning
31911 | Trinity CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
31912 | Trinity CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13573SF+30d |  | 0 | Start No Earlier Than | Warning
31913 | Trinity CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13574SF+30d |  | 0 | Start No Earlier Than | Warning
31914 | Trinity CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13575SF+30d |  | 0 | Start No Earlier Than | Warning
31915 | Trinity CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13576SF+30d |  | 0 | Start No Earlier Than | Warning
31916 | Trinity CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13577SF+30d |  | 0 | Start No Earlier Than | Warning
31919 | Trinity CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
31920 | Trinity CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13579FS+12d | 0 | Start No Earlier Than | Warning
31921 | Trinity CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
31922 | Trinity CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13579SF+60d | 0 | Start No Earlier Than | Warning
31923 | Trinity CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13562SF+30d | 0 | Start No Earlier Than | Warning
31924 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13563SF+30d | 0 | Start No Earlier Than | Warning
31925 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13564SF+30d | 0 | Start No Earlier Than | Warning
31926 | Trinity CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13565SF+30d | 0 | Start No Earlier Than | Warning
31927 | Trinity CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13566SF+30d | 0 | Start No Earlier Than | Warning
31928 | Trinity CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
31936 | Tulare CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
31937 | Tulare CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
31938 | Tulare CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
31939 | Tulare CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
31940 | Tulare CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
31941 | Tulare CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
31963 | Tulare CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31964 | Tulare CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
31965 | Tulare CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
31966 | Tulare CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
31967 | Tulare CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
31968 | Tulare CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
31969 | Tulare CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
31970 | Tulare CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
31971 | Tulare CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
31972 | Tulare CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
31973 | Tulare CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
31974 | Tulare CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
31975 | Tulare CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
31976 | Tulare CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31977 | Tulare CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
31984 | Tulare CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
31985 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13636SS | 0 | Start No Earlier Than | Warning
31987 | Tulare CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31988 | Tulare CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
31989 | Tulare CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
31990 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13641SS | 0 | Start No Earlier Than | Warning
31992 | Tulare CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
31993 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13644SS | 0 | Start No Earlier Than | Warning
31994 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13643SS |  | 0 | Start No Earlier Than | Warning
31995 | Tulare CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
31996 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13647SS | 0 | Start No Earlier Than | Warning
31998 | Tulare CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
31999 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13650SS | 0 | Start No Earlier Than | Warning
32001 | Tulare CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
32009 | Tulare CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32013 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32014 | Tulare CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 13665 | 1 | Start No Earlier Than | Warning
32017 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32018 | Tulare CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 13669 | 0.2 | Start No Earlier Than | Warning
32021 | Tulare CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32022 | Tulare CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13673 | 0 | Start No Earlier Than | Warning
32025 | Tulare CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32026 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32043 | Tulare CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13691SF+30d |  | 0 | Start No Earlier Than | Warning
32044 | Tulare CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32058 | Tulare CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 13702,13709SS | 1 | Start No Earlier Than | Warning
32061 | Tulare CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
32062 | Tulare CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32076 | Tulare CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
32078 | Tulare CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 195d |  | 13735 | 0.2 | Start No Earlier Than | Warning
32079 | Tulare CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32080 | Tulare CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32081 | Tulare CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32082 | Tulare CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
32083 | Tulare CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13742 | 0 | Start No Earlier Than | Warning
32084 | Tulare CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13743 | 0 | Start No Earlier Than | Warning
32086 | Tulare CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32087 | Tulare CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13748SF+30d |  | 0 | Start No Earlier Than | Warning
32088 | Tulare CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13749SF+30d |  | 0 | Start No Earlier Than | Warning
32089 | Tulare CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13750SF+30d |  | 0 | Start No Earlier Than | Warning
32090 | Tulare CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13751SF+30d |  | 0 | Start No Earlier Than | Warning
32091 | Tulare CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13752SF+30d |  | 0 | Start No Earlier Than | Warning
32094 | Tulare CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
32095 | Tulare CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13754FS+12d | 0 | Start No Earlier Than | Warning
32096 | Tulare CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
32097 | Tulare CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13754SF+60d | 0 | Start No Earlier Than | Warning
32098 | Tulare CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13737SF+30d | 0 | Start No Earlier Than | Warning
32099 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13738SF+30d | 0 | Start No Earlier Than | Warning
32100 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13739SF+30d | 0 | Start No Earlier Than | Warning
32101 | Tulare CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13740SF+30d | 0 | Start No Earlier Than | Warning
32102 | Tulare CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13741SF+30d | 0 | Start No Earlier Than | Warning
32103 | Tulare CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32111 | Yolo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32112 | Yolo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0.2 | Start No Earlier Than | Warning
32113 | Yolo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32114 | Yolo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
32115 | Yolo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
32116 | Yolo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
32138 | Yolo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32139 | Yolo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32140 | Yolo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
32141 | Yolo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
32142 | Yolo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
32143 | Yolo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
32144 | Yolo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
32145 | Yolo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
32146 | Yolo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
32147 | Yolo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
32148 | Yolo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
32149 | Yolo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
32150 | Yolo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
32151 | Yolo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32152 | Yolo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
32159 | Yolo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
32160 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13811SS | 0 | Start No Earlier Than | Warning
32162 | Yolo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32163 | Yolo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32164 | Yolo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
32165 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13816SS | 0 | Start No Earlier Than | Warning
32167 | Yolo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
32168 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13819SS | 0 | Start No Earlier Than | Warning
32169 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13818SS |  | 0 | Start No Earlier Than | Warning
32170 | Yolo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
32171 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13822SS | 0 | Start No Earlier Than | Warning
32173 | Yolo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32174 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 13825SS | 0 | Start No Earlier Than | Warning
32176 | Yolo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
32184 | Yolo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32188 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32189 | Yolo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 13840 | 1 | Start No Earlier Than | Warning
32192 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32193 | Yolo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 13844 | 1 | Start No Earlier Than | Warning
32196 | Yolo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32197 | Yolo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 13848 | 0 | Start No Earlier Than | Warning
32200 | Yolo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32201 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32218 | Yolo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13866SF+30d |  | 0 | Start No Earlier Than | Warning
32219 | Yolo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32233 | Yolo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 13877,13884SS | 0.6 | Start No Earlier Than | Warning
32236 | Yolo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
32237 | Yolo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32251 | Yolo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
32254 | Yolo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32255 | Yolo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32256 | Yolo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32257 | Yolo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
32258 | Yolo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13917 | 0 | Start No Earlier Than | Warning
32259 | Yolo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 13918 | 0 | Start No Earlier Than | Warning
32261 | Yolo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32262 | Yolo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13923SF+30d |  | 0 | Start No Earlier Than | Warning
32263 | Yolo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13924SF+30d |  | 0 | Start No Earlier Than | Warning
32264 | Yolo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13925SF+30d |  | 0 | Start No Earlier Than | Warning
32265 | Yolo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13926SF+30d |  | 0 | Start No Earlier Than | Warning
32266 | Yolo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 13927SF+30d |  | 0 | Start No Earlier Than | Warning
32269 | Yolo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
32270 | Yolo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 13929FS+12d | 0 | Start No Earlier Than | Warning
32271 | Yolo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
32272 | Yolo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 13929SF+60d | 0 | Start No Earlier Than | Warning
32273 | Yolo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13912SF+30d | 0 | Start No Earlier Than | Warning
32274 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13913SF+30d | 0 | Start No Earlier Than | Warning
32275 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13914SF+30d | 0 | Start No Earlier Than | Warning
32276 | Yolo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13915SF+30d | 0 | Start No Earlier Than | Warning
32277 | Yolo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 13916SF+30d | 0 | Start No Earlier Than | Warning
32278 | Yolo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32286 | Yuba CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32287 | Yuba CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32288 | Yuba CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32289 | Yuba CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
32290 | Yuba CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 245d |  |  | 0 | Start No Earlier Than | Warning
32291 | Yuba CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
32313 | Yuba CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32314 | Yuba CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32315 | Yuba CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
32316 | Yuba CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
32317 | Yuba CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
32318 | Yuba CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
32319 | Yuba CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
32320 | Yuba CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
32321 | Yuba CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
32322 | Yuba CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
32323 | Yuba CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
32324 | Yuba CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
32325 | Yuba CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
32326 | Yuba CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32327 | Yuba CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
32334 | Yuba CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
32335 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 13986SS | 0 | Start No Earlier Than | Warning
32337 | Yuba CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32338 | Yuba CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32339 | Yuba CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
32340 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 352d |  | 13991SS | 0 | Start No Earlier Than | Warning
32342 | Yuba CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
32343 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 288d |  | 13994SS | 0 | Start No Earlier Than | Warning
32344 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 13993SS |  | 0 | Start No Earlier Than | Warning
32345 | Yuba CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
32346 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 268d |  | 13997SS | 0 | Start No Earlier Than | Warning
32348 | Yuba CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32349 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 14000SS | 0 | Start No Earlier Than | Warning
32351 | Yuba CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
32359 | Yuba CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32363 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32364 | Yuba CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14015 | 1 | Start No Earlier Than | Warning
32367 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32368 | Yuba CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14019 | 0.2 | Start No Earlier Than | Warning
32371 | Yuba CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32372 | Yuba CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14023 | 0 | Start No Earlier Than | Warning
32375 | Yuba CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32376 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32393 | Yuba CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14041SF+30d |  | 0 | Start No Earlier Than | Warning
32394 | Yuba CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32408 | Yuba CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 14052,14059SS | 1 | Start No Earlier Than | Warning
32411 | Yuba CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
32412 | Yuba CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32426 | Yuba CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
32429 | Yuba CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32430 | Yuba CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32431 | Yuba CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32432 | Yuba CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM | 21 | 321d |  |  | 0 | Start No Earlier Than | Warning
32433 | Yuba CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 14092 | 0 | Start No Earlier Than | Warning
32434 | Yuba CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 14093 | 0 | Start No Earlier Than | Warning
32436 | Yuba CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32437 | Yuba CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14098SF+30d |  | 0 | Start No Earlier Than | Warning
32438 | Yuba CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14099SF+30d |  | 0 | Start No Earlier Than | Warning
32439 | Yuba CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14100SF+30d |  | 0 | Start No Earlier Than | Warning
32440 | Yuba CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14101SF+30d |  | 0 | Start No Earlier Than | Warning
32441 | Yuba CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 14102SF+30d |  | 0 | Start No Earlier Than | Warning
32444 | Yuba CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
32445 | Yuba CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 14104FS+12d | 0 | Start No Earlier Than | Warning
32446 | Yuba CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
32447 | Yuba CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  | 14104SF+60d | 0 | Start No Earlier Than | Warning
32448 | Yuba CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14087SF+30d | 0 | Start No Earlier Than | Warning
32449 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14088SF+30d | 0 | Start No Earlier Than | Warning
32450 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14089SF+30d | 0 | Start No Earlier Than | Warning
32451 | Yuba CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14090SF+30d | 0 | Start No Earlier Than | Warning
32452 | Yuba CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 14091SF+30d | 0 | Start No Earlier Than | Warning
32453 | Yuba CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32461 | Butte CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32462 | Butte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32463 | Butte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32464 | Butte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
32465 | Butte CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
32487 | Butte CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32488 | Butte CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32489 | Butte CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
32490 | Butte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
32491 | Butte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
32492 | Butte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
32493 | Butte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
32494 | Butte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
32495 | Butte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
32496 | Butte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
32497 | Butte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
32498 | Butte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
32499 | Butte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
32500 | Butte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32501 | Butte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
32508 | Butte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
32509 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14160SS | 0 | Start No Earlier Than | Warning
32511 | Butte CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32512 | Butte CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32513 | Butte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
32514 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14165SS | 0 | Finish No Earlier Than | Warning
32515 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14164SS |  | 0 | Start No Earlier Than | Warning
32516 | Butte CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
32517 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14168SS | 0 | Finish No Earlier Than | Warning
32518 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14167SS |  | 0 | Finish No Earlier Than | Warning
32519 | Butte CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
32520 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14171SS | 0 | Finish No Earlier Than | Warning
32521 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14170SS |  | 0 | Finish No Earlier Than | Warning
32522 | Butte CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
32523 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14174SS | 0 | Finish No Earlier Than | Warning
32524 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14173SS |  | 0 | Start No Earlier Than | Warning
32525 | Butte CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
32529 | Butte CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14178 |  | 0.2 | Finish No Earlier Than | Warning
32533 | Butte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32537 | Butte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32538 | Butte CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14189 | 1 | Start No Earlier Than | Warning
32541 | Butte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32542 | Butte CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 14193 | 1 | Start No Earlier Than | Warning
32545 | Butte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32546 | Butte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14197 | 0 | Start No Earlier Than | Warning
32549 | Butte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32550 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32567 | Butte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14215SF+30d |  | 0 | Start No Earlier Than | Warning
32568 | Butte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32582 | Butte CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 14226,14233SS | 1 | Start No Earlier Than | Warning
32585 | Butte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
32586 | Butte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32600 | Butte CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
32602 | Butte CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14259 | 0.2 | Start No Earlier Than | Warning
32603 | Butte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32604 | Butte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32605 | Butte CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32606 | Butte CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32607 | Butte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14266 | 0 | Start No Earlier Than | Warning
32608 | Butte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14267 | 0 | Start No Earlier Than | Warning
32610 | Butte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32611 | Butte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14272SF+30d | 0 | Finish No Earlier Than | Warning
32612 | Butte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14273SF+30d | 0 | Start No Earlier Than | Warning
32613 | Butte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14274SF+30d | 0 | Start No Earlier Than | Warning
32614 | Butte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14275SF+30d | 0 | Start No Earlier Than | Warning
32615 | Butte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14276SF+30d | 0 | Finish No Earlier Than | Warning
32618 | Butte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
32619 | Butte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14278FS+12d | 0 | Start No Earlier Than | Warning
32620 | Butte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32621 | Butte CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14278SF+60d | 0 | Finish No Earlier Than | Warning
32622 | Butte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14261SF+30d |  | 0 | Finish No Earlier Than | Warning
32623 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14262SF+30d |  | 0 | Finish No Earlier Than | Warning
32624 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14263SF+30d |  | 0 | Finish No Earlier Than | Warning
32625 | Butte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14264SF+30d |  | 0 | Finish No Earlier Than | Warning
32626 | Butte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14265SF+30d |  | 0 | Finish No Earlier Than | Warning
32627 | Butte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32628 | Butte CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14269FS+12d,14271SF+60d |  | 0 | Finish No Earlier Than | Warning
32635 | Fresno CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32636 | Fresno CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32637 | Fresno CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32638 | Fresno CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
32639 | Fresno CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
32661 | Fresno CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32662 | Fresno CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32663 | Fresno CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
32664 | Fresno CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
32665 | Fresno CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
32666 | Fresno CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
32667 | Fresno CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
32668 | Fresno CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
32669 | Fresno CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
32670 | Fresno CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
32671 | Fresno CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
32672 | Fresno CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
32673 | Fresno CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
32674 | Fresno CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32675 | Fresno CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
32682 | Fresno CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
32683 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14334SS | 0 | Start No Earlier Than | Warning
32685 | Fresno CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32686 | Fresno CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32687 | Fresno CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
32688 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14339SS | 0 | Finish No Earlier Than | Warning
32689 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14338SS |  | 0 | Start No Earlier Than | Warning
32690 | Fresno CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
32691 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14342SS | 0 | Finish No Earlier Than | Warning
32692 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14341SS |  | 0 | Finish No Earlier Than | Warning
32693 | Fresno CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
32694 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14345SS | 0 | Finish No Earlier Than | Warning
32695 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14344SS |  | 0 | Finish No Earlier Than | Warning
32696 | Fresno CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
32697 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14348SS | 0 | Finish No Earlier Than | Warning
32698 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14347SS |  | 0 | Start No Earlier Than | Warning
32699 | Fresno CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
32703 | Fresno CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14352 |  | 0.6 | Finish No Earlier Than | Warning
32707 | Fresno CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32711 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32712 | Fresno CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14363 | 1 | Start No Earlier Than | Warning
32715 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32716 | Fresno CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14367 | 0.2 | Start No Earlier Than | Warning
32719 | Fresno CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32720 | Fresno CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14371 | 0 | Start No Earlier Than | Warning
32723 | Fresno CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32724 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32741 | Fresno CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14389SF+30d |  | 0 | Start No Earlier Than | Warning
32742 | Fresno CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32756 | Fresno CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 14400,14407SS | 1 | Start No Earlier Than | Warning
32759 | Fresno CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
32760 | Fresno CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32774 | Fresno CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
32777 | Fresno CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32778 | Fresno CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32779 | Fresno CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32780 | Fresno CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32781 | Fresno CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14440 | 0 | Start No Earlier Than | Warning
32782 | Fresno CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14441 | 0 | Start No Earlier Than | Warning
32784 | Fresno CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32785 | Fresno CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14446SF+30d | 0 | Finish No Earlier Than | Warning
32786 | Fresno CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14447SF+30d | 0 | Start No Earlier Than | Warning
32787 | Fresno CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14448SF+30d | 0 | Start No Earlier Than | Warning
32788 | Fresno CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14449SF+30d | 0 | Start No Earlier Than | Warning
32789 | Fresno CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14450SF+30d | 0 | Finish No Earlier Than | Warning
32792 | Fresno CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
32793 | Fresno CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14452FS+12d | 0 | Start No Earlier Than | Warning
32794 | Fresno CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32795 | Fresno CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14452SF+60d | 0 | Finish No Earlier Than | Warning
32796 | Fresno CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14435SF+30d |  | 0 | Finish No Earlier Than | Warning
32797 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14436SF+30d |  | 0 | Finish No Earlier Than | Warning
32798 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14437SF+30d |  | 0 | Finish No Earlier Than | Warning
32799 | Fresno CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14438SF+30d |  | 0 | Finish No Earlier Than | Warning
32800 | Fresno CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14439SF+30d |  | 0 | Finish No Earlier Than | Warning
32801 | Fresno CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32802 | Fresno CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14443FS+12d,14445SF+60d |  | 0 | Finish No Earlier Than | Warning
32809 | San Diego CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32810 | San Diego CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32811 | San Diego CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32812 | San Diego CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
32813 | San Diego CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
32835 | San Diego CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32836 | San Diego CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
32837 | San Diego CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
32838 | San Diego CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
32839 | San Diego CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
32840 | San Diego CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
32841 | San Diego CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
32842 | San Diego CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
32843 | San Diego CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
32844 | San Diego CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
32845 | San Diego CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
32846 | San Diego CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
32847 | San Diego CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
32848 | San Diego CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
32849 | San Diego CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
32856 | San Diego CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
32857 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14508SS | 0 | Start No Earlier Than | Warning
32859 | San Diego CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32860 | San Diego CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
32861 | San Diego CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
32862 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14513SS | 0 | Finish No Earlier Than | Warning
32863 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14512SS |  | 0 | Start No Earlier Than | Warning
32864 | San Diego CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
32865 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14516SS | 0 | Finish No Earlier Than | Warning
32866 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14515SS |  | 0 | Finish No Earlier Than | Warning
32867 | San Diego CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
32868 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14519SS | 0 | Finish No Earlier Than | Warning
32869 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14518SS |  | 0 | Finish No Earlier Than | Warning
32870 | San Diego CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
32871 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14522SS | 0 | Finish No Earlier Than | Warning
32872 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14521SS |  | 0 | Start No Earlier Than | Warning
32873 | San Diego CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
32877 | San Diego CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14526 |  | 0.2 | Finish No Earlier Than | Warning
32881 | San Diego CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32885 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32886 | San Diego CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14537 | 1 | Start No Earlier Than | Warning
32889 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32890 | San Diego CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14541 | 0.6 | Start No Earlier Than | Warning
32893 | San Diego CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32894 | San Diego CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14545 | 0 | Start No Earlier Than | Warning
32897 | San Diego CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
32898 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
32901 | San Diego CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 14552SS | 1 | Start No Earlier Than | Warning
32915 | San Diego CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14563SF+30d |  | 0 | Start No Earlier Than | Warning
32916 | San Diego CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32919 | San Diego CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 0d |  | 14570SS | 1 | Start No Earlier Than | Warning
32930 | San Diego CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 508d |  | 14574,14581SS | 0.2 | Start No Earlier Than | Warning
32933 | San Diego CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
32934 | San Diego CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
32948 | San Diego CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
32950 | San Diego CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14607 | 0 | Start No Earlier Than | Warning
32951 | San Diego CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
32952 | San Diego CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
32953 | San Diego CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32954 | San Diego CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32955 | San Diego CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14614 | 0 | Start No Earlier Than | Warning
32956 | San Diego CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14615 | 0 | Start No Earlier Than | Warning
32958 | San Diego CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
32959 | San Diego CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14620SF+30d | 0 | Finish No Earlier Than | Warning
32960 | San Diego CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14621SF+30d | 0 | Start No Earlier Than | Warning
32961 | San Diego CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14622SF+30d | 0 | Start No Earlier Than | Warning
32962 | San Diego CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14623SF+30d | 0 | Start No Earlier Than | Warning
32963 | San Diego CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14624SF+30d | 0 | Finish No Earlier Than | Warning
32966 | San Diego CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
32967 | San Diego CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14626FS+12d | 0 | Start No Earlier Than | Warning
32968 | San Diego CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
32969 | San Diego CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14626SF+60d | 0 | Finish No Earlier Than | Warning
32970 | San Diego CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14609SF+30d |  | 0 | Finish No Earlier Than | Warning
32971 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14610SF+30d |  | 0 | Finish No Earlier Than | Warning
32972 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14611SF+30d |  | 0 | Finish No Earlier Than | Warning
32973 | San Diego CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14612SF+30d |  | 0 | Finish No Earlier Than | Warning
32974 | San Diego CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14613SF+30d |  | 0 | Finish No Earlier Than | Warning
32975 | San Diego CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
32976 | San Diego CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14617FS+12d,14619SF+60d |  | 0 | Finish No Earlier Than | Warning
32983 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
32984 | San Mateo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
32985 | San Mateo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
32986 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
32987 | San Mateo CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33009 | San Mateo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33010 | San Mateo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33011 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
33012 | San Mateo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33013 | San Mateo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33014 | San Mateo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33015 | San Mateo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33016 | San Mateo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33017 | San Mateo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33018 | San Mateo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33019 | San Mateo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33020 | San Mateo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33021 | San Mateo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33022 | San Mateo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33023 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33030 | San Mateo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
33031 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14682SS | 0 | Start No Earlier Than | Warning
33033 | San Mateo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33034 | San Mateo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33035 | San Mateo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33036 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14687SS | 0 | Finish No Earlier Than | Warning
33037 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14686SS |  | 0 | Start No Earlier Than | Warning
33038 | San Mateo CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33039 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14690SS | 0 | Finish No Earlier Than | Warning
33040 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14689SS |  | 0 | Finish No Earlier Than | Warning
33041 | San Mateo CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33042 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14693SS | 0 | Finish No Earlier Than | Warning
33043 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14692SS |  | 0 | Finish No Earlier Than | Warning
33044 | San Mateo CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33045 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14696SS | 0 | Finish No Earlier Than | Warning
33046 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14695SS |  | 0 | Start No Earlier Than | Warning
33047 | San Mateo CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33051 | San Mateo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14700 |  | 0.6 | Finish No Earlier Than | Warning
33055 | San Mateo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33059 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33060 | San Mateo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14711 | 1 | Start No Earlier Than | Warning
33063 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33064 | San Mateo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 14715 | 1 | Start No Earlier Than | Warning
33067 | San Mateo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33068 | San Mateo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 0d |  | 14719 | 1 | Start No Earlier Than | Warning
33071 | San Mateo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33072 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33089 | San Mateo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14737SF+30d |  | 0 | Start No Earlier Than | Warning
33090 | San Mateo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33104 | San Mateo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 14748,14755SS | 1 | Start No Earlier Than | Warning
33107 | San Mateo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
33108 | San Mateo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33122 | San Mateo CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33125 | San Mateo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33126 | San Mateo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33127 | San Mateo CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33128 | San Mateo CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33129 | San Mateo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14788 | 0 | Start No Earlier Than | Warning
33130 | San Mateo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14789 | 0 | Start No Earlier Than | Warning
33132 | San Mateo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
33133 | San Mateo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14794SF+30d | 0 | Finish No Earlier Than | Warning
33134 | San Mateo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14795SF+30d | 0 | Start No Earlier Than | Warning
33135 | San Mateo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14796SF+30d | 0 | Start No Earlier Than | Warning
33136 | San Mateo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14797SF+30d | 0 | Start No Earlier Than | Warning
33137 | San Mateo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14798SF+30d | 0 | Finish No Earlier Than | Warning
33140 | San Mateo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
33141 | San Mateo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14800FS+12d | 0 | Start No Earlier Than | Warning
33142 | San Mateo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
33143 | San Mateo CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14800SF+60d | 0 | Finish No Earlier Than | Warning
33144 | San Mateo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14783SF+30d |  | 0 | Finish No Earlier Than | Warning
33145 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14784SF+30d |  | 0 | Finish No Earlier Than | Warning
33146 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14785SF+30d |  | 0 | Finish No Earlier Than | Warning
33147 | San Mateo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14786SF+30d |  | 0 | Finish No Earlier Than | Warning
33148 | San Mateo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14787SF+30d |  | 0 | Finish No Earlier Than | Warning
33149 | San Mateo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
33150 | San Mateo CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14791FS+12d,14793SF+60d |  | 0 | Finish No Earlier Than | Warning
33157 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
33158 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33159 | Tuolumne CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
33160 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
33161 | Tuolumne CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33183 | Tuolumne CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33184 | Tuolumne CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33185 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
33186 | Tuolumne CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33187 | Tuolumne CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33188 | Tuolumne CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33189 | Tuolumne CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33190 | Tuolumne CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33191 | Tuolumne CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33192 | Tuolumne CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33193 | Tuolumne CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33194 | Tuolumne CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33195 | Tuolumne CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33196 | Tuolumne CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33197 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33204 | Tuolumne CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
33205 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 14856SS | 0 | Start No Earlier Than | Warning
33207 | Tuolumne CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33208 | Tuolumne CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33209 | Tuolumne CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33210 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 14861SS | 0 | Finish No Earlier Than | Warning
33211 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 14860SS |  | 0 | Start No Earlier Than | Warning
33212 | Tuolumne CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33213 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 14864SS | 0 | Finish No Earlier Than | Warning
33214 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 14863SS |  | 0 | Finish No Earlier Than | Warning
33215 | Tuolumne CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33216 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 14867SS | 0 | Finish No Earlier Than | Warning
33217 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 14866SS |  | 0 | Finish No Earlier Than | Warning
33218 | Tuolumne CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33219 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 14870SS | 0 | Finish No Earlier Than | Warning
33220 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 14869SS |  | 0 | Start No Earlier Than | Warning
33221 | Tuolumne CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33225 | Tuolumne CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 14874 |  | 0.2 | Finish No Earlier Than | Warning
33229 | Tuolumne CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33233 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33234 | Tuolumne CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 14885 | 1 | Start No Earlier Than | Warning
33237 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33238 | Tuolumne CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 14889 | 0.6 | Start No Earlier Than | Warning
33241 | Tuolumne CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33242 | Tuolumne CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 14893 | 0 | Start No Earlier Than | Warning
33245 | Tuolumne CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33246 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33263 | Tuolumne CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14911SF+30d |  | 0 | Start No Earlier Than | Warning
33264 | Tuolumne CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33278 | Tuolumne CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 14922,14929SS | 1 | Start No Earlier Than | Warning
33281 | Tuolumne CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
33282 | Tuolumne CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33296 | Tuolumne CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33298 | Tuolumne CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 14955 | 0.2 | Start No Earlier Than | Warning
33299 | Tuolumne CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33300 | Tuolumne CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33301 | Tuolumne CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33302 | Tuolumne CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33303 | Tuolumne CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14962 | 0 | Start No Earlier Than | Warning
33304 | Tuolumne CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 14963 | 0 | Start No Earlier Than | Warning
33306 | Tuolumne CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
33307 | Tuolumne CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14968SF+30d | 0 | Finish No Earlier Than | Warning
33308 | Tuolumne CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14969SF+30d | 0 | Start No Earlier Than | Warning
33309 | Tuolumne CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14970SF+30d | 0 | Start No Earlier Than | Warning
33310 | Tuolumne CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14971SF+30d | 0 | Start No Earlier Than | Warning
33311 | Tuolumne CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 14972SF+30d | 0 | Finish No Earlier Than | Warning
33314 | Tuolumne CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
33315 | Tuolumne CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 14974FS+12d | 0 | Start No Earlier Than | Warning
33316 | Tuolumne CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
33317 | Tuolumne CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 14974SF+60d | 0 | Finish No Earlier Than | Warning
33318 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14957SF+30d |  | 0 | Finish No Earlier Than | Warning
33319 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14958SF+30d |  | 0 | Finish No Earlier Than | Warning
33320 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14959SF+30d |  | 0 | Finish No Earlier Than | Warning
33321 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14960SF+30d |  | 0 | Finish No Earlier Than | Warning
33322 | Tuolumne CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 14961SF+30d |  | 0 | Finish No Earlier Than | Warning
33323 | Tuolumne CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
33324 | Tuolumne CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 14965FS+12d,14967SF+60d |  | 0 | Finish No Earlier Than | Warning
33331 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
33332 | Calaveras CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33333 | Calaveras CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
33334 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
33335 | Calaveras CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33357 | Calaveras CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33358 | Calaveras CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33359 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
33360 | Calaveras CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33361 | Calaveras CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33362 | Calaveras CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33363 | Calaveras CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33364 | Calaveras CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33365 | Calaveras CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33366 | Calaveras CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33367 | Calaveras CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33368 | Calaveras CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33369 | Calaveras CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33370 | Calaveras CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33371 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33378 | Calaveras CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
33379 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15030SS | 0 | Start No Earlier Than | Warning
33381 | Calaveras CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33382 | Calaveras CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33383 | Calaveras CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33384 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15035SS | 0 | Finish No Earlier Than | Warning
33385 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15034SS |  | 0 | Start No Earlier Than | Warning
33386 | Calaveras CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33387 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15038SS | 0 | Finish No Earlier Than | Warning
33388 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15037SS |  | 0 | Finish No Earlier Than | Warning
33389 | Calaveras CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33390 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15041SS | 0 | Finish No Earlier Than | Warning
33391 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15040SS |  | 0 | Finish No Earlier Than | Warning
33392 | Calaveras CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33393 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15044SS | 0 | Finish No Earlier Than | Warning
33394 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15043SS |  | 0 | Start No Earlier Than | Warning
33395 | Calaveras CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33399 | Calaveras CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15048 |  | 0.2 | Finish No Earlier Than | Warning
33403 | Calaveras CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33407 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33408 | Calaveras CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 15059 | 1 | Start No Earlier Than | Warning
33411 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33412 | Calaveras CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15063 | 0.6 | Start No Earlier Than | Warning
33415 | Calaveras CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33416 | Calaveras CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15067 | 0 | Start No Earlier Than | Warning
33419 | Calaveras CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33420 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33423 | Calaveras CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 15074SS | 0.6 | Start No Earlier Than | Warning
33437 | Calaveras CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15085SF+30d |  | 0 | Start No Earlier Than | Warning
33438 | Calaveras CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33441 | Calaveras CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 190 | 485d |  | 15092SS | 0.8 | Start No Earlier Than | Warning
33452 | Calaveras CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 15096,15103SS | 1 | Start No Earlier Than | Warning
33455 | Calaveras CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Start No Earlier Than | Warning
33456 | Calaveras CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33470 | Calaveras CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33472 | Calaveras CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15129 | 0.2 | Start No Earlier Than | Warning
33473 | Calaveras CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33474 | Calaveras CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33475 | Calaveras CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33476 | Calaveras CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33477 | Calaveras CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15136 | 0 | Start No Earlier Than | Warning
33478 | Calaveras CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15137 | 0 | Start No Earlier Than | Warning
33480 | Calaveras CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
33481 | Calaveras CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15142SF+30d | 0 | Finish No Earlier Than | Warning
33482 | Calaveras CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15143SF+30d | 0 | Start No Earlier Than | Warning
33483 | Calaveras CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15144SF+30d | 0 | Start No Earlier Than | Warning
33484 | Calaveras CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15145SF+30d | 0 | Start No Earlier Than | Warning
33485 | Calaveras CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15146SF+30d | 0 | Finish No Earlier Than | Warning
33488 | Calaveras CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
33489 | Calaveras CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15148FS+12d | 0 | Start No Earlier Than | Warning
33490 | Calaveras CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
33491 | Calaveras CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15148SF+60d | 0 | Finish No Earlier Than | Warning
33492 | Calaveras CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15131SF+30d |  | 0 | Finish No Earlier Than | Warning
33493 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15132SF+30d |  | 0 | Finish No Earlier Than | Warning
33494 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15133SF+30d |  | 0 | Finish No Earlier Than | Warning
33495 | Calaveras CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15134SF+30d |  | 0 | Finish No Earlier Than | Warning
33496 | Calaveras CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15135SF+30d |  | 0 | Finish No Earlier Than | Warning
33497 | Calaveras CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
33498 | Calaveras CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15139FS+12d,15141SF+60d |  | 0 | Finish No Earlier Than | Warning
33505 | Kings CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
33506 | Kings CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33507 | Kings CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
33508 | Kings CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
33509 | Kings CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33531 | Kings CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33532 | Kings CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33533 | Kings CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
33534 | Kings CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33535 | Kings CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33536 | Kings CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33537 | Kings CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33538 | Kings CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33539 | Kings CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33540 | Kings CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33541 | Kings CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33542 | Kings CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33543 | Kings CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33544 | Kings CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33545 | Kings CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33552 | Kings CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
33553 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15204SS | 0 | Start No Earlier Than | Warning
33555 | Kings CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33556 | Kings CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33557 | Kings CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33558 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15209SS | 0 | Finish No Earlier Than | Warning
33559 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15208SS |  | 0 | Start No Earlier Than | Warning
33560 | Kings CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33561 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15212SS | 0 | Finish No Earlier Than | Warning
33562 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15211SS |  | 0 | Finish No Earlier Than | Warning
33563 | Kings CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33564 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15215SS | 0 | Finish No Earlier Than | Warning
33565 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15214SS |  | 0 | Finish No Earlier Than | Warning
33566 | Kings CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33567 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15218SS | 0 | Finish No Earlier Than | Warning
33568 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15217SS |  | 0 | Start No Earlier Than | Warning
33569 | Kings CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33573 | Kings CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15222 |  | 0.2 | Finish No Earlier Than | Warning
33577 | Kings CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33581 | Kings CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33582 | Kings CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 15233 | 1 | Start No Earlier Than | Warning
33585 | Kings CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33586 | Kings CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15237 | 0.2 | Start No Earlier Than | Warning
33589 | Kings CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33590 | Kings CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15241 | 0 | Start No Earlier Than | Warning
33593 | Kings CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33594 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33611 | Kings CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15259SF+30d |  | 0 | Start No Earlier Than | Warning
33612 | Kings CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33626 | Kings CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 15270,15277SS | 1 | Start No Earlier Than | Warning
33629 | Kings CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
33630 | Kings CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33644 | Kings CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33646 | Kings CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15303 | 0.2 | Start No Earlier Than | Warning
33647 | Kings CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33648 | Kings CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33649 | Kings CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33650 | Kings CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33651 | Kings CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15310 | 0 | Start No Earlier Than | Warning
33652 | Kings CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15311 | 0 | Start No Earlier Than | Warning
33654 | Kings CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
33655 | Kings CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15316SF+30d | 0 | Finish No Earlier Than | Warning
33656 | Kings CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15317SF+30d | 0 | Start No Earlier Than | Warning
33657 | Kings CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15318SF+30d | 0 | Start No Earlier Than | Warning
33658 | Kings CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15319SF+30d | 0 | Start No Earlier Than | Warning
33659 | Kings CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15320SF+30d | 0 | Finish No Earlier Than | Warning
33662 | Kings CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
33663 | Kings CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15322FS+12d | 0 | Start No Earlier Than | Warning
33664 | Kings CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
33665 | Kings CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15322SF+60d | 0 | Finish No Earlier Than | Warning
33666 | Kings CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15305SF+30d |  | 0 | Finish No Earlier Than | Warning
33667 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15306SF+30d |  | 0 | Finish No Earlier Than | Warning
33668 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15307SF+30d |  | 0 | Finish No Earlier Than | Warning
33669 | Kings CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15308SF+30d |  | 0 | Finish No Earlier Than | Warning
33670 | Kings CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15309SF+30d |  | 0 | Finish No Earlier Than | Warning
33671 | Kings CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
33672 | Kings CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15313FS+12d,15315SF+60d |  | 0 | Finish No Earlier Than | Warning
33679 | Riverside CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
33680 | Riverside CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33681 | Riverside CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
33682 | Riverside CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
33683 | Riverside CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33705 | Riverside CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33706 | Riverside CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33707 | Riverside CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
33708 | Riverside CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33709 | Riverside CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33710 | Riverside CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33711 | Riverside CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33712 | Riverside CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33713 | Riverside CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33714 | Riverside CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33715 | Riverside CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33716 | Riverside CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33717 | Riverside CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33718 | Riverside CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33719 | Riverside CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33726 | Riverside CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
33727 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15378SS | 0 | Start No Earlier Than | Warning
33729 | Riverside CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33730 | Riverside CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33731 | Riverside CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33732 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15383SS | 0 | Finish No Earlier Than | Warning
33733 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15382SS |  | 0 | Start No Earlier Than | Warning
33734 | Riverside CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33735 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15386SS | 0 | Finish No Earlier Than | Warning
33736 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15385SS |  | 0 | Finish No Earlier Than | Warning
33737 | Riverside CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33738 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15389SS | 0 | Finish No Earlier Than | Warning
33739 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15388SS |  | 0 | Finish No Earlier Than | Warning
33740 | Riverside CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33741 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15392SS | 0 | Finish No Earlier Than | Warning
33742 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15391SS |  | 0 | Start No Earlier Than | Warning
33743 | Riverside CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33747 | Riverside CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15396 |  | 0.4 | Finish No Earlier Than | Warning
33751 | Riverside CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33755 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33756 | Riverside CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 15407 | 1 | Start No Earlier Than | Warning
33759 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33760 | Riverside CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15411 | 0.2 | Start No Earlier Than | Warning
33763 | Riverside CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning