33764 | Riverside CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15415 | 0 | Start No Earlier Than | Warning
33767 | Riverside CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33768 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33785 | Riverside CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15433SF+30d |  | 0 | Start No Earlier Than | Warning
33786 | Riverside CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33800 | Riverside CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 15444,15451SS | 1 | Start No Earlier Than | Warning
33803 | Riverside CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
33804 | Riverside CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33818 | Riverside CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33820 | Riverside CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 256d |  | 15477 | 0.2 | Start No Earlier Than | Warning
33821 | Riverside CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33822 | Riverside CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33823 | Riverside CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33824 | Riverside CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33825 | Riverside CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15484 | 0 | Start No Earlier Than | Warning
33826 | Riverside CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15485 | 0 | Start No Earlier Than | Warning
33828 | Riverside CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
33829 | Riverside CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15490SF+30d | 0 | Finish No Earlier Than | Warning
33830 | Riverside CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15491SF+30d | 0 | Start No Earlier Than | Warning
33831 | Riverside CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15492SF+30d | 0 | Start No Earlier Than | Warning
33832 | Riverside CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15493SF+30d | 0 | Start No Earlier Than | Warning
33833 | Riverside CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15494SF+30d | 0 | Finish No Earlier Than | Warning
33836 | Riverside CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
33837 | Riverside CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15496FS+12d | 0 | Start No Earlier Than | Warning
33838 | Riverside CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
33839 | Riverside CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15496SF+60d | 0 | Finish No Earlier Than | Warning
33840 | Riverside CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15479SF+30d |  | 0 | Finish No Earlier Than | Warning
33841 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15480SF+30d |  | 0 | Finish No Earlier Than | Warning
33842 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15481SF+30d |  | 0 | Finish No Earlier Than | Warning
33843 | Riverside CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15482SF+30d |  | 0 | Finish No Earlier Than | Warning
33844 | Riverside CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15483SF+30d |  | 0 | Finish No Earlier Than | Warning
33845 | Riverside CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
33846 | Riverside CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15487FS+12d,15489SF+60d |  | 0 | Finish No Earlier Than | Warning
33853 | Ventura CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
33854 | Ventura CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33855 | Ventura CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
33856 | Ventura CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Finish No Earlier Than | Warning
33857 | Ventura CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 43 | 235d |  |  | 0 | Finish No Earlier Than | Warning
33879 | Ventura CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33880 | Ventura CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
33881 | Ventura CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 486d |  |  | 0 | Start No Earlier Than | Warning
33882 | Ventura CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
33883 | Ventura CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
33884 | Ventura CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
33885 | Ventura CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
33886 | Ventura CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Finish No Earlier Than | Warning
33887 | Ventura CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
33888 | Ventura CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
33889 | Ventura CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
33890 | Ventura CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
33891 | Ventura CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
33892 | Ventura CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
33893 | Ventura CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
33900 | Ventura CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
33901 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15552SS | 0 | Start No Earlier Than | Warning
33903 | Ventura CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33904 | Ventura CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
33905 | Ventura CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 64 | 342d |  |  | 0 | Start No Earlier Than | Warning
33906 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  | 15557SS | 0 | Finish No Earlier Than | Warning
33907 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 35 | 371d | 15556SS |  | 0 | Start No Earlier Than | Warning
33908 | Ventura CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
33909 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  | 15560SS | 0 | Finish No Earlier Than | Warning
33910 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 31 | 332d | 15559SS |  | 0 | Finish No Earlier Than | Warning
33911 | Ventura CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
33912 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15563SS | 0 | Finish No Earlier Than | Warning
33913 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 15562SS |  | 0 | Finish No Earlier Than | Warning
33914 | Ventura CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
33915 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  | 15566SS | 0 | Finish No Earlier Than | Warning
33916 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 32 | 289d | 15565SS |  | 0 | Start No Earlier Than | Warning
33917 | Ventura CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
33921 | Ventura CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 588 | 277d | 15570 |  | 0.4 | Finish No Earlier Than | Warning
33925 | Ventura CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33929 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33930 | Ventura CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 43 | 0d |  | 15581 | 1 | Start No Earlier Than | Warning
33933 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33934 | Ventura CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 15585 | 0.4 | Start No Earlier Than | Warning
33937 | Ventura CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33938 | Ventura CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 362d |  | 15589 | 0 | Start No Earlier Than | Warning
33941 | Ventura CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
33942 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Finish No Earlier Than | Warning
33959 | Ventura CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15607SF+30d |  | 0 | Start No Earlier Than | Warning
33960 | Ventura CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33974 | Ventura CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 64 | 0d |  | 15618,15625SS | 1 | Start No Earlier Than | Warning
33977 | Ventura CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Start No Earlier Than | Warning
33978 | Ventura CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Finish No Earlier Than | Warning
33992 | Ventura CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
33995 | Ventura CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
33996 | Ventura CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
33997 | Ventura CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33998 | Ventura CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
33999 | Ventura CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15658 | 0 | Start No Earlier Than | Warning
34000 | Ventura CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 15659 | 0 | Start No Earlier Than | Warning
34002 | Ventura CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
34003 | Ventura CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15664SF+30d | 0 | Finish No Earlier Than | Warning
34004 | Ventura CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15665SF+30d | 0 | Start No Earlier Than | Warning
34005 | Ventura CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15666SF+30d | 0 | Start No Earlier Than | Warning
34006 | Ventura CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15667SF+30d | 0 | Start No Earlier Than | Warning
34007 | Ventura CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 333d |  | 15668SF+30d | 0 | Finish No Earlier Than | Warning
34010 | Ventura CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
34011 | Ventura CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 15670FS+12d | 0 | Start No Earlier Than | Warning
34012 | Ventura CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Finish No Earlier Than | Warning
34013 | Ventura CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d |  | 15670SF+60d | 0 | Finish No Earlier Than | Warning
34014 | Ventura CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15653SF+30d |  | 0 | Finish No Earlier Than | Warning
34015 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15654SF+30d |  | 0 | Finish No Earlier Than | Warning
34016 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15655SF+30d |  | 0 | Finish No Earlier Than | Warning
34017 | Ventura CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15656SF+30d |  | 0 | Finish No Earlier Than | Warning
34018 | Ventura CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 299d | 15657SF+30d |  | 0 | Finish No Earlier Than | Warning
34019 | Ventura CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34020 | Ventura CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20 | 279d | 15661FS+12d,15663SF+60d |  | 0 | Finish No Earlier Than | Warning
34030 | Alameda PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34031 | Alameda PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34032 | Alameda PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34033 | Alameda PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34034 | Alameda PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34035 | Alameda PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34036 | Alameda PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34037 | Alameda PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34038 | Alameda PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34039 | Alameda PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34040 | Alameda PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34041 | Alameda PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34042 | Alameda PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34043 | Alameda PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34044 | Alameda PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34045 | Alameda PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34046 | Alameda PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34047 | Alameda PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34048 | Alameda PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34049 | Alameda PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34050 | Alameda PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34051 | Alameda PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34052 | Alameda PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34053 | Alameda PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34054 | Alameda PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34055 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15701SS | 0 | Start No Earlier Than | Warning
34056 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15700SS |  | 0 | Finish No Earlier Than | Warning
34057 | Alameda PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15703SS | 0 | Start No Earlier Than | Warning
34058 | Alameda PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15702SS |  | 0 | Start No Earlier Than | Warning
34059 | Alameda PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
34060 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15706SS | 0 | Finish No Earlier Than | Warning
34061 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15705SS |  | 0 | Finish No Earlier Than | Warning
34062 | Alameda PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
34063 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15709SS | 0 | Finish No Earlier Than | Warning
34065 | Alameda PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
34066 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15712SS | 0 | Finish No Earlier Than | Warning
34067 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15711SS |  | 0 | Start No Earlier Than | Warning
34068 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15714SS | 0 | Start No Earlier Than | Warning
34069 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15713SS |  | 0 | Start No Earlier Than | Warning
34070 | Alameda PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34071 | Alameda PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
34074 | Alameda PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34075 | Alameda PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34076 | Alameda PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
34077 | Alameda PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 15723FS+10d | 0 | Start No Earlier Than | Warning
34078 | Alameda PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 15722FS+10d |  | 0 | Start No Earlier Than | Warning
34080 | Alameda PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 15727FS-1d | 1 | Start No Earlier Than | Warning
34081 | Alameda PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34082 | Alameda PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 15725FS-1d |  | 0.2 | Start No Earlier Than | Warning
34083 | Alameda PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34084 | Alameda PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 15730 | 1 | Start No Earlier Than | Warning
34085 | Alameda PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15729 |  | 0 | Start No Earlier Than | Warning
34086 | Alameda PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34087 | Alameda PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 15733FS+19d | 0 | Finish No Earlier Than | Warning
34088 | Alameda PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 15732FS+19d | 15734 | 0 | Start No Earlier Than | Warning
34090 | Alameda PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34091 | Alameda PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 15737 | 0 | Start No Earlier Than | Warning
34092 | Alameda PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 15736 | 15738FS-1d | 0 | Start No Earlier Than | Warning
34093 | Alameda PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 15737FS-1d |  | 0 | Finish No Earlier Than | Warning
34094 | Alameda PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34095 | Alameda PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34098 | Alameda PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15744SS | 0 | Finish No Earlier Than | Warning
34099 | Alameda PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15743SS |  | 0 | Finish No Earlier Than | Warning
34100 | Alameda PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34101 | Alameda PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34103 | Alameda PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15749SS | 0 | Finish No Earlier Than | Warning
34104 | Alameda PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15748SS | 15763SS | 0 | Start No Earlier Than | Warning
34106 | Alameda PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34107 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34109 | Alameda PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 15755SS | 0 | Start No Earlier Than | Warning
34110 | Alameda PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15754SS | 15756SS,15757 | 0 | Finish No Earlier Than | Warning
34112 | Alameda PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15755,15756 |  | 0 | Finish No Earlier Than | Warning
34113 | Alameda PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34115 | Alameda PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15761SS | 0 | Finish No Earlier Than | Warning
34116 | Alameda PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15760SS |  | 0 | Finish No Earlier Than | Warning
34117 | Alameda PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34118 | Alameda PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15749SS |  | 0 | Finish No Earlier Than | Warning
34120 | Alameda PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15766SS | 0 | Finish No Earlier Than | Warning
34121 | Alameda PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15765SS |  | 0 | Finish No Earlier Than | Warning
34123 | Alameda PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 15769SS+18d | 0 | Start No Earlier Than | Warning
34124 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 15768SS+18d |  | 0 | Finish No Earlier Than | Warning
34126 | Alameda PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 15772SS | 0 | Start No Earlier Than | Warning
34127 | Alameda PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 15771SS |  | 0 | Finish No Earlier Than | Warning
34128 | Alameda PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15774 | 0 | Start No Earlier Than | Warning
34129 | Alameda PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15773 |  | 0 | Finish No Earlier Than | Warning
34130 | Alameda PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34132 | Alameda PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 15778SS | 0 | Start No Earlier Than | Warning
34133 | Alameda PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15777SS | 15779SS | 0 | Finish No Earlier Than | Warning
34134 | Alameda PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15778SS | 15780SS | 0 | Finish No Earlier Than | Warning
34135 | Alameda PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15779SS | 15781SS | 0 | Finish No Earlier Than | Warning
34136 | Alameda PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15780SS | 15782SS | 0 | Finish No Earlier Than | Warning
34137 | Alameda PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15781SS | 15783SS | 0 | Finish No Earlier Than | Warning
34138 | Alameda PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15782SS | 15784SS | 0 | Finish No Earlier Than | Warning
34139 | Alameda PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15783SS | 15785SS | 0 | Finish No Earlier Than | Warning
34140 | Alameda PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15784SS | 15786SS | 0 | Finish No Earlier Than | Warning
34141 | Alameda PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15785SS | 15787SS | 0 | Finish No Earlier Than | Warning
34142 | Alameda PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15786SS |  | 0 | Finish No Earlier Than | Warning
34143 | Alameda PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
34144 | Alameda PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
34146 | Alameda PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 15792SS,15796 | 0 | Start No Earlier Than | Warning
34147 | Alameda PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 15791SS |  | 0 | Start No Earlier Than | Warning
34148 | Alameda PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34149 | Alameda PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15802 | 0 | Start No Earlier Than | Warning
34150 | Alameda PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15803 | 0 | Start No Earlier Than | Warning
34151 | Alameda PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 15791 |  | 0 | Start No Earlier Than | Warning
34152 | Alameda PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34153 | Alameda PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 15799SS,15807SS+20d | 0 | Start No Earlier Than | Warning
34154 | Alameda PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15798SS | 15800SS,15808SS+20d | 0 | Finish No Earlier Than | Warning
34155 | Alameda PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15799SS | 15809SS+20d | 0 | Finish No Earlier Than | Warning
34156 | Alameda PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34157 | Alameda PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15794 | 15803SS | 0 | Start No Earlier Than | Warning
34158 | Alameda PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15795,15802SS |  | 0 | Finish No Earlier Than | Warning
34159 | Alameda PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 15812FS+12d | 0 | Start No Earlier Than | Warning
34160 | Alameda PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15806SS | 0 | Start No Earlier Than | Warning
34161 | Alameda PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 15805SS |  | 0 | Start No Earlier Than | Warning
34165 | Alameda PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 15812SS+44d | 0 | Start No Earlier Than | Warning
34166 | Alameda PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34171 | Alpine PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34172 | Alpine PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34173 | Alpine PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34174 | Alpine PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34175 | Alpine PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34176 | Alpine PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34177 | Alpine PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34178 | Alpine PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34179 | Alpine PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34180 | Alpine PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34181 | Alpine PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34182 | Alpine PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34183 | Alpine PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34184 | Alpine PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34185 | Alpine PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34186 | Alpine PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34187 | Alpine PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34188 | Alpine PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34189 | Alpine PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34190 | Alpine PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34191 | Alpine PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34192 | Alpine PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34193 | Alpine PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34194 | Alpine PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34195 | Alpine PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34196 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15842SS | 0 | Start No Earlier Than | Warning
34197 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15841SS |  | 0 | Finish No Earlier Than | Warning
34198 | Alpine PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15844SS | 0 | Start No Earlier Than | Warning
34199 | Alpine PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15843SS |  | 0 | Start No Earlier Than | Warning
34200 | Alpine PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
34201 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15847SS | 0 | Finish No Earlier Than | Warning
34202 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15846SS |  | 0 | Finish No Earlier Than | Warning
34203 | Alpine PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
34204 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15850SS | 0 | Finish No Earlier Than | Warning
34206 | Alpine PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
34207 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15853SS | 0 | Finish No Earlier Than | Warning
34208 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15852SS |  | 0 | Start No Earlier Than | Warning
34209 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15855SS | 0 | Start No Earlier Than | Warning
34210 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15854SS |  | 0 | Start No Earlier Than | Warning
34211 | Alpine PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34212 | Alpine PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
34215 | Alpine PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34216 | Alpine PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34217 | Alpine PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
34218 | Alpine PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 15864FS+10d | 0 | Start No Earlier Than | Warning
34219 | Alpine PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 15863FS+10d |  | 0 | Start No Earlier Than | Warning
34221 | Alpine PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 15868FS-1d | 1 | Start No Earlier Than | Warning
34222 | Alpine PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34223 | Alpine PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 15866FS-1d |  | 0.6 | Start No Earlier Than | Warning
34224 | Alpine PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34225 | Alpine PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 15871 | 1 | Start No Earlier Than | Warning
34226 | Alpine PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15870 |  | 0 | Start No Earlier Than | Warning
34227 | Alpine PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34228 | Alpine PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 15874FS+19d | 0 | Finish No Earlier Than | Warning
34229 | Alpine PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 15873FS+19d | 15875 | 0 | Start No Earlier Than | Warning
34231 | Alpine PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34232 | Alpine PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 15878 | 0 | Start No Earlier Than | Warning
34233 | Alpine PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 15877 | 15879FS-1d | 0 | Start No Earlier Than | Warning
34234 | Alpine PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 15878FS-1d |  | 0 | Finish No Earlier Than | Warning
34235 | Alpine PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34236 | Alpine PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34239 | Alpine PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15885SS | 0 | Finish No Earlier Than | Warning
34240 | Alpine PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15884SS |  | 0 | Finish No Earlier Than | Warning
34241 | Alpine PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34242 | Alpine PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34244 | Alpine PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15890SS | 0 | Finish No Earlier Than | Warning
34245 | Alpine PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15889SS | 15904SS | 0 | Start No Earlier Than | Warning
34247 | Alpine PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34248 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34250 | Alpine PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 15896SS | 0 | Start No Earlier Than | Warning
34251 | Alpine PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15895SS | 15897SS,15898 | 0 | Finish No Earlier Than | Warning
34253 | Alpine PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15896,15897 |  | 0 | Finish No Earlier Than | Warning
34254 | Alpine PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34256 | Alpine PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15902SS | 0 | Finish No Earlier Than | Warning
34257 | Alpine PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 15901SS |  | 0 | Finish No Earlier Than | Warning
34258 | Alpine PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34259 | Alpine PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15890SS |  | 0 | Finish No Earlier Than | Warning
34261 | Alpine PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 15907SS | 0 | Finish No Earlier Than | Warning
34262 | Alpine PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 15906SS |  | 0 | Finish No Earlier Than | Warning
34264 | Alpine PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 15910SS+18d | 0 | Start No Earlier Than | Warning
34265 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 15909SS+18d |  | 0 | Finish No Earlier Than | Warning
34267 | Alpine PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 15913SS | 0 | Start No Earlier Than | Warning
34268 | Alpine PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 15912SS |  | 0 | Finish No Earlier Than | Warning
34269 | Alpine PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15915 | 0 | Start No Earlier Than | Warning
34270 | Alpine PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 15914 |  | 0 | Finish No Earlier Than | Warning
34271 | Alpine PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34273 | Alpine PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 15919SS | 0 | Start No Earlier Than | Warning
34274 | Alpine PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15918SS | 15920SS | 0 | Finish No Earlier Than | Warning
34275 | Alpine PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15919SS | 15921SS | 0 | Finish No Earlier Than | Warning
34276 | Alpine PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15920SS | 15922SS | 0 | Finish No Earlier Than | Warning
34277 | Alpine PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15921SS | 15923SS | 0 | Finish No Earlier Than | Warning
34278 | Alpine PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15922SS | 15924SS | 0 | Finish No Earlier Than | Warning
34279 | Alpine PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15923SS | 15925SS | 0 | Finish No Earlier Than | Warning
34280 | Alpine PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15924SS | 15926SS | 0 | Finish No Earlier Than | Warning
34281 | Alpine PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15925SS | 15927SS | 0 | Finish No Earlier Than | Warning
34282 | Alpine PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15926SS | 15928SS | 0 | Finish No Earlier Than | Warning
34283 | Alpine PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 15927SS |  | 0 | Finish No Earlier Than | Warning
34284 | Alpine PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
34285 | Alpine PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
34287 | Alpine PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 15933SS,15937 | 0 | Start No Earlier Than | Warning
34288 | Alpine PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 15932SS |  | 0 | Start No Earlier Than | Warning
34289 | Alpine PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34290 | Alpine PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15943 | 0 | Start No Earlier Than | Warning
34291 | Alpine PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 15944 | 0 | Start No Earlier Than | Warning
34292 | Alpine PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 15932 |  | 0 | Start No Earlier Than | Warning
34293 | Alpine PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34294 | Alpine PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 15940SS,15948SS+20d | 0 | Start No Earlier Than | Warning
34295 | Alpine PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15939SS | 15941SS,15949SS+20d | 0 | Finish No Earlier Than | Warning
34296 | Alpine PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 15940SS | 15950SS+20d | 0 | Finish No Earlier Than | Warning
34297 | Alpine PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34298 | Alpine PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15935 | 15944SS | 0 | Start No Earlier Than | Warning
34299 | Alpine PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 15936,15943SS |  | 0 | Finish No Earlier Than | Warning
34300 | Alpine PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 15953FS+12d | 0 | Start No Earlier Than | Warning
34301 | Alpine PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 15947SS | 0 | Start No Earlier Than | Warning
34302 | Alpine PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 15946SS |  | 0 | Start No Earlier Than | Warning
34306 | Alpine PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 15953SS+44d | 0 | Start No Earlier Than | Warning
34307 | Alpine PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34312 | Amador PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34313 | Amador PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34314 | Amador PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34315 | Amador PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34316 | Amador PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34317 | Amador PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34318 | Amador PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34319 | Amador PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34320 | Amador PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34321 | Amador PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34322 | Amador PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34323 | Amador PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34324 | Amador PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34325 | Amador PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34326 | Amador PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34327 | Amador PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34328 | Amador PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34329 | Amador PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34330 | Amador PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34331 | Amador PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34332 | Amador PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34333 | Amador PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34334 | Amador PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34335 | Amador PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34336 | Amador PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34337 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 15983SS | 0 | Start No Earlier Than | Warning
34338 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 15982SS |  | 0 | Finish No Earlier Than | Warning
34339 | Amador PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 15985SS | 0 | Start No Earlier Than | Warning
34340 | Amador PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 15984SS |  | 0 | Start No Earlier Than | Warning
34341 | Amador PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
34342 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 15988SS | 0 | Finish No Earlier Than | Warning
34343 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 15987SS |  | 0 | Finish No Earlier Than | Warning
34344 | Amador PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
34345 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 15991SS | 0 | Finish No Earlier Than | Warning
34347 | Amador PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
34348 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 15994SS | 0 | Finish No Earlier Than | Warning
34349 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 15993SS |  | 0 | Start No Earlier Than | Warning
34350 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 15996SS | 0 | Start No Earlier Than | Warning
34351 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 15995SS |  | 0 | Start No Earlier Than | Warning
34352 | Amador PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34353 | Amador PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
34356 | Amador PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34357 | Amador PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34358 | Amador PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
34359 | Amador PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 16005FS+10d | 0 | Start No Earlier Than | Warning
34360 | Amador PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 16004FS+10d |  | 0 | Start No Earlier Than | Warning
34362 | Amador PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16009FS-1d | 1 | Start No Earlier Than | Warning
34363 | Amador PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34364 | Amador PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16007FS-1d |  | 0.6 | Start No Earlier Than | Warning
34365 | Amador PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34366 | Amador PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16012 | 1 | Start No Earlier Than | Warning
34367 | Amador PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16011 |  | 0 | Start No Earlier Than | Warning
34368 | Amador PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34369 | Amador PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16015FS+19d | 0 | Finish No Earlier Than | Warning
34370 | Amador PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16014FS+19d | 16016 | 0 | Start No Earlier Than | Warning
34372 | Amador PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34373 | Amador PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16019 | 0 | Start No Earlier Than | Warning
34374 | Amador PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16018 | 16020FS-1d | 0 | Start No Earlier Than | Warning
34375 | Amador PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16019FS-1d |  | 0 | Finish No Earlier Than | Warning
34376 | Amador PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34377 | Amador PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34380 | Amador PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16026SS | 0 | Finish No Earlier Than | Warning
34381 | Amador PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16025SS |  | 0 | Finish No Earlier Than | Warning
34382 | Amador PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34383 | Amador PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34385 | Amador PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16031SS | 0 | Finish No Earlier Than | Warning
34386 | Amador PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16030SS | 16045SS | 0 | Start No Earlier Than | Warning
34388 | Amador PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34389 | Amador PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34391 | Amador PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16037SS | 0 | Start No Earlier Than | Warning
34392 | Amador PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16036SS | 16038SS,16039 | 0 | Finish No Earlier Than | Warning
34394 | Amador PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16037,16038 |  | 0 | Finish No Earlier Than | Warning
34395 | Amador PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34397 | Amador PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16043SS | 0 | Finish No Earlier Than | Warning
34398 | Amador PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16042SS |  | 0 | Finish No Earlier Than | Warning
34399 | Amador PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34400 | Amador PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16031SS |  | 0 | Finish No Earlier Than | Warning
34402 | Amador PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16048SS | 0 | Finish No Earlier Than | Warning
34403 | Amador PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16047SS |  | 0 | Finish No Earlier Than | Warning
34405 | Amador PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16051SS+18d | 0 | Start No Earlier Than | Warning
34406 | Amador PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16050SS+18d |  | 0 | Finish No Earlier Than | Warning
34408 | Amador PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16054SS | 0 | Start No Earlier Than | Warning
34409 | Amador PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16053SS |  | 0 | Finish No Earlier Than | Warning
34410 | Amador PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16056 | 0 | Start No Earlier Than | Warning
34411 | Amador PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16055 |  | 0 | Finish No Earlier Than | Warning
34412 | Amador PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34414 | Amador PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16060SS | 0 | Start No Earlier Than | Warning
34415 | Amador PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16059SS | 16061SS | 0 | Finish No Earlier Than | Warning
34416 | Amador PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16060SS | 16062SS | 0 | Finish No Earlier Than | Warning
34417 | Amador PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16061SS | 16063SS | 0 | Finish No Earlier Than | Warning
34418 | Amador PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16062SS | 16064SS | 0 | Finish No Earlier Than | Warning
34419 | Amador PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16063SS | 16065SS | 0 | Finish No Earlier Than | Warning
34420 | Amador PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16064SS | 16066SS | 0 | Finish No Earlier Than | Warning
34421 | Amador PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16065SS | 16067SS | 0 | Finish No Earlier Than | Warning
34422 | Amador PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16066SS | 16068SS | 0 | Finish No Earlier Than | Warning
34423 | Amador PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16067SS | 16069SS | 0 | Finish No Earlier Than | Warning
34424 | Amador PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16068SS |  | 0 | Finish No Earlier Than | Warning
34425 | Amador PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
34426 | Amador PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
34428 | Amador PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16074SS,16078 | 0 | Start No Earlier Than | Warning
34429 | Amador PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16073SS |  | 0 | Start No Earlier Than | Warning
34430 | Amador PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34431 | Amador PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16084 | 0 | Start No Earlier Than | Warning
34432 | Amador PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16085 | 0 | Start No Earlier Than | Warning
34433 | Amador PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16073 |  | 0 | Start No Earlier Than | Warning
34434 | Amador PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34435 | Amador PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16081SS,16089SS+20d | 0 | Start No Earlier Than | Warning
34436 | Amador PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16080SS | 16082SS,16090SS+20d | 0 | Finish No Earlier Than | Warning
34437 | Amador PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16081SS | 16091SS+20d | 0 | Finish No Earlier Than | Warning
34438 | Amador PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34439 | Amador PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16076 | 16085SS | 0 | Start No Earlier Than | Warning
34440 | Amador PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16077,16084SS |  | 0 | Finish No Earlier Than | Warning
34441 | Amador PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16094FS+12d | 0 | Start No Earlier Than | Warning
34442 | Amador PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16088SS | 0 | Start No Earlier Than | Warning
34443 | Amador PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16087SS |  | 0 | Start No Earlier Than | Warning
34447 | Amador PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16094SS+44d | 0 | Start No Earlier Than | Warning
34448 | Amador PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34453 | Butte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34454 | Butte PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34455 | Butte PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34456 | Butte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34457 | Butte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34458 | Butte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34459 | Butte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34460 | Butte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34461 | Butte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34462 | Butte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34463 | Butte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34464 | Butte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34465 | Butte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34466 | Butte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34467 | Butte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34468 | Butte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34469 | Butte PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34470 | Butte PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34471 | Butte PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34472 | Butte PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34473 | Butte PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34474 | Butte PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34475 | Butte PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34476 | Butte PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34477 | Butte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34478 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16124SS | 0 | Start No Earlier Than | Warning
34479 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16123SS |  | 0 | Finish No Earlier Than | Warning
34480 | Butte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16126SS | 0 | Start No Earlier Than | Warning
34481 | Butte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16125SS |  | 0 | Start No Earlier Than | Warning
34482 | Butte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16129SS,16128SS | 0 | Finish No Earlier Than | Warning
34485 | Butte PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
34486 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16132SS | 0 | Start No Earlier Than | Warning
34488 | Butte PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
34489 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16135SS | 0 | Start No Earlier Than | Warning
34490 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16134SS |  | 0 | Start No Earlier Than | Warning
34491 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16137SS | 0 | Start No Earlier Than | Warning
34493 | Butte PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
34494 | Butte PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
34497 | Butte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34498 | Butte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34499 | Butte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
34500 | Butte PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
34502 | Butte PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16149FS-1d | 1 | Start No Earlier Than | Warning
34503 | Butte PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34504 | Butte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16147FS-1d |  | 0.2 | Start No Earlier Than | Warning
34505 | Butte PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34506 | Butte PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16152 | 1 | Start No Earlier Than | Warning
34507 | Butte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16151 |  | 0 | Start No Earlier Than | Warning
34508 | Butte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34509 | Butte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16155FS+19d | 0 | Finish No Earlier Than | Warning
34510 | Butte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16154FS+19d | 16156 | 0 | Start No Earlier Than | Warning
34512 | Butte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34513 | Butte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16159 | 0 | Start No Earlier Than | Warning
34514 | Butte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16158 | 16160FS-1d | 0 | Start No Earlier Than | Warning
34515 | Butte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16159FS-1d |  | 0 | Finish No Earlier Than | Warning
34516 | Butte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34517 | Butte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34520 | Butte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16166SS | 0 | Finish No Earlier Than | Warning
34521 | Butte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16165SS |  | 0 | Finish No Earlier Than | Warning
34522 | Butte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34523 | Butte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34525 | Butte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16171SS | 0 | Finish No Earlier Than | Warning
34526 | Butte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16170SS | 16185SS | 0 | Start No Earlier Than | Warning
34528 | Butte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34529 | Butte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34531 | Butte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16177SS | 0 | Start No Earlier Than | Warning
34532 | Butte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16176SS | 16178SS,16179 | 0 | Finish No Earlier Than | Warning
34534 | Butte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16177,16178 |  | 0 | Finish No Earlier Than | Warning
34535 | Butte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34537 | Butte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16183SS | 0 | Finish No Earlier Than | Warning
34538 | Butte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16182SS |  | 0 | Finish No Earlier Than | Warning
34539 | Butte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34540 | Butte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16171SS |  | 0 | Finish No Earlier Than | Warning
34542 | Butte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16188SS | 0 | Finish No Earlier Than | Warning
34543 | Butte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16187SS |  | 0 | Finish No Earlier Than | Warning
34545 | Butte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16191SS+18d | 0 | Start No Earlier Than | Warning
34546 | Butte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16190SS+18d |  | 0 | Finish No Earlier Than | Warning
34548 | Butte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16194SS | 0 | Start No Earlier Than | Warning
34549 | Butte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16193SS |  | 0 | Finish No Earlier Than | Warning
34550 | Butte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16196 | 0 | Start No Earlier Than | Warning
34551 | Butte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16195 |  | 0 | Finish No Earlier Than | Warning
34552 | Butte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34554 | Butte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16200SS | 0 | Start No Earlier Than | Warning
34555 | Butte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16199SS | 16201SS | 0 | Finish No Earlier Than | Warning
34556 | Butte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16200SS | 16202SS | 0 | Finish No Earlier Than | Warning
34557 | Butte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16201SS | 16203SS | 0 | Finish No Earlier Than | Warning
34558 | Butte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16202SS | 16204SS | 0 | Finish No Earlier Than | Warning
34559 | Butte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16203SS | 16205SS | 0 | Finish No Earlier Than | Warning
34560 | Butte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16204SS | 16206SS | 0 | Finish No Earlier Than | Warning
34561 | Butte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16205SS | 16207SS | 0 | Finish No Earlier Than | Warning
34562 | Butte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16206SS | 16208SS | 0 | Finish No Earlier Than | Warning
34563 | Butte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16207SS | 16209SS | 0 | Finish No Earlier Than | Warning
34564 | Butte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16208SS |  | 0 | Finish No Earlier Than | Warning
34565 | Butte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
34566 | Butte PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
34568 | Butte PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16214SS,16218 | 0 | Start No Earlier Than | Warning
34569 | Butte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16213SS |  | 0 | Start No Earlier Than | Warning
34570 | Butte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34571 | Butte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16224 | 0 | Start No Earlier Than | Warning
34572 | Butte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16225 | 0 | Start No Earlier Than | Warning
34573 | Butte PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16213 |  | 0 | Start No Earlier Than | Warning
34574 | Butte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34575 | Butte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 16221SS,16229SS+20d | 0 | Start No Earlier Than | Warning
34578 | Butte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34579 | Butte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16216 | 16225SS | 0 | Start No Earlier Than | Warning
34581 | Butte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 16234FS+12d | 0 | Start No Earlier Than | Warning
34582 | Butte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16228SS | 0 | Start No Earlier Than | Warning
34583 | Butte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16227SS |  | 0 | Start No Earlier Than | Warning
34587 | Butte PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 16234SS+44d | 0 | Start No Earlier Than | Warning
34588 | Butte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34593 | Calaveras PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34594 | Calaveras PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34595 | Calaveras PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34596 | Calaveras PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34597 | Calaveras PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34598 | Calaveras PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34599 | Calaveras PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34600 | Calaveras PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34601 | Calaveras PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34602 | Calaveras PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34603 | Calaveras PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34604 | Calaveras PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34605 | Calaveras PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34606 | Calaveras PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34607 | Calaveras PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34608 | Calaveras PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34609 | Calaveras PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34610 | Calaveras PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34611 | Calaveras PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34612 | Calaveras PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34613 | Calaveras PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34614 | Calaveras PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34615 | Calaveras PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34616 | Calaveras PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34617 | Calaveras PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34618 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16264SS | 0 | Start No Earlier Than | Warning
34619 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16263SS |  | 0 | Finish No Earlier Than | Warning
34620 | Calaveras PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16266SS | 0 | Start No Earlier Than | Warning
34621 | Calaveras PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16265SS |  | 0 | Start No Earlier Than | Warning
34622 | Calaveras PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16269SS,16268SS | 0 | Finish No Earlier Than | Warning
34625 | Calaveras PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
34626 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16272SS | 0 | Start No Earlier Than | Warning
34628 | Calaveras PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
34629 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16275SS | 0 | Start No Earlier Than | Warning
34630 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16274SS |  | 0 | Start No Earlier Than | Warning
34631 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16277SS | 0 | Start No Earlier Than | Warning
34633 | Calaveras PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
34634 | Calaveras PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
34637 | Calaveras PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34638 | Calaveras PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34639 | Calaveras PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
34640 | Calaveras PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
34642 | Calaveras PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16289FS-1d | 1 | Start No Earlier Than | Warning
34643 | Calaveras PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34644 | Calaveras PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16287FS-1d |  | 0.4 | Start No Earlier Than | Warning
34645 | Calaveras PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34646 | Calaveras PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16292 | 1 | Start No Earlier Than | Warning
34647 | Calaveras PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16291 |  | 0 | Start No Earlier Than | Warning
34648 | Calaveras PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34649 | Calaveras PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16295FS+19d | 0 | Finish No Earlier Than | Warning
34650 | Calaveras PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16294FS+19d | 16296 | 0 | Start No Earlier Than | Warning
34652 | Calaveras PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34653 | Calaveras PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16299 | 0 | Start No Earlier Than | Warning
34654 | Calaveras PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16298 | 16300FS-1d | 0 | Start No Earlier Than | Warning
34655 | Calaveras PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16299FS-1d |  | 0 | Finish No Earlier Than | Warning
34656 | Calaveras PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34657 | Calaveras PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34660 | Calaveras PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16306SS | 0 | Finish No Earlier Than | Warning
34661 | Calaveras PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16305SS |  | 0 | Finish No Earlier Than | Warning
34662 | Calaveras PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34663 | Calaveras PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34665 | Calaveras PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16311SS | 0 | Finish No Earlier Than | Warning
34666 | Calaveras PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16310SS | 16325SS | 0 | Start No Earlier Than | Warning
34668 | Calaveras PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34669 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34671 | Calaveras PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16317SS | 0 | Start No Earlier Than | Warning
34672 | Calaveras PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16316SS | 16318SS,16319 | 0 | Finish No Earlier Than | Warning
34674 | Calaveras PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16317,16318 |  | 0 | Finish No Earlier Than | Warning
34675 | Calaveras PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34677 | Calaveras PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16323SS | 0 | Finish No Earlier Than | Warning
34678 | Calaveras PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16322SS |  | 0 | Finish No Earlier Than | Warning
34679 | Calaveras PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34680 | Calaveras PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16311SS |  | 0 | Finish No Earlier Than | Warning
34682 | Calaveras PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16328SS | 0 | Finish No Earlier Than | Warning
34683 | Calaveras PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16327SS |  | 0 | Finish No Earlier Than | Warning
34685 | Calaveras PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16331SS+18d | 0 | Start No Earlier Than | Warning
34686 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16330SS+18d |  | 0 | Finish No Earlier Than | Warning
34688 | Calaveras PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16334SS | 0 | Start No Earlier Than | Warning
34689 | Calaveras PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16333SS |  | 0 | Finish No Earlier Than | Warning
34690 | Calaveras PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16336 | 0 | Start No Earlier Than | Warning
34691 | Calaveras PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16335 |  | 0 | Finish No Earlier Than | Warning
34692 | Calaveras PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34694 | Calaveras PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16340SS | 0 | Start No Earlier Than | Warning
34695 | Calaveras PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16339SS | 16341SS | 0 | Finish No Earlier Than | Warning
34696 | Calaveras PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16340SS | 16342SS | 0 | Finish No Earlier Than | Warning
34697 | Calaveras PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16341SS | 16343SS | 0 | Finish No Earlier Than | Warning
34698 | Calaveras PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16342SS | 16344SS | 0 | Finish No Earlier Than | Warning
34699 | Calaveras PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16343SS | 16345SS | 0 | Finish No Earlier Than | Warning
34700 | Calaveras PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16344SS | 16346SS | 0 | Finish No Earlier Than | Warning
34701 | Calaveras PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16345SS | 16347SS | 0 | Finish No Earlier Than | Warning
34702 | Calaveras PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16346SS | 16348SS | 0 | Finish No Earlier Than | Warning
34703 | Calaveras PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16347SS | 16349SS | 0 | Finish No Earlier Than | Warning
34704 | Calaveras PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16348SS |  | 0 | Finish No Earlier Than | Warning
34705 | Calaveras PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
34706 | Calaveras PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
34708 | Calaveras PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16354SS,16358 | 0 | Start No Earlier Than | Warning
34709 | Calaveras PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16353SS |  | 0 | Start No Earlier Than | Warning
34710 | Calaveras PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34711 | Calaveras PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16364 | 0 | Start No Earlier Than | Warning
34712 | Calaveras PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 16365 | 0 | Start No Earlier Than | Warning
34713 | Calaveras PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16353 |  | 0 | Start No Earlier Than | Warning
34714 | Calaveras PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34715 | Calaveras PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 16361SS,16369SS+20d | 0 | Start No Earlier Than | Warning
34718 | Calaveras PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34719 | Calaveras PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16356 | 16365SS | 0 | Start No Earlier Than | Warning
34721 | Calaveras PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 16374FS+12d | 0 | Start No Earlier Than | Warning
34722 | Calaveras PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16368SS | 0 | Start No Earlier Than | Warning
34723 | Calaveras PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16367SS |  | 0 | Start No Earlier Than | Warning
34727 | Calaveras PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 16374SS+44d | 0 | Start No Earlier Than | Warning
34728 | Calaveras PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34733 | Colusa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34734 | Colusa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34735 | Colusa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34736 | Colusa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34737 | Colusa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34738 | Colusa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34739 | Colusa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34740 | Colusa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34741 | Colusa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34742 | Colusa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34743 | Colusa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34744 | Colusa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34745 | Colusa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34746 | Colusa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34747 | Colusa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34748 | Colusa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34749 | Colusa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34750 | Colusa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34751 | Colusa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34752 | Colusa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34753 | Colusa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34754 | Colusa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34755 | Colusa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34756 | Colusa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34757 | Colusa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
34758 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16404SS | 0 | Start No Earlier Than | Warning
34759 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16403SS |  | 0 | Finish No Earlier Than | Warning
34760 | Colusa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16406SS | 0 | Start No Earlier Than | Warning
34761 | Colusa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16405SS |  | 0 | Start No Earlier Than | Warning
34762 | Colusa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
34763 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16409SS | 0 | Finish No Earlier Than | Warning
34764 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16408SS |  | 0 | Finish No Earlier Than | Warning
34765 | Colusa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
34766 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16412SS | 0 | Finish No Earlier Than | Warning
34768 | Colusa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
34769 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16415SS | 0 | Finish No Earlier Than | Warning
34770 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16414SS |  | 0 | Start No Earlier Than | Warning
34771 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16417SS | 0 | Start No Earlier Than | Warning
34772 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16416SS |  | 0 | Start No Earlier Than | Warning
34773 | Colusa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34774 | Colusa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
34777 | Colusa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34778 | Colusa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34779 | Colusa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
34780 | Colusa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 16426FS+10d | 0 | Start No Earlier Than | Warning
34781 | Colusa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 16425FS+10d |  | 0 | Start No Earlier Than | Warning
34783 | Colusa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16430FS-1d | 1 | Start No Earlier Than | Warning
34784 | Colusa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34785 | Colusa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16428FS-1d |  | 0.2 | Start No Earlier Than | Warning
34786 | Colusa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34787 | Colusa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16433 | 1 | Start No Earlier Than | Warning
34788 | Colusa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16432 |  | 0 | Start No Earlier Than | Warning
34789 | Colusa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34790 | Colusa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16436FS+19d | 0 | Finish No Earlier Than | Warning
34791 | Colusa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16435FS+19d | 16437 | 0 | Start No Earlier Than | Warning
34793 | Colusa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34794 | Colusa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16440 | 0 | Start No Earlier Than | Warning
34795 | Colusa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16439 | 16441FS-1d | 0 | Start No Earlier Than | Warning
34796 | Colusa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16440FS-1d |  | 0 | Finish No Earlier Than | Warning
34797 | Colusa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34798 | Colusa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34801 | Colusa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16447SS | 0 | Start No Earlier Than | Warning
34802 | Colusa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16446SS | 16448SS | 0 | Finish No Earlier Than | Warning
34803 | Colusa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16447SS | 16449SS | 0 | Finish No Earlier Than | Warning
34804 | Colusa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16448SS | 16450SS | 0 | Finish No Earlier Than | Warning
34805 | Colusa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16449SS | 16451SS | 0 | Finish No Earlier Than | Warning
34806 | Colusa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16450SS | 16452SS | 0 | Finish No Earlier Than | Warning
34807 | Colusa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16451SS | 16453SS | 0 | Finish No Earlier Than | Warning
34808 | Colusa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16452SS | 16454SS | 0 | Finish No Earlier Than | Warning
34809 | Colusa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16453SS | 16455SS | 0 | Finish No Earlier Than | Warning
34810 | Colusa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16454SS | 16456SS | 0 | Finish No Earlier Than | Warning
34811 | Colusa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16455SS |  | 0 | Finish No Earlier Than | Warning
34812 | Colusa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
34813 | Colusa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
34815 | Colusa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16461SS,16465 | 0 | Start No Earlier Than | Warning
34816 | Colusa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16460SS |  | 0 | Start No Earlier Than | Warning
34817 | Colusa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34818 | Colusa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16471 | 0 | Start No Earlier Than | Warning
34819 | Colusa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16472 | 0 | Start No Earlier Than | Warning
34820 | Colusa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16460 |  | 0 | Start No Earlier Than | Warning
34821 | Colusa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34822 | Colusa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16468SS,16476SS+20d | 0 | Start No Earlier Than | Warning
34823 | Colusa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16467SS | 16469SS,16477SS+20d | 0 | Finish No Earlier Than | Warning
34824 | Colusa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16468SS | 16478SS+20d | 0 | Finish No Earlier Than | Warning
34825 | Colusa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34826 | Colusa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16463 | 16472SS | 0 | Start No Earlier Than | Warning
34827 | Colusa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16464,16471SS |  | 0 | Finish No Earlier Than | Warning
34828 | Colusa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16481FS+12d | 0 | Start No Earlier Than | Warning
34829 | Colusa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16475SS | 0 | Start No Earlier Than | Warning
34830 | Colusa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16474SS |  | 0 | Start No Earlier Than | Warning
34834 | Colusa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16481SS+44d | 0 | Start No Earlier Than | Warning
34835 | Colusa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34840 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34841 | Contra Costa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34842 | Contra Costa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34843 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34844 | Contra Costa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34845 | Contra Costa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34846 | Contra Costa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34847 | Contra Costa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34848 | Contra Costa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34849 | Contra Costa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34850 | Contra Costa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34851 | Contra Costa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34852 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34853 | Contra Costa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34854 | Contra Costa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34855 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34856 | Contra Costa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34857 | Contra Costa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34858 | Contra Costa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34859 | Contra Costa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34860 | Contra Costa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34861 | Contra Costa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34862 | Contra Costa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34863 | Contra Costa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34864 | Contra Costa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
34865 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16511SS | 0 | Start No Earlier Than | Warning
34866 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16510SS |  | 0 | Finish No Earlier Than | Warning
34867 | Contra Costa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16513SS | 0 | Start No Earlier Than | Warning
34868 | Contra Costa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16512SS |  | 0 | Start No Earlier Than | Warning
34869 | Contra Costa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
34870 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16516SS | 0 | Finish No Earlier Than | Warning
34871 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16515SS |  | 0 | Finish No Earlier Than | Warning
34872 | Contra Costa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
34873 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16519SS | 0 | Finish No Earlier Than | Warning
34875 | Contra Costa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
34876 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16522SS | 0 | Finish No Earlier Than | Warning
34877 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16521SS |  | 0 | Start No Earlier Than | Warning
34878 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16524SS | 0 | Start No Earlier Than | Warning
34879 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16523SS |  | 0 | Start No Earlier Than | Warning
34880 | Contra Costa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34881 | Contra Costa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
34884 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
34885 | Contra Costa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
34886 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
34887 | Contra Costa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 16533FS+10d | 0 | Start No Earlier Than | Warning
34888 | Contra Costa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 16532FS+10d |  | 0 | Start No Earlier Than | Warning
34890 | Contra Costa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16537FS-1d | 1 | Start No Earlier Than | Warning
34891 | Contra Costa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34892 | Contra Costa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16535FS-1d |  | 0.2 | Start No Earlier Than | Warning
34893 | Contra Costa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | November 20, 2025 5:00 PM | 100 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34894 | Contra Costa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16540 | 1 | Start No Earlier Than | Warning
34895 | Contra Costa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16539 |  | 0 | Start No Earlier Than | Warning
34896 | Contra Costa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34897 | Contra Costa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applica | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16543FS+19d | 0 | Finish No Earlier Than | Warning
34898 | Contra Costa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16542FS+19d | 16544 | 0 | Start No Earlier Than | Warning
34900 | Contra Costa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
34901 | Contra Costa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16547 | 0 | Start No Earlier Than | Warning
34902 | Contra Costa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16546 | 16548FS-1d | 0 | Start No Earlier Than | Warning
34903 | Contra Costa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16547FS-1d |  | 0 | Finish No Earlier Than | Warning
34904 | Contra Costa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
34905 | Contra Costa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
34908 | Contra Costa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16554SS | 0 | Finish No Earlier Than | Warning
34909 | Contra Costa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16553SS |  | 0 | Finish No Earlier Than | Warning
34910 | Contra Costa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34911 | Contra Costa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
34913 | Contra Costa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16559SS | 0 | Finish No Earlier Than | Warning
34914 | Contra Costa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16558SS | 16573SS | 0 | Start No Earlier Than | Warning
34916 | Contra Costa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
34917 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
34919 | Contra Costa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16565SS | 0 | Start No Earlier Than | Warning
34920 | Contra Costa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16564SS | 16566SS,16567 | 0 | Finish No Earlier Than | Warning
34922 | Contra Costa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16565,16566 |  | 0 | Finish No Earlier Than | Warning
34923 | Contra Costa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34925 | Contra Costa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16571SS | 0 | Finish No Earlier Than | Warning
34926 | Contra Costa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16570SS |  | 0 | Finish No Earlier Than | Warning
34927 | Contra Costa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
34928 | Contra Costa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16559SS |  | 0 | Finish No Earlier Than | Warning
34930 | Contra Costa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16576SS | 0 | Finish No Earlier Than | Warning
34931 | Contra Costa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16575SS |  | 0 | Finish No Earlier Than | Warning
34933 | Contra Costa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16579SS+18d | 0 | Start No Earlier Than | Warning
34934 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16578SS+18d |  | 0 | Finish No Earlier Than | Warning
34936 | Contra Costa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16582SS | 0 | Start No Earlier Than | Warning
34937 | Contra Costa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16581SS |  | 0 | Finish No Earlier Than | Warning
34938 | Contra Costa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16584 | 0 | Start No Earlier Than | Warning
34939 | Contra Costa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16583 |  | 0 | Finish No Earlier Than | Warning
34940 | Contra Costa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
34942 | Contra Costa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16588SS | 0 | Start No Earlier Than | Warning
34943 | Contra Costa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16587SS | 16589SS | 0 | Finish No Earlier Than | Warning
34944 | Contra Costa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16588SS | 16590SS | 0 | Finish No Earlier Than | Warning
34945 | Contra Costa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16589SS | 16591SS | 0 | Finish No Earlier Than | Warning
34946 | Contra Costa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16590SS | 16592SS | 0 | Finish No Earlier Than | Warning
34947 | Contra Costa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16591SS | 16593SS | 0 | Finish No Earlier Than | Warning
34948 | Contra Costa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16592SS | 16594SS | 0 | Finish No Earlier Than | Warning
34949 | Contra Costa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16593SS | 16595SS | 0 | Finish No Earlier Than | Warning
34950 | Contra Costa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16594SS | 16596SS | 0 | Finish No Earlier Than | Warning
34951 | Contra Costa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16595SS | 16597SS | 0 | Finish No Earlier Than | Warning
34952 | Contra Costa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16596SS |  | 0 | Finish No Earlier Than | Warning
34953 | Contra Costa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
34954 | Contra Costa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
34956 | Contra Costa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16602SS,16606 | 0.2 | Start No Earlier Than | Warning
34957 | Contra Costa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16601SS |  | 0 | Start No Earlier Than | Warning
34958 | Contra Costa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
34959 | Contra Costa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16612 | 0 | Start No Earlier Than | Warning
34960 | Contra Costa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16613 | 0 | Start No Earlier Than | Warning
34961 | Contra Costa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16601 |  | 0 | Start No Earlier Than | Warning
34962 | Contra Costa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
34963 | Contra Costa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16609SS,16617SS+20d | 0 | Start No Earlier Than | Warning
34964 | Contra Costa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16608SS | 16610SS,16618SS+20d | 0 | Finish No Earlier Than | Warning
34965 | Contra Costa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16609SS | 16619SS+20d | 0 | Finish No Earlier Than | Warning
34966 | Contra Costa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
34967 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16604 | 16613SS | 0 | Start No Earlier Than | Warning
34968 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16605,16612SS |  | 0 | Finish No Earlier Than | Warning
34969 | Contra Costa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16622FS+12d | 0 | Start No Earlier Than | Warning
34970 | Contra Costa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16616SS | 0 | Start No Earlier Than | Warning
34971 | Contra Costa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16615SS |  | 0 | Start No Earlier Than | Warning
34975 | Contra Costa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16622SS+44d | 0 | Start No Earlier Than | Warning
34976 | Contra Costa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
34981 | Del Norte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34982 | Del Norte PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
34983 | Del Norte PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
34984 | Del Norte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
34985 | Del Norte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 18 | 467d |  |  | 0 | Start No Earlier Than | Warning
34986 | Del Norte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
34987 | Del Norte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
34988 | Del Norte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
34989 | Del Norte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
34990 | Del Norte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
34991 | Del Norte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
34992 | Del Norte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
34993 | Del Norte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
34994 | Del Norte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
34995 | Del Norte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
34996 | Del Norte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
34997 | Del Norte PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34998 | Del Norte PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
34999 | Del Norte PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35000 | Del Norte PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35001 | Del Norte PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35002 | Del Norte PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35003 | Del Norte PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35004 | Del Norte PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35005 | Del Norte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35006 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16652SS | 0 | Start No Earlier Than | Warning
35007 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16651SS |  | 0 | Finish No Earlier Than | Warning
35008 | Del Norte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16654SS | 0 | Start No Earlier Than | Warning
35009 | Del Norte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16653SS |  | 0 | Start No Earlier Than | Warning
35010 | Del Norte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35011 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16657SS | 0 | Finish No Earlier Than | Warning
35012 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16656SS |  | 0 | Finish No Earlier Than | Warning
35013 | Del Norte PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35014 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16660SS | 0 | Finish No Earlier Than | Warning
35016 | Del Norte PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35017 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16663SS | 0 | Finish No Earlier Than | Warning
35018 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16662SS |  | 0 | Start No Earlier Than | Warning
35019 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16665SS | 0 | Start No Earlier Than | Warning
35020 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16664SS |  | 0 | Start No Earlier Than | Warning
35021 | Del Norte PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35022 | Del Norte PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35025 | Del Norte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35026 | Del Norte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35027 | Del Norte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35028 | Del Norte PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 16674FS+10d | 0 | Start No Earlier Than | Warning
35029 | Del Norte PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 16673FS+10d |  | 0 | Start No Earlier Than | Warning
35031 | Del Norte PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16678FS-1d | 1 | Start No Earlier Than | Warning
35032 | Del Norte PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35033 | Del Norte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16676FS-1d |  | 0.2 | Start No Earlier Than | Warning
35034 | Del Norte PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35035 | Del Norte PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16681 | 1 | Start No Earlier Than | Warning
35036 | Del Norte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16680 |  | 0 | Start No Earlier Than | Warning
35037 | Del Norte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35038 | Del Norte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16684FS+19d | 0 | Finish No Earlier Than | Warning
35039 | Del Norte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16683FS+19d | 16685 | 0 | Start No Earlier Than | Warning
35041 | Del Norte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35042 | Del Norte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16688 | 0 | Start No Earlier Than | Warning
35043 | Del Norte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16687 | 16689FS-1d | 0 | Start No Earlier Than | Warning
35044 | Del Norte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16688FS-1d |  | 0 | Finish No Earlier Than | Warning
35045 | Del Norte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35046 | Del Norte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35049 | Del Norte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16695SS | 0 | Finish No Earlier Than | Warning
35050 | Del Norte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16694SS |  | 0 | Finish No Earlier Than | Warning
35051 | Del Norte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35052 | Del Norte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35054 | Del Norte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16700SS | 0 | Finish No Earlier Than | Warning
35055 | Del Norte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16699SS | 16714SS | 0 | Start No Earlier Than | Warning
35057 | Del Norte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35058 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35060 | Del Norte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16706SS | 0 | Start No Earlier Than | Warning
35061 | Del Norte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16705SS | 16707SS,16708 | 0 | Finish No Earlier Than | Warning
35063 | Del Norte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16706,16707 |  | 0 | Finish No Earlier Than | Warning
35064 | Del Norte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35066 | Del Norte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16712SS | 0 | Finish No Earlier Than | Warning
35067 | Del Norte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16711SS |  | 0 | Finish No Earlier Than | Warning
35068 | Del Norte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35069 | Del Norte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16700SS |  | 0 | Finish No Earlier Than | Warning
35071 | Del Norte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16717SS | 0 | Finish No Earlier Than | Warning
35072 | Del Norte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16716SS |  | 0 | Finish No Earlier Than | Warning
35074 | Del Norte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16720SS+18d | 0 | Start No Earlier Than | Warning
35075 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16719SS+18d |  | 0 | Finish No Earlier Than | Warning
35077 | Del Norte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16723SS | 0 | Start No Earlier Than | Warning
35078 | Del Norte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16722SS |  | 0 | Finish No Earlier Than | Warning
35079 | Del Norte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16725 | 0 | Start No Earlier Than | Warning
35080 | Del Norte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16724 |  | 0 | Finish No Earlier Than | Warning
35081 | Del Norte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35083 | Del Norte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16729SS | 0 | Start No Earlier Than | Warning
35084 | Del Norte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16728SS | 16730SS | 0 | Finish No Earlier Than | Warning
35085 | Del Norte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16729SS | 16731SS | 0 | Finish No Earlier Than | Warning
35086 | Del Norte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16730SS | 16732SS | 0 | Finish No Earlier Than | Warning
35087 | Del Norte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16731SS | 16733SS | 0 | Finish No Earlier Than | Warning
35088 | Del Norte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16732SS | 16734SS | 0 | Finish No Earlier Than | Warning
35089 | Del Norte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16733SS | 16735SS | 0 | Finish No Earlier Than | Warning
35090 | Del Norte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16734SS | 16736SS | 0 | Finish No Earlier Than | Warning
35091 | Del Norte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16735SS | 16737SS | 0 | Finish No Earlier Than | Warning
35092 | Del Norte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16736SS | 16738SS | 0 | Finish No Earlier Than | Warning
35093 | Del Norte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16737SS |  | 0 | Finish No Earlier Than | Warning
35094 | Del Norte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35095 | Del Norte PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35097 | Del Norte PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16743SS,16747 | 0 | Start No Earlier Than | Warning
35098 | Del Norte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16742SS |  | 0 | Start No Earlier Than | Warning
35099 | Del Norte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35100 | Del Norte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16753 | 0 | Start No Earlier Than | Warning
35101 | Del Norte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16754 | 0 | Start No Earlier Than | Warning
35102 | Del Norte PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16742 |  | 0 | Start No Earlier Than | Warning
35103 | Del Norte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35104 | Del Norte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16750SS,16758SS+20d | 0 | Start No Earlier Than | Warning
35105 | Del Norte PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16749SS | 16751SS,16759SS+20d | 0 | Finish No Earlier Than | Warning
35106 | Del Norte PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16750SS | 16760SS+20d | 0 | Finish No Earlier Than | Warning
35107 | Del Norte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35108 | Del Norte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16745 | 16754SS | 0 | Start No Earlier Than | Warning
35109 | Del Norte PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16746,16753SS |  | 0 | Finish No Earlier Than | Warning
35110 | Del Norte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16763FS+12d | 0 | Start No Earlier Than | Warning
35111 | Del Norte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16757SS | 0 | Start No Earlier Than | Warning
35112 | Del Norte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16756SS |  | 0 | Start No Earlier Than | Warning
35116 | Del Norte PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16763SS+44d | 0 | Start No Earlier Than | Warning
35117 | Del Norte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35122 | El Dorado PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35123 | El Dorado PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35124 | El Dorado PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35125 | El Dorado PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35126 | El Dorado PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35127 | El Dorado PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35128 | El Dorado PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35129 | El Dorado PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35130 | El Dorado PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35131 | El Dorado PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35132 | El Dorado PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35133 | El Dorado PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35134 | El Dorado PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35135 | El Dorado PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35136 | El Dorado PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35137 | El Dorado PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35138 | El Dorado PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35139 | El Dorado PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35140 | El Dorado PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35141 | El Dorado PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35142 | El Dorado PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35143 | El Dorado PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35144 | El Dorado PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35145 | El Dorado PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35146 | El Dorado PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35147 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16793SS | 0 | Start No Earlier Than | Warning
35148 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16792SS |  | 0 | Finish No Earlier Than | Warning
35149 | El Dorado PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16795SS | 0 | Start No Earlier Than | Warning
35150 | El Dorado PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16794SS |  | 0 | Start No Earlier Than | Warning
35151 | El Dorado PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35152 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 16798SS | 0 | Finish No Earlier Than | Warning
35153 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 16797SS |  | 0 | Finish No Earlier Than | Warning
35154 | El Dorado PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35155 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 16801SS | 0 | Finish No Earlier Than | Warning
35157 | El Dorado PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35158 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 16804SS | 0 | Finish No Earlier Than | Warning
35159 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 16803SS |  | 0 | Start No Earlier Than | Warning
35160 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 16806SS | 0 | Start No Earlier Than | Warning
35161 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 16805SS |  | 0 | Start No Earlier Than | Warning
35162 | El Dorado PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35163 | El Dorado PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35166 | El Dorado PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35167 | El Dorado PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35168 | El Dorado PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35169 | El Dorado PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 16815FS+10d | 0 | Start No Earlier Than | Warning
35170 | El Dorado PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 16814FS+10d |  | 0 | Start No Earlier Than | Warning
35172 | El Dorado PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16819FS-1d | 1 | Start No Earlier Than | Warning
35173 | El Dorado PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35174 | El Dorado PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 16817FS-1d |  | 0.2 | Start No Earlier Than | Warning
35175 | El Dorado PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35176 | El Dorado PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16822 | 1 | Start No Earlier Than | Warning
35177 | El Dorado PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16821 |  | 0 | Start No Earlier Than | Warning
35178 | El Dorado PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35179 | El Dorado PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16825FS+19d | 0 | Finish No Earlier Than | Warning
35180 | El Dorado PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16824FS+19d | 16826 | 0 | Start No Earlier Than | Warning
35182 | El Dorado PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35183 | El Dorado PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16829 | 0 | Start No Earlier Than | Warning
35184 | El Dorado PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16828 | 16830FS-1d | 0 | Start No Earlier Than | Warning
35185 | El Dorado PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16829FS-1d |  | 0 | Finish No Earlier Than | Warning
35186 | El Dorado PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35187 | El Dorado PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35190 | El Dorado PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16836SS | 0 | Finish No Earlier Than | Warning
35191 | El Dorado PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16835SS |  | 0 | Finish No Earlier Than | Warning
35192 | El Dorado PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35193 | El Dorado PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35195 | El Dorado PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16841SS | 0 | Finish No Earlier Than | Warning
35196 | El Dorado PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16840SS | 16855SS | 0 | Start No Earlier Than | Warning
35198 | El Dorado PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35199 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35201 | El Dorado PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 16847SS | 0 | Start No Earlier Than | Warning
35202 | El Dorado PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16846SS | 16848SS,16849 | 0 | Finish No Earlier Than | Warning
35204 | El Dorado PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16847,16848 |  | 0 | Finish No Earlier Than | Warning
35205 | El Dorado PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35207 | El Dorado PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16853SS | 0 | Finish No Earlier Than | Warning
35208 | El Dorado PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 16852SS |  | 0 | Finish No Earlier Than | Warning
35209 | El Dorado PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35210 | El Dorado PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16841SS |  | 0 | Finish No Earlier Than | Warning
35212 | El Dorado PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16858SS | 0 | Finish No Earlier Than | Warning
35213 | El Dorado PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16857SS |  | 0 | Finish No Earlier Than | Warning
35215 | El Dorado PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 16861SS+18d | 0 | Start No Earlier Than | Warning
35216 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 16860SS+18d |  | 0 | Finish No Earlier Than | Warning
35218 | El Dorado PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 16864SS | 0 | Start No Earlier Than | Warning
35219 | El Dorado PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 16863SS |  | 0 | Finish No Earlier Than | Warning
35220 | El Dorado PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16866 | 0 | Start No Earlier Than | Warning
35221 | El Dorado PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 16865 |  | 0 | Finish No Earlier Than | Warning
35222 | El Dorado PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35224 | El Dorado PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16870SS | 0 | Start No Earlier Than | Warning
35225 | El Dorado PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16869SS | 16871SS | 0 | Finish No Earlier Than | Warning
35226 | El Dorado PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16870SS | 16872SS | 0 | Finish No Earlier Than | Warning
35227 | El Dorado PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16871SS | 16873SS | 0 | Finish No Earlier Than | Warning
35228 | El Dorado PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16872SS | 16874SS | 0 | Finish No Earlier Than | Warning
35229 | El Dorado PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16873SS | 16875SS | 0 | Finish No Earlier Than | Warning
35230 | El Dorado PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16874SS | 16876SS | 0 | Finish No Earlier Than | Warning
35231 | El Dorado PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16875SS | 16877SS | 0 | Finish No Earlier Than | Warning
35232 | El Dorado PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16876SS | 16878SS | 0 | Finish No Earlier Than | Warning
35233 | El Dorado PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16877SS | 16879SS | 0 | Finish No Earlier Than | Warning
35234 | El Dorado PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16878SS |  | 0 | Finish No Earlier Than | Warning
35235 | El Dorado PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35236 | El Dorado PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35238 | El Dorado PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16884SS,16888 | 0 | Start No Earlier Than | Warning
35239 | El Dorado PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16883SS |  | 0 | Start No Earlier Than | Warning
35240 | El Dorado PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35241 | El Dorado PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16894 | 0 | Start No Earlier Than | Warning
35242 | El Dorado PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 16895 | 0 | Start No Earlier Than | Warning
35243 | El Dorado PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16883 |  | 0 | Start No Earlier Than | Warning
35244 | El Dorado PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35245 | El Dorado PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 16891SS,16899SS+20d | 0 | Start No Earlier Than | Warning
35246 | El Dorado PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16890SS | 16892SS,16900SS+20d | 0 | Finish No Earlier Than | Warning
35247 | El Dorado PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 16891SS | 16901SS+20d | 0 | Finish No Earlier Than | Warning
35248 | El Dorado PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35249 | El Dorado PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16886 | 16895SS | 0 | Start No Earlier Than | Warning
35250 | El Dorado PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 16887,16894SS |  | 0 | Finish No Earlier Than | Warning
35251 | El Dorado PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 16904FS+12d | 0 | Start No Earlier Than | Warning
35252 | El Dorado PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 16898SS | 0 | Start No Earlier Than | Warning
35253 | El Dorado PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 16897SS |  | 0 | Start No Earlier Than | Warning
35257 | El Dorado PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 16904SS+44d | 0 | Start No Earlier Than | Warning
35258 | El Dorado PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35263 | Fresno PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35264 | Fresno PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35265 | Fresno PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35266 | Fresno PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35267 | Fresno PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35268 | Fresno PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35269 | Fresno PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35270 | Fresno PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35271 | Fresno PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35272 | Fresno PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35273 | Fresno PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35274 | Fresno PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35275 | Fresno PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35276 | Fresno PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35277 | Fresno PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35278 | Fresno PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35279 | Fresno PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35280 | Fresno PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35281 | Fresno PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35282 | Fresno PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35283 | Fresno PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35284 | Fresno PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35285 | Fresno PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35286 | Fresno PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35287 | Fresno PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35288 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 16934SS | 0 | Start No Earlier Than | Warning
35289 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 16933SS |  | 0 | Finish No Earlier Than | Warning
35290 | Fresno PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 16936SS | 0 | Start No Earlier Than | Warning
35291 | Fresno PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 16935SS |  | 0 | Start No Earlier Than | Warning
35292 | Fresno PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 16939SS,16938SS | 0 | Finish No Earlier Than | Warning
35295 | Fresno PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
35296 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 16942SS | 0 | Start No Earlier Than | Warning
35298 | Fresno PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
35299 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 16945SS | 0 | Start No Earlier Than | Warning
35300 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 16944SS |  | 0 | Start No Earlier Than | Warning
35301 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 16947SS | 0 | Start No Earlier Than | Warning
35303 | Fresno PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
35304 | Fresno PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
35307 | Fresno PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35308 | Fresno PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35309 | Fresno PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
35310 | Fresno PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
35312 | Fresno PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 16959FS-1d | 1 | Start No Earlier Than | Warning
35313 | Fresno PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35314 | Fresno PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 16957FS-1d |  | 0.6 | Start No Earlier Than | Warning
35315 | Fresno PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35316 | Fresno PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 16962 | 1 | Start No Earlier Than | Warning
35317 | Fresno PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16961 |  | 0 | Start No Earlier Than | Warning
35318 | Fresno PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35319 | Fresno PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 16965FS+19d | 0 | Finish No Earlier Than | Warning
35320 | Fresno PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 16964FS+19d | 16966 | 0 | Start No Earlier Than | Warning
35322 | Fresno PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35323 | Fresno PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 16969 | 0 | Start No Earlier Than | Warning
35324 | Fresno PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 16968 | 16970FS-1d | 0 | Start No Earlier Than | Warning
35325 | Fresno PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 16969FS-1d |  | 0 | Finish No Earlier Than | Warning
35326 | Fresno PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35327 | Fresno PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35330 | Fresno PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 16976SS | 0 | Finish No Earlier Than | Warning
35331 | Fresno PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 16975SS |  | 0 | Start No Earlier Than | Warning
35333 | Fresno PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 16979SS | 0 | Start No Earlier Than | Warning
35334 | Fresno PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16978SS | 16980SS | 0 | Finish No Earlier Than | Warning
35335 | Fresno PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16979SS | 16981SS | 0 | Finish No Earlier Than | Warning
35336 | Fresno PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16980SS | 16982SS | 0 | Finish No Earlier Than | Warning
35337 | Fresno PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16981SS | 16983SS | 0 | Finish No Earlier Than | Warning
35338 | Fresno PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16982SS | 16984SS | 0 | Finish No Earlier Than | Warning
35339 | Fresno PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16983SS | 16985SS | 0 | Finish No Earlier Than | Warning
35340 | Fresno PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16984SS | 16986SS | 0 | Finish No Earlier Than | Warning
35341 | Fresno PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16985SS | 16987SS | 0 | Finish No Earlier Than | Warning
35342 | Fresno PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16986SS | 16988SS | 0 | Finish No Earlier Than | Warning
35343 | Fresno PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 16987SS |  | 0 | Finish No Earlier Than | Warning
35344 | Fresno PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
35345 | Fresno PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
35347 | Fresno PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 16993SS,16997 | 0 | Start No Earlier Than | Warning
35348 | Fresno PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 16992SS |  | 0 | Start No Earlier Than | Warning
35349 | Fresno PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35350 | Fresno PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17003 | 0 | Start No Earlier Than | Warning
35351 | Fresno PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17004 | 0 | Start No Earlier Than | Warning
35352 | Fresno PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 16992 |  | 0 | Start No Earlier Than | Warning
35353 | Fresno PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35354 | Fresno PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 17000SS,17008SS+20d | 0 | Start No Earlier Than | Warning
35357 | Fresno PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35358 | Fresno PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 16995 | 17004SS | 0 | Start No Earlier Than | Warning
35360 | Fresno PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 17013FS+12d | 0 | Start No Earlier Than | Warning
35361 | Fresno PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17007SS | 0 | Start No Earlier Than | Warning
35362 | Fresno PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17006SS |  | 0 | Start No Earlier Than | Warning
35366 | Fresno PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 17013SS+44d | 0 | Start No Earlier Than | Warning
35367 | Fresno PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35372 | Glenn PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35373 | Glenn PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35374 | Glenn PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35375 | Glenn PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35376 | Glenn PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35377 | Glenn PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35378 | Glenn PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35379 | Glenn PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35380 | Glenn PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35381 | Glenn PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35382 | Glenn PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35383 | Glenn PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35384 | Glenn PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35385 | Glenn PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35386 | Glenn PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35387 | Glenn PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35388 | Glenn PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35389 | Glenn PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35390 | Glenn PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35391 | Glenn PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35392 | Glenn PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35393 | Glenn PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35394 | Glenn PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35395 | Glenn PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35396 | Glenn PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35397 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17043SS | 0 | Start No Earlier Than | Warning
35398 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17042SS |  | 0 | Finish No Earlier Than | Warning
35399 | Glenn PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17045SS | 0 | Start No Earlier Than | Warning
35400 | Glenn PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17044SS |  | 0 | Start No Earlier Than | Warning
35401 | Glenn PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35402 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17048SS | 0 | Finish No Earlier Than | Warning
35403 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17047SS |  | 0 | Finish No Earlier Than | Warning
35404 | Glenn PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35405 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17051SS | 0 | Finish No Earlier Than | Warning
35407 | Glenn PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35408 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17054SS | 0 | Finish No Earlier Than | Warning
35409 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17053SS |  | 0 | Start No Earlier Than | Warning
35410 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17056SS | 0 | Start No Earlier Than | Warning
35411 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17055SS |  | 0 | Start No Earlier Than | Warning
35412 | Glenn PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35413 | Glenn PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35416 | Glenn PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35417 | Glenn PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35418 | Glenn PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35419 | Glenn PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17065FS+10d | 0 | Start No Earlier Than | Warning
35420 | Glenn PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17064FS+10d |  | 0 | Start No Earlier Than | Warning
35422 | Glenn PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17069FS-1d | 1 | Start No Earlier Than | Warning
35423 | Glenn PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35424 | Glenn PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17067FS-1d |  | 0.2 | Start No Earlier Than | Warning
35425 | Glenn PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35426 | Glenn PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17072 | 1 | Start No Earlier Than | Warning
35427 | Glenn PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17071 |  | 0 | Start No Earlier Than | Warning
35428 | Glenn PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35429 | Glenn PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17075FS+19d | 0 | Finish No Earlier Than | Warning
35430 | Glenn PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17074FS+19d | 17076 | 0 | Start No Earlier Than | Warning
35432 | Glenn PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35433 | Glenn PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17079 | 0 | Start No Earlier Than | Warning
35434 | Glenn PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17078 | 17080FS-1d | 0 | Start No Earlier Than | Warning
35435 | Glenn PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17079FS-1d |  | 0 | Finish No Earlier Than | Warning
35436 | Glenn PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35437 | Glenn PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35440 | Glenn PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17086SS | 0 | Start No Earlier Than | Warning
35441 | Glenn PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17085SS | 17087SS | 0 | Finish No Earlier Than | Warning
35442 | Glenn PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17086SS | 17088SS | 0 | Finish No Earlier Than | Warning
35443 | Glenn PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17087SS | 17089SS | 0 | Finish No Earlier Than | Warning
35444 | Glenn PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17088SS | 17090SS | 0 | Finish No Earlier Than | Warning
35445 | Glenn PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17089SS | 17091SS | 0 | Finish No Earlier Than | Warning
35446 | Glenn PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17090SS | 17092SS | 0 | Finish No Earlier Than | Warning
35447 | Glenn PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17091SS | 17093SS | 0 | Finish No Earlier Than | Warning
35448 | Glenn PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17092SS | 17094SS | 0 | Finish No Earlier Than | Warning
35449 | Glenn PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17093SS | 17095SS | 0 | Finish No Earlier Than | Warning
35450 | Glenn PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17094SS |  | 0 | Finish No Earlier Than | Warning
35451 | Glenn PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35452 | Glenn PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35454 | Glenn PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17100SS,17104 | 0 | Start No Earlier Than | Warning
35455 | Glenn PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17099SS |  | 0 | Start No Earlier Than | Warning
35456 | Glenn PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35457 | Glenn PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17110 | 0 | Start No Earlier Than | Warning
35458 | Glenn PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17111 | 0 | Start No Earlier Than | Warning
35459 | Glenn PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17099 |  | 0 | Start No Earlier Than | Warning
35460 | Glenn PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35461 | Glenn PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17107SS,17115SS+20d | 0 | Start No Earlier Than | Warning
35462 | Glenn PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17106SS | 17108SS,17116SS+20d | 0 | Finish No Earlier Than | Warning
35463 | Glenn PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17107SS | 17117SS+20d | 0 | Finish No Earlier Than | Warning
35464 | Glenn PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35465 | Glenn PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17102 | 17111SS | 0 | Start No Earlier Than | Warning
35466 | Glenn PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17103,17110SS |  | 0 | Finish No Earlier Than | Warning
35467 | Glenn PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17120FS+12d | 0 | Start No Earlier Than | Warning
35468 | Glenn PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17114SS | 0 | Start No Earlier Than | Warning
35469 | Glenn PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17113SS |  | 0 | Start No Earlier Than | Warning
35473 | Glenn PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17120SS+44d | 0 | Start No Earlier Than | Warning
35474 | Glenn PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35479 | Humboldt PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35480 | Humboldt PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35481 | Humboldt PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35482 | Humboldt PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35483 | Humboldt PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35484 | Humboldt PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35485 | Humboldt PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35486 | Humboldt PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35487 | Humboldt PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35488 | Humboldt PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35489 | Humboldt PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35490 | Humboldt PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35491 | Humboldt PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35492 | Humboldt PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35493 | Humboldt PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35494 | Humboldt PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35495 | Humboldt PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35496 | Humboldt PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35497 | Humboldt PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35498 | Humboldt PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35499 | Humboldt PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35500 | Humboldt PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35501 | Humboldt PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35502 | Humboldt PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35503 | Humboldt PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35504 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17150SS | 0 | Start No Earlier Than | Warning
35505 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17149SS |  | 0 | Finish No Earlier Than | Warning
35506 | Humboldt PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17152SS | 0 | Start No Earlier Than | Warning
35507 | Humboldt PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17151SS |  | 0 | Start No Earlier Than | Warning
35508 | Humboldt PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35509 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17155SS | 0 | Finish No Earlier Than | Warning
35510 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17154SS |  | 0 | Finish No Earlier Than | Warning
35511 | Humboldt PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35512 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17158SS | 0 | Finish No Earlier Than | Warning
35514 | Humboldt PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35515 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17161SS | 0 | Finish No Earlier Than | Warning
35516 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17160SS |  | 0 | Start No Earlier Than | Warning
35517 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17163SS | 0 | Start No Earlier Than | Warning
35518 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17162SS |  | 0 | Start No Earlier Than | Warning
35519 | Humboldt PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35520 | Humboldt PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35523 | Humboldt PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35524 | Humboldt PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35525 | Humboldt PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35526 | Humboldt PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17172FS+10d | 0 | Start No Earlier Than | Warning
35527 | Humboldt PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17171FS+10d |  | 0 | Start No Earlier Than | Warning
35529 | Humboldt PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17176FS-1d | 1 | Start No Earlier Than | Warning
35530 | Humboldt PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35531 | Humboldt PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17174FS-1d |  | 0 | Start No Earlier Than | Warning
35532 | Humboldt PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35533 | Humboldt PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17179 | 1 | Start No Earlier Than | Warning
35534 | Humboldt PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17178 |  | 0 | Start No Earlier Than | Warning
35535 | Humboldt PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35536 | Humboldt PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17182FS+19d | 0 | Finish No Earlier Than | Warning
35537 | Humboldt PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17181FS+19d | 17183 | 0 | Start No Earlier Than | Warning
35539 | Humboldt PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35540 | Humboldt PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17186 | 0 | Start No Earlier Than | Warning
35541 | Humboldt PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17185 | 17187FS-1d | 0 | Start No Earlier Than | Warning
35542 | Humboldt PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17186FS-1d |  | 0 | Finish No Earlier Than | Warning
35543 | Humboldt PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35544 | Humboldt PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35547 | Humboldt PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17193SS | 0 | Finish No Earlier Than | Warning
35548 | Humboldt PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17192SS |  | 0 | Finish No Earlier Than | Warning
35549 | Humboldt PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35550 | Humboldt PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35552 | Humboldt PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17198SS | 0 | Finish No Earlier Than | Warning
35553 | Humboldt PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17197SS | 17212SS | 0 | Start No Earlier Than | Warning
35555 | Humboldt PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35556 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35558 | Humboldt PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17204SS | 0 | Start No Earlier Than | Warning
35559 | Humboldt PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17203SS | 17205SS,17206 | 0 | Finish No Earlier Than | Warning
35561 | Humboldt PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17204,17205 |  | 0 | Finish No Earlier Than | Warning
35562 | Humboldt PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35564 | Humboldt PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17210SS | 0 | Finish No Earlier Than | Warning
35565 | Humboldt PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17209SS |  | 0 | Finish No Earlier Than | Warning
35566 | Humboldt PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35567 | Humboldt PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17198SS |  | 0 | Finish No Earlier Than | Warning
35569 | Humboldt PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17215SS | 0 | Finish No Earlier Than | Warning
35570 | Humboldt PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17214SS |  | 0 | Finish No Earlier Than | Warning
35572 | Humboldt PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17218SS+18d | 0 | Start No Earlier Than | Warning
35573 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17217SS+18d |  | 0 | Finish No Earlier Than | Warning
35575 | Humboldt PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17221SS | 0 | Start No Earlier Than | Warning
35576 | Humboldt PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17220SS |  | 0 | Finish No Earlier Than | Warning
35577 | Humboldt PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17223 | 0 | Start No Earlier Than | Warning
35578 | Humboldt PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17222 |  | 0 | Finish No Earlier Than | Warning
35579 | Humboldt PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35581 | Humboldt PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17227SS | 0 | Start No Earlier Than | Warning
35582 | Humboldt PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17226SS | 17228SS | 0 | Finish No Earlier Than | Warning
35583 | Humboldt PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17227SS | 17229SS | 0 | Finish No Earlier Than | Warning
35584 | Humboldt PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17228SS | 17230SS | 0 | Finish No Earlier Than | Warning
35585 | Humboldt PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17229SS | 17231SS | 0 | Finish No Earlier Than | Warning
35586 | Humboldt PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17230SS | 17232SS | 0 | Finish No Earlier Than | Warning
35587 | Humboldt PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17231SS | 17233SS | 0 | Finish No Earlier Than | Warning
35588 | Humboldt PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17232SS | 17234SS | 0 | Finish No Earlier Than | Warning
35589 | Humboldt PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17233SS | 17235SS | 0 | Finish No Earlier Than | Warning
35590 | Humboldt PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17234SS | 17236SS | 0 | Finish No Earlier Than | Warning
35591 | Humboldt PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17235SS |  | 0 | Finish No Earlier Than | Warning
35592 | Humboldt PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35593 | Humboldt PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35595 | Humboldt PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17241SS,17245 | 0 | Start No Earlier Than | Warning
35596 | Humboldt PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17240SS |  | 0 | Start No Earlier Than | Warning
35597 | Humboldt PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35598 | Humboldt PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17251 | 0 | Start No Earlier Than | Warning
35599 | Humboldt PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17252 | 0 | Start No Earlier Than | Warning
35600 | Humboldt PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17240 |  | 0 | Start No Earlier Than | Warning
35601 | Humboldt PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35602 | Humboldt PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17248SS,17256SS+20d | 0 | Start No Earlier Than | Warning
35603 | Humboldt PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17247SS | 17249SS,17257SS+20d | 0 | Finish No Earlier Than | Warning
35604 | Humboldt PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17248SS | 17258SS+20d | 0 | Finish No Earlier Than | Warning
35605 | Humboldt PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35606 | Humboldt PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17243 | 17252SS | 0 | Start No Earlier Than | Warning
35607 | Humboldt PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17244,17251SS |  | 0 | Finish No Earlier Than | Warning
35608 | Humboldt PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17261FS+12d | 0 | Start No Earlier Than | Warning
35609 | Humboldt PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17255SS | 0 | Start No Earlier Than | Warning
35610 | Humboldt PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17254SS |  | 0 | Start No Earlier Than | Warning
35614 | Humboldt PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17261SS+44d | 0 | Start No Earlier Than | Warning
35615 | Humboldt PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35620 | Imperial PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35621 | Imperial PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35622 | Imperial PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35623 | Imperial PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35624 | Imperial PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35625 | Imperial PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35626 | Imperial PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35627 | Imperial PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35628 | Imperial PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35629 | Imperial PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35630 | Imperial PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35631 | Imperial PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35632 | Imperial PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35633 | Imperial PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35634 | Imperial PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35635 | Imperial PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35636 | Imperial PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35637 | Imperial PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35638 | Imperial PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35639 | Imperial PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35640 | Imperial PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35641 | Imperial PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35642 | Imperial PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35643 | Imperial PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35644 | Imperial PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35645 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17291SS | 0 | Start No Earlier Than | Warning
35646 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17290SS |  | 0 | Finish No Earlier Than | Warning
35647 | Imperial PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17293SS | 0 | Start No Earlier Than | Warning
35648 | Imperial PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17292SS |  | 0 | Start No Earlier Than | Warning
35649 | Imperial PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35650 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17296SS | 0 | Finish No Earlier Than | Warning
35651 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17295SS |  | 0 | Finish No Earlier Than | Warning
35652 | Imperial PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35653 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17299SS | 0 | Finish No Earlier Than | Warning
35655 | Imperial PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35656 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17302SS | 0 | Finish No Earlier Than | Warning
35657 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17301SS |  | 0 | Start No Earlier Than | Warning
35658 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17304SS | 0 | Start No Earlier Than | Warning
35659 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17303SS |  | 0 | Start No Earlier Than | Warning
35660 | Imperial PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35661 | Imperial PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35664 | Imperial PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35665 | Imperial PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35666 | Imperial PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35667 | Imperial PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17313FS+10d | 0 | Start No Earlier Than | Warning
35668 | Imperial PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17312FS+10d |  | 0 | Start No Earlier Than | Warning
35670 | Imperial PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17317FS-1d | 1 | Start No Earlier Than | Warning
35671 | Imperial PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35672 | Imperial PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17315FS-1d |  | 0 | Start No Earlier Than | Warning
35673 | Imperial PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35674 | Imperial PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17320 | 1 | Start No Earlier Than | Warning
35675 | Imperial PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17319 |  | 0 | Start No Earlier Than | Warning
35676 | Imperial PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35677 | Imperial PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17323FS+19d | 0 | Finish No Earlier Than | Warning
35678 | Imperial PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17322FS+19d | 17324 | 0 | Start No Earlier Than | Warning
35680 | Imperial PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35681 | Imperial PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17327 | 0 | Start No Earlier Than | Warning
35682 | Imperial PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17326 | 17328FS-1d | 0 | Start No Earlier Than | Warning
35683 | Imperial PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17327FS-1d |  | 0 | Finish No Earlier Than | Warning
35684 | Imperial PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35685 | Imperial PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35688 | Imperial PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17334SS | 0 | Finish No Earlier Than | Warning
35689 | Imperial PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17333SS |  | 0 | Finish No Earlier Than | Warning
35690 | Imperial PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35691 | Imperial PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35693 | Imperial PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17339SS | 0 | Finish No Earlier Than | Warning
35694 | Imperial PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17338SS | 17353SS | 0 | Start No Earlier Than | Warning
35696 | Imperial PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35697 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35699 | Imperial PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17345SS | 0 | Start No Earlier Than | Warning
35700 | Imperial PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17344SS | 17346SS,17347 | 0 | Finish No Earlier Than | Warning
35702 | Imperial PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17345,17346 |  | 0 | Finish No Earlier Than | Warning
35703 | Imperial PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35705 | Imperial PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17351SS | 0 | Finish No Earlier Than | Warning
35706 | Imperial PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17350SS |  | 0 | Finish No Earlier Than | Warning
35707 | Imperial PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35708 | Imperial PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17339SS |  | 0 | Finish No Earlier Than | Warning
35710 | Imperial PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17356SS | 0 | Finish No Earlier Than | Warning
35711 | Imperial PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17355SS |  | 0 | Finish No Earlier Than | Warning
35713 | Imperial PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17359SS+18d | 0 | Start No Earlier Than | Warning
35714 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17358SS+18d |  | 0 | Finish No Earlier Than | Warning
35716 | Imperial PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17362SS | 0 | Start No Earlier Than | Warning
35717 | Imperial PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17361SS |  | 0 | Finish No Earlier Than | Warning
35718 | Imperial PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17364 | 0 | Start No Earlier Than | Warning
35719 | Imperial PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17363 |  | 0 | Finish No Earlier Than | Warning
35720 | Imperial PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35722 | Imperial PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17368SS | 0 | Start No Earlier Than | Warning
35723 | Imperial PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17367SS | 17369SS | 0 | Finish No Earlier Than | Warning
35724 | Imperial PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17368SS | 17370SS | 0 | Finish No Earlier Than | Warning
35725 | Imperial PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17369SS | 17371SS | 0 | Finish No Earlier Than | Warning
35726 | Imperial PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17370SS | 17372SS | 0 | Finish No Earlier Than | Warning
35727 | Imperial PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17371SS | 17373SS | 0 | Finish No Earlier Than | Warning
35728 | Imperial PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17372SS | 17374SS | 0 | Finish No Earlier Than | Warning
35729 | Imperial PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17373SS | 17375SS | 0 | Finish No Earlier Than | Warning
35730 | Imperial PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17374SS | 17376SS | 0 | Finish No Earlier Than | Warning
35731 | Imperial PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17375SS | 17377SS | 0 | Finish No Earlier Than | Warning
35732 | Imperial PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17376SS |  | 0 | Finish No Earlier Than | Warning
35733 | Imperial PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35734 | Imperial PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35736 | Imperial PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17382SS,17386 | 0 | Start No Earlier Than | Warning
35737 | Imperial PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17381SS |  | 0 | Start No Earlier Than | Warning
35738 | Imperial PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35739 | Imperial PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17392 | 0 | Start No Earlier Than | Warning
35740 | Imperial PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17393 | 0 | Start No Earlier Than | Warning
35741 | Imperial PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17381 |  | 0 | Start No Earlier Than | Warning
35742 | Imperial PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35743 | Imperial PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17389SS,17397SS+20d | 0 | Start No Earlier Than | Warning
35744 | Imperial PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17388SS | 17390SS,17398SS+20d | 0 | Finish No Earlier Than | Warning
35745 | Imperial PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17389SS | 17399SS+20d | 0 | Finish No Earlier Than | Warning
35746 | Imperial PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35747 | Imperial PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17384 | 17393SS | 0 | Start No Earlier Than | Warning
35748 | Imperial PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17385,17392SS |  | 0 | Finish No Earlier Than | Warning
35749 | Imperial PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17402FS+12d | 0 | Start No Earlier Than | Warning
35750 | Imperial PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17396SS | 0 | Start No Earlier Than | Warning
35751 | Imperial PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17395SS |  | 0 | Start No Earlier Than | Warning
35755 | Imperial PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17402SS+44d | 0 | Start No Earlier Than | Warning
35756 | Imperial PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35761 | Inyo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35762 | Inyo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35763 | Inyo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35764 | Inyo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35765 | Inyo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35766 | Inyo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35767 | Inyo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35768 | Inyo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35769 | Inyo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35770 | Inyo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35771 | Inyo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35772 | Inyo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35773 | Inyo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35774 | Inyo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35775 | Inyo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35776 | Inyo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35777 | Inyo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35778 | Inyo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35779 | Inyo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35780 | Inyo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35781 | Inyo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35782 | Inyo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35783 | Inyo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35784 | Inyo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35785 | Inyo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35786 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17432SS | 0 | Start No Earlier Than | Warning
35787 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17431SS |  | 0 | Finish No Earlier Than | Warning
35788 | Inyo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17434SS | 0 | Start No Earlier Than | Warning
35789 | Inyo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17433SS |  | 0 | Start No Earlier Than | Warning
35790 | Inyo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35791 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17437SS | 0 | Finish No Earlier Than | Warning
35792 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17436SS |  | 0 | Finish No Earlier Than | Warning
35793 | Inyo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35794 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17440SS | 0 | Finish No Earlier Than | Warning
35796 | Inyo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35797 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17443SS | 0 | Finish No Earlier Than | Warning
35798 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17442SS |  | 0 | Start No Earlier Than | Warning
35799 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17445SS | 0 | Start No Earlier Than | Warning
35800 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17444SS |  | 0 | Start No Earlier Than | Warning
35801 | Inyo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35802 | Inyo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35805 | Inyo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35806 | Inyo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35807 | Inyo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35808 | Inyo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17454FS+10d | 0 | Start No Earlier Than | Warning
35809 | Inyo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17453FS+10d |  | 0 | Start No Earlier Than | Warning
35811 | Inyo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17458FS-1d | 1 | Start No Earlier Than | Warning
35812 | Inyo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35813 | Inyo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17456FS-1d |  | 0 | Start No Earlier Than | Warning
35814 | Inyo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35815 | Inyo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17461 | 1 | Start No Earlier Than | Warning
35816 | Inyo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17460 |  | 0 | Start No Earlier Than | Warning
35817 | Inyo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35818 | Inyo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17464FS+19d | 0 | Finish No Earlier Than | Warning
35819 | Inyo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17463FS+19d | 17465 | 0 | Start No Earlier Than | Warning
35821 | Inyo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35822 | Inyo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17468 | 0 | Start No Earlier Than | Warning
35823 | Inyo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17467 | 17469FS-1d | 0 | Start No Earlier Than | Warning
35824 | Inyo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17468FS-1d |  | 0 | Finish No Earlier Than | Warning
35825 | Inyo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35826 | Inyo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35829 | Inyo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17475SS | 0 | Finish No Earlier Than | Warning
35830 | Inyo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17474SS |  | 0 | Finish No Earlier Than | Warning
35831 | Inyo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35832 | Inyo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35834 | Inyo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17480SS | 0 | Finish No Earlier Than | Warning
35835 | Inyo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17479SS | 17494SS | 0 | Start No Earlier Than | Warning
35837 | Inyo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35838 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35840 | Inyo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17486SS | 0 | Start No Earlier Than | Warning
35841 | Inyo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17485SS | 17487SS,17488 | 0 | Finish No Earlier Than | Warning
35843 | Inyo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17486,17487 |  | 0 | Finish No Earlier Than | Warning
35844 | Inyo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35846 | Inyo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17492SS | 0 | Finish No Earlier Than | Warning
35847 | Inyo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17491SS |  | 0 | Finish No Earlier Than | Warning
35848 | Inyo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35849 | Inyo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17480SS |  | 0 | Finish No Earlier Than | Warning
35851 | Inyo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17497SS | 0 | Finish No Earlier Than | Warning
35852 | Inyo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17496SS |  | 0 | Finish No Earlier Than | Warning
35854 | Inyo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17500SS+18d | 0 | Start No Earlier Than | Warning
35855 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17499SS+18d |  | 0 | Finish No Earlier Than | Warning
35857 | Inyo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17503SS | 0 | Start No Earlier Than | Warning
35858 | Inyo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17502SS |  | 0 | Finish No Earlier Than | Warning
35859 | Inyo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17505 | 0 | Start No Earlier Than | Warning
35860 | Inyo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17504 |  | 0 | Finish No Earlier Than | Warning
35861 | Inyo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35863 | Inyo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17509SS | 0 | Start No Earlier Than | Warning
35864 | Inyo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17508SS | 17510SS | 0 | Finish No Earlier Than | Warning
35865 | Inyo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17509SS | 17511SS | 0 | Finish No Earlier Than | Warning
35866 | Inyo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17510SS | 17512SS | 0 | Finish No Earlier Than | Warning
35867 | Inyo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17511SS | 17513SS | 0 | Finish No Earlier Than | Warning
35868 | Inyo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17512SS | 17514SS | 0 | Finish No Earlier Than | Warning
35869 | Inyo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17513SS | 17515SS | 0 | Finish No Earlier Than | Warning
35870 | Inyo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17514SS | 17516SS | 0 | Finish No Earlier Than | Warning
35871 | Inyo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17515SS | 17517SS | 0 | Finish No Earlier Than | Warning
35872 | Inyo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17516SS | 17518SS | 0 | Finish No Earlier Than | Warning
35873 | Inyo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17517SS |  | 0 | Finish No Earlier Than | Warning
35874 | Inyo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
35875 | Inyo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
35877 | Inyo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17523SS,17527 | 0 | Start No Earlier Than | Warning
35878 | Inyo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17522SS |  | 0 | Start No Earlier Than | Warning
35879 | Inyo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
35880 | Inyo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17533 | 0 | Start No Earlier Than | Warning
35881 | Inyo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17534 | 0 | Start No Earlier Than | Warning
35882 | Inyo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17522 |  | 0 | Start No Earlier Than | Warning
35883 | Inyo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
35884 | Inyo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17530SS,17538SS+20d | 0 | Start No Earlier Than | Warning
35885 | Inyo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17529SS | 17531SS,17539SS+20d | 0 | Finish No Earlier Than | Warning
35886 | Inyo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17530SS | 17540SS+20d | 0 | Finish No Earlier Than | Warning
35887 | Inyo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
35888 | Inyo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17525 | 17534SS | 0 | Start No Earlier Than | Warning
35889 | Inyo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17526,17533SS |  | 0 | Finish No Earlier Than | Warning
35890 | Inyo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17543FS+12d | 0 | Start No Earlier Than | Warning
35891 | Inyo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17537SS | 0 | Start No Earlier Than | Warning
35892 | Inyo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17536SS |  | 0 | Start No Earlier Than | Warning
35896 | Inyo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17543SS+44d | 0 | Start No Earlier Than | Warning
35897 | Inyo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
35902 | Kern PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35903 | Kern PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35904 | Kern PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
35905 | Kern PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
35906 | Kern PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
35907 | Kern PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
35908 | Kern PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
35909 | Kern PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
35910 | Kern PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
35911 | Kern PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
35912 | Kern PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
35913 | Kern PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
35914 | Kern PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
35915 | Kern PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
35916 | Kern PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35917 | Kern PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
35918 | Kern PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35919 | Kern PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35920 | Kern PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35921 | Kern PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35922 | Kern PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35923 | Kern PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35924 | Kern PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35925 | Kern PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35926 | Kern PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
35927 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17573SS | 0 | Start No Earlier Than | Warning
35928 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17572SS |  | 0 | Finish No Earlier Than | Warning
35929 | Kern PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17575SS | 0 | Start No Earlier Than | Warning
35930 | Kern PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17574SS |  | 0 | Start No Earlier Than | Warning
35931 | Kern PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
35932 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17578SS | 0 | Finish No Earlier Than | Warning
35933 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17577SS |  | 0 | Finish No Earlier Than | Warning
35934 | Kern PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
35935 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17581SS | 0 | Finish No Earlier Than | Warning
35937 | Kern PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
35938 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17584SS | 0 | Finish No Earlier Than | Warning
35939 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17583SS |  | 0 | Start No Earlier Than | Warning
35940 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17586SS | 0 | Start No Earlier Than | Warning
35941 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17585SS |  | 0 | Start No Earlier Than | Warning
35942 | Kern PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
35943 | Kern PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
35946 | Kern PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
35947 | Kern PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
35948 | Kern PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
35949 | Kern PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17595FS+10d | 0 | Start No Earlier Than | Warning
35950 | Kern PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17594FS+10d |  | 0 | Start No Earlier Than | Warning
35952 | Kern PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17599FS-1d | 1 | Start No Earlier Than | Warning
35953 | Kern PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
35954 | Kern PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17597FS-1d |  | 0.2 | Start No Earlier Than | Warning
35955 | Kern PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
35956 | Kern PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17602 | 1 | Start No Earlier Than | Warning
35957 | Kern PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17601 |  | 0 | Start No Earlier Than | Warning
35958 | Kern PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35959 | Kern PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17605FS+19d | 0 | Finish No Earlier Than | Warning
35960 | Kern PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17604FS+19d | 17606 | 0 | Start No Earlier Than | Warning
35962 | Kern PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
35963 | Kern PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17609 | 0 | Start No Earlier Than | Warning
35964 | Kern PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17608 | 17610FS-1d | 0 | Start No Earlier Than | Warning
35965 | Kern PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17609FS-1d |  | 0 | Finish No Earlier Than | Warning
35966 | Kern PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
35967 | Kern PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
35970 | Kern PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17616SS | 0 | Finish No Earlier Than | Warning
35971 | Kern PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17615SS |  | 0 | Finish No Earlier Than | Warning
35972 | Kern PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35973 | Kern PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
35975 | Kern PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17621SS | 0 | Finish No Earlier Than | Warning
35976 | Kern PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17620SS | 17635SS | 0 | Start No Earlier Than | Warning
35978 | Kern PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
35979 | Kern PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
35981 | Kern PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17627SS | 0 | Start No Earlier Than | Warning
35982 | Kern PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17626SS | 17628SS,17629 | 0 | Finish No Earlier Than | Warning
35984 | Kern PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17627,17628 |  | 0 | Finish No Earlier Than | Warning
35985 | Kern PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
35987 | Kern PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17633SS | 0 | Finish No Earlier Than | Warning
35988 | Kern PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17632SS |  | 0 | Finish No Earlier Than | Warning
35989 | Kern PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
35990 | Kern PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17621SS |  | 0 | Finish No Earlier Than | Warning
35992 | Kern PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17638SS | 0 | Finish No Earlier Than | Warning
35993 | Kern PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17637SS |  | 0 | Finish No Earlier Than | Warning
35995 | Kern PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17641SS+18d | 0 | Start No Earlier Than | Warning
35996 | Kern PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17640SS+18d |  | 0 | Finish No Earlier Than | Warning
35998 | Kern PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17644SS | 0 | Start No Earlier Than | Warning
35999 | Kern PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17643SS |  | 0 | Finish No Earlier Than | Warning
36000 | Kern PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17646 | 0 | Start No Earlier Than | Warning
36001 | Kern PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17645 |  | 0 | Finish No Earlier Than | Warning
36002 | Kern PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36004 | Kern PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17650SS | 0 | Start No Earlier Than | Warning
36005 | Kern PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17649SS | 17651SS | 0 | Finish No Earlier Than | Warning
36006 | Kern PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17650SS | 17652SS | 0 | Finish No Earlier Than | Warning
36007 | Kern PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17651SS | 17653SS | 0 | Finish No Earlier Than | Warning
36008 | Kern PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17652SS | 17654SS | 0 | Finish No Earlier Than | Warning
36009 | Kern PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17653SS | 17655SS | 0 | Finish No Earlier Than | Warning
36010 | Kern PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17654SS | 17656SS | 0 | Finish No Earlier Than | Warning
36011 | Kern PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17655SS | 17657SS | 0 | Finish No Earlier Than | Warning
36012 | Kern PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17656SS | 17658SS | 0 | Finish No Earlier Than | Warning
36013 | Kern PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17657SS | 17659SS | 0 | Finish No Earlier Than | Warning
36014 | Kern PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17658SS |  | 0 | Finish No Earlier Than | Warning
36015 | Kern PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36016 | Kern PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36018 | Kern PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17664SS,17668 | 0 | Start No Earlier Than | Warning
36019 | Kern PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17663SS |  | 0 | Start No Earlier Than | Warning
36020 | Kern PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36021 | Kern PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17674 | 0 | Start No Earlier Than | Warning
36022 | Kern PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17675 | 0 | Start No Earlier Than | Warning
36023 | Kern PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17663 |  | 0 | Start No Earlier Than | Warning
36024 | Kern PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36025 | Kern PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17671SS,17679SS+20d | 0 | Start No Earlier Than | Warning
36026 | Kern PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17670SS | 17672SS,17680SS+20d | 0 | Finish No Earlier Than | Warning
36027 | Kern PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17671SS | 17681SS+20d | 0 | Finish No Earlier Than | Warning
36028 | Kern PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36029 | Kern PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17666 | 17675SS | 0 | Start No Earlier Than | Warning
36030 | Kern PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17667,17674SS |  | 0 | Finish No Earlier Than | Warning
36031 | Kern PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17684FS+12d | 0 | Start No Earlier Than | Warning
36032 | Kern PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17678SS | 0 | Start No Earlier Than | Warning
36033 | Kern PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17677SS |  | 0 | Start No Earlier Than | Warning
36037 | Kern PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17684SS+44d | 0 | Start No Earlier Than | Warning
36038 | Kern PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36043 | Kings PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36044 | Kings PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36045 | Kings PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36046 | Kings PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
36047 | Kings PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36048 | Kings PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36049 | Kings PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36050 | Kings PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36051 | Kings PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36052 | Kings PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36053 | Kings PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36054 | Kings PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36055 | Kings PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36056 | Kings PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36057 | Kings PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36058 | Kings PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36059 | Kings PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36060 | Kings PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36061 | Kings PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36062 | Kings PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36063 | Kings PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36064 | Kings PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36065 | Kings PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36066 | Kings PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36067 | Kings PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
36068 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17714SS | 0 | Start No Earlier Than | Warning
36069 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17713SS |  | 0 | Finish No Earlier Than | Warning
36070 | Kings PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17716SS | 0 | Start No Earlier Than | Warning
36071 | Kings PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17715SS |  | 0 | Start No Earlier Than | Warning
36072 | Kings PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 17719SS,17718SS | 0 | Finish No Earlier Than | Warning
36075 | Kings PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
36076 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 17722SS | 0 | Start No Earlier Than | Warning
36078 | Kings PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
36079 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 17725SS | 0 | Start No Earlier Than | Warning
36080 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 17724SS |  | 0 | Start No Earlier Than | Warning
36081 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 17727SS | 0 | Start No Earlier Than | Warning
36083 | Kings PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
36084 | Kings PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
36087 | Kings PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36088 | Kings PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36089 | Kings PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
36090 | Kings PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
36092 | Kings PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17739FS-1d | 1 | Start No Earlier Than | Warning
36093 | Kings PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36094 | Kings PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 17737FS-1d |  | 0.2 | Start No Earlier Than | Warning
36095 | Kings PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36096 | Kings PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17742 | 1 | Start No Earlier Than | Warning
36097 | Kings PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17741 |  | 0.2 | Start No Earlier Than | Warning
36098 | Kings PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36099 | Kings PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17745FS+19d | 0.2 | Finish No Earlier Than | Warning
36100 | Kings PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17744FS+19d | 17746 | 0 | Start No Earlier Than | Warning
36102 | Kings PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36103 | Kings PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17749 | 0 | Start No Earlier Than | Warning
36104 | Kings PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17748 | 17750FS-1d | 0 | Start No Earlier Than | Warning
36105 | Kings PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17749FS-1d |  | 0 | Finish No Earlier Than | Warning
36106 | Kings PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36107 | Kings PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36110 | Kings PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17756SS | 0 | Finish No Earlier Than | Warning
36111 | Kings PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17755SS |  | 0 | Finish No Earlier Than | Warning
36112 | Kings PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36113 | Kings PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | Start No Earlier Than | Warning
36115 | Kings PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17761SS | 0 | Finish No Earlier Than | Warning
36116 | Kings PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17760SS | 17775SS | 0 | Start No Earlier Than | Warning
36118 | Kings PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36119 | Kings PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36121 | Kings PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17767SS | 0 | Start No Earlier Than | Warning
36122 | Kings PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17766SS | 17768SS,17769 | 0 | Finish No Earlier Than | Warning
36124 | Kings PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17767,17768 |  | 0 | Finish No Earlier Than | Warning
36125 | Kings PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36127 | Kings PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17773SS | 0 | Finish No Earlier Than | Warning
36128 | Kings PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17772SS |  | 0 | Finish No Earlier Than | Warning
36129 | Kings PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36130 | Kings PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17761SS |  | 0 | Finish No Earlier Than | Warning
36132 | Kings PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17778SS | 0 | Finish No Earlier Than | Warning
36133 | Kings PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17777SS |  | 0 | Finish No Earlier Than | Warning
36135 | Kings PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17781SS+18d | 0 | Start No Earlier Than | Warning
36136 | Kings PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17780SS+18d |  | 0 | Finish No Earlier Than | Warning
36138 | Kings PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17784SS | 0 | Start No Earlier Than | Warning
36139 | Kings PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17783SS |  | 0 | Finish No Earlier Than | Warning
36140 | Kings PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17786 | 0 | Start No Earlier Than | Warning
36141 | Kings PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17785 |  | 0 | Finish No Earlier Than | Warning
36142 | Kings PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36144 | Kings PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17790SS | 0 | Start No Earlier Than | Warning
36145 | Kings PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17789SS | 17791SS | 0 | Finish No Earlier Than | Warning
36146 | Kings PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17790SS | 17792SS | 0 | Finish No Earlier Than | Warning
36147 | Kings PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17791SS | 17793SS | 0 | Finish No Earlier Than | Warning
36148 | Kings PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17792SS | 17794SS | 0 | Finish No Earlier Than | Warning
36149 | Kings PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17793SS | 17795SS | 0 | Finish No Earlier Than | Warning
36150 | Kings PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17794SS | 17796SS | 0 | Finish No Earlier Than | Warning
36151 | Kings PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17795SS | 17797SS | 0 | Finish No Earlier Than | Warning
36152 | Kings PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17796SS | 17798SS | 0 | Finish No Earlier Than | Warning
36153 | Kings PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17797SS | 17799SS | 0 | Finish No Earlier Than | Warning
36154 | Kings PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17798SS |  | 0 | Finish No Earlier Than | Warning
36155 | Kings PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
36156 | Kings PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
36158 | Kings PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17804SS,17808 | 0 | Start No Earlier Than | Warning
36159 | Kings PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17803SS |  | 0 | Start No Earlier Than | Warning
36160 | Kings PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36161 | Kings PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17814 | 0 | Start No Earlier Than | Warning
36162 | Kings PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 17815 | 0 | Start No Earlier Than | Warning
36163 | Kings PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17803 |  | 0 | Start No Earlier Than | Warning
36164 | Kings PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36165 | Kings PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 17811SS,17819SS+20d | 0 | Start No Earlier Than | Warning
36168 | Kings PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36169 | Kings PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 17806 | 17815SS | 0 | Start No Earlier Than | Warning
36171 | Kings PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 17824FS+12d | 0 | Start No Earlier Than | Warning
36172 | Kings PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17818SS | 0 | Start No Earlier Than | Warning
36173 | Kings PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17817SS |  | 0 | Start No Earlier Than | Warning
36177 | Kings PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 17824SS+44d | 0 | Start No Earlier Than | Warning
36178 | Kings PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36183 | Lake PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36184 | Lake PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36185 | Lake PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36186 | Lake PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
36187 | Lake PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36188 | Lake PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36189 | Lake PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36190 | Lake PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36191 | Lake PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36192 | Lake PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36193 | Lake PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36194 | Lake PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36195 | Lake PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36196 | Lake PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36197 | Lake PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36198 | Lake PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36199 | Lake PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36200 | Lake PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36201 | Lake PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36202 | Lake PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36203 | Lake PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36204 | Lake PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36205 | Lake PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36206 | Lake PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36207 | Lake PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
36208 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17854SS | 0 | Start No Earlier Than | Warning
36209 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17853SS |  | 0 | Finish No Earlier Than | Warning
36210 | Lake PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17856SS | 0 | Start No Earlier Than | Warning
36211 | Lake PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17855SS |  | 0 | Start No Earlier Than | Warning
36212 | Lake PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36213 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 17859SS | 0 | Finish No Earlier Than | Warning
36214 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17858SS |  | 0 | Finish No Earlier Than | Warning
36215 | Lake PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36216 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 17862SS | 0 | Finish No Earlier Than | Warning
36218 | Lake PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36219 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 17865SS | 0 | Finish No Earlier Than | Warning
36220 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 17864SS |  | 0 | Start No Earlier Than | Warning
36221 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 17867SS | 0 | Start No Earlier Than | Warning
36222 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 17866SS |  | 0 | Start No Earlier Than | Warning
36223 | Lake PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36224 | Lake PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36227 | Lake PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36228 | Lake PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36229 | Lake PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36230 | Lake PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 17876FS+10d | 0 | Start No Earlier Than | Warning
36231 | Lake PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 17875FS+10d |  | 0 | Start No Earlier Than | Warning
36233 | Lake PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 17880FS-1d | 1 | Start No Earlier Than | Warning
36234 | Lake PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36235 | Lake PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 17878FS-1d |  | 0.2 | Start No Earlier Than | Warning
36236 | Lake PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36237 | Lake PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 17883 | 1 | Start No Earlier Than | Warning
36238 | Lake PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17882 |  | 0 | Start No Earlier Than | Warning
36239 | Lake PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36240 | Lake PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 17886FS+19d | 0 | Finish No Earlier Than | Warning
36241 | Lake PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 17885FS+19d | 17887 | 0 | Start No Earlier Than | Warning
36243 | Lake PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36244 | Lake PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 17890 | 0 | Start No Earlier Than | Warning
36245 | Lake PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 17889 | 17891FS-1d | 0 | Start No Earlier Than | Warning
36246 | Lake PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 17890FS-1d |  | 0 | Finish No Earlier Than | Warning
36247 | Lake PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36248 | Lake PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36251 | Lake PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17897SS | 0 | Finish No Earlier Than | Warning
36252 | Lake PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17896SS |  | 0 | Finish No Earlier Than | Warning
36253 | Lake PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36254 | Lake PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
36256 | Lake PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17902SS | 0 | Finish No Earlier Than | Warning
36257 | Lake PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17901SS | 17916SS | 0 | Start No Earlier Than | Warning
36259 | Lake PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36260 | Lake PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36262 | Lake PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 17908SS | 0 | Start No Earlier Than | Warning
36263 | Lake PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17907SS | 17909SS,17910 | 0 | Finish No Earlier Than | Warning
36265 | Lake PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17908,17909 |  | 0 | Finish No Earlier Than | Warning
36266 | Lake PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36268 | Lake PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17914SS | 0 | Finish No Earlier Than | Warning
36269 | Lake PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 17913SS |  | 0 | Finish No Earlier Than | Warning
36270 | Lake PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36271 | Lake PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17902SS |  | 0 | Finish No Earlier Than | Warning
36273 | Lake PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 17919SS | 0 | Finish No Earlier Than | Warning
36274 | Lake PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 17918SS |  | 0 | Finish No Earlier Than | Warning
36276 | Lake PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 17922SS+18d | 0 | Start No Earlier Than | Warning
36277 | Lake PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 17921SS+18d |  | 0 | Finish No Earlier Than | Warning
36279 | Lake PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 17925SS | 0 | Start No Earlier Than | Warning
36280 | Lake PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 17924SS |  | 0 | Finish No Earlier Than | Warning
36281 | Lake PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17927 | 0 | Start No Earlier Than | Warning
36282 | Lake PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 17926 |  | 0 | Finish No Earlier Than | Warning
36283 | Lake PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36285 | Lake PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 17931SS | 0 | Start No Earlier Than | Warning
36286 | Lake PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17930SS | 17932SS | 0 | Finish No Earlier Than | Warning
36287 | Lake PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17931SS | 17933SS | 0 | Finish No Earlier Than | Warning
36288 | Lake PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17932SS | 17934SS | 0 | Finish No Earlier Than | Warning
36289 | Lake PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17933SS | 17935SS | 0 | Finish No Earlier Than | Warning
36290 | Lake PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17934SS | 17936SS | 0 | Finish No Earlier Than | Warning
36291 | Lake PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17935SS | 17937SS | 0 | Finish No Earlier Than | Warning
36292 | Lake PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17936SS | 17938SS | 0 | Finish No Earlier Than | Warning
36293 | Lake PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17937SS | 17939SS | 0 | Finish No Earlier Than | Warning
36294 | Lake PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17938SS | 17940SS | 0 | Finish No Earlier Than | Warning
36295 | Lake PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 17939SS |  | 0 | Finish No Earlier Than | Warning
36296 | Lake PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36297 | Lake PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36299 | Lake PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 17945SS,17949 | 0 | Start No Earlier Than | Warning
36300 | Lake PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 17944SS |  | 0 | Start No Earlier Than | Warning
36301 | Lake PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36302 | Lake PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17955 | 0 | Start No Earlier Than | Warning
36303 | Lake PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 17956 | 0 | Start No Earlier Than | Warning
36304 | Lake PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 17944 |  | 0 | Start No Earlier Than | Warning
36305 | Lake PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36306 | Lake PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 17952SS,17960SS+20d | 0 | Start No Earlier Than | Warning
36307 | Lake PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17951SS | 17953SS,17961SS+20d | 0 | Finish No Earlier Than | Warning
36308 | Lake PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 17952SS | 17962SS+20d | 0 | Finish No Earlier Than | Warning
36309 | Lake PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36310 | Lake PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17947 | 17956SS | 0 | Start No Earlier Than | Warning
36311 | Lake PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 17948,17955SS |  | 0 | Finish No Earlier Than | Warning
36312 | Lake PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 17965FS+12d | 0 | Start No Earlier Than | Warning
36313 | Lake PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 17959SS | 0 | Start No Earlier Than | Warning
36314 | Lake PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 17958SS |  | 0 | Start No Earlier Than | Warning
36318 | Lake PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 17965SS+44d | 0 | Start No Earlier Than | Warning
36319 | Lake PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36324 | Lassen PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36325 | Lassen PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36326 | Lassen PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36327 | Lassen PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
36328 | Lassen PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36329 | Lassen PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36330 | Lassen PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36331 | Lassen PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36332 | Lassen PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36333 | Lassen PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36334 | Lassen PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36335 | Lassen PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36336 | Lassen PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36337 | Lassen PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36338 | Lassen PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36339 | Lassen PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36340 | Lassen PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36341 | Lassen PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36342 | Lassen PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36343 | Lassen PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36344 | Lassen PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36345 | Lassen PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36346 | Lassen PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36347 | Lassen PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36348 | Lassen PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
36349 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 17995SS | 0 | Start No Earlier Than | Warning
36350 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 17994SS |  | 0 | Finish No Earlier Than | Warning
36351 | Lassen PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 17997SS | 0 | Start No Earlier Than | Warning
36352 | Lassen PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 17996SS |  | 0 | Start No Earlier Than | Warning
36353 | Lassen PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36354 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18000SS | 0 | Finish No Earlier Than | Warning
36355 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 17999SS |  | 0 | Finish No Earlier Than | Warning
36356 | Lassen PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36357 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18003SS | 0 | Finish No Earlier Than | Warning
36359 | Lassen PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36360 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18006SS | 0 | Finish No Earlier Than | Warning
36361 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18005SS |  | 0 | Start No Earlier Than | Warning
36362 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18008SS | 0 | Start No Earlier Than | Warning
36363 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18007SS |  | 0 | Start No Earlier Than | Warning
36364 | Lassen PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36365 | Lassen PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36368 | Lassen PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36369 | Lassen PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36370 | Lassen PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36371 | Lassen PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18017FS+10d | 0 | Start No Earlier Than | Warning
36372 | Lassen PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18016FS+10d |  | 0 | Start No Earlier Than | Warning
36374 | Lassen PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36375 | Lassen PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d |  |  | 0.2 | Start No Earlier Than | Warning
36376 | Lassen PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36377 | Lassen PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18023 | 1 | Start No Earlier Than | Warning
36378 | Lassen PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18022 |  | 0 | Start No Earlier Than | Warning
36379 | Lassen PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36380 | Lassen PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18026FS+19d | 0 | Finish No Earlier Than | Warning
36381 | Lassen PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18025FS+19d | 18027 | 0 | Start No Earlier Than | Warning
36383 | Lassen PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36384 | Lassen PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18030 | 0 | Start No Earlier Than | Warning
36385 | Lassen PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18029 | 18031FS-1d | 0 | Start No Earlier Than | Warning
36386 | Lassen PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18030FS-1d |  | 0 | Finish No Earlier Than | Warning
36387 | Lassen PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36388 | Lassen PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36391 | Lassen PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18037SS | 0 | Finish No Earlier Than | Warning
36392 | Lassen PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18036SS |  | 0 | Finish No Earlier Than | Warning
36393 | Lassen PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36394 | Lassen PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
36396 | Lassen PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18042SS | 0 | Finish No Earlier Than | Warning
36397 | Lassen PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18041SS | 18056SS | 0 | Start No Earlier Than | Warning
36399 | Lassen PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36400 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36402 | Lassen PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18048SS | 0 | Start No Earlier Than | Warning
36403 | Lassen PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18047SS | 18049SS,18050 | 0 | Finish No Earlier Than | Warning
36405 | Lassen PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18048,18049 |  | 0 | Finish No Earlier Than | Warning
36406 | Lassen PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36408 | Lassen PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18054SS | 0 | Finish No Earlier Than | Warning
36409 | Lassen PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18053SS |  | 0 | Finish No Earlier Than | Warning
36410 | Lassen PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36411 | Lassen PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18042SS |  | 0 | Finish No Earlier Than | Warning
36413 | Lassen PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18059SS | 0 | Finish No Earlier Than | Warning
36414 | Lassen PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18058SS |  | 0 | Finish No Earlier Than | Warning
36416 | Lassen PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18062SS+18d | 0 | Start No Earlier Than | Warning
36417 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18061SS+18d |  | 0 | Finish No Earlier Than | Warning
36419 | Lassen PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18065SS | 0 | Start No Earlier Than | Warning
36420 | Lassen PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18064SS |  | 0 | Finish No Earlier Than | Warning
36421 | Lassen PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18067 | 0 | Start No Earlier Than | Warning
36422 | Lassen PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18066 |  | 0 | Finish No Earlier Than | Warning
36423 | Lassen PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36425 | Lassen PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18071SS | 0 | Start No Earlier Than | Warning
36426 | Lassen PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18070SS | 18072SS | 0 | Finish No Earlier Than | Warning
36427 | Lassen PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18071SS | 18073SS | 0 | Finish No Earlier Than | Warning
36428 | Lassen PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18072SS | 18074SS | 0 | Finish No Earlier Than | Warning
36429 | Lassen PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18073SS | 18075SS | 0 | Finish No Earlier Than | Warning
36430 | Lassen PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18074SS | 18076SS | 0 | Finish No Earlier Than | Warning
36431 | Lassen PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18075SS | 18077SS | 0 | Finish No Earlier Than | Warning
36432 | Lassen PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18076SS | 18078SS | 0 | Finish No Earlier Than | Warning
36433 | Lassen PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18077SS | 18079SS | 0 | Finish No Earlier Than | Warning
36434 | Lassen PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18078SS | 18080SS | 0 | Finish No Earlier Than | Warning
36435 | Lassen PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18079SS |  | 0 | Finish No Earlier Than | Warning
36436 | Lassen PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36437 | Lassen PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36439 | Lassen PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18085SS,18089 | 0 | Start No Earlier Than | Warning
36440 | Lassen PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18084SS |  | 0 | Start No Earlier Than | Warning
36441 | Lassen PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36442 | Lassen PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18095 | 0 | Start No Earlier Than | Warning
36443 | Lassen PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18096 | 0 | Start No Earlier Than | Warning
36444 | Lassen PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18084 |  | 0 | Start No Earlier Than | Warning
36445 | Lassen PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36446 | Lassen PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18092SS,18100SS+20d | 0 | Start No Earlier Than | Warning
36447 | Lassen PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18091SS | 18093SS,18101SS+20d | 0 | Finish No Earlier Than | Warning
36448 | Lassen PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18092SS | 18102SS+20d | 0 | Finish No Earlier Than | Warning
36449 | Lassen PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36450 | Lassen PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18087 | 18096SS | 0 | Start No Earlier Than | Warning
36451 | Lassen PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18088,18095SS |  | 0 | Finish No Earlier Than | Warning
36452 | Lassen PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18105FS+12d | 0 | Start No Earlier Than | Warning
36453 | Lassen PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18099SS | 0 | Start No Earlier Than | Warning
36454 | Lassen PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18098SS |  | 0 | Start No Earlier Than | Warning
36458 | Lassen PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18105SS+44d | 0 | Start No Earlier Than | Warning
36459 | Lassen PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36464 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36465 | Los Angeles PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36466 | Los Angeles PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36467 | Los Angeles PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
36468 | Los Angeles PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36469 | Los Angeles PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36470 | Los Angeles PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36471 | Los Angeles PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36472 | Los Angeles PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36473 | Los Angeles PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36474 | Los Angeles PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36475 | Los Angeles PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36476 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36477 | Los Angeles PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36478 | Los Angeles PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36479 | Los Angeles PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36480 | Los Angeles PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36481 | Los Angeles PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36482 | Los Angeles PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36483 | Los Angeles PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36484 | Los Angeles PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36485 | Los Angeles PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36486 | Los Angeles PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36487 | Los Angeles PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36488 | Los Angeles PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
36489 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18135SS | 0 | Start No Earlier Than | Warning
36490 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18134SS |  | 0 | Finish No Earlier Than | Warning
36491 | Los Angeles PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18137SS | 0 | Start No Earlier Than | Warning
36492 | Los Angeles PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18136SS |  | 0 | Start No Earlier Than | Warning
36493 | Los Angeles PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36494 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18140SS | 0 | Finish No Earlier Than | Warning
36495 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18139SS |  | 0 | Finish No Earlier Than | Warning
36496 | Los Angeles PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36497 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18143SS | 0 | Finish No Earlier Than | Warning
36499 | Los Angeles PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36500 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18146SS | 0 | Finish No Earlier Than | Warning
36501 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18145SS |  | 0 | Start No Earlier Than | Warning
36502 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18148SS | 0 | Start No Earlier Than | Warning
36503 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18147SS |  | 0 | Start No Earlier Than | Warning
36504 | Los Angeles PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36505 | Los Angeles PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36508 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36509 | Los Angeles PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36510 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36511 | Los Angeles PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18157FS+10d | 0 | Start No Earlier Than | Warning
36512 | Los Angeles PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18156FS+10d |  | 0 | Start No Earlier Than | Warning
36514 | Los Angeles PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18161FS-1d | 1 | Start No Earlier Than | Warning
36515 | Los Angeles PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36516 | Los Angeles PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18159FS-1d |  | 0.2 | Start No Earlier Than | Warning
36517 | Los Angeles PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36518 | Los Angeles PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18164 | 1 | Start No Earlier Than | Warning
36519 | Los Angeles PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18163 |  | 0.2 | Start No Earlier Than | Warning
36520 | Los Angeles PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36521 | Los Angeles PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18167FS+19d | 0.2 | Finish No Earlier Than | Warning
36522 | Los Angeles PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18166FS+19d | 18168 | 0 | Start No Earlier Than | Warning
36524 | Los Angeles PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36525 | Los Angeles PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18171 | 0 | Start No Earlier Than | Warning
36526 | Los Angeles PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18170 | 18172FS-1d | 0 | Start No Earlier Than | Warning
36527 | Los Angeles PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18171FS-1d |  | 0 | Finish No Earlier Than | Warning
36528 | Los Angeles PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36529 | Los Angeles PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36532 | Los Angeles PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18178SS | 0 | Finish No Earlier Than | Warning
36533 | Los Angeles PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18177SS |  | 0 | Finish No Earlier Than | Warning
36534 | Los Angeles PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36535 | Los Angeles PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
36537 | Los Angeles PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18183SS | 0 | Finish No Earlier Than | Warning
36538 | Los Angeles PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18182SS | 18197SS | 0 | Start No Earlier Than | Warning
36540 | Los Angeles PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36541 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36543 | Los Angeles PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18189SS | 0 | Start No Earlier Than | Warning
36544 | Los Angeles PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18188SS | 18190SS,18191 | 0 | Finish No Earlier Than | Warning
36546 | Los Angeles PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18189,18190 |  | 0 | Finish No Earlier Than | Warning
36547 | Los Angeles PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36549 | Los Angeles PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18195SS | 0 | Finish No Earlier Than | Warning
36550 | Los Angeles PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18194SS |  | 0 | Finish No Earlier Than | Warning
36551 | Los Angeles PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36552 | Los Angeles PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18183SS |  | 0 | Finish No Earlier Than | Warning
36554 | Los Angeles PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18200SS | 0 | Finish No Earlier Than | Warning
36555 | Los Angeles PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18199SS |  | 0 | Finish No Earlier Than | Warning
36557 | Los Angeles PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18203SS+18d | 0 | Start No Earlier Than | Warning
36558 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18202SS+18d |  | 0 | Finish No Earlier Than | Warning
36560 | Los Angeles PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18206SS | 0 | Start No Earlier Than | Warning
36561 | Los Angeles PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18205SS |  | 0 | Finish No Earlier Than | Warning
36562 | Los Angeles PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18208 | 0 | Start No Earlier Than | Warning
36563 | Los Angeles PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18207 |  | 0 | Finish No Earlier Than | Warning
36564 | Los Angeles PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36566 | Los Angeles PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18212SS | 0 | Start No Earlier Than | Warning
36567 | Los Angeles PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18211SS | 18213SS | 0 | Finish No Earlier Than | Warning
36568 | Los Angeles PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18212SS | 18214SS | 0 | Finish No Earlier Than | Warning
36569 | Los Angeles PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18213SS | 18215SS | 0 | Finish No Earlier Than | Warning
36570 | Los Angeles PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18214SS | 18216SS | 0 | Finish No Earlier Than | Warning
36571 | Los Angeles PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18215SS | 18217SS | 0 | Finish No Earlier Than | Warning
36572 | Los Angeles PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18216SS | 18218SS | 0 | Finish No Earlier Than | Warning
36573 | Los Angeles PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18217SS | 18219SS | 0 | Finish No Earlier Than | Warning
36574 | Los Angeles PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18218SS | 18220SS | 0 | Finish No Earlier Than | Warning
36575 | Los Angeles PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18219SS | 18221SS | 0 | Finish No Earlier Than | Warning
36576 | Los Angeles PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18220SS |  | 0 | Finish No Earlier Than | Warning
36577 | Los Angeles PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36578 | Los Angeles PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36580 | Los Angeles PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18226SS,18230 | 0 | Start No Earlier Than | Warning
36581 | Los Angeles PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18225SS |  | 0 | Start No Earlier Than | Warning
36582 | Los Angeles PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36583 | Los Angeles PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18236 | 0 | Start No Earlier Than | Warning
36584 | Los Angeles PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18237 | 0 | Start No Earlier Than | Warning
36585 | Los Angeles PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18225 |  | 0 | Start No Earlier Than | Warning
36586 | Los Angeles PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36587 | Los Angeles PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18233SS,18241SS+20d | 0 | Start No Earlier Than | Warning
36588 | Los Angeles PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18232SS | 18234SS,18242SS+20d | 0 | Finish No Earlier Than | Warning
36589 | Los Angeles PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18233SS | 18243SS+20d | 0 | Finish No Earlier Than | Warning
36590 | Los Angeles PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36591 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18228 | 18237SS | 0 | Start No Earlier Than | Warning
36592 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18229,18236SS |  | 0 | Finish No Earlier Than | Warning
36593 | Los Angeles PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18246FS+12d | 0 | Start No Earlier Than | Warning
36594 | Los Angeles PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18240SS | 0 | Start No Earlier Than | Warning
36595 | Los Angeles PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18239SS |  | 0 | Start No Earlier Than | Warning
36599 | Los Angeles PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18246SS+44d | 0 | Start No Earlier Than | Warning
36600 | Los Angeles PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36605 | Madera PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36606 | Madera PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36607 | Madera PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36608 | Madera PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
36609 | Madera PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36610 | Madera PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36611 | Madera PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36612 | Madera PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36613 | Madera PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36614 | Madera PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36615 | Madera PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36616 | Madera PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36617 | Madera PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36618 | Madera PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36619 | Madera PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36620 | Madera PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36621 | Madera PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36622 | Madera PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36623 | Madera PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36624 | Madera PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36625 | Madera PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36626 | Madera PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36627 | Madera PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36628 | Madera PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36629 | Madera PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
36630 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18276SS | 0 | Start No Earlier Than | Warning
36631 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18275SS |  | 0 | Finish No Earlier Than | Warning
36632 | Madera PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18278SS | 0 | Start No Earlier Than | Warning
36633 | Madera PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18277SS |  | 0 | Start No Earlier Than | Warning
36634 | Madera PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36635 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18281SS | 0 | Finish No Earlier Than | Warning
36636 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18280SS |  | 0 | Finish No Earlier Than | Warning
36637 | Madera PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36638 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18284SS | 0 | Finish No Earlier Than | Warning
36640 | Madera PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36641 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18287SS | 0 | Finish No Earlier Than | Warning
36642 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18286SS |  | 0 | Start No Earlier Than | Warning
36643 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18289SS | 0 | Start No Earlier Than | Warning
36644 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18288SS |  | 0 | Start No Earlier Than | Warning
36645 | Madera PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36646 | Madera PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36649 | Madera PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36650 | Madera PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36651 | Madera PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36652 | Madera PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18298FS+10d | 0 | Start No Earlier Than | Warning
36653 | Madera PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18297FS+10d |  | 0 | Start No Earlier Than | Warning
36655 | Madera PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18302FS-1d | 1 | Start No Earlier Than | Warning
36656 | Madera PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36657 | Madera PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18300FS-1d |  | 0 | Start No Earlier Than | Warning
36658 | Madera PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36659 | Madera PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18305 | 1 | Start No Earlier Than | Warning
36660 | Madera PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18304 |  | 0 | Start No Earlier Than | Warning
36661 | Madera PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36662 | Madera PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  | 18308FS+19d | 1 | Finish No Earlier Than | Warning
36663 | Madera PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18307FS+19d | 18309 | 0 | Start No Earlier Than | Warning
36665 | Madera PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36666 | Madera PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18312 | 0 | Start No Earlier Than | Warning
36667 | Madera PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18311 | 18313FS-1d | 0 | Start No Earlier Than | Warning
36668 | Madera PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18312FS-1d |  | 0 | Finish No Earlier Than | Warning
36669 | Madera PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36670 | Madera PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36673 | Madera PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18319SS | 0 | Finish No Earlier Than | Warning
36674 | Madera PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18318SS |  | 0 | Finish No Earlier Than | Warning
36675 | Madera PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36676 | Madera PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
36678 | Madera PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18324SS | 0 | Finish No Earlier Than | Warning
36679 | Madera PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18323SS | 18338SS | 0 | Start No Earlier Than | Warning
36681 | Madera PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36682 | Madera PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36684 | Madera PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18330SS | 0 | Start No Earlier Than | Warning
36685 | Madera PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18329SS | 18331SS,18332 | 0 | Finish No Earlier Than | Warning
36687 | Madera PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18330,18331 |  | 0 | Finish No Earlier Than | Warning
36688 | Madera PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36690 | Madera PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18336SS | 0 | Finish No Earlier Than | Warning
36691 | Madera PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18335SS |  | 0 | Finish No Earlier Than | Warning
36692 | Madera PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36693 | Madera PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18324SS |  | 0 | Finish No Earlier Than | Warning
36695 | Madera PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18341SS | 0 | Finish No Earlier Than | Warning
36696 | Madera PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18340SS |  | 0 | Finish No Earlier Than | Warning
36698 | Madera PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18344SS+18d | 0 | Start No Earlier Than | Warning
36699 | Madera PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18343SS+18d |  | 0 | Finish No Earlier Than | Warning
36701 | Madera PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18347SS | 0 | Start No Earlier Than | Warning
36702 | Madera PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18346SS |  | 0 | Finish No Earlier Than | Warning
36703 | Madera PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18349 | 0 | Start No Earlier Than | Warning
36704 | Madera PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18348 |  | 0 | Finish No Earlier Than | Warning
36705 | Madera PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36707 | Madera PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18353SS | 0 | Start No Earlier Than | Warning
36708 | Madera PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18352SS | 18354SS | 0 | Finish No Earlier Than | Warning
36709 | Madera PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18353SS | 18355SS | 0 | Finish No Earlier Than | Warning
36710 | Madera PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18354SS | 18356SS | 0 | Finish No Earlier Than | Warning
36711 | Madera PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18355SS | 18357SS | 0 | Finish No Earlier Than | Warning
36712 | Madera PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18356SS | 18358SS | 0 | Finish No Earlier Than | Warning
36713 | Madera PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18357SS | 18359SS | 0 | Finish No Earlier Than | Warning
36714 | Madera PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18358SS | 18360SS | 0 | Finish No Earlier Than | Warning
36715 | Madera PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18359SS | 18361SS | 0 | Finish No Earlier Than | Warning
36716 | Madera PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18360SS | 18362SS | 0 | Finish No Earlier Than | Warning
36717 | Madera PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18361SS |  | 0 | Finish No Earlier Than | Warning
36718 | Madera PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36719 | Madera PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36721 | Madera PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18367SS,18371 | 0 | Start No Earlier Than | Warning
36722 | Madera PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18366SS |  | 0 | Start No Earlier Than | Warning
36723 | Madera PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36724 | Madera PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18377 | 0 | Start No Earlier Than | Warning
36725 | Madera PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18378 | 0 | Start No Earlier Than | Warning
36726 | Madera PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18366 |  | 0 | Start No Earlier Than | Warning
36727 | Madera PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36728 | Madera PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18374SS,18382SS+20d | 0 | Start No Earlier Than | Warning
36729 | Madera PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18373SS | 18375SS,18383SS+20d | 0 | Finish No Earlier Than | Warning
36730 | Madera PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18374SS | 18384SS+20d | 0 | Finish No Earlier Than | Warning
36731 | Madera PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36732 | Madera PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18369 | 18378SS | 0 | Start No Earlier Than | Warning
36733 | Madera PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18370,18377SS |  | 0 | Finish No Earlier Than | Warning
36734 | Madera PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18387FS+12d | 0 | Start No Earlier Than | Warning
36735 | Madera PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18381SS | 0 | Start No Earlier Than | Warning
36736 | Madera PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18380SS |  | 0 | Start No Earlier Than | Warning
36740 | Madera PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18387SS+44d | 0 | Start No Earlier Than | Warning
36741 | Madera PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36746 | Marin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36747 | Marin PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36748 | Marin PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36749 | Marin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
36750 | Marin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36751 | Marin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36752 | Marin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36753 | Marin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36754 | Marin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36755 | Marin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36756 | Marin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36757 | Marin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36758 | Marin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36759 | Marin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36760 | Marin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36761 | Marin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36762 | Marin PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36763 | Marin PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36764 | Marin PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36765 | Marin PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36766 | Marin PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36767 | Marin PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36768 | Marin PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36769 | Marin PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36770 | Marin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
36771 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18417SS | 0 | Start No Earlier Than | Warning
36772 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18416SS |  | 0 | Finish No Earlier Than | Warning
36773 | Marin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18419SS | 0 | Start No Earlier Than | Warning
36774 | Marin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18418SS |  | 0 | Start No Earlier Than | Warning
36775 | Marin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36776 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18422SS | 0 | Finish No Earlier Than | Warning
36777 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18421SS |  | 0 | Finish No Earlier Than | Warning
36778 | Marin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36779 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18425SS | 0 | Finish No Earlier Than | Warning
36781 | Marin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36782 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18428SS | 0 | Finish No Earlier Than | Warning
36783 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18427SS |  | 0 | Start No Earlier Than | Warning
36784 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18430SS | 0 | Start No Earlier Than | Warning
36785 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18429SS |  | 0 | Start No Earlier Than | Warning
36786 | Marin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36787 | Marin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36790 | Marin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36791 | Marin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36792 | Marin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36793 | Marin PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18439FS+10d | 0 | Start No Earlier Than | Warning
36794 | Marin PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18438FS+10d |  | 0 | Start No Earlier Than | Warning
36796 | Marin PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18443FS-1d | 1 | Start No Earlier Than | Warning
36797 | Marin PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36798 | Marin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18441FS-1d |  | 0.2 | Start No Earlier Than | Warning
36799 | Marin PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36800 | Marin PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18446 | 1 | Start No Earlier Than | Warning
36801 | Marin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18445 |  | 0.2 | Start No Earlier Than | Warning
36802 | Marin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36803 | Marin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18449FS+19d | 0 | Finish No Earlier Than | Warning
36804 | Marin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18448FS+19d | 18450 | 0 | Start No Earlier Than | Warning
36806 | Marin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36807 | Marin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18453 | 0 | Start No Earlier Than | Warning
36808 | Marin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18452 | 18454FS-1d | 0 | Start No Earlier Than | Warning
36809 | Marin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18453FS-1d |  | 0 | Finish No Earlier Than | Warning
36810 | Marin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36811 | Marin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36814 | Marin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18460SS | 0 | Finish No Earlier Than | Warning
36815 | Marin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18459SS |  | 0 | Finish No Earlier Than | Warning
36816 | Marin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36817 | Marin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
36819 | Marin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18465SS | 0 | Finish No Earlier Than | Warning
36820 | Marin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18464SS | 18479SS | 0 | Start No Earlier Than | Warning
36822 | Marin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
36823 | Marin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
36825 | Marin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18471SS | 0 | Start No Earlier Than | Warning
36826 | Marin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18470SS | 18472SS,18473 | 0 | Finish No Earlier Than | Warning
36828 | Marin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18471,18472 |  | 0 | Finish No Earlier Than | Warning
36829 | Marin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36831 | Marin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18477SS | 0 | Finish No Earlier Than | Warning
36832 | Marin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18476SS |  | 0 | Finish No Earlier Than | Warning
36833 | Marin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
36834 | Marin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18465SS |  | 0 | Finish No Earlier Than | Warning
36836 | Marin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18482SS | 0 | Finish No Earlier Than | Warning
36837 | Marin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18481SS |  | 0 | Finish No Earlier Than | Warning
36839 | Marin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18485SS+18d | 0 | Start No Earlier Than | Warning
36840 | Marin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18484SS+18d |  | 0 | Finish No Earlier Than | Warning
36842 | Marin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18488SS | 0 | Start No Earlier Than | Warning
36843 | Marin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18487SS |  | 0 | Finish No Earlier Than | Warning
36844 | Marin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18490 | 0 | Start No Earlier Than | Warning
36845 | Marin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18489 |  | 0 | Finish No Earlier Than | Warning
36846 | Marin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
36848 | Marin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18494SS | 0 | Start No Earlier Than | Warning
36849 | Marin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18493SS | 18495SS | 0 | Finish No Earlier Than | Warning
36850 | Marin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18494SS | 18496SS | 0 | Finish No Earlier Than | Warning
36851 | Marin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18495SS | 18497SS | 0 | Finish No Earlier Than | Warning
36852 | Marin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18496SS | 18498SS | 0 | Finish No Earlier Than | Warning
36853 | Marin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18497SS | 18499SS | 0 | Finish No Earlier Than | Warning
36854 | Marin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18498SS | 18500SS | 0 | Finish No Earlier Than | Warning
36855 | Marin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18499SS | 18501SS | 0 | Finish No Earlier Than | Warning
36856 | Marin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18500SS | 18502SS | 0 | Finish No Earlier Than | Warning
36857 | Marin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18501SS | 18503SS | 0 | Finish No Earlier Than | Warning
36858 | Marin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18502SS |  | 0 | Finish No Earlier Than | Warning
36859 | Marin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36860 | Marin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36862 | Marin PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18508SS,18512 | 0 | Start No Earlier Than | Warning
36863 | Marin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18507SS |  | 0 | Start No Earlier Than | Warning
36864 | Marin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36865 | Marin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18518 | 0 | Start No Earlier Than | Warning
36866 | Marin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18519 | 0 | Start No Earlier Than | Warning
36867 | Marin PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18507 |  | 0 | Start No Earlier Than | Warning
36868 | Marin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36869 | Marin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18515SS,18523SS+20d | 0 | Start No Earlier Than | Warning
36870 | Marin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18514SS | 18516SS,18524SS+20d | 0 | Finish No Earlier Than | Warning
36871 | Marin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18515SS | 18525SS+20d | 0 | Finish No Earlier Than | Warning
36872 | Marin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36873 | Marin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18510 | 18519SS | 0 | Start No Earlier Than | Warning
36874 | Marin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18511,18518SS |  | 0 | Finish No Earlier Than | Warning
36875 | Marin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18528FS+12d | 0 | Start No Earlier Than | Warning
36876 | Marin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18522SS | 0 | Start No Earlier Than | Warning
36877 | Marin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18521SS |  | 0 | Start No Earlier Than | Warning
36881 | Marin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18528SS+44d | 0 | Start No Earlier Than | Warning
36882 | Marin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36887 | Mariposa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36888 | Mariposa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36889 | Mariposa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36890 | Mariposa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
36891 | Mariposa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36892 | Mariposa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
36893 | Mariposa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
36894 | Mariposa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
36895 | Mariposa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
36896 | Mariposa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
36897 | Mariposa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
36898 | Mariposa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
36899 | Mariposa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
36900 | Mariposa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
36901 | Mariposa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36902 | Mariposa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
36903 | Mariposa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36904 | Mariposa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36905 | Mariposa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36906 | Mariposa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36907 | Mariposa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36908 | Mariposa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36909 | Mariposa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36910 | Mariposa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36911 | Mariposa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
36912 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18558SS | 0 | Start No Earlier Than | Warning
36913 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18557SS |  | 0 | Finish No Earlier Than | Warning
36914 | Mariposa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18560SS | 0 | Start No Earlier Than | Warning
36915 | Mariposa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18559SS |  | 0 | Start No Earlier Than | Warning
36916 | Mariposa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
36917 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18563SS | 0 | Finish No Earlier Than | Warning
36918 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18562SS |  | 0 | Finish No Earlier Than | Warning
36919 | Mariposa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
36920 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18566SS | 0 | Finish No Earlier Than | Warning
36922 | Mariposa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
36923 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18569SS | 0 | Finish No Earlier Than | Warning
36924 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18568SS |  | 0 | Start No Earlier Than | Warning
36925 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18571SS | 0 | Start No Earlier Than | Warning
36926 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18570SS |  | 0 | Start No Earlier Than | Warning
36927 | Mariposa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
36928 | Mariposa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
36931 | Mariposa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
36932 | Mariposa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
36933 | Mariposa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
36934 | Mariposa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18580FS+10d | 0 | Start No Earlier Than | Warning
36935 | Mariposa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18579FS+10d |  | 0 | Start No Earlier Than | Warning
36937 | Mariposa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18584FS-1d | 1 | Start No Earlier Than | Warning
36938 | Mariposa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36939 | Mariposa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18582FS-1d |  | 0.2 | Start No Earlier Than | Warning
36940 | Mariposa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
36941 | Mariposa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18587 | 1 | Start No Earlier Than | Warning
36942 | Mariposa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18586 |  | 0 | Start No Earlier Than | Warning
36943 | Mariposa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36944 | Mariposa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 18590FS+19d | 1 | Finish No Earlier Than | Warning
36945 | Mariposa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18589FS+19d | 18591 | 0 | Start No Earlier Than | Warning
36947 | Mariposa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
36948 | Mariposa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18594 | 0 | Start No Earlier Than | Warning
36949 | Mariposa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18593 | 18595FS-1d | 0 | Start No Earlier Than | Warning
36950 | Mariposa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18594FS-1d |  | 0 | Finish No Earlier Than | Warning
36951 | Mariposa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
36952 | Mariposa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
36955 | Mariposa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18601SS | 0 | Start No Earlier Than | Warning
36956 | Mariposa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18600SS | 18602SS | 0 | Finish No Earlier Than | Warning
36957 | Mariposa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18601SS | 18603SS | 0 | Finish No Earlier Than | Warning
36958 | Mariposa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18602SS | 18604SS | 0 | Finish No Earlier Than | Warning
36959 | Mariposa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18603SS | 18605SS | 0 | Finish No Earlier Than | Warning
36960 | Mariposa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18604SS | 18606SS | 0 | Finish No Earlier Than | Warning
36961 | Mariposa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18605SS | 18607SS | 0 | Finish No Earlier Than | Warning
36962 | Mariposa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18606SS | 18608SS | 0 | Finish No Earlier Than | Warning
36963 | Mariposa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18607SS | 18609SS | 0 | Finish No Earlier Than | Warning
36964 | Mariposa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18608SS | 18610SS | 0 | Finish No Earlier Than | Warning
36965 | Mariposa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18609SS |  | 0 | Finish No Earlier Than | Warning
36966 | Mariposa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
36967 | Mariposa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
36969 | Mariposa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18615SS,18619 | 0 | Start No Earlier Than | Warning
36970 | Mariposa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18614SS |  | 0 | Start No Earlier Than | Warning
36971 | Mariposa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
36972 | Mariposa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18625 | 0 | Start No Earlier Than | Warning
36973 | Mariposa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18626 | 0 | Start No Earlier Than | Warning
36974 | Mariposa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18614 |  | 0 | Start No Earlier Than | Warning
36975 | Mariposa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
36976 | Mariposa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18622SS,18630SS+20d | 0 | Start No Earlier Than | Warning
36977 | Mariposa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18621SS | 18623SS,18631SS+20d | 0 | Finish No Earlier Than | Warning
36978 | Mariposa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18622SS | 18632SS+20d | 0 | Finish No Earlier Than | Warning
36979 | Mariposa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
36980 | Mariposa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18617 | 18626SS | 0 | Start No Earlier Than | Warning
36981 | Mariposa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18618,18625SS |  | 0 | Finish No Earlier Than | Warning
36982 | Mariposa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18635FS+12d | 0 | Start No Earlier Than | Warning
36983 | Mariposa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18629SS | 0 | Start No Earlier Than | Warning
36984 | Mariposa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18628SS |  | 0 | Start No Earlier Than | Warning
36988 | Mariposa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18635SS+44d | 0 | Start No Earlier Than | Warning
36989 | Mariposa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
36994 | Mendocino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36995 | Mendocino PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
36996 | Mendocino PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
36997 | Mendocino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
36998 | Mendocino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
36999 | Mendocino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37000 | Mendocino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37001 | Mendocino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37002 | Mendocino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37003 | Mendocino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37004 | Mendocino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37005 | Mendocino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37006 | Mendocino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37007 | Mendocino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37008 | Mendocino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37009 | Mendocino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37010 | Mendocino PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37011 | Mendocino PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37012 | Mendocino PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37013 | Mendocino PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37014 | Mendocino PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37015 | Mendocino PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37016 | Mendocino PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37017 | Mendocino PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37018 | Mendocino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
37019 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18665SS | 0 | Start No Earlier Than | Warning
37020 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18664SS |  | 0 | Finish No Earlier Than | Warning
37021 | Mendocino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18667SS | 0 | Start No Earlier Than | Warning
37022 | Mendocino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18666SS |  | 0 | Start No Earlier Than | Warning
37023 | Mendocino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37024 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18670SS | 0 | Finish No Earlier Than | Warning
37025 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18669SS |  | 0 | Finish No Earlier Than | Warning
37026 | Mendocino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37027 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18673SS | 0 | Finish No Earlier Than | Warning
37029 | Mendocino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37030 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18676SS | 0 | Finish No Earlier Than | Warning
37031 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18675SS |  | 0 | Start No Earlier Than | Warning
37032 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18678SS | 0 | Start No Earlier Than | Warning
37033 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18677SS |  | 0 | Start No Earlier Than | Warning
37034 | Mendocino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37035 | Mendocino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37038 | Mendocino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37039 | Mendocino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37040 | Mendocino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37041 | Mendocino PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18687FS+10d | 0 | Start No Earlier Than | Warning
37042 | Mendocino PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18686FS+10d |  | 0 | Start No Earlier Than | Warning
37044 | Mendocino PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18691FS-1d | 1 | Start No Earlier Than | Warning
37045 | Mendocino PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 528d |  |  | 0 | Start No Earlier Than | Warning
37046 | Mendocino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18689FS-1d |  | 0.2 | Start No Earlier Than | Warning
37047 | Mendocino PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37048 | Mendocino PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18694 | 1 | Start No Earlier Than | Warning
37049 | Mendocino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18693 |  | 0 | Start No Earlier Than | Warning
37050 | Mendocino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37051 | Mendocino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18697FS+19d | 0 | Finish No Earlier Than | Warning
37052 | Mendocino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18696FS+19d | 18698 | 0 | Start No Earlier Than | Warning
37054 | Mendocino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37055 | Mendocino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18701 | 0 | Start No Earlier Than | Warning
37056 | Mendocino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18700 | 18702FS-1d | 0 | Start No Earlier Than | Warning
37057 | Mendocino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18701FS-1d |  | 0 | Finish No Earlier Than | Warning
37058 | Mendocino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37059 | Mendocino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37062 | Mendocino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18708SS | 0 | Finish No Earlier Than | Warning
37063 | Mendocino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18707SS |  | 0 | Finish No Earlier Than | Warning
37064 | Mendocino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37065 | Mendocino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
37067 | Mendocino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18713SS | 0 | Finish No Earlier Than | Warning
37068 | Mendocino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18712SS | 18727SS | 0 | Start No Earlier Than | Warning
37070 | Mendocino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37071 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37073 | Mendocino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18719SS | 0 | Start No Earlier Than | Warning
37074 | Mendocino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18718SS | 18720SS,18721 | 0 | Finish No Earlier Than | Warning
37076 | Mendocino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18719,18720 |  | 0 | Finish No Earlier Than | Warning
37077 | Mendocino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37079 | Mendocino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18725SS | 0 | Finish No Earlier Than | Warning
37080 | Mendocino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18724SS |  | 0 | Finish No Earlier Than | Warning
37081 | Mendocino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37082 | Mendocino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18713SS |  | 0 | Finish No Earlier Than | Warning
37084 | Mendocino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18730SS | 0 | Finish No Earlier Than | Warning
37085 | Mendocino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18729SS |  | 0 | Finish No Earlier Than | Warning
37087 | Mendocino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18733SS+18d | 0 | Start No Earlier Than | Warning
37088 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18732SS+18d |  | 0 | Finish No Earlier Than | Warning
37090 | Mendocino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18736SS | 0 | Start No Earlier Than | Warning
37091 | Mendocino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18735SS |  | 0 | Finish No Earlier Than | Warning
37092 | Mendocino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18738 | 0 | Start No Earlier Than | Warning
37093 | Mendocino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18737 |  | 0 | Finish No Earlier Than | Warning
37094 | Mendocino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37096 | Mendocino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18742SS | 0 | Start No Earlier Than | Warning
37097 | Mendocino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18741SS | 18743SS | 0 | Finish No Earlier Than | Warning
37098 | Mendocino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18742SS | 18744SS | 0 | Finish No Earlier Than | Warning
37099 | Mendocino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18743SS | 18745SS | 0 | Finish No Earlier Than | Warning
37100 | Mendocino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18744SS | 18746SS | 0 | Finish No Earlier Than | Warning
37101 | Mendocino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18745SS | 18747SS | 0 | Finish No Earlier Than | Warning
37102 | Mendocino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18746SS | 18748SS | 0 | Finish No Earlier Than | Warning
37103 | Mendocino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18747SS | 18749SS | 0 | Finish No Earlier Than | Warning
37104 | Mendocino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18748SS | 18750SS | 0 | Finish No Earlier Than | Warning
37105 | Mendocino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18749SS | 18751SS | 0 | Finish No Earlier Than | Warning
37106 | Mendocino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18750SS |  | 0 | Finish No Earlier Than | Warning
37107 | Mendocino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37108 | Mendocino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37110 | Mendocino PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18756SS,18760 | 0 | Start No Earlier Than | Warning
37111 | Mendocino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18755SS |  | 0 | Start No Earlier Than | Warning
37112 | Mendocino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37113 | Mendocino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18766 | 0 | Start No Earlier Than | Warning
37114 | Mendocino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18767 | 0 | Start No Earlier Than | Warning
37115 | Mendocino PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18755 |  | 0 | Start No Earlier Than | Warning
37116 | Mendocino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37117 | Mendocino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18763SS,18771SS+20d | 0 | Start No Earlier Than | Warning
37118 | Mendocino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18762SS | 18764SS,18772SS+20d | 0 | Finish No Earlier Than | Warning
37119 | Mendocino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18763SS | 18773SS+20d | 0 | Finish No Earlier Than | Warning
37120 | Mendocino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37121 | Mendocino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18758 | 18767SS | 0 | Start No Earlier Than | Warning
37122 | Mendocino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18759,18766SS |  | 0 | Finish No Earlier Than | Warning
37123 | Mendocino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18776FS+12d | 0 | Start No Earlier Than | Warning
37124 | Mendocino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18770SS | 0 | Start No Earlier Than | Warning
37125 | Mendocino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18769SS |  | 0 | Start No Earlier Than | Warning
37129 | Mendocino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18776SS+44d | 0 | Start No Earlier Than | Warning
37130 | Mendocino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37135 | Merced PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37136 | Merced PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37137 | Merced PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37138 | Merced PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
37139 | Merced PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37140 | Merced PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37141 | Merced PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37142 | Merced PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37143 | Merced PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37144 | Merced PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37145 | Merced PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37146 | Merced PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37147 | Merced PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37148 | Merced PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37149 | Merced PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37150 | Merced PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37151 | Merced PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37152 | Merced PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37153 | Merced PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37154 | Merced PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37155 | Merced PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37156 | Merced PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37157 | Merced PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37158 | Merced PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37159 | Merced PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
37160 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18806SS | 0 | Start No Earlier Than | Warning
37161 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18805SS |  | 0 | Finish No Earlier Than | Warning
37162 | Merced PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18808SS | 0 | Start No Earlier Than | Warning
37163 | Merced PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18807SS |  | 0 | Start No Earlier Than | Warning
37164 | Merced PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37165 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18811SS | 0 | Finish No Earlier Than | Warning
37166 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18810SS |  | 0 | Finish No Earlier Than | Warning
37167 | Merced PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37168 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18814SS | 0 | Finish No Earlier Than | Warning
37170 | Merced PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37171 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18817SS | 0 | Finish No Earlier Than | Warning
37172 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18816SS |  | 0 | Start No Earlier Than | Warning
37173 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18819SS | 0 | Start No Earlier Than | Warning
37174 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18818SS |  | 0 | Start No Earlier Than | Warning
37175 | Merced PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37176 | Merced PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37179 | Merced PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37180 | Merced PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37181 | Merced PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37182 | Merced PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18828FS+10d | 0 | Start No Earlier Than | Warning
37183 | Merced PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18827FS+10d |  | 0 | Start No Earlier Than | Warning
37185 | Merced PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18832FS-1d | 1 | Start No Earlier Than | Warning
37186 | Merced PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37187 | Merced PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18830FS-1d |  | 0.2 | Start No Earlier Than | Warning
37188 | Merced PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 31, 2025 12:00 AM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37189 | Merced PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18835 | 1 | Start No Earlier Than | Warning
37190 | Merced PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18834 |  | 0 | Start No Earlier Than | Warning
37191 | Merced PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37192 | Merced PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 18838FS+19d | 1 | Finish No Earlier Than | Warning
37193 | Merced PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18837FS+19d | 18839 | 0 | Start No Earlier Than | Warning
37195 | Merced PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37196 | Merced PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18842 | 0 | Start No Earlier Than | Warning
37197 | Merced PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18841 | 18843FS-1d | 0 | Start No Earlier Than | Warning
37198 | Merced PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18842FS-1d |  | 0 | Finish No Earlier Than | Warning
37199 | Merced PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37200 | Merced PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37203 | Merced PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18849SS | 0 | Finish No Earlier Than | Warning
37204 | Merced PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18848SS |  | 0 | Finish No Earlier Than | Warning
37205 | Merced PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37206 | Merced PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
37208 | Merced PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18854SS | 0 | Finish No Earlier Than | Warning
37209 | Merced PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18853SS | 18868SS | 0 | Start No Earlier Than | Warning
37211 | Merced PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37212 | Merced PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37214 | Merced PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 18860SS | 0 | Start No Earlier Than | Warning
37215 | Merced PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18859SS | 18861SS,18862 | 0 | Finish No Earlier Than | Warning
37217 | Merced PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18860,18861 |  | 0 | Finish No Earlier Than | Warning
37218 | Merced PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37220 | Merced PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18866SS | 0 | Finish No Earlier Than | Warning
37221 | Merced PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18865SS |  | 0 | Finish No Earlier Than | Warning
37222 | Merced PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37223 | Merced PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18854SS |  | 0 | Finish No Earlier Than | Warning
37225 | Merced PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18871SS | 0 | Finish No Earlier Than | Warning
37226 | Merced PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18870SS |  | 0 | Finish No Earlier Than | Warning
37228 | Merced PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 18874SS+18d | 0 | Start No Earlier Than | Warning
37229 | Merced PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 18873SS+18d |  | 0 | Finish No Earlier Than | Warning
37231 | Merced PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 18877SS | 0 | Start No Earlier Than | Warning
37232 | Merced PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 18876SS |  | 0 | Finish No Earlier Than | Warning
37233 | Merced PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18879 | 0 | Start No Earlier Than | Warning
37234 | Merced PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 18878 |  | 0 | Finish No Earlier Than | Warning
37235 | Merced PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37237 | Merced PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 18883SS | 0 | Start No Earlier Than | Warning
37238 | Merced PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18882SS | 18884SS | 0 | Finish No Earlier Than | Warning
37239 | Merced PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18883SS | 18885SS | 0 | Finish No Earlier Than | Warning
37240 | Merced PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18884SS | 18886SS | 0 | Finish No Earlier Than | Warning
37241 | Merced PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18885SS | 18887SS | 0 | Finish No Earlier Than | Warning
37242 | Merced PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18886SS | 18888SS | 0 | Finish No Earlier Than | Warning
37243 | Merced PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18887SS | 18889SS | 0 | Finish No Earlier Than | Warning
37244 | Merced PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18888SS | 18890SS | 0 | Finish No Earlier Than | Warning
37245 | Merced PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18889SS | 18891SS | 0 | Finish No Earlier Than | Warning
37246 | Merced PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18890SS | 18892SS | 0 | Finish No Earlier Than | Warning
37247 | Merced PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 18891SS |  | 0 | Finish No Earlier Than | Warning
37248 | Merced PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37249 | Merced PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37251 | Merced PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 18897SS,18901 | 0.2 | Start No Earlier Than | Warning
37252 | Merced PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 18896SS |  | 0 | Start No Earlier Than | Warning
37253 | Merced PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37254 | Merced PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18907 | 0 | Start No Earlier Than | Warning
37255 | Merced PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 18908 | 0 | Start No Earlier Than | Warning
37256 | Merced PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 18896 |  | 0 | Start No Earlier Than | Warning
37257 | Merced PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37258 | Merced PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 18904SS,18912SS+20d | 0 | Start No Earlier Than | Warning
37259 | Merced PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18903SS | 18905SS,18913SS+20d | 0 | Finish No Earlier Than | Warning
37260 | Merced PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 18904SS | 18914SS+20d | 0 | Finish No Earlier Than | Warning
37261 | Merced PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37262 | Merced PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18899 | 18908SS | 0 | Start No Earlier Than | Warning
37263 | Merced PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 18900,18907SS |  | 0 | Finish No Earlier Than | Warning
37264 | Merced PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 18917FS+12d | 0 | Start No Earlier Than | Warning
37265 | Merced PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 18911SS | 0 | Start No Earlier Than | Warning
37266 | Merced PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 18910SS |  | 0 | Start No Earlier Than | Warning
37270 | Merced PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 18917SS+44d | 0 | Start No Earlier Than | Warning
37271 | Merced PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37276 | Modoc PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37277 | Modoc PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37278 | Modoc PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37279 | Modoc PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
37280 | Modoc PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37281 | Modoc PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37282 | Modoc PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37283 | Modoc PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37284 | Modoc PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37285 | Modoc PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37286 | Modoc PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37287 | Modoc PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37288 | Modoc PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37289 | Modoc PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37290 | Modoc PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37291 | Modoc PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37292 | Modoc PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37293 | Modoc PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37294 | Modoc PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37295 | Modoc PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37296 | Modoc PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37297 | Modoc PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37298 | Modoc PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37299 | Modoc PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37300 | Modoc PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
37301 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 18947SS | 0 | Start No Earlier Than | Warning
37302 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 18946SS |  | 0 | Finish No Earlier Than | Warning
37303 | Modoc PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 18949SS | 0 | Start No Earlier Than | Warning
37304 | Modoc PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 18948SS |  | 0 | Start No Earlier Than | Warning
37305 | Modoc PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37306 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 18952SS | 0 | Finish No Earlier Than | Warning
37307 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 18951SS |  | 0 | Finish No Earlier Than | Warning
37308 | Modoc PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37309 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 18955SS | 0 | Finish No Earlier Than | Warning
37311 | Modoc PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37312 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 18958SS | 0 | Finish No Earlier Than | Warning
37313 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 18957SS |  | 0 | Start No Earlier Than | Warning
37314 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 18960SS | 0 | Start No Earlier Than | Warning
37315 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 18959SS |  | 0 | Start No Earlier Than | Warning
37316 | Modoc PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37317 | Modoc PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37320 | Modoc PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37321 | Modoc PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37322 | Modoc PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37323 | Modoc PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 18969FS+10d | 0 | Start No Earlier Than | Warning
37324 | Modoc PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 18968FS+10d |  | 0 | Start No Earlier Than | Warning
37326 | Modoc PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 18973FS-1d | 1 | Start No Earlier Than | Warning
37327 | Modoc PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37328 | Modoc PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 18971FS-1d |  | 0.2 | Start No Earlier Than | Warning
37329 | Modoc PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37330 | Modoc PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 18976 | 1 | Start No Earlier Than | Warning
37331 | Modoc PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18975 |  | 0.2 | Start No Earlier Than | Warning
37332 | Modoc PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37333 | Modoc PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 18979FS+19d | 0.4 | Finish No Earlier Than | Warning
37334 | Modoc PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 18978FS+19d | 18980 | 0 | Start No Earlier Than | Warning
37336 | Modoc PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37337 | Modoc PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 18983 | 0 | Start No Earlier Than | Warning
37338 | Modoc PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 18982 | 18984FS-1d | 0 | Start No Earlier Than | Warning
37339 | Modoc PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 18983FS-1d |  | 0 | Finish No Earlier Than | Warning
37340 | Modoc PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37341 | Modoc PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37344 | Modoc PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18990SS | 0 | Finish No Earlier Than | Warning
37345 | Modoc PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 18989SS |  | 0 | Finish No Earlier Than | Warning
37346 | Modoc PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37347 | Modoc PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
37349 | Modoc PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 18995SS | 0 | Finish No Earlier Than | Warning
37350 | Modoc PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18994SS | 19009SS | 0 | Start No Earlier Than | Warning
37352 | Modoc PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37353 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37355 | Modoc PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19001SS | 0 | Start No Earlier Than | Warning
37356 | Modoc PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19000SS | 19002SS,19003 | 0 | Finish No Earlier Than | Warning
37358 | Modoc PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19001,19002 |  | 0 | Finish No Earlier Than | Warning
37359 | Modoc PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37361 | Modoc PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19007SS | 0 | Finish No Earlier Than | Warning
37362 | Modoc PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19006SS |  | 0 | Finish No Earlier Than | Warning
37363 | Modoc PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37364 | Modoc PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 18995SS |  | 0 | Finish No Earlier Than | Warning
37366 | Modoc PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19012SS | 0 | Finish No Earlier Than | Warning
37367 | Modoc PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19011SS |  | 0 | Finish No Earlier Than | Warning
37369 | Modoc PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19015SS+18d | 0 | Start No Earlier Than | Warning
37370 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19014SS+18d |  | 0 | Finish No Earlier Than | Warning
37372 | Modoc PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19018SS | 0 | Start No Earlier Than | Warning
37373 | Modoc PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19017SS |  | 0 | Finish No Earlier Than | Warning
37374 | Modoc PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19020 | 0 | Start No Earlier Than | Warning
37375 | Modoc PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19019 |  | 0 | Finish No Earlier Than | Warning
37376 | Modoc PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37378 | Modoc PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19024SS | 0 | Start No Earlier Than | Warning
37379 | Modoc PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19023SS | 19025SS | 0 | Finish No Earlier Than | Warning
37380 | Modoc PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19024SS | 19026SS | 0 | Finish No Earlier Than | Warning
37381 | Modoc PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19025SS | 19027SS | 0 | Finish No Earlier Than | Warning
37382 | Modoc PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19026SS | 19028SS | 0 | Finish No Earlier Than | Warning
37383 | Modoc PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19027SS | 19029SS | 0 | Finish No Earlier Than | Warning
37384 | Modoc PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19028SS | 19030SS | 0 | Finish No Earlier Than | Warning
37385 | Modoc PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19029SS | 19031SS | 0 | Finish No Earlier Than | Warning
37386 | Modoc PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19030SS | 19032SS | 0 | Finish No Earlier Than | Warning
37387 | Modoc PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19031SS | 19033SS | 0 | Finish No Earlier Than | Warning
37388 | Modoc PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19032SS |  | 0 | Finish No Earlier Than | Warning
37389 | Modoc PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37390 | Modoc PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37392 | Modoc PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19038SS,19042 | 0 | Start No Earlier Than | Warning
37393 | Modoc PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19037SS |  | 0 | Start No Earlier Than | Warning
37394 | Modoc PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37395 | Modoc PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19048 | 0 | Start No Earlier Than | Warning
37396 | Modoc PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19049 | 0 | Start No Earlier Than | Warning
37397 | Modoc PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19037 |  | 0 | Start No Earlier Than | Warning
37398 | Modoc PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37399 | Modoc PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19045SS,19053SS+20d | 0 | Start No Earlier Than | Warning
37400 | Modoc PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19044SS | 19046SS,19054SS+20d | 0 | Finish No Earlier Than | Warning
37401 | Modoc PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19045SS | 19055SS+20d | 0 | Finish No Earlier Than | Warning
37402 | Modoc PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37403 | Modoc PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19040 | 19049SS | 0 | Start No Earlier Than | Warning
37404 | Modoc PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19041,19048SS |  | 0 | Finish No Earlier Than | Warning
37405 | Modoc PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19058FS+12d | 0 | Start No Earlier Than | Warning
37406 | Modoc PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19052SS | 0 | Start No Earlier Than | Warning
37407 | Modoc PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19051SS |  | 0 | Start No Earlier Than | Warning
37411 | Modoc PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19058SS+44d | 0 | Start No Earlier Than | Warning
37412 | Modoc PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37417 | Mono PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37418 | Mono PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37419 | Mono PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37420 | Mono PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
37421 | Mono PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37422 | Mono PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37423 | Mono PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37424 | Mono PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37425 | Mono PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37426 | Mono PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37427 | Mono PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37428 | Mono PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37429 | Mono PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37430 | Mono PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37431 | Mono PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37432 | Mono PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37433 | Mono PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37434 | Mono PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37435 | Mono PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37436 | Mono PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37437 | Mono PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37438 | Mono PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37439 | Mono PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37440 | Mono PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37441 | Mono PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
37442 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19088SS | 0 | Start No Earlier Than | Warning
37443 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19087SS |  | 0 | Finish No Earlier Than | Warning
37444 | Mono PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19090SS | 0 | Start No Earlier Than | Warning
37445 | Mono PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19089SS |  | 0 | Start No Earlier Than | Warning
37446 | Mono PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37447 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19093SS | 0 | Finish No Earlier Than | Warning
37448 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19092SS |  | 0 | Finish No Earlier Than | Warning
37449 | Mono PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37450 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19096SS | 0 | Finish No Earlier Than | Warning
37452 | Mono PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37453 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19099SS | 0 | Finish No Earlier Than | Warning
37454 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19098SS |  | 0 | Start No Earlier Than | Warning
37455 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19101SS | 0 | Start No Earlier Than | Warning
37456 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19100SS |  | 0 | Start No Earlier Than | Warning
37457 | Mono PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37458 | Mono PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37461 | Mono PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37462 | Mono PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37463 | Mono PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37464 | Mono PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19110FS+10d | 0 | Start No Earlier Than | Warning
37465 | Mono PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19109FS+10d |  | 0 | Start No Earlier Than | Warning
37467 | Mono PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19114FS-1d | 1 | Start No Earlier Than | Warning
37468 | Mono PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37469 | Mono PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19112FS-1d |  | 0.2 | Start No Earlier Than | Warning
37470 | Mono PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37471 | Mono PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 8.4d |  | 19117 | 0.2 | Start No Earlier Than | Warning
37472 | Mono PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19116 |  | 0.2 | Start No Earlier Than | Warning
37473 | Mono PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37474 | Mono PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 19120FS+19d | 1 | Finish No Earlier Than | Warning
37475 | Mono PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19119FS+19d | 19121 | 0 | Start No Earlier Than | Warning
37477 | Mono PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37478 | Mono PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19124 | 0 | Start No Earlier Than | Warning
37479 | Mono PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19123 | 19125FS-1d | 0 | Start No Earlier Than | Warning
37480 | Mono PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19124FS-1d |  | 0 | Finish No Earlier Than | Warning
37481 | Mono PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37482 | Mono PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37485 | Mono PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19131SS | 0 | Start No Earlier Than | Warning
37486 | Mono PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19130SS | 19132SS | 0 | Finish No Earlier Than | Warning
37487 | Mono PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19131SS | 19133SS | 0 | Finish No Earlier Than | Warning
37488 | Mono PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19132SS | 19134SS | 0 | Finish No Earlier Than | Warning
37489 | Mono PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19133SS | 19135SS | 0 | Finish No Earlier Than | Warning
37490 | Mono PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19134SS | 19136SS | 0 | Finish No Earlier Than | Warning
37491 | Mono PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19135SS | 19137SS | 0 | Finish No Earlier Than | Warning
37492 | Mono PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19136SS | 19138SS | 0 | Finish No Earlier Than | Warning
37493 | Mono PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19137SS | 19139SS | 0 | Finish No Earlier Than | Warning
37494 | Mono PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19138SS | 19140SS | 0 | Finish No Earlier Than | Warning
37495 | Mono PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19139SS |  | 0 | Finish No Earlier Than | Warning
37496 | Mono PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37497 | Mono PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37499 | Mono PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19145SS,19149 | 0 | Start No Earlier Than | Warning
37500 | Mono PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19144SS |  | 0 | Start No Earlier Than | Warning
37501 | Mono PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37502 | Mono PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19155 | 0 | Start No Earlier Than | Warning
37503 | Mono PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19156 | 0 | Start No Earlier Than | Warning
37504 | Mono PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19144 |  | 0 | Start No Earlier Than | Warning
37505 | Mono PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37506 | Mono PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19152SS,19160SS+20d | 0 | Start No Earlier Than | Warning
37507 | Mono PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19151SS | 19153SS,19161SS+20d | 0 | Finish No Earlier Than | Warning
37508 | Mono PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19152SS | 19162SS+20d | 0 | Finish No Earlier Than | Warning
37509 | Mono PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37510 | Mono PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19147 | 19156SS | 0 | Start No Earlier Than | Warning
37511 | Mono PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19148,19155SS |  | 0 | Finish No Earlier Than | Warning
37512 | Mono PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19165FS+12d | 0 | Start No Earlier Than | Warning
37513 | Mono PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19159SS | 0 | Start No Earlier Than | Warning
37514 | Mono PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19158SS |  | 0 | Start No Earlier Than | Warning
37518 | Mono PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19165SS+44d | 0 | Start No Earlier Than | Warning
37519 | Mono PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37524 | Monterey PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37525 | Monterey PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37526 | Monterey PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37527 | Monterey PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
37528 | Monterey PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37529 | Monterey PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37530 | Monterey PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37531 | Monterey PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37532 | Monterey PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37533 | Monterey PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37534 | Monterey PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37535 | Monterey PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37536 | Monterey PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37537 | Monterey PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37538 | Monterey PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37539 | Monterey PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37540 | Monterey PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37541 | Monterey PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37542 | Monterey PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37543 | Monterey PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37544 | Monterey PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37545 | Monterey PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37546 | Monterey PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37547 | Monterey PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37548 | Monterey PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.95 | Start No Earlier Than | Warning
37549 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19195SS | 0 | Start No Earlier Than | Warning
37550 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19194SS |  | 0 | Finish No Earlier Than | Warning
37551 | Monterey PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19197SS | 0 | Start No Earlier Than | Warning
37552 | Monterey PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19196SS |  | 0 | Start No Earlier Than | Warning
37553 | Monterey PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37554 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19200SS | 0 | Finish No Earlier Than | Warning
37555 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19199SS |  | 0 | Finish No Earlier Than | Warning
37556 | Monterey PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37557 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19203SS | 0 | Finish No Earlier Than | Warning
37559 | Monterey PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37560 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19206SS | 0 | Finish No Earlier Than | Warning
37561 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19205SS |  | 0 | Start No Earlier Than | Warning
37562 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19208SS | 0 | Start No Earlier Than | Warning
37563 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19207SS |  | 0 | Start No Earlier Than | Warning
37564 | Monterey PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37565 | Monterey PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37568 | Monterey PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37569 | Monterey PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37570 | Monterey PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37571 | Monterey PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19217FS+10d | 0 | Start No Earlier Than | Warning
37572 | Monterey PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19216FS+10d |  | 0 | Start No Earlier Than | Warning
37574 | Monterey PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19221FS-1d | 1 | Start No Earlier Than | Warning
37575 | Monterey PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37576 | Monterey PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19219FS-1d |  | 0.2 | Start No Earlier Than | Warning
37577 | Monterey PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37578 | Monterey PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19224 | 1 | Start No Earlier Than | Warning
37579 | Monterey PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19223 |  | 0.2 | Start No Earlier Than | Warning
37580 | Monterey PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37581 | Monterey PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 19227FS+19d | 1 | Finish No Earlier Than | Warning
37582 | Monterey PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19226FS+19d | 19228 | 0 | Start No Earlier Than | Warning
37584 | Monterey PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37585 | Monterey PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19231 | 0 | Start No Earlier Than | Warning
37586 | Monterey PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19230 | 19232FS-1d | 0 | Start No Earlier Than | Warning
37587 | Monterey PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19231FS-1d |  | 0 | Finish No Earlier Than | Warning
37588 | Monterey PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37589 | Monterey PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37592 | Monterey PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19238SS | 0 | Start No Earlier Than | Warning
37593 | Monterey PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19237SS | 19239SS | 0 | Finish No Earlier Than | Warning
37594 | Monterey PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19238SS | 19240SS | 0 | Finish No Earlier Than | Warning
37595 | Monterey PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19239SS | 19241SS | 0 | Finish No Earlier Than | Warning
37596 | Monterey PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19240SS | 19242SS | 0 | Finish No Earlier Than | Warning
37597 | Monterey PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19241SS | 19243SS | 0 | Finish No Earlier Than | Warning
37598 | Monterey PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19242SS | 19244SS | 0 | Finish No Earlier Than | Warning
37599 | Monterey PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19243SS | 19245SS | 0 | Finish No Earlier Than | Warning
37600 | Monterey PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19244SS | 19246SS | 0 | Finish No Earlier Than | Warning
37601 | Monterey PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19245SS | 19247SS | 0 | Finish No Earlier Than | Warning
37602 | Monterey PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19246SS |  | 0 | Finish No Earlier Than | Warning
37603 | Monterey PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37604 | Monterey PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37606 | Monterey PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19252SS,19256 | 0 | Start No Earlier Than | Warning
37607 | Monterey PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19251SS |  | 0 | Start No Earlier Than | Warning
37608 | Monterey PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37609 | Monterey PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19262 | 0 | Start No Earlier Than | Warning
37610 | Monterey PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19263 | 0 | Start No Earlier Than | Warning
37611 | Monterey PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19251 |  | 0 | Start No Earlier Than | Warning
37612 | Monterey PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37613 | Monterey PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19259SS,19267SS+20d | 0 | Start No Earlier Than | Warning
37614 | Monterey PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19258SS | 19260SS,19268SS+20d | 0 | Finish No Earlier Than | Warning
37615 | Monterey PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19259SS | 19269SS+20d | 0 | Finish No Earlier Than | Warning
37616 | Monterey PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37617 | Monterey PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19254 | 19263SS | 0 | Start No Earlier Than | Warning
37618 | Monterey PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19255,19262SS |  | 0 | Finish No Earlier Than | Warning
37619 | Monterey PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19272FS+12d | 0 | Start No Earlier Than | Warning
37620 | Monterey PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19266SS | 0 | Start No Earlier Than | Warning
37621 | Monterey PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19265SS |  | 0 | Start No Earlier Than | Warning
37625 | Monterey PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19272SS+44d | 0 | Start No Earlier Than | Warning
37626 | Monterey PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37631 | Napa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37632 | Napa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37633 | Napa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37634 | Napa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
37635 | Napa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37636 | Napa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37637 | Napa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37638 | Napa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37639 | Napa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37640 | Napa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37641 | Napa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37642 | Napa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37643 | Napa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37644 | Napa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37645 | Napa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37646 | Napa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37647 | Napa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37648 | Napa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37649 | Napa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37650 | Napa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37651 | Napa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37652 | Napa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37653 | Napa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37654 | Napa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37655 | Napa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
37656 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19302SS | 0 | Start No Earlier Than | Warning
37657 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19301SS |  | 0 | Finish No Earlier Than | Warning
37658 | Napa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19304SS | 0 | Start No Earlier Than | Warning
37659 | Napa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19303SS |  | 0 | Start No Earlier Than | Warning
37660 | Napa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37661 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19307SS | 0 | Finish No Earlier Than | Warning
37662 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19306SS |  | 0 | Finish No Earlier Than | Warning
37663 | Napa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37664 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19310SS | 0 | Finish No Earlier Than | Warning
37666 | Napa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37667 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19313SS | 0 | Finish No Earlier Than | Warning
37668 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19312SS |  | 0 | Start No Earlier Than | Warning
37669 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19315SS | 0 | Start No Earlier Than | Warning
37670 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19314SS |  | 0 | Start No Earlier Than | Warning
37671 | Napa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37672 | Napa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37675 | Napa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37676 | Napa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37677 | Napa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37678 | Napa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19324FS+10d | 0 | Start No Earlier Than | Warning
37679 | Napa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19323FS+10d |  | 0 | Start No Earlier Than | Warning
37681 | Napa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19328FS-1d | 1 | Start No Earlier Than | Warning
37682 | Napa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37683 | Napa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19326FS-1d |  | 0.2 | Start No Earlier Than | Warning
37684 | Napa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37685 | Napa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19331 | 1 | Start No Earlier Than | Warning
37686 | Napa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19330 |  | 0 | Start No Earlier Than | Warning
37687 | Napa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37688 | Napa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19334FS+19d | 0 | Finish No Earlier Than | Warning
37689 | Napa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19333FS+19d | 19335 | 0 | Start No Earlier Than | Warning
37691 | Napa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37692 | Napa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19338 | 0 | Start No Earlier Than | Warning
37693 | Napa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19337 | 19339FS-1d | 0 | Start No Earlier Than | Warning
37694 | Napa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19338FS-1d |  | 0 | Finish No Earlier Than | Warning
37695 | Napa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37696 | Napa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37699 | Napa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19345SS | 0 | Finish No Earlier Than | Warning
37700 | Napa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19344SS |  | 0 | Finish No Earlier Than | Warning
37701 | Napa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37702 | Napa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
37704 | Napa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19350SS | 0 | Finish No Earlier Than | Warning
37705 | Napa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19349SS | 19364SS | 0 | Start No Earlier Than | Warning
37707 | Napa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37708 | Napa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37710 | Napa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19356SS | 0 | Start No Earlier Than | Warning
37711 | Napa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19355SS | 19357SS,19358 | 0 | Finish No Earlier Than | Warning
37713 | Napa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19356,19357 |  | 0 | Finish No Earlier Than | Warning
37714 | Napa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37716 | Napa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19362SS | 0 | Finish No Earlier Than | Warning
37717 | Napa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19361SS |  | 0 | Finish No Earlier Than | Warning
37718 | Napa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37719 | Napa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19350SS |  | 0 | Finish No Earlier Than | Warning
37721 | Napa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19367SS | 0 | Finish No Earlier Than | Warning
37722 | Napa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19366SS |  | 0 | Finish No Earlier Than | Warning
37724 | Napa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19370SS+18d | 0 | Start No Earlier Than | Warning
37725 | Napa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19369SS+18d |  | 0 | Finish No Earlier Than | Warning
37727 | Napa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19373SS | 0 | Start No Earlier Than | Warning
37728 | Napa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19372SS |  | 0 | Finish No Earlier Than | Warning
37729 | Napa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19375 | 0 | Start No Earlier Than | Warning
37730 | Napa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19374 |  | 0 | Finish No Earlier Than | Warning
37731 | Napa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37733 | Napa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19379SS | 0 | Start No Earlier Than | Warning
37734 | Napa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19378SS | 19380SS | 0 | Finish No Earlier Than | Warning
37735 | Napa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19379SS | 19381SS | 0 | Finish No Earlier Than | Warning
37736 | Napa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19380SS | 19382SS | 0 | Finish No Earlier Than | Warning
37737 | Napa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19381SS | 19383SS | 0 | Finish No Earlier Than | Warning
37738 | Napa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19382SS | 19384SS | 0 | Finish No Earlier Than | Warning
37739 | Napa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19383SS | 19385SS | 0 | Finish No Earlier Than | Warning
37740 | Napa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19384SS | 19386SS | 0 | Finish No Earlier Than | Warning
37741 | Napa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19385SS | 19387SS | 0 | Finish No Earlier Than | Warning
37742 | Napa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19386SS | 19388SS | 0 | Finish No Earlier Than | Warning
37743 | Napa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19387SS |  | 0 | Finish No Earlier Than | Warning
37744 | Napa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37745 | Napa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37747 | Napa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19393SS,19397 | 0 | Start No Earlier Than | Warning
37748 | Napa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19392SS |  | 0 | Start No Earlier Than | Warning
37749 | Napa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37750 | Napa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19403 | 0 | Start No Earlier Than | Warning
37751 | Napa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19404 | 0 | Start No Earlier Than | Warning
37752 | Napa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19392 |  | 0 | Start No Earlier Than | Warning
37753 | Napa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37754 | Napa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19400SS,19408SS+20d | 0 | Start No Earlier Than | Warning
37755 | Napa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19399SS | 19401SS,19409SS+20d | 0 | Finish No Earlier Than | Warning
37756 | Napa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19400SS | 19410SS+20d | 0 | Finish No Earlier Than | Warning
37757 | Napa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37758 | Napa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19395 | 19404SS | 0 | Start No Earlier Than | Warning
37759 | Napa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19396,19403SS |  | 0 | Finish No Earlier Than | Warning
37760 | Napa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19413FS+12d | 0 | Start No Earlier Than | Warning
37761 | Napa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19407SS | 0 | Start No Earlier Than | Warning
37762 | Napa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19406SS |  | 0 | Start No Earlier Than | Warning
37766 | Napa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19413SS+44d | 0 | Start No Earlier Than | Warning
37767 | Napa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37772 | Nevada PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37773 | Nevada PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37774 | Nevada PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37775 | Nevada PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
37776 | Nevada PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37777 | Nevada PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37778 | Nevada PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37779 | Nevada PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37780 | Nevada PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37781 | Nevada PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37782 | Nevada PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37783 | Nevada PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37784 | Nevada PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37785 | Nevada PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37786 | Nevada PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37787 | Nevada PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37788 | Nevada PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37789 | Nevada PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37790 | Nevada PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37791 | Nevada PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37792 | Nevada PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37793 | Nevada PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37794 | Nevada PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37795 | Nevada PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37796 | Nevada PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
37797 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19443SS | 0 | Start No Earlier Than | Warning
37798 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19442SS |  | 0 | Finish No Earlier Than | Warning
37799 | Nevada PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19445SS | 0 | Start No Earlier Than | Warning
37800 | Nevada PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19444SS |  | 0 | Start No Earlier Than | Warning
37801 | Nevada PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37802 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19448SS | 0 | Finish No Earlier Than | Warning
37803 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19447SS |  | 0 | Finish No Earlier Than | Warning
37804 | Nevada PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37805 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19451SS | 0 | Finish No Earlier Than | Warning
37807 | Nevada PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37808 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19454SS | 0 | Finish No Earlier Than | Warning
37809 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19453SS |  | 0 | Start No Earlier Than | Warning
37810 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19456SS | 0 | Start No Earlier Than | Warning
37811 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19455SS |  | 0 | Start No Earlier Than | Warning
37812 | Nevada PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37813 | Nevada PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37816 | Nevada PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37817 | Nevada PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37818 | Nevada PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37819 | Nevada PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19465FS+10d | 0 | Start No Earlier Than | Warning
37820 | Nevada PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19464FS+10d |  | 0 | Start No Earlier Than | Warning
37822 | Nevada PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
37823 | Nevada PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37824 | Nevada PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37825 | Nevada PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19471 | 1 | Start No Earlier Than | Warning
37826 | Nevada PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19470 |  | 0 | Start No Earlier Than | Warning
37827 | Nevada PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37828 | Nevada PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 19474FS+19d | 1 | Finish No Earlier Than | Warning
37829 | Nevada PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19473FS+19d | 19475 | 0 | Start No Earlier Than | Warning
37831 | Nevada PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37832 | Nevada PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19478 | 0 | Start No Earlier Than | Warning
37833 | Nevada PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19477 | 19479FS-1d | 0 | Start No Earlier Than | Warning
37834 | Nevada PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19478FS-1d |  | 0 | Finish No Earlier Than | Warning
37835 | Nevada PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37836 | Nevada PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37839 | Nevada PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 19485SS | 1 | Finish No Earlier Than | Warning
37840 | Nevada PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 0d | 19484SS |  | 1 | Finish No Earlier Than | Warning
37841 | Nevada PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0.2 | Start No Earlier Than | Warning
37842 | Nevada PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 0d |  |  | 1 | Start No Earlier Than | Warning
37844 | Nevada PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19490SS | 0.2 | Finish No Earlier Than | Warning
37845 | Nevada PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19489SS | 19504SS | 0.2 | Start No Earlier Than | Warning
37847 | Nevada PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37848 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37850 | Nevada PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19496SS | 0 | Start No Earlier Than | Warning
37851 | Nevada PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19495SS | 19497SS,19498 | 0 | Finish No Earlier Than | Warning
37853 | Nevada PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19496,19497 |  | 0 | Finish No Earlier Than | Warning
37854 | Nevada PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37856 | Nevada PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19502SS | 0 | Finish No Earlier Than | Warning
37857 | Nevada PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19501SS |  | 0 | Finish No Earlier Than | Warning
37858 | Nevada PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37859 | Nevada PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19490SS |  | 0 | Finish No Earlier Than | Warning
37861 | Nevada PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19507SS | 0.2 | Finish No Earlier Than | Warning
37862 | Nevada PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19506SS |  | 0.2 | Finish No Earlier Than | Warning
37864 | Nevada PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19510SS+18d | 0 | Start No Earlier Than | Warning
37865 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19509SS+18d |  | 0 | Finish No Earlier Than | Warning
37867 | Nevada PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19513SS | 0 | Start No Earlier Than | Warning
37868 | Nevada PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19512SS |  | 0 | Finish No Earlier Than | Warning
37869 | Nevada PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19515 | 0 | Start No Earlier Than | Warning
37870 | Nevada PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19514 |  | 0 | Finish No Earlier Than | Warning
37871 | Nevada PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37873 | Nevada PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19519SS | 0 | Start No Earlier Than | Warning
37874 | Nevada PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19518SS | 19520SS | 0 | Finish No Earlier Than | Warning
37875 | Nevada PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19519SS | 19521SS | 0 | Finish No Earlier Than | Warning
37876 | Nevada PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19520SS | 19522SS | 0 | Finish No Earlier Than | Warning
37877 | Nevada PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19521SS | 19523SS | 0 | Finish No Earlier Than | Warning
37878 | Nevada PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19522SS | 19524SS | 0 | Finish No Earlier Than | Warning
37879 | Nevada PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19523SS | 19525SS | 0 | Finish No Earlier Than | Warning
37880 | Nevada PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19524SS | 19526SS | 0 | Finish No Earlier Than | Warning
37881 | Nevada PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19525SS | 19527SS | 0 | Finish No Earlier Than | Warning
37882 | Nevada PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19526SS | 19528SS | 0 | Finish No Earlier Than | Warning
37883 | Nevada PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19527SS |  | 0 | Finish No Earlier Than | Warning
37884 | Nevada PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
37885 | Nevada PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
37887 | Nevada PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19533SS,19537 | 0 | Start No Earlier Than | Warning
37888 | Nevada PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19532SS |  | 0 | Start No Earlier Than | Warning
37889 | Nevada PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
37890 | Nevada PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19543 | 0 | Start No Earlier Than | Warning
37891 | Nevada PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19544 | 0 | Start No Earlier Than | Warning
37892 | Nevada PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19532 |  | 0 | Start No Earlier Than | Warning
37893 | Nevada PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
37894 | Nevada PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19540SS,19548SS+20d | 0 | Start No Earlier Than | Warning
37895 | Nevada PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19539SS | 19541SS,19549SS+20d | 0 | Finish No Earlier Than | Warning
37896 | Nevada PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19540SS | 19550SS+20d | 0 | Finish No Earlier Than | Warning
37897 | Nevada PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
37898 | Nevada PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19535 | 19544SS | 0 | Start No Earlier Than | Warning
37899 | Nevada PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19536,19543SS |  | 0 | Finish No Earlier Than | Warning
37900 | Nevada PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19553FS+12d | 0 | Start No Earlier Than | Warning
37901 | Nevada PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19547SS | 0 | Start No Earlier Than | Warning
37902 | Nevada PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19546SS |  | 0 | Start No Earlier Than | Warning
37906 | Nevada PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19553SS+44d | 0 | Start No Earlier Than | Warning
37907 | Nevada PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
37912 | Orange PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37913 | Orange PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37914 | Orange PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
37915 | Orange PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
37916 | Orange PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
37917 | Orange PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
37918 | Orange PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
37919 | Orange PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
37920 | Orange PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
37921 | Orange PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
37922 | Orange PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
37923 | Orange PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
37924 | Orange PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
37925 | Orange PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
37926 | Orange PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37927 | Orange PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
37928 | Orange PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37929 | Orange PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37930 | Orange PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37931 | Orange PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37932 | Orange PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37933 | Orange PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37934 | Orange PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37935 | Orange PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37936 | Orange PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
37937 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19583SS | 0 | Start No Earlier Than | Warning
37938 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19582SS |  | 0 | Finish No Earlier Than | Warning
37939 | Orange PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19585SS | 0 | Start No Earlier Than | Warning
37940 | Orange PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19584SS |  | 0 | Start No Earlier Than | Warning
37941 | Orange PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
37942 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19588SS | 0 | Finish No Earlier Than | Warning
37943 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19587SS |  | 0 | Finish No Earlier Than | Warning
37944 | Orange PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
37945 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19591SS | 0 | Finish No Earlier Than | Warning
37947 | Orange PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
37948 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19594SS | 0 | Finish No Earlier Than | Warning
37949 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19593SS |  | 0 | Start No Earlier Than | Warning
37950 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19596SS | 0 | Start No Earlier Than | Warning
37951 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19595SS |  | 0 | Start No Earlier Than | Warning
37952 | Orange PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
37953 | Orange PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
37956 | Orange PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
37957 | Orange PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
37958 | Orange PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
37959 | Orange PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19605FS+10d | 0 | Start No Earlier Than | Warning
37960 | Orange PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19604FS+10d |  | 0 | Start No Earlier Than | Warning
37962 | Orange PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19609FS-1d | 1 | Start No Earlier Than | Warning
37963 | Orange PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
37964 | Orange PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19607FS-1d |  | 0.2 | Start No Earlier Than | Warning
37965 | Orange PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
37966 | Orange PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19612 | 1 | Start No Earlier Than | Warning
37967 | Orange PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19611 |  | 0 | Start No Earlier Than | Warning
37968 | Orange PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37969 | Orange PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19615FS+19d | 0 | Finish No Earlier Than | Warning
37970 | Orange PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19614FS+19d | 19616 | 0 | Start No Earlier Than | Warning
37972 | Orange PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
37973 | Orange PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19619 | 0 | Start No Earlier Than | Warning
37974 | Orange PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19618 | 19620FS-1d | 0 | Start No Earlier Than | Warning
37975 | Orange PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19619FS-1d |  | 0 | Finish No Earlier Than | Warning
37976 | Orange PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
37977 | Orange PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
37980 | Orange PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19626SS | 0 | Finish No Earlier Than | Warning
37981 | Orange PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19625SS |  | 0 | Finish No Earlier Than | Warning
37982 | Orange PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
37983 | Orange PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
37985 | Orange PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19631SS | 0 | Finish No Earlier Than | Warning
37986 | Orange PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19630SS | 19645SS | 0 | Start No Earlier Than | Warning
37988 | Orange PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
37989 | Orange PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
37991 | Orange PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19637SS | 0 | Start No Earlier Than | Warning
37992 | Orange PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19636SS | 19638SS,19639 | 0 | Finish No Earlier Than | Warning
37994 | Orange PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19637,19638 |  | 0 | Finish No Earlier Than | Warning
37995 | Orange PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
37997 | Orange PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19643SS | 0 | Finish No Earlier Than | Warning
37998 | Orange PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19642SS |  | 0 | Finish No Earlier Than | Warning
37999 | Orange PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38000 | Orange PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19631SS |  | 0 | Finish No Earlier Than | Warning
38002 | Orange PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19648SS | 0 | Finish No Earlier Than | Warning
38003 | Orange PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19647SS |  | 0 | Finish No Earlier Than | Warning
38005 | Orange PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19651SS+18d | 0 | Start No Earlier Than | Warning
38006 | Orange PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19650SS+18d |  | 0 | Finish No Earlier Than | Warning
38008 | Orange PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19654SS | 0 | Start No Earlier Than | Warning
38009 | Orange PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19653SS |  | 0 | Finish No Earlier Than | Warning
38010 | Orange PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19656 | 0 | Start No Earlier Than | Warning
38011 | Orange PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19655 |  | 0 | Finish No Earlier Than | Warning
38012 | Orange PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38014 | Orange PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19660SS | 0 | Start No Earlier Than | Warning
38015 | Orange PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19659SS | 19661SS | 0 | Finish No Earlier Than | Warning
38016 | Orange PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19660SS | 19662SS | 0 | Finish No Earlier Than | Warning
38017 | Orange PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19661SS | 19663SS | 0 | Finish No Earlier Than | Warning
38018 | Orange PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19662SS | 19664SS | 0 | Finish No Earlier Than | Warning
38019 | Orange PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19663SS | 19665SS | 0 | Finish No Earlier Than | Warning
38020 | Orange PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19664SS | 19666SS | 0 | Finish No Earlier Than | Warning
38021 | Orange PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19665SS | 19667SS | 0 | Finish No Earlier Than | Warning
38022 | Orange PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19666SS | 19668SS | 0 | Finish No Earlier Than | Warning
38023 | Orange PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19667SS | 19669SS | 0 | Finish No Earlier Than | Warning
38024 | Orange PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19668SS |  | 0 | Finish No Earlier Than | Warning
38025 | Orange PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38026 | Orange PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38028 | Orange PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19674SS,19678 | 0 | Start No Earlier Than | Warning
38029 | Orange PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19673SS |  | 0 | Start No Earlier Than | Warning
38030 | Orange PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38031 | Orange PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19684 | 0 | Start No Earlier Than | Warning
38032 | Orange PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19685 | 0 | Start No Earlier Than | Warning
38033 | Orange PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19673 |  | 0 | Start No Earlier Than | Warning
38034 | Orange PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38035 | Orange PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19681SS,19689SS+20d | 0 | Start No Earlier Than | Warning
38036 | Orange PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19680SS | 19682SS,19690SS+20d | 0 | Finish No Earlier Than | Warning
38037 | Orange PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19681SS | 19691SS+20d | 0 | Finish No Earlier Than | Warning
38038 | Orange PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38039 | Orange PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19676 | 19685SS | 0 | Start No Earlier Than | Warning
38040 | Orange PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19677,19684SS |  | 0 | Finish No Earlier Than | Warning
38041 | Orange PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19694FS+12d | 0 | Start No Earlier Than | Warning
38042 | Orange PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19688SS | 0 | Start No Earlier Than | Warning
38043 | Orange PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19687SS |  | 0 | Start No Earlier Than | Warning
38047 | Orange PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19694SS+44d | 0 | Start No Earlier Than | Warning
38048 | Orange PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38053 | Placer PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38054 | Placer PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38055 | Placer PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38056 | Placer PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38057 | Placer PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38058 | Placer PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38059 | Placer PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38060 | Placer PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38061 | Placer PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38062 | Placer PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38063 | Placer PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38064 | Placer PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38065 | Placer PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38066 | Placer PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38067 | Placer PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38068 | Placer PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38069 | Placer PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38070 | Placer PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38071 | Placer PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38072 | Placer PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38073 | Placer PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38074 | Placer PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38075 | Placer PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38076 | Placer PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38077 | Placer PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38078 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19724SS | 0 | Start No Earlier Than | Warning
38079 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19723SS |  | 0 | Finish No Earlier Than | Warning
38080 | Placer PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19726SS | 0 | Start No Earlier Than | Warning
38081 | Placer PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19725SS |  | 0 | Start No Earlier Than | Warning
38082 | Placer PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
38083 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19729SS | 0 | Finish No Earlier Than | Warning
38084 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19728SS |  | 0 | Finish No Earlier Than | Warning
38085 | Placer PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
38086 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19732SS | 0 | Finish No Earlier Than | Warning
38088 | Placer PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
38089 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19735SS | 0 | Finish No Earlier Than | Warning
38090 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19734SS |  | 0 | Start No Earlier Than | Warning
38091 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19737SS | 0 | Start No Earlier Than | Warning
38092 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19736SS |  | 0 | Start No Earlier Than | Warning
38093 | Placer PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38094 | Placer PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
38097 | Placer PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38098 | Placer PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38099 | Placer PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
38100 | Placer PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19746FS+10d | 0 | Start No Earlier Than | Warning
38101 | Placer PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19745FS+10d |  | 0 | Start No Earlier Than | Warning
38103 | Placer PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19750FS-1d | 1 | Start No Earlier Than | Warning
38104 | Placer PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38105 | Placer PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19748FS-1d |  | 0.2 | Start No Earlier Than | Warning
38106 | Placer PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38107 | Placer PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19753 | 1 | Start No Earlier Than | Warning
38108 | Placer PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19752 |  | 0 | Start No Earlier Than | Warning
38109 | Placer PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38110 | Placer PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19756FS+19d | 0.2 | Finish No Earlier Than | Warning
38111 | Placer PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19755FS+19d | 19757 | 0 | Start No Earlier Than | Warning
38113 | Placer PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38114 | Placer PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19760 | 0 | Start No Earlier Than | Warning
38115 | Placer PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19759 | 19761FS-1d | 0 | Start No Earlier Than | Warning
38116 | Placer PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19760FS-1d |  | 0 | Finish No Earlier Than | Warning
38117 | Placer PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38118 | Placer PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38121 | Placer PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19767SS | 0 | Finish No Earlier Than | Warning
38122 | Placer PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19766SS |  | 0 | Finish No Earlier Than | Warning
38123 | Placer PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38124 | Placer PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0.2 | Start No Earlier Than | Warning
38126 | Placer PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19772SS | 0 | Finish No Earlier Than | Warning
38127 | Placer PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 8.4d | 19771SS | 19786SS | 0 | Start No Earlier Than | Warning
38129 | Placer PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 0d |  |  | 1 | Start No Earlier Than | Warning
38130 | Placer PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38132 | Placer PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 0d |  | 19778SS | 1 | Start No Earlier Than | Warning
38133 | Placer PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19777SS | 19779SS,19780 | 0 | Finish No Earlier Than | Warning
38135 | Placer PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19778,19779 |  | 0 | Finish No Earlier Than | Warning
38136 | Placer PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38138 | Placer PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19784SS | 0 | Finish No Earlier Than | Warning
38139 | Placer PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19783SS |  | 0 | Finish No Earlier Than | Warning
38140 | Placer PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38141 | Placer PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19772SS |  | 0.2 | Finish No Earlier Than | Warning
38143 | Placer PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19789SS | 0.2 | Finish No Earlier Than | Warning
38144 | Placer PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19788SS |  | 0.2 | Finish No Earlier Than | Warning
38146 | Placer PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19792SS+18d | 0 | Start No Earlier Than | Warning
38147 | Placer PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19791SS+18d |  | 0 | Finish No Earlier Than | Warning
38149 | Placer PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19795SS | 0 | Start No Earlier Than | Warning
38150 | Placer PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19794SS |  | 0 | Finish No Earlier Than | Warning
38151 | Placer PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19797 | 0 | Start No Earlier Than | Warning
38152 | Placer PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19796 |  | 0 | Finish No Earlier Than | Warning
38153 | Placer PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38155 | Placer PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19801SS | 0 | Start No Earlier Than | Warning
38156 | Placer PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19800SS | 19802SS | 0 | Finish No Earlier Than | Warning
38157 | Placer PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19801SS | 19803SS | 0 | Finish No Earlier Than | Warning
38158 | Placer PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19802SS | 19804SS | 0 | Finish No Earlier Than | Warning
38159 | Placer PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19803SS | 19805SS | 0 | Finish No Earlier Than | Warning
38160 | Placer PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19804SS | 19806SS | 0 | Finish No Earlier Than | Warning
38161 | Placer PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19805SS | 19807SS | 0 | Finish No Earlier Than | Warning
38162 | Placer PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19806SS | 19808SS | 0 | Finish No Earlier Than | Warning
38163 | Placer PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19807SS | 19809SS | 0 | Finish No Earlier Than | Warning
38164 | Placer PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19808SS | 19810SS | 0 | Finish No Earlier Than | Warning
38165 | Placer PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19809SS |  | 0 | Finish No Earlier Than | Warning
38166 | Placer PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38167 | Placer PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38169 | Placer PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19815SS,19819 | 0.2 | Start No Earlier Than | Warning
38170 | Placer PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19814SS |  | 0 | Start No Earlier Than | Warning
38171 | Placer PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38172 | Placer PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19825 | 0 | Start No Earlier Than | Warning
38173 | Placer PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19826 | 0 | Start No Earlier Than | Warning
38174 | Placer PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19814 |  | 0 | Start No Earlier Than | Warning
38175 | Placer PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38176 | Placer PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19822SS,19830SS+20d | 0 | Start No Earlier Than | Warning
38177 | Placer PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19821SS | 19823SS,19831SS+20d | 0 | Finish No Earlier Than | Warning
38178 | Placer PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19822SS | 19832SS+20d | 0 | Finish No Earlier Than | Warning
38179 | Placer PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38180 | Placer PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19817 | 19826SS | 0 | Start No Earlier Than | Warning
38181 | Placer PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19818,19825SS |  | 0 | Finish No Earlier Than | Warning
38182 | Placer PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19835FS+12d | 0 | Start No Earlier Than | Warning
38183 | Placer PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19829SS | 0 | Start No Earlier Than | Warning
38184 | Placer PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19828SS |  | 0 | Start No Earlier Than | Warning
38188 | Placer PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19835SS+44d | 0 | Start No Earlier Than | Warning
38189 | Placer PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38194 | Plumas PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38195 | Plumas PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38196 | Plumas PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38197 | Plumas PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38198 | Plumas PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38199 | Plumas PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38200 | Plumas PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38201 | Plumas PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38202 | Plumas PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38203 | Plumas PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38204 | Plumas PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38205 | Plumas PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38206 | Plumas PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38207 | Plumas PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38208 | Plumas PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38209 | Plumas PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38210 | Plumas PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38211 | Plumas PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38212 | Plumas PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38213 | Plumas PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38214 | Plumas PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38215 | Plumas PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38216 | Plumas PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38217 | Plumas PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38218 | Plumas PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38219 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 19865SS | 0 | Start No Earlier Than | Warning
38220 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 19864SS |  | 0 | Finish No Earlier Than | Warning
38221 | Plumas PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 19867SS | 0 | Start No Earlier Than | Warning
38222 | Plumas PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 19866SS |  | 0 | Start No Earlier Than | Warning
38223 | Plumas PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
38224 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 19870SS | 0 | Finish No Earlier Than | Warning
38225 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 19869SS |  | 0 | Finish No Earlier Than | Warning
38226 | Plumas PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
38227 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 19873SS | 0 | Finish No Earlier Than | Warning
38229 | Plumas PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
38230 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 19876SS | 0 | Finish No Earlier Than | Warning
38231 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 19875SS |  | 0 | Start No Earlier Than | Warning
38232 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 19878SS | 0 | Start No Earlier Than | Warning
38233 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 19877SS |  | 0 | Start No Earlier Than | Warning
38234 | Plumas PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38235 | Plumas PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
38238 | Plumas PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38239 | Plumas PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38240 | Plumas PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
38241 | Plumas PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 19887FS+10d | 0 | Start No Earlier Than | Warning
38242 | Plumas PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 19886FS+10d |  | 0 | Start No Earlier Than | Warning
38244 | Plumas PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 19891FS-1d | 1 | Start No Earlier Than | Warning
38245 | Plumas PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38246 | Plumas PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 19889FS-1d |  | 0.2 | Start No Earlier Than | Warning
38247 | Plumas PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38248 | Plumas PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 19894 | 1 | Start No Earlier Than | Warning
38249 | Plumas PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19893 |  | 0 | Start No Earlier Than | Warning
38250 | Plumas PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38251 | Plumas PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 19897FS+19d | 0 | Finish No Earlier Than | Warning
38252 | Plumas PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 19896FS+19d | 19898 | 0 | Start No Earlier Than | Warning
38254 | Plumas PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38255 | Plumas PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 19901 | 0 | Start No Earlier Than | Warning
38256 | Plumas PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 19900 | 19902FS-1d | 0 | Start No Earlier Than | Warning
38257 | Plumas PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 19901FS-1d |  | 0 | Finish No Earlier Than | Warning
38258 | Plumas PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38259 | Plumas PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38262 | Plumas PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19908SS | 0 | Finish No Earlier Than | Warning
38263 | Plumas PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19907SS |  | 0 | Finish No Earlier Than | Warning
38264 | Plumas PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38265 | Plumas PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
38267 | Plumas PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19913SS | 0 | Finish No Earlier Than | Warning
38268 | Plumas PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19912SS | 19927SS | 0 | Start No Earlier Than | Warning
38270 | Plumas PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
38271 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38273 | Plumas PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 19919SS | 0 | Start No Earlier Than | Warning
38274 | Plumas PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19918SS | 19920SS,19921 | 0 | Finish No Earlier Than | Warning
38276 | Plumas PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19919,19920 |  | 0 | Finish No Earlier Than | Warning
38277 | Plumas PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38279 | Plumas PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19925SS | 0 | Finish No Earlier Than | Warning
38280 | Plumas PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 19924SS |  | 0 | Finish No Earlier Than | Warning
38281 | Plumas PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38282 | Plumas PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19913SS |  | 0 | Finish No Earlier Than | Warning
38284 | Plumas PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 19930SS | 0 | Finish No Earlier Than | Warning
38285 | Plumas PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 19929SS |  | 0 | Finish No Earlier Than | Warning
38287 | Plumas PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 19933SS+18d | 0 | Start No Earlier Than | Warning
38288 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 19932SS+18d |  | 0 | Finish No Earlier Than | Warning
38290 | Plumas PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 19936SS | 0 | Start No Earlier Than | Warning
38291 | Plumas PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 19935SS |  | 0 | Finish No Earlier Than | Warning
38292 | Plumas PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19938 | 0 | Start No Earlier Than | Warning
38293 | Plumas PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 19937 |  | 0 | Finish No Earlier Than | Warning
38294 | Plumas PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38296 | Plumas PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 19942SS | 0 | Start No Earlier Than | Warning
38297 | Plumas PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19941SS | 19943SS | 0 | Finish No Earlier Than | Warning
38298 | Plumas PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19942SS | 19944SS | 0 | Finish No Earlier Than | Warning
38299 | Plumas PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19943SS | 19945SS | 0 | Finish No Earlier Than | Warning
38300 | Plumas PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19944SS | 19946SS | 0 | Finish No Earlier Than | Warning
38301 | Plumas PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19945SS | 19947SS | 0 | Finish No Earlier Than | Warning
38302 | Plumas PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19946SS | 19948SS | 0 | Finish No Earlier Than | Warning
38303 | Plumas PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19947SS | 19949SS | 0 | Finish No Earlier Than | Warning
38304 | Plumas PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19948SS | 19950SS | 0 | Finish No Earlier Than | Warning
38305 | Plumas PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19949SS | 19951SS | 0 | Finish No Earlier Than | Warning
38306 | Plumas PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 19950SS |  | 0 | Finish No Earlier Than | Warning
38307 | Plumas PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38308 | Plumas PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38310 | Plumas PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 19956SS,19960 | 0 | Start No Earlier Than | Warning
38311 | Plumas PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 19955SS |  | 0 | Start No Earlier Than | Warning
38312 | Plumas PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38313 | Plumas PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19966 | 0 | Start No Earlier Than | Warning
38314 | Plumas PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 19967 | 0 | Start No Earlier Than | Warning
38315 | Plumas PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 19955 |  | 0 | Start No Earlier Than | Warning
38316 | Plumas PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38317 | Plumas PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 19963SS,19971SS+20d | 0 | Start No Earlier Than | Warning
38318 | Plumas PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19962SS | 19964SS,19972SS+20d | 0 | Finish No Earlier Than | Warning
38319 | Plumas PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 19963SS | 19973SS+20d | 0 | Finish No Earlier Than | Warning
38320 | Plumas PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38321 | Plumas PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19958 | 19967SS | 0 | Start No Earlier Than | Warning
38322 | Plumas PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 19959,19966SS |  | 0 | Finish No Earlier Than | Warning
38323 | Plumas PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 19976FS+12d | 0 | Start No Earlier Than | Warning
38324 | Plumas PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 19970SS | 0 | Start No Earlier Than | Warning
38325 | Plumas PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 19969SS |  | 0 | Start No Earlier Than | Warning
38329 | Plumas PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 19976SS+44d | 0 | Start No Earlier Than | Warning
38330 | Plumas PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38335 | Riverside PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38336 | Riverside PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38337 | Riverside PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38338 | Riverside PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38339 | Riverside PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38340 | Riverside PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38341 | Riverside PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38342 | Riverside PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38343 | Riverside PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38344 | Riverside PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38345 | Riverside PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38346 | Riverside PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38347 | Riverside PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38348 | Riverside PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38349 | Riverside PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38350 | Riverside PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38351 | Riverside PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38352 | Riverside PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38353 | Riverside PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38354 | Riverside PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38355 | Riverside PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38356 | Riverside PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38357 | Riverside PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38358 | Riverside PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38359 | Riverside PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38360 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20006SS | 0 | Start No Earlier Than | Warning
38361 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20005SS |  | 0 | Finish No Earlier Than | Warning
38362 | Riverside PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20008SS | 0 | Start No Earlier Than | Warning
38363 | Riverside PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20007SS |  | 0 | Start No Earlier Than | Warning
38364 | Riverside PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 20011SS,20010SS | 0 | Finish No Earlier Than | Warning
38367 | Riverside PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
38368 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 20014SS | 0 | Start No Earlier Than | Warning
38370 | Riverside PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
38371 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 20017SS | 0 | Start No Earlier Than | Warning
38372 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 20016SS |  | 0 | Start No Earlier Than | Warning
38373 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 20019SS | 0 | Start No Earlier Than | Warning
38375 | Riverside PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
38376 | Riverside PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
38379 | Riverside PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38380 | Riverside PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38381 | Riverside PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
38382 | Riverside PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
38384 | Riverside PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20031FS-1d | 1 | Start No Earlier Than | Warning
38385 | Riverside PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38386 | Riverside PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 20029FS-1d |  | 0.2 | Start No Earlier Than | Warning
38387 | Riverside PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38388 | Riverside PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20034 | 1 | Start No Earlier Than | Warning
38389 | Riverside PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20033 |  | 0 | Start No Earlier Than | Warning
38390 | Riverside PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38391 | Riverside PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20037FS+19d | 0.2 | Finish No Earlier Than | Warning
38392 | Riverside PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20036FS+19d | 20038 | 0 | Start No Earlier Than | Warning
38394 | Riverside PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38395 | Riverside PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20041 | 0 | Start No Earlier Than | Warning
38396 | Riverside PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20040 | 20042FS-1d | 0 | Start No Earlier Than | Warning
38397 | Riverside PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20041FS-1d |  | 0 | Finish No Earlier Than | Warning
38398 | Riverside PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38399 | Riverside PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38402 | Riverside PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20048SS | 0 | Finish No Earlier Than | Warning
38403 | Riverside PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20047SS |  | 0 | Finish No Earlier Than | Warning
38404 | Riverside PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38405 | Riverside PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
38407 | Riverside PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20053SS | 0 | Finish No Earlier Than | Warning
38408 | Riverside PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20052SS | 20067SS | 0 | Start No Earlier Than | Warning
38410 | Riverside PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
38411 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38413 | Riverside PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20059SS | 0 | Start No Earlier Than | Warning
38414 | Riverside PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20058SS | 20060SS,20061 | 0 | Finish No Earlier Than | Warning
38416 | Riverside PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20059,20060 |  | 0 | Finish No Earlier Than | Warning
38417 | Riverside PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38419 | Riverside PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20065SS | 0 | Finish No Earlier Than | Warning
38420 | Riverside PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20064SS |  | 0 | Finish No Earlier Than | Warning
38421 | Riverside PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38422 | Riverside PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20053SS |  | 0 | Finish No Earlier Than | Warning
38424 | Riverside PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20070SS | 0 | Finish No Earlier Than | Warning
38425 | Riverside PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20069SS |  | 0 | Finish No Earlier Than | Warning
38427 | Riverside PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20073SS+18d | 0 | Start No Earlier Than | Warning
38428 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20072SS+18d |  | 0 | Finish No Earlier Than | Warning
38430 | Riverside PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20076SS | 0 | Start No Earlier Than | Warning
38431 | Riverside PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20075SS |  | 0 | Finish No Earlier Than | Warning
38432 | Riverside PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20078 | 0 | Start No Earlier Than | Warning
38433 | Riverside PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20077 |  | 0 | Finish No Earlier Than | Warning
38434 | Riverside PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38436 | Riverside PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20082SS | 0 | Start No Earlier Than | Warning
38437 | Riverside PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20081SS | 20083SS | 0 | Finish No Earlier Than | Warning
38438 | Riverside PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20082SS | 20084SS | 0 | Finish No Earlier Than | Warning
38439 | Riverside PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20083SS | 20085SS | 0 | Finish No Earlier Than | Warning
38440 | Riverside PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20084SS | 20086SS | 0 | Finish No Earlier Than | Warning
38441 | Riverside PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20085SS | 20087SS | 0 | Finish No Earlier Than | Warning
38442 | Riverside PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20086SS | 20088SS | 0 | Finish No Earlier Than | Warning
38443 | Riverside PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20087SS | 20089SS | 0 | Finish No Earlier Than | Warning
38444 | Riverside PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20088SS | 20090SS | 0 | Finish No Earlier Than | Warning
38445 | Riverside PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20089SS | 20091SS | 0 | Finish No Earlier Than | Warning
38446 | Riverside PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20090SS |  | 0 | Finish No Earlier Than | Warning
38447 | Riverside PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
38448 | Riverside PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
38450 | Riverside PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20096SS,20100 | 0 | Start No Earlier Than | Warning
38451 | Riverside PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20095SS |  | 0 | Start No Earlier Than | Warning
38452 | Riverside PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38453 | Riverside PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20106 | 0 | Start No Earlier Than | Warning
38454 | Riverside PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20107 | 0 | Start No Earlier Than | Warning
38455 | Riverside PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20095 |  | 0 | Start No Earlier Than | Warning
38456 | Riverside PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38457 | Riverside PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 20103SS,20111SS+20d | 0 | Start No Earlier Than | Warning
38460 | Riverside PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38461 | Riverside PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20098 | 20107SS | 0 | Start No Earlier Than | Warning
38463 | Riverside PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 20116FS+12d | 0 | Start No Earlier Than | Warning
38464 | Riverside PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20110SS | 0 | Start No Earlier Than | Warning
38465 | Riverside PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20109SS |  | 0 | Start No Earlier Than | Warning
38469 | Riverside PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 20116SS+44d | 0 | Start No Earlier Than | Warning
38470 | Riverside PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38475 | Sacramento PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38476 | Sacramento PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38477 | Sacramento PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38478 | Sacramento PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38479 | Sacramento PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38480 | Sacramento PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38481 | Sacramento PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38482 | Sacramento PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38483 | Sacramento PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38484 | Sacramento PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38485 | Sacramento PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38486 | Sacramento PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38487 | Sacramento PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38488 | Sacramento PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38489 | Sacramento PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38490 | Sacramento PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38491 | Sacramento PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38492 | Sacramento PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38493 | Sacramento PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38494 | Sacramento PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38495 | Sacramento PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38496 | Sacramento PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38497 | Sacramento PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38498 | Sacramento PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38499 | Sacramento PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38500 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20146SS | 0 | Start No Earlier Than | Warning
38501 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20145SS |  | 0 | Finish No Earlier Than | Warning
38502 | Sacramento PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20148SS | 0 | Start No Earlier Than | Warning
38503 | Sacramento PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20147SS |  | 0 | Start No Earlier Than | Warning
38504 | Sacramento PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
38505 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20151SS | 0 | Finish No Earlier Than | Warning
38506 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20150SS |  | 0 | Finish No Earlier Than | Warning
38507 | Sacramento PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
38508 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20154SS | 0 | Finish No Earlier Than | Warning
38510 | Sacramento PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
38511 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20157SS | 0 | Finish No Earlier Than | Warning
38512 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20156SS |  | 0 | Start No Earlier Than | Warning
38513 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20159SS | 0 | Start No Earlier Than | Warning
38514 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20158SS |  | 0 | Start No Earlier Than | Warning
38515 | Sacramento PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38516 | Sacramento PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
38519 | Sacramento PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38520 | Sacramento PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38521 | Sacramento PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
38522 | Sacramento PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20168FS+10d | 0 | Start No Earlier Than | Warning
38523 | Sacramento PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20167FS+10d |  | 0 | Start No Earlier Than | Warning
38525 | Sacramento PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20172FS-1d | 1 | Start No Earlier Than | Warning
38526 | Sacramento PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38527 | Sacramento PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20170FS-1d |  | 0.2 | Start No Earlier Than | Warning
38528 | Sacramento PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38529 | Sacramento PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20175 | 1 | Start No Earlier Than | Warning
38530 | Sacramento PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 0d | 20174 |  | 1 | Start No Earlier Than | Warning
38531 | Sacramento PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38532 | Sacramento PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20178FS+19d | 0 | Finish No Earlier Than | Warning
38533 | Sacramento PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20177FS+19d | 20179 | 0 | Start No Earlier Than | Warning
38535 | Sacramento PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38536 | Sacramento PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20182 | 0 | Start No Earlier Than | Warning
38537 | Sacramento PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20181 | 20183FS-1d | 0 | Start No Earlier Than | Warning
38538 | Sacramento PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20182FS-1d |  | 0 | Finish No Earlier Than | Warning
38539 | Sacramento PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38540 | Sacramento PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38543 | Sacramento PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20189SS | 0 | Finish No Earlier Than | Warning
38544 | Sacramento PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20188SS |  | 0 | Finish No Earlier Than | Warning
38545 | Sacramento PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38546 | Sacramento PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
38548 | Sacramento PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20194SS | 0 | Finish No Earlier Than | Warning
38549 | Sacramento PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20193SS | 20208SS | 0 | Start No Earlier Than | Warning
38551 | Sacramento PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
38552 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38554 | Sacramento PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20200SS | 0 | Start No Earlier Than | Warning
38555 | Sacramento PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20199SS | 20201SS,20202 | 0 | Finish No Earlier Than | Warning
38557 | Sacramento PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20200,20201 |  | 0 | Finish No Earlier Than | Warning
38558 | Sacramento PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38560 | Sacramento PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20206SS | 0 | Finish No Earlier Than | Warning
38561 | Sacramento PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20205SS |  | 0 | Finish No Earlier Than | Warning
38562 | Sacramento PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38563 | Sacramento PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20194SS |  | 0 | Finish No Earlier Than | Warning
38565 | Sacramento PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20211SS | 0 | Finish No Earlier Than | Warning
38566 | Sacramento PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20210SS |  | 0 | Finish No Earlier Than | Warning
38568 | Sacramento PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20214SS+18d | 0 | Start No Earlier Than | Warning
38569 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20213SS+18d |  | 0 | Finish No Earlier Than | Warning
38571 | Sacramento PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20217SS | 0 | Start No Earlier Than | Warning
38572 | Sacramento PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20216SS |  | 0 | Finish No Earlier Than | Warning
38573 | Sacramento PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20219 | 0 | Start No Earlier Than | Warning
38574 | Sacramento PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20218 |  | 0 | Finish No Earlier Than | Warning
38575 | Sacramento PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38577 | Sacramento PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20223SS | 0 | Start No Earlier Than | Warning
38578 | Sacramento PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20222SS | 20224SS | 0 | Finish No Earlier Than | Warning
38579 | Sacramento PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20223SS | 20225SS | 0 | Finish No Earlier Than | Warning
38580 | Sacramento PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20224SS | 20226SS | 0 | Finish No Earlier Than | Warning
38581 | Sacramento PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20225SS | 20227SS | 0 | Finish No Earlier Than | Warning
38582 | Sacramento PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20226SS | 20228SS | 0 | Finish No Earlier Than | Warning
38583 | Sacramento PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20227SS | 20229SS | 0 | Finish No Earlier Than | Warning
38584 | Sacramento PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20228SS | 20230SS | 0 | Finish No Earlier Than | Warning
38585 | Sacramento PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20229SS | 20231SS | 0 | Finish No Earlier Than | Warning
38586 | Sacramento PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20230SS | 20232SS | 0 | Finish No Earlier Than | Warning
38587 | Sacramento PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20231SS |  | 0 | Finish No Earlier Than | Warning
38588 | Sacramento PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38589 | Sacramento PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38591 | Sacramento PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20237SS,20241 | 0 | Start No Earlier Than | Warning
38592 | Sacramento PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20236SS |  | 0 | Start No Earlier Than | Warning
38593 | Sacramento PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38594 | Sacramento PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20247 | 0 | Start No Earlier Than | Warning
38595 | Sacramento PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20248 | 0 | Start No Earlier Than | Warning
38596 | Sacramento PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20236 |  | 0 | Start No Earlier Than | Warning
38597 | Sacramento PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38598 | Sacramento PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20244SS,20252SS+20d | 0 | Start No Earlier Than | Warning
38599 | Sacramento PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20243SS | 20245SS,20253SS+20d | 0 | Finish No Earlier Than | Warning
38600 | Sacramento PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20244SS | 20254SS+20d | 0 | Finish No Earlier Than | Warning
38601 | Sacramento PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38602 | Sacramento PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20239 | 20248SS | 0 | Start No Earlier Than | Warning
38603 | Sacramento PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20240,20247SS |  | 0 | Finish No Earlier Than | Warning
38604 | Sacramento PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20257FS+12d | 0 | Start No Earlier Than | Warning
38605 | Sacramento PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20251SS | 0 | Start No Earlier Than | Warning
38606 | Sacramento PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20250SS |  | 0 | Start No Earlier Than | Warning
38610 | Sacramento PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20257SS+44d | 0 | Start No Earlier Than | Warning
38611 | Sacramento PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38616 | San Benito PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38617 | San Benito PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38618 | San Benito PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38619 | San Benito PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38620 | San Benito PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38621 | San Benito PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38622 | San Benito PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38623 | San Benito PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38624 | San Benito PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38625 | San Benito PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38626 | San Benito PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38627 | San Benito PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38628 | San Benito PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38629 | San Benito PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38630 | San Benito PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38631 | San Benito PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38632 | San Benito PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38633 | San Benito PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38634 | San Benito PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38635 | San Benito PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38636 | San Benito PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38637 | San Benito PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38638 | San Benito PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38639 | San Benito PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38640 | San Benito PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38641 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20287SS | 0 | Start No Earlier Than | Warning
38642 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20286SS |  | 0 | Finish No Earlier Than | Warning
38643 | San Benito PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20289SS | 0 | Start No Earlier Than | Warning
38644 | San Benito PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20288SS |  | 0 | Start No Earlier Than | Warning
38645 | San Benito PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
38646 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20292SS | 0 | Finish No Earlier Than | Warning
38647 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20291SS |  | 0 | Finish No Earlier Than | Warning
38648 | San Benito PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
38649 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20295SS | 0 | Finish No Earlier Than | Warning
38651 | San Benito PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
38652 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20298SS | 0 | Finish No Earlier Than | Warning
38653 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20297SS |  | 0 | Start No Earlier Than | Warning
38654 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20300SS | 0 | Start No Earlier Than | Warning
38655 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20299SS |  | 0 | Start No Earlier Than | Warning
38656 | San Benito PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38657 | San Benito PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
38660 | San Benito PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38661 | San Benito PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38662 | San Benito PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
38663 | San Benito PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20309FS+10d | 0 | Start No Earlier Than | Warning
38664 | San Benito PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20308FS+10d |  | 0 | Start No Earlier Than | Warning
38666 | San Benito PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20313FS-1d | 1 | Start No Earlier Than | Warning
38667 | San Benito PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38668 | San Benito PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20311FS-1d |  | 0.2 | Start No Earlier Than | Warning
38669 | San Benito PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38670 | San Benito PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20316 | 1 | Start No Earlier Than | Warning
38671 | San Benito PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20315 |  | 0 | Start No Earlier Than | Warning
38672 | San Benito PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38673 | San Benito PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20319FS+19d | 0 | Finish No Earlier Than | Warning
38674 | San Benito PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20318FS+19d | 20320 | 0 | Start No Earlier Than | Warning
38676 | San Benito PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38677 | San Benito PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20323 | 0 | Start No Earlier Than | Warning
38678 | San Benito PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20322 | 20324FS-1d | 0 | Start No Earlier Than | Warning
38679 | San Benito PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20323FS-1d |  | 0 | Finish No Earlier Than | Warning
38680 | San Benito PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38681 | San Benito PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38684 | San Benito PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20330SS | 0 | Start No Earlier Than | Warning
38685 | San Benito PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20329SS | 20331SS | 0 | Finish No Earlier Than | Warning
38686 | San Benito PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20330SS | 20332SS | 0 | Finish No Earlier Than | Warning
38687 | San Benito PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20331SS | 20333SS | 0 | Finish No Earlier Than | Warning
38688 | San Benito PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20332SS | 20334SS | 0 | Finish No Earlier Than | Warning
38689 | San Benito PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20333SS | 20335SS | 0 | Finish No Earlier Than | Warning
38690 | San Benito PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20334SS | 20336SS | 0 | Finish No Earlier Than | Warning
38691 | San Benito PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20335SS | 20337SS | 0 | Finish No Earlier Than | Warning
38692 | San Benito PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20336SS | 20338SS | 0 | Finish No Earlier Than | Warning
38693 | San Benito PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20337SS | 20339SS | 0 | Finish No Earlier Than | Warning
38694 | San Benito PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20338SS |  | 0 | Finish No Earlier Than | Warning
38695 | San Benito PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38696 | San Benito PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38698 | San Benito PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20344SS,20348 | 0 | Start No Earlier Than | Warning
38699 | San Benito PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20343SS |  | 0 | Start No Earlier Than | Warning
38700 | San Benito PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38701 | San Benito PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20354 | 0 | Start No Earlier Than | Warning
38702 | San Benito PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20355 | 0 | Start No Earlier Than | Warning
38703 | San Benito PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20343 |  | 0 | Start No Earlier Than | Warning
38704 | San Benito PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38705 | San Benito PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20351SS,20359SS+20d | 0 | Start No Earlier Than | Warning
38706 | San Benito PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20350SS | 20352SS,20360SS+20d | 0 | Finish No Earlier Than | Warning
38707 | San Benito PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20351SS | 20361SS+20d | 0 | Finish No Earlier Than | Warning
38708 | San Benito PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38709 | San Benito PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20346 | 20355SS | 0 | Start No Earlier Than | Warning
38710 | San Benito PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20347,20354SS |  | 0 | Finish No Earlier Than | Warning
38711 | San Benito PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20364FS+12d | 0 | Start No Earlier Than | Warning
38712 | San Benito PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20358SS | 0 | Start No Earlier Than | Warning
38713 | San Benito PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20357SS |  | 0 | Start No Earlier Than | Warning
38717 | San Benito PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20364SS+44d | 0 | Start No Earlier Than | Warning
38718 | San Benito PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38723 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38724 | San Bernardino PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38725 | San Bernardino PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38726 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38727 | San Bernardino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38728 | San Bernardino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38729 | San Bernardino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38730 | San Bernardino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38731 | San Bernardino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38732 | San Bernardino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38733 | San Bernardino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38734 | San Bernardino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38735 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38736 | San Bernardino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38737 | San Bernardino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38738 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38739 | San Bernardino PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38740 | San Bernardino PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38741 | San Bernardino PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38742 | San Bernardino PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38743 | San Bernardino PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38744 | San Bernardino PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38745 | San Bernardino PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38746 | San Bernardino PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38747 | San Bernardino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38748 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20394SS | 0 | Start No Earlier Than | Warning
38749 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20393SS |  | 0 | Finish No Earlier Than | Warning
38750 | San Bernardino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20396SS | 0 | Start No Earlier Than | Warning
38751 | San Bernardino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20395SS |  | 0 | Start No Earlier Than | Warning
38752 | San Bernardino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
38753 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20399SS | 0 | Finish No Earlier Than | Warning
38754 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20398SS |  | 0 | Finish No Earlier Than | Warning
38755 | San Bernardino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
38756 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20402SS | 0 | Finish No Earlier Than | Warning
38758 | San Bernardino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
38759 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20405SS | 0 | Finish No Earlier Than | Warning
38760 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20404SS |  | 0 | Start No Earlier Than | Warning
38761 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20407SS | 0 | Start No Earlier Than | Warning
38762 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20406SS |  | 0 | Start No Earlier Than | Warning
38763 | San Bernardino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38764 | San Bernardino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
38767 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38768 | San Bernardino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38769 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
38770 | San Bernardino PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20416FS+10d | 0 | Start No Earlier Than | Warning
38771 | San Bernardino PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20415FS+10d |  | 0 | Start No Earlier Than | Warning
38773 | San Bernardino PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20420FS-1d | 1 | Start No Earlier Than | Warning
38774 | San Bernardino PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38775 | San Bernardino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20418FS-1d |  | 0 | Start No Earlier Than | Warning
38776 | San Bernardino PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38777 | San Bernardino PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20423 | 1 | Start No Earlier Than | Warning
38778 | San Bernardino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20422 |  | 0 | Start No Earlier Than | Warning
38779 | San Bernardino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38780 | San Bernardino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if appli | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20426FS+19d | 0 | Finish No Earlier Than | Warning
38781 | San Bernardino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20425FS+19d | 20427 | 0 | Start No Earlier Than | Warning
38783 | San Bernardino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38784 | San Bernardino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and op | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20430 | 0 | Start No Earlier Than | Warning
38785 | San Bernardino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20429 | 20431FS-1d | 0 | Start No Earlier Than | Warning
38786 | San Bernardino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20430FS-1d |  | 0 | Finish No Earlier Than | Warning
38787 | San Bernardino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38788 | San Bernardino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38791 | San Bernardino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20437SS | 0 | Finish No Earlier Than | Warning
38792 | San Bernardino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20436SS |  | 0 | Finish No Earlier Than | Warning
38793 | San Bernardino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38794 | San Bernardino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
38796 | San Bernardino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20442SS | 0 | Finish No Earlier Than | Warning
38797 | San Bernardino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20441SS | 20456SS | 0 | Start No Earlier Than | Warning
38799 | San Bernardino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
38800 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38802 | San Bernardino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20448SS | 0 | Start No Earlier Than | Warning
38803 | San Bernardino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20447SS | 20449SS,20450 | 0 | Finish No Earlier Than | Warning
38805 | San Bernardino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20448,20449 |  | 0 | Finish No Earlier Than | Warning
38806 | San Bernardino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38808 | San Bernardino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20454SS | 0 | Finish No Earlier Than | Warning
38809 | San Bernardino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20453SS |  | 0 | Finish No Earlier Than | Warning
38810 | San Bernardino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38811 | San Bernardino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20442SS |  | 0 | Finish No Earlier Than | Warning
38813 | San Bernardino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20459SS | 0 | Finish No Earlier Than | Warning
38814 | San Bernardino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20458SS |  | 0 | Finish No Earlier Than | Warning
38816 | San Bernardino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20462SS+18d | 0 | Start No Earlier Than | Warning
38817 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20461SS+18d |  | 0 | Finish No Earlier Than | Warning
38819 | San Bernardino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20465SS | 0 | Start No Earlier Than | Warning
38820 | San Bernardino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20464SS |  | 0 | Finish No Earlier Than | Warning
38821 | San Bernardino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20467 | 0 | Start No Earlier Than | Warning
38822 | San Bernardino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20466 |  | 0 | Finish No Earlier Than | Warning
38823 | San Bernardino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38825 | San Bernardino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20471SS | 0 | Start No Earlier Than | Warning
38826 | San Bernardino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20470SS | 20472SS | 0 | Finish No Earlier Than | Warning
38827 | San Bernardino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20471SS | 20473SS | 0 | Finish No Earlier Than | Warning
38828 | San Bernardino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20472SS | 20474SS | 0 | Finish No Earlier Than | Warning
38829 | San Bernardino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20473SS | 20475SS | 0 | Finish No Earlier Than | Warning
38830 | San Bernardino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20474SS | 20476SS | 0 | Finish No Earlier Than | Warning
38831 | San Bernardino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20475SS | 20477SS | 0 | Finish No Earlier Than | Warning
38832 | San Bernardino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Da | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20476SS | 20478SS | 0 | Finish No Earlier Than | Warning
38833 | San Bernardino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20477SS | 20479SS | 0 | Finish No Earlier Than | Warning
38834 | San Bernardino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20478SS | 20480SS | 0 | Finish No Earlier Than | Warning
38835 | San Bernardino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20479SS |  | 0 | Finish No Earlier Than | Warning
38836 | San Bernardino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
38837 | San Bernardino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
38839 | San Bernardino PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20485SS,20489 | 0 | Start No Earlier Than | Warning
38840 | San Bernardino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20484SS |  | 0 | Start No Earlier Than | Warning
38841 | San Bernardino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38842 | San Bernardino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20495 | 0 | Start No Earlier Than | Warning
38843 | San Bernardino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20496 | 0 | Start No Earlier Than | Warning
38844 | San Bernardino PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20484 |  | 0 | Start No Earlier Than | Warning
38845 | San Bernardino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38846 | San Bernardino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20492SS,20500SS+20d | 0 | Start No Earlier Than | Warning
38847 | San Bernardino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20491SS | 20493SS,20501SS+20d | 0 | Finish No Earlier Than | Warning
38848 | San Bernardino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20492SS | 20502SS+20d | 0 | Finish No Earlier Than | Warning
38849 | San Bernardino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38850 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20487 | 20496SS | 0 | Start No Earlier Than | Warning
38851 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20488,20495SS |  | 0 | Finish No Earlier Than | Warning
38852 | San Bernardino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20505FS+12d | 0 | Start No Earlier Than | Warning
38853 | San Bernardino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20499SS | 0 | Start No Earlier Than | Warning
38854 | San Bernardino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20498SS |  | 0 | Start No Earlier Than | Warning
38858 | San Bernardino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20505SS+44d | 0 | Start No Earlier Than | Warning
38859 | San Bernardino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
38864 | San Diego PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38865 | San Diego PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38866 | San Diego PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
38867 | San Diego PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
38868 | San Diego PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
38869 | San Diego PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
38870 | San Diego PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
38871 | San Diego PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
38872 | San Diego PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
38873 | San Diego PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
38874 | San Diego PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
38875 | San Diego PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
38876 | San Diego PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
38877 | San Diego PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
38878 | San Diego PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
38879 | San Diego PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
38880 | San Diego PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38881 | San Diego PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38882 | San Diego PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38883 | San Diego PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38884 | San Diego PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38885 | San Diego PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38886 | San Diego PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38887 | San Diego PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38888 | San Diego PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
38889 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20535SS | 0 | Start No Earlier Than | Warning
38890 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20534SS |  | 0 | Finish No Earlier Than | Warning
38891 | San Diego PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20537SS | 0 | Start No Earlier Than | Warning
38892 | San Diego PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20536SS |  | 0 | Start No Earlier Than | Warning
38893 | San Diego PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 20540SS,20539SS | 0 | Finish No Earlier Than | Warning
38896 | San Diego PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
38897 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 20543SS | 0 | Start No Earlier Than | Warning
38899 | San Diego PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
38900 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 20546SS | 0 | Start No Earlier Than | Warning
38901 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 20545SS |  | 0 | Start No Earlier Than | Warning
38902 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 20548SS | 0 | Start No Earlier Than | Warning
38904 | San Diego PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
38905 | San Diego PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
38908 | San Diego PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
38909 | San Diego PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
38910 | San Diego PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
38911 | San Diego PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
38913 | San Diego PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20560FS-1d | 1 | Start No Earlier Than | Warning
38914 | San Diego PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
38915 | San Diego PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 20558FS-1d |  | 0.2 | Start No Earlier Than | Warning
38916 | San Diego PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
38917 | San Diego PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20563 | 1 | Start No Earlier Than | Warning
38918 | San Diego PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20562 |  | 0 | Start No Earlier Than | Warning
38919 | San Diego PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38920 | San Diego PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20566FS+19d | 0 | Finish No Earlier Than | Warning
38921 | San Diego PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20565FS+19d | 20567 | 0 | Start No Earlier Than | Warning
38923 | San Diego PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
38924 | San Diego PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20570 | 0 | Start No Earlier Than | Warning
38925 | San Diego PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20569 | 20571FS-1d | 0 | Start No Earlier Than | Warning
38926 | San Diego PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20570FS-1d |  | 0 | Finish No Earlier Than | Warning
38927 | San Diego PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
38928 | San Diego PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
38931 | San Diego PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20577SS | 0 | Finish No Earlier Than | Warning
38932 | San Diego PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20576SS |  | 0 | Finish No Earlier Than | Warning
38933 | San Diego PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38934 | San Diego PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
38936 | San Diego PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20582SS | 0 | Finish No Earlier Than | Warning
38937 | San Diego PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20581SS | 20596SS | 0 | Start No Earlier Than | Warning
38939 | San Diego PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
38940 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
38942 | San Diego PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20588SS | 0 | Start No Earlier Than | Warning
38943 | San Diego PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20587SS | 20589SS,20590 | 0 | Finish No Earlier Than | Warning
38945 | San Diego PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20588,20589 |  | 0 | Finish No Earlier Than | Warning
38946 | San Diego PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38948 | San Diego PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20594SS | 0 | Finish No Earlier Than | Warning
38949 | San Diego PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20593SS |  | 0 | Finish No Earlier Than | Warning
38950 | San Diego PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
38951 | San Diego PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20582SS |  | 0 | Finish No Earlier Than | Warning
38953 | San Diego PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20599SS | 0 | Finish No Earlier Than | Warning
38954 | San Diego PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20598SS |  | 0 | Finish No Earlier Than | Warning
38956 | San Diego PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20602SS+18d | 0 | Start No Earlier Than | Warning
38957 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20601SS+18d |  | 0 | Finish No Earlier Than | Warning
38959 | San Diego PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20605SS | 0 | Start No Earlier Than | Warning
38960 | San Diego PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20604SS |  | 0 | Finish No Earlier Than | Warning
38961 | San Diego PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20607 | 0 | Start No Earlier Than | Warning
38962 | San Diego PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20606 |  | 0 | Finish No Earlier Than | Warning
38963 | San Diego PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
38965 | San Diego PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20611SS | 0 | Start No Earlier Than | Warning
38966 | San Diego PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20610SS | 20612SS | 0 | Finish No Earlier Than | Warning
38967 | San Diego PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20611SS | 20613SS | 0 | Finish No Earlier Than | Warning
38968 | San Diego PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20612SS | 20614SS | 0 | Finish No Earlier Than | Warning
38969 | San Diego PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20613SS | 20615SS | 0 | Finish No Earlier Than | Warning
38970 | San Diego PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20614SS | 20616SS | 0 | Finish No Earlier Than | Warning
38971 | San Diego PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20615SS | 20617SS | 0 | Finish No Earlier Than | Warning
38972 | San Diego PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20616SS | 20618SS | 0 | Finish No Earlier Than | Warning
38973 | San Diego PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20617SS | 20619SS | 0 | Finish No Earlier Than | Warning
38974 | San Diego PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20618SS | 20620SS | 0 | Finish No Earlier Than | Warning
38975 | San Diego PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20619SS |  | 0 | Finish No Earlier Than | Warning
38976 | San Diego PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
38977 | San Diego PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
38979 | San Diego PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20625SS,20629 | 0 | Start No Earlier Than | Warning
38980 | San Diego PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20624SS |  | 0 | Start No Earlier Than | Warning
38981 | San Diego PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
38982 | San Diego PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20635 | 0 | Start No Earlier Than | Warning
38983 | San Diego PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 20636 | 0 | Start No Earlier Than | Warning
38984 | San Diego PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20624 |  | 0 | Start No Earlier Than | Warning
38985 | San Diego PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
38986 | San Diego PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 20632SS,20640SS+20d | 0 | Start No Earlier Than | Warning
38989 | San Diego PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
38990 | San Diego PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 20627 | 20636SS | 0 | Start No Earlier Than | Warning
38992 | San Diego PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 20645FS+12d | 0 | Start No Earlier Than | Warning
38993 | San Diego PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20639SS | 0 | Start No Earlier Than | Warning
38994 | San Diego PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20638SS |  | 0 | Start No Earlier Than | Warning
38998 | San Diego PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 20645SS+44d | 0 | Start No Earlier Than | Warning
38999 | San Diego PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39004 | San Francisco PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39005 | San Francisco PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39006 | San Francisco PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39007 | San Francisco PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39008 | San Francisco PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39009 | San Francisco PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39010 | San Francisco PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39011 | San Francisco PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39012 | San Francisco PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39013 | San Francisco PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39014 | San Francisco PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39015 | San Francisco PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39016 | San Francisco PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39017 | San Francisco PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39018 | San Francisco PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39019 | San Francisco PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39020 | San Francisco PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39021 | San Francisco PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39022 | San Francisco PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39023 | San Francisco PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39024 | San Francisco PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39025 | San Francisco PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39026 | San Francisco PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39027 | San Francisco PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39028 | San Francisco PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39029 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20675SS | 0 | Start No Earlier Than | Warning
39030 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20674SS |  | 0 | Finish No Earlier Than | Warning
39031 | San Francisco PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20677SS | 0 | Start No Earlier Than | Warning
39032 | San Francisco PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20676SS |  | 0 | Start No Earlier Than | Warning
39033 | San Francisco PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39034 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20680SS | 0 | Finish No Earlier Than | Warning
39035 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20679SS |  | 0 | Finish No Earlier Than | Warning
39036 | San Francisco PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39037 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20683SS | 0 | Finish No Earlier Than | Warning
39039 | San Francisco PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39040 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20686SS | 0 | Finish No Earlier Than | Warning
39041 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20685SS |  | 0 | Start No Earlier Than | Warning
39042 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20688SS | 0 | Start No Earlier Than | Warning
39043 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20687SS |  | 0 | Start No Earlier Than | Warning
39044 | San Francisco PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39045 | San Francisco PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39048 | San Francisco PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39049 | San Francisco PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39050 | San Francisco PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39051 | San Francisco PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20697FS+10d | 0 | Start No Earlier Than | Warning
39052 | San Francisco PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20696FS+10d |  | 0 | Start No Earlier Than | Warning
39054 | San Francisco PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20701FS-1d | 1 | Start No Earlier Than | Warning
39055 | San Francisco PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39056 | San Francisco PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20699FS-1d |  | 0 | Start No Earlier Than | Warning
39057 | San Francisco PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39058 | San Francisco PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20704 | 1 | Start No Earlier Than | Warning
39059 | San Francisco PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20703 |  | 0 | Start No Earlier Than | Warning
39060 | San Francisco PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39061 | San Francisco PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20707FS+19d | 0 | Finish No Earlier Than | Warning
39062 | San Francisco PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20706FS+19d | 20708 | 0 | Start No Earlier Than | Warning
39064 | San Francisco PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39065 | San Francisco PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20711 | 0 | Start No Earlier Than | Warning
39066 | San Francisco PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20710 | 20712FS-1d | 0 | Start No Earlier Than | Warning
39067 | San Francisco PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20711FS-1d |  | 0 | Finish No Earlier Than | Warning
39068 | San Francisco PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39069 | San Francisco PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39072 | San Francisco PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20718SS | 0 | Start No Earlier Than | Warning
39073 | San Francisco PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20717SS | 20719SS | 0 | Finish No Earlier Than | Warning
39074 | San Francisco PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20718SS | 20720SS | 0 | Finish No Earlier Than | Warning
39075 | San Francisco PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20719SS | 20721SS | 0 | Finish No Earlier Than | Warning
39076 | San Francisco PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20720SS | 20722SS | 0 | Finish No Earlier Than | Warning
39077 | San Francisco PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20721SS | 20723SS | 0 | Finish No Earlier Than | Warning
39078 | San Francisco PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20722SS | 20724SS | 0 | Finish No Earlier Than | Warning
39079 | San Francisco PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20723SS | 20725SS | 0 | Finish No Earlier Than | Warning
39080 | San Francisco PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20724SS | 20726SS | 0 | Finish No Earlier Than | Warning
39081 | San Francisco PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20725SS | 20727SS | 0 | Finish No Earlier Than | Warning
39082 | San Francisco PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20726SS |  | 0 | Finish No Earlier Than | Warning
39083 | San Francisco PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39084 | San Francisco PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39086 | San Francisco PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20732SS,20736 | 0 | Start No Earlier Than | Warning
39087 | San Francisco PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20731SS |  | 0 | Start No Earlier Than | Warning
39088 | San Francisco PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39089 | San Francisco PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20742 | 0 | Start No Earlier Than | Warning
39090 | San Francisco PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20743 | 0 | Start No Earlier Than | Warning
39091 | San Francisco PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20731 |  | 0 | Start No Earlier Than | Warning
39092 | San Francisco PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39093 | San Francisco PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20739SS,20747SS+20d | 0 | Start No Earlier Than | Warning
39094 | San Francisco PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20738SS | 20740SS,20748SS+20d | 0 | Finish No Earlier Than | Warning
39095 | San Francisco PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20739SS | 20749SS+20d | 0 | Finish No Earlier Than | Warning
39096 | San Francisco PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39097 | San Francisco PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20734 | 20743SS | 0 | Start No Earlier Than | Warning
39098 | San Francisco PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20735,20742SS |  | 0 | Finish No Earlier Than | Warning
39099 | San Francisco PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20752FS+12d | 0 | Start No Earlier Than | Warning
39100 | San Francisco PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20746SS | 0 | Start No Earlier Than | Warning
39101 | San Francisco PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20745SS |  | 0 | Start No Earlier Than | Warning
39105 | San Francisco PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20752SS+44d | 0 | Start No Earlier Than | Warning
39106 | San Francisco PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39111 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39112 | San Joaquin PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39113 | San Joaquin PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39114 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39115 | San Joaquin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39116 | San Joaquin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39117 | San Joaquin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39118 | San Joaquin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39119 | San Joaquin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39120 | San Joaquin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39121 | San Joaquin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39122 | San Joaquin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39123 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39124 | San Joaquin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39125 | San Joaquin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39126 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39127 | San Joaquin PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39128 | San Joaquin PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39129 | San Joaquin PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39130 | San Joaquin PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39131 | San Joaquin PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39132 | San Joaquin PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39133 | San Joaquin PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39134 | San Joaquin PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39135 | San Joaquin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
39136 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20782SS | 0 | Start No Earlier Than | Warning
39137 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20781SS |  | 0 | Finish No Earlier Than | Warning
39138 | San Joaquin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20784SS | 0.2 | Start No Earlier Than | Warning
39139 | San Joaquin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20783SS |  | 0 | Start No Earlier Than | Warning
39140 | San Joaquin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39141 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20787SS | 0 | Finish No Earlier Than | Warning
39142 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20786SS |  | 0 | Finish No Earlier Than | Warning
39143 | San Joaquin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39144 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20790SS | 0 | Finish No Earlier Than | Warning
39146 | San Joaquin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39147 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20793SS | 0 | Finish No Earlier Than | Warning
39148 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20792SS |  | 0 | Start No Earlier Than | Warning
39149 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20795SS | 0 | Start No Earlier Than | Warning
39150 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20794SS |  | 0 | Start No Earlier Than | Warning
39151 | San Joaquin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39152 | San Joaquin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39155 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39156 | San Joaquin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39157 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39158 | San Joaquin PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20804FS+10d | 0 | Start No Earlier Than | Warning
39159 | San Joaquin PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20803FS+10d |  | 0 | Start No Earlier Than | Warning
39161 | San Joaquin PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20808FS-1d | 1 | Start No Earlier Than | Warning
39162 | San Joaquin PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39163 | San Joaquin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20806FS-1d |  | 0.2 | Start No Earlier Than | Warning
39164 | San Joaquin PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39165 | San Joaquin PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20811 | 1 | Start No Earlier Than | Warning
39166 | San Joaquin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20810 |  | 0 | Start No Earlier Than | Warning
39167 | San Joaquin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39168 | San Joaquin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 20814FS+19d | 0 | Finish No Earlier Than | Warning
39169 | San Joaquin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20813FS+19d | 20815 | 0 | Start No Earlier Than | Warning
39171 | San Joaquin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39172 | San Joaquin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20818 | 0 | Start No Earlier Than | Warning
39173 | San Joaquin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20817 | 20819FS-1d | 0 | Start No Earlier Than | Warning
39174 | San Joaquin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20818FS-1d |  | 0 | Finish No Earlier Than | Warning
39175 | San Joaquin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39176 | San Joaquin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39179 | San Joaquin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20825SS | 0 | Finish No Earlier Than | Warning
39180 | San Joaquin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20824SS |  | 0 | Finish No Earlier Than | Warning
39181 | San Joaquin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39182 | San Joaquin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39184 | San Joaquin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20830SS | 0 | Finish No Earlier Than | Warning
39185 | San Joaquin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20829SS | 20844SS | 0 | Start No Earlier Than | Warning
39187 | San Joaquin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39188 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39190 | San Joaquin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20836SS | 0 | Start No Earlier Than | Warning
39191 | San Joaquin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20835SS | 20837SS,20838 | 0 | Finish No Earlier Than | Warning
39193 | San Joaquin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20836,20837 |  | 0 | Finish No Earlier Than | Warning
39194 | San Joaquin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39196 | San Joaquin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20842SS | 0 | Finish No Earlier Than | Warning
39197 | San Joaquin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20841SS |  | 0 | Finish No Earlier Than | Warning
39198 | San Joaquin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39199 | San Joaquin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20830SS |  | 0 | Finish No Earlier Than | Warning
39201 | San Joaquin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20847SS | 0 | Finish No Earlier Than | Warning
39202 | San Joaquin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20846SS |  | 0 | Finish No Earlier Than | Warning
39204 | San Joaquin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20850SS+18d | 0 | Start No Earlier Than | Warning
39205 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20849SS+18d |  | 0 | Finish No Earlier Than | Warning
39207 | San Joaquin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20853SS | 0 | Start No Earlier Than | Warning
39208 | San Joaquin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20852SS |  | 0 | Finish No Earlier Than | Warning
39209 | San Joaquin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20855 | 0 | Start No Earlier Than | Warning
39210 | San Joaquin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20854 |  | 0 | Finish No Earlier Than | Warning
39211 | San Joaquin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39213 | San Joaquin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20859SS | 0 | Start No Earlier Than | Warning
39214 | San Joaquin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20858SS | 20860SS | 0 | Finish No Earlier Than | Warning
39215 | San Joaquin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20859SS | 20861SS | 0 | Finish No Earlier Than | Warning
39216 | San Joaquin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20860SS | 20862SS | 0 | Finish No Earlier Than | Warning
39217 | San Joaquin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20861SS | 20863SS | 0 | Finish No Earlier Than | Warning
39218 | San Joaquin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20862SS | 20864SS | 0 | Finish No Earlier Than | Warning
39219 | San Joaquin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20863SS | 20865SS | 0 | Finish No Earlier Than | Warning
39220 | San Joaquin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20864SS | 20866SS | 0 | Finish No Earlier Than | Warning
39221 | San Joaquin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20865SS | 20867SS | 0 | Finish No Earlier Than | Warning
39222 | San Joaquin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20866SS | 20868SS | 0 | Finish No Earlier Than | Warning
39223 | San Joaquin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20867SS |  | 0 | Finish No Earlier Than | Warning
39224 | San Joaquin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39225 | San Joaquin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39227 | San Joaquin PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 20873SS,20877 | 0.2 | Start No Earlier Than | Warning
39228 | San Joaquin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 20872SS |  | 0 | Start No Earlier Than | Warning
39229 | San Joaquin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39230 | San Joaquin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20883 | 0 | Start No Earlier Than | Warning
39231 | San Joaquin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 20884 | 0 | Start No Earlier Than | Warning
39232 | San Joaquin PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 20872 |  | 0 | Start No Earlier Than | Warning
39233 | San Joaquin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39234 | San Joaquin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 20880SS,20888SS+20d | 0 | Start No Earlier Than | Warning
39235 | San Joaquin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20879SS | 20881SS,20889SS+20d | 0 | Finish No Earlier Than | Warning
39236 | San Joaquin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 20880SS | 20890SS+20d | 0 | Finish No Earlier Than | Warning
39237 | San Joaquin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39238 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20875 | 20884SS | 0 | Start No Earlier Than | Warning
39239 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 20876,20883SS |  | 0 | Finish No Earlier Than | Warning
39240 | San Joaquin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 20893FS+12d | 0 | Start No Earlier Than | Warning
39241 | San Joaquin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 20887SS | 0 | Start No Earlier Than | Warning
39242 | San Joaquin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 20886SS |  | 0 | Start No Earlier Than | Warning
39246 | San Joaquin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 20893SS+44d | 0 | Start No Earlier Than | Warning
39247 | San Joaquin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39252 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39253 | San Luis Obispo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39254 | San Luis Obispo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39255 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39256 | San Luis Obispo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39257 | San Luis Obispo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39258 | San Luis Obispo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39259 | San Luis Obispo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39260 | San Luis Obispo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39261 | San Luis Obispo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39262 | San Luis Obispo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39263 | San Luis Obispo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39264 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39265 | San Luis Obispo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39266 | San Luis Obispo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39267 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39268 | San Luis Obispo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39269 | San Luis Obispo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39270 | San Luis Obispo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39271 | San Luis Obispo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39272 | San Luis Obispo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39273 | San Luis Obispo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39274 | San Luis Obispo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39275 | San Luis Obispo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39276 | San Luis Obispo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39277 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 20923SS | 0 | Start No Earlier Than | Warning
39278 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 20922SS |  | 0 | Finish No Earlier Than | Warning
39279 | San Luis Obispo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 20925SS | 0 | Start No Earlier Than | Warning
39280 | San Luis Obispo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 20924SS |  | 0 | Start No Earlier Than | Warning
39281 | San Luis Obispo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39282 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 20928SS | 0 | Finish No Earlier Than | Warning
39283 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 20927SS |  | 0 | Finish No Earlier Than | Warning
39284 | San Luis Obispo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39285 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 20931SS | 0 | Finish No Earlier Than | Warning
39287 | San Luis Obispo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39288 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 20934SS | 0 | Finish No Earlier Than | Warning
39289 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 20933SS |  | 0 | Start No Earlier Than | Warning
39290 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 20936SS | 0 | Start No Earlier Than | Warning
39291 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 20935SS |  | 0 | Start No Earlier Than | Warning
39292 | San Luis Obispo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39293 | San Luis Obispo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39296 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39297 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39298 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39299 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 20945FS+10d | 0 | Start No Earlier Than | Warning
39300 | San Luis Obispo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 20944FS+10d |  | 0 | Start No Earlier Than | Warning
39302 | San Luis Obispo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 20949FS-1d | 1 | Start No Earlier Than | Warning
39303 | San Luis Obispo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39304 | San Luis Obispo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 20947FS-1d |  | 0.2 | Start No Earlier Than | Warning
39305 | San Luis Obispo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39306 | San Luis Obispo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 20952 | 1 | Start No Earlier Than | Warning
39307 | San Luis Obispo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 20951 |  | 0 | Start No Earlier Than | Warning
39308 | San Luis Obispo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39309 | San Luis Obispo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if appl | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  | 20955FS+19d | 1 | Finish No Earlier Than | Warning
39310 | San Luis Obispo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 20954FS+19d | 20956 | 0 | Start No Earlier Than | Warning
39312 | San Luis Obispo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39313 | San Luis Obispo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and o | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 20959 | 0 | Start No Earlier Than | Warning
39314 | San Luis Obispo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 20958 | 20960FS-1d | 0 | Start No Earlier Than | Warning
39315 | San Luis Obispo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 20959FS-1d |  | 0 | Finish No Earlier Than | Warning
39316 | San Luis Obispo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39317 | San Luis Obispo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39320 | San Luis Obispo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20966SS | 0 | Finish No Earlier Than | Warning
39321 | San Luis Obispo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20965SS |  | 0 | Finish No Earlier Than | Warning
39322 | San Luis Obispo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39323 | San Luis Obispo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39325 | San Luis Obispo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39326 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39328 | San Luis Obispo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 20974SS | 0 | Start No Earlier Than | Warning
39329 | San Luis Obispo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20973SS | 20975SS,20976 | 0 | Finish No Earlier Than | Warning
39331 | San Luis Obispo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20974,20975 |  | 0 | Finish No Earlier Than | Warning
39332 | San Luis Obispo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39334 | San Luis Obispo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 20980SS | 0 | Finish No Earlier Than | Warning
39335 | San Luis Obispo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 20979SS |  | 0 | Finish No Earlier Than | Warning
39336 | San Luis Obispo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39337 | San Luis Obispo PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM | 42 | 467d |  |  | 0 | Finish No Earlier Than | Warning
39339 | San Luis Obispo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 20985SS+18d | 0 | Start No Earlier Than | Warning
39340 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 20984SS+18d |  | 0 | Finish No Earlier Than | Warning
39342 | San Luis Obispo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 20988SS | 0 | Start No Earlier Than | Warning
39343 | San Luis Obispo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 20987SS |  | 0 | Finish No Earlier Than | Warning
39344 | San Luis Obispo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20990 | 0 | Start No Earlier Than | Warning
39345 | San Luis Obispo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 20989 |  | 0 | Finish No Earlier Than | Warning
39346 | San Luis Obispo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39348 | San Luis Obispo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 20994SS | 0 | Start No Earlier Than | Warning
39349 | San Luis Obispo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20993SS | 20995SS | 0 | Finish No Earlier Than | Warning
39350 | San Luis Obispo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20994SS | 20996SS | 0 | Finish No Earlier Than | Warning
39351 | San Luis Obispo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20995SS | 20997SS | 0 | Finish No Earlier Than | Warning
39352 | San Luis Obispo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20996SS | 20998SS | 0 | Finish No Earlier Than | Warning
39353 | San Luis Obispo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20997SS | 20999SS | 0 | Finish No Earlier Than | Warning
39354 | San Luis Obispo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20998SS | 21000SS | 0 | Finish No Earlier Than | Warning
39355 | San Luis Obispo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 20999SS | 21001SS | 0 | Finish No Earlier Than | Warning
39356 | San Luis Obispo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21000SS | 21002SS | 0 | Finish No Earlier Than | Warning
39357 | San Luis Obispo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21001SS | 21003SS | 0 | Finish No Earlier Than | Warning
39358 | San Luis Obispo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21002SS |  | 0 | Finish No Earlier Than | Warning
39359 | San Luis Obispo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39360 | San Luis Obispo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39362 | San Luis Obispo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21008SS,21012 | 0 | Start No Earlier Than | Warning
39363 | San Luis Obispo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21007SS |  | 0 | Start No Earlier Than | Warning
39364 | San Luis Obispo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39365 | San Luis Obispo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21018 | 0 | Start No Earlier Than | Warning
39366 | San Luis Obispo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21019 | 0 | Start No Earlier Than | Warning
39367 | San Luis Obispo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21007 |  | 0 | Start No Earlier Than | Warning
39368 | San Luis Obispo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39369 | San Luis Obispo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21015SS,21023SS+20d | 0 | Start No Earlier Than | Warning
39370 | San Luis Obispo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21014SS | 21016SS,21024SS+20d | 0 | Finish No Earlier Than | Warning
39371 | San Luis Obispo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21015SS | 21025SS+20d | 0 | Finish No Earlier Than | Warning
39372 | San Luis Obispo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39373 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21010 | 21019SS | 0 | Start No Earlier Than | Warning
39374 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21011,21018SS |  | 0 | Finish No Earlier Than | Warning
39375 | San Luis Obispo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21028FS+12d | 0 | Start No Earlier Than | Warning
39376 | San Luis Obispo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21022SS | 0 | Start No Earlier Than | Warning
39377 | San Luis Obispo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21021SS |  | 0 | Start No Earlier Than | Warning
39381 | San Luis Obispo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21028SS+44d | 0 | Start No Earlier Than | Warning
39382 | San Luis Obispo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39387 | San Mateo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39388 | San Mateo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39389 | San Mateo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39390 | San Mateo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39391 | San Mateo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39392 | San Mateo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39393 | San Mateo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39394 | San Mateo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39395 | San Mateo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39396 | San Mateo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39397 | San Mateo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39398 | San Mateo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39399 | San Mateo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39400 | San Mateo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39401 | San Mateo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39402 | San Mateo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39403 | San Mateo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39404 | San Mateo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39405 | San Mateo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39406 | San Mateo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39407 | San Mateo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39408 | San Mateo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39409 | San Mateo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39410 | San Mateo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39411 | San Mateo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39412 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21058SS | 0 | Start No Earlier Than | Warning
39413 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21057SS |  | 0 | Finish No Earlier Than | Warning
39414 | San Mateo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21060SS | 0 | Start No Earlier Than | Warning
39415 | San Mateo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21059SS |  | 0 | Start No Earlier Than | Warning
39416 | San Mateo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 21063SS,21062SS | 0 | Finish No Earlier Than | Warning
39419 | San Mateo PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
39420 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 21066SS | 0 | Start No Earlier Than | Warning
39422 | San Mateo PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
39423 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 21069SS | 0 | Start No Earlier Than | Warning
39424 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 21068SS |  | 0 | Start No Earlier Than | Warning
39425 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 21071SS | 0 | Start No Earlier Than | Warning
39427 | San Mateo PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
39428 | San Mateo PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
39431 | San Mateo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39432 | San Mateo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39433 | San Mateo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
39434 | San Mateo PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
39436 | San Mateo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21083FS-1d | 1 | Start No Earlier Than | Warning
39437 | San Mateo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39438 | San Mateo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 21081FS-1d |  | 0.2 | Start No Earlier Than | Warning
39439 | San Mateo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39440 | San Mateo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21086 | 1 | Start No Earlier Than | Warning
39441 | San Mateo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21085 |  | 0 | Start No Earlier Than | Warning
39442 | San Mateo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39443 | San Mateo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21089FS+19d | 0 | Finish No Earlier Than | Warning
39444 | San Mateo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21088FS+19d | 21090 | 0 | Start No Earlier Than | Warning
39446 | San Mateo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39447 | San Mateo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21093 | 0 | Start No Earlier Than | Warning
39448 | San Mateo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21092 | 21094FS-1d | 0 | Start No Earlier Than | Warning
39449 | San Mateo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21093FS-1d |  | 0 | Finish No Earlier Than | Warning
39450 | San Mateo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39451 | San Mateo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39454 | San Mateo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21100SS | 0 | Finish No Earlier Than | Warning
39455 | San Mateo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21099SS |  | 0 | Finish No Earlier Than | Warning
39456 | San Mateo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39457 | San Mateo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39459 | San Mateo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21105SS | 0 | Finish No Earlier Than | Warning
39460 | San Mateo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21104SS | 21119SS | 0 | Start No Earlier Than | Warning
39462 | San Mateo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39463 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39465 | San Mateo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21111SS | 0 | Start No Earlier Than | Warning
39466 | San Mateo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21110SS | 21112SS,21113 | 0 | Finish No Earlier Than | Warning
39468 | San Mateo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21111,21112 |  | 0 | Finish No Earlier Than | Warning
39469 | San Mateo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39471 | San Mateo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21117SS | 0 | Finish No Earlier Than | Warning
39472 | San Mateo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21116SS |  | 0 | Finish No Earlier Than | Warning
39473 | San Mateo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39474 | San Mateo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21105SS |  | 0 | Finish No Earlier Than | Warning
39476 | San Mateo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21122SS | 0 | Finish No Earlier Than | Warning
39477 | San Mateo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21121SS |  | 0 | Finish No Earlier Than | Warning
39479 | San Mateo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21125SS+18d | 0 | Start No Earlier Than | Warning
39480 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21124SS+18d |  | 0 | Finish No Earlier Than | Warning
39482 | San Mateo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21128SS | 0 | Start No Earlier Than | Warning
39483 | San Mateo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21127SS |  | 0 | Finish No Earlier Than | Warning
39484 | San Mateo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21130 | 0 | Start No Earlier Than | Warning
39485 | San Mateo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21129 |  | 0 | Finish No Earlier Than | Warning
39486 | San Mateo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39488 | San Mateo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21134SS | 0 | Start No Earlier Than | Warning
39489 | San Mateo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21133SS | 21135SS | 0 | Finish No Earlier Than | Warning
39490 | San Mateo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21134SS | 21136SS | 0 | Finish No Earlier Than | Warning
39491 | San Mateo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21135SS | 21137SS | 0 | Finish No Earlier Than | Warning
39492 | San Mateo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21136SS | 21138SS | 0 | Finish No Earlier Than | Warning
39493 | San Mateo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21137SS | 21139SS | 0 | Finish No Earlier Than | Warning
39494 | San Mateo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21138SS | 21140SS | 0 | Finish No Earlier Than | Warning
39495 | San Mateo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21139SS | 21141SS | 0 | Finish No Earlier Than | Warning
39496 | San Mateo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21140SS | 21142SS | 0 | Finish No Earlier Than | Warning
39497 | San Mateo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21141SS | 21143SS | 0 | Finish No Earlier Than | Warning
39498 | San Mateo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21142SS |  | 0 | Finish No Earlier Than | Warning
39499 | San Mateo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
39500 | San Mateo PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
39502 | San Mateo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21148SS,21152 | 0.2 | Start No Earlier Than | Warning
39503 | San Mateo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21147SS |  | 0 | Start No Earlier Than | Warning
39504 | San Mateo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39505 | San Mateo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 21158 | 0 | Start No Earlier Than | Warning
39506 | San Mateo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 21159 | 0 | Start No Earlier Than | Warning
39507 | San Mateo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21147 |  | 0 | Start No Earlier Than | Warning
39508 | San Mateo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39509 | San Mateo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 21155SS,21163SS+20d | 0 | Start No Earlier Than | Warning
39512 | San Mateo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39513 | San Mateo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 21150 | 21159SS | 0 | Start No Earlier Than | Warning
39515 | San Mateo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 21168FS+12d | 0 | Start No Earlier Than | Warning
39516 | San Mateo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21162SS | 0 | Start No Earlier Than | Warning
39517 | San Mateo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21161SS |  | 0 | Start No Earlier Than | Warning
39521 | San Mateo PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 21168SS+44d | 0 | Start No Earlier Than | Warning
39522 | San Mateo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39527 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39528 | Santa Barbara PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39529 | Santa Barbara PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39530 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39531 | Santa Barbara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39532 | Santa Barbara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39533 | Santa Barbara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39534 | Santa Barbara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39535 | Santa Barbara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39536 | Santa Barbara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39537 | Santa Barbara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39538 | Santa Barbara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39539 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39540 | Santa Barbara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39541 | Santa Barbara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39542 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39543 | Santa Barbara PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39544 | Santa Barbara PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39545 | Santa Barbara PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39546 | Santa Barbara PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39547 | Santa Barbara PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39548 | Santa Barbara PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39549 | Santa Barbara PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39550 | Santa Barbara PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39551 | Santa Barbara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
39552 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21198SS | 0 | Start No Earlier Than | Warning
39553 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21197SS |  | 0 | Finish No Earlier Than | Warning
39554 | Santa Barbara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21200SS | 0 | Start No Earlier Than | Warning
39555 | Santa Barbara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21199SS |  | 0 | Start No Earlier Than | Warning
39556 | Santa Barbara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39557 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21203SS | 0 | Finish No Earlier Than | Warning
39558 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21202SS |  | 0 | Finish No Earlier Than | Warning
39559 | Santa Barbara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39560 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21206SS | 0 | Finish No Earlier Than | Warning
39562 | Santa Barbara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39563 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21209SS | 0 | Finish No Earlier Than | Warning
39564 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21208SS |  | 0 | Start No Earlier Than | Warning
39565 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21211SS | 0 | Start No Earlier Than | Warning
39566 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21210SS |  | 0 | Start No Earlier Than | Warning
39567 | Santa Barbara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39568 | Santa Barbara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39571 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39572 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39573 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39574 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21220FS+10d | 0 | Start No Earlier Than | Warning
39575 | Santa Barbara PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21219FS+10d |  | 0 | Start No Earlier Than | Warning
39577 | Santa Barbara PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21224FS-1d | 1 | Start No Earlier Than | Warning
39578 | Santa Barbara PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39579 | Santa Barbara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21222FS-1d |  | 0 | Start No Earlier Than | Warning
39580 | Santa Barbara PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39581 | Santa Barbara PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21227 | 1 | Start No Earlier Than | Warning
39582 | Santa Barbara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21226 |  | 0 | Start No Earlier Than | Warning
39583 | Santa Barbara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39584 | Santa Barbara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21230FS+19d | 0 | Finish No Earlier Than | Warning
39585 | Santa Barbara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21229FS+19d | 21231 | 0 | Start No Earlier Than | Warning
39587 | Santa Barbara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39588 | Santa Barbara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21234 | 0 | Start No Earlier Than | Warning
39589 | Santa Barbara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21233 | 21235FS-1d | 0 | Start No Earlier Than | Warning
39590 | Santa Barbara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21234FS-1d |  | 0 | Finish No Earlier Than | Warning
39591 | Santa Barbara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39592 | Santa Barbara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39595 | Santa Barbara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21241SS | 0 | Finish No Earlier Than | Warning
39596 | Santa Barbara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21240SS |  | 0 | Finish No Earlier Than | Warning
39597 | Santa Barbara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39598 | Santa Barbara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39600 | Santa Barbara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39601 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39603 | Santa Barbara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 424d |  | 21249SS | 0.6 | Start No Earlier Than | Warning
39604 | Santa Barbara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21248SS | 21250SS,21251 | 0 | Finish No Earlier Than | Warning
39606 | Santa Barbara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21249,21250 |  | 0 | Finish No Earlier Than | Warning
39607 | Santa Barbara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39609 | Santa Barbara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21255SS | 0 | Finish No Earlier Than | Warning
39610 | Santa Barbara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21254SS |  | 0 | Finish No Earlier Than | Warning
39611 | Santa Barbara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39612 | Santa Barbara PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM | 42 | 467d |  |  | 0 | Finish No Earlier Than | Warning
39614 | Santa Barbara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21260SS+18d | 0 | Start No Earlier Than | Warning
39615 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21259SS+18d |  | 0 | Finish No Earlier Than | Warning
39617 | Santa Barbara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 424d |  | 21263SS | 0.6 | Start No Earlier Than | Warning
39618 | Santa Barbara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21262SS |  | 0 | Finish No Earlier Than | Warning
39619 | Santa Barbara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21265 | 0 | Start No Earlier Than | Warning
39620 | Santa Barbara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21264 |  | 0 | Finish No Earlier Than | Warning
39621 | Santa Barbara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39623 | Santa Barbara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21269SS | 0 | Start No Earlier Than | Warning
39624 | Santa Barbara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21268SS | 21270SS | 0 | Finish No Earlier Than | Warning
39625 | Santa Barbara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21269SS | 21271SS | 0 | Finish No Earlier Than | Warning
39626 | Santa Barbara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21270SS | 21272SS | 0 | Finish No Earlier Than | Warning
39627 | Santa Barbara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21271SS | 21273SS | 0 | Finish No Earlier Than | Warning
39628 | Santa Barbara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21272SS | 21274SS | 0 | Finish No Earlier Than | Warning
39629 | Santa Barbara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21273SS | 21275SS | 0 | Finish No Earlier Than | Warning
39630 | Santa Barbara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21274SS | 21276SS | 0 | Finish No Earlier Than | Warning
39631 | Santa Barbara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21275SS | 21277SS | 0 | Finish No Earlier Than | Warning
39632 | Santa Barbara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21276SS | 21278SS | 0 | Finish No Earlier Than | Warning
39633 | Santa Barbara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21277SS |  | 0 | Finish No Earlier Than | Warning
39634 | Santa Barbara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39635 | Santa Barbara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39637 | Santa Barbara PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21283SS,21287 | 0 | Start No Earlier Than | Warning
39638 | Santa Barbara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21282SS |  | 0 | Start No Earlier Than | Warning
39639 | Santa Barbara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39640 | Santa Barbara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21293 | 0 | Start No Earlier Than | Warning
39641 | Santa Barbara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21294 | 0 | Start No Earlier Than | Warning
39642 | Santa Barbara PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21282 |  | 0 | Start No Earlier Than | Warning
39643 | Santa Barbara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39644 | Santa Barbara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21290SS,21298SS+20d | 0 | Start No Earlier Than | Warning
39645 | Santa Barbara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21289SS | 21291SS,21299SS+20d | 0 | Finish No Earlier Than | Warning
39646 | Santa Barbara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21290SS | 21300SS+20d | 0 | Finish No Earlier Than | Warning
39647 | Santa Barbara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39648 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21285 | 21294SS | 0 | Start No Earlier Than | Warning
39649 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21286,21293SS |  | 0 | Finish No Earlier Than | Warning
39650 | Santa Barbara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21303FS+12d | 0 | Start No Earlier Than | Warning
39651 | Santa Barbara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21297SS | 0 | Start No Earlier Than | Warning
39652 | Santa Barbara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21296SS |  | 0 | Start No Earlier Than | Warning
39656 | Santa Barbara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21303SS+44d | 0 | Start No Earlier Than | Warning
39657 | Santa Barbara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39662 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39663 | Santa Clara PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39664 | Santa Clara PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39665 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39666 | Santa Clara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39667 | Santa Clara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39668 | Santa Clara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39669 | Santa Clara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39670 | Santa Clara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39671 | Santa Clara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39672 | Santa Clara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39673 | Santa Clara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39674 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39675 | Santa Clara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39676 | Santa Clara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39677 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39678 | Santa Clara PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39679 | Santa Clara PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39680 | Santa Clara PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39681 | Santa Clara PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39682 | Santa Clara PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39683 | Santa Clara PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39684 | Santa Clara PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39685 | Santa Clara PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39686 | Santa Clara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39687 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21333SS | 0 | Start No Earlier Than | Warning
39688 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21332SS |  | 0 | Finish No Earlier Than | Warning
39689 | Santa Clara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21335SS | 0 | Start No Earlier Than | Warning
39690 | Santa Clara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21334SS |  | 0 | Start No Earlier Than | Warning
39691 | Santa Clara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39692 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21338SS | 0 | Finish No Earlier Than | Warning
39693 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21337SS |  | 0 | Finish No Earlier Than | Warning
39694 | Santa Clara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39695 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21341SS | 0 | Finish No Earlier Than | Warning
39697 | Santa Clara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39698 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21344SS | 0 | Finish No Earlier Than | Warning
39699 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21343SS |  | 0 | Start No Earlier Than | Warning
39700 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21346SS | 0 | Start No Earlier Than | Warning
39701 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21345SS |  | 0 | Start No Earlier Than | Warning
39702 | Santa Clara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39703 | Santa Clara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39706 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39707 | Santa Clara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39708 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39709 | Santa Clara PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21355FS+10d | 0 | Start No Earlier Than | Warning
39710 | Santa Clara PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21354FS+10d |  | 0 | Start No Earlier Than | Warning
39712 | Santa Clara PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21359FS-1d | 1 | Start No Earlier Than | Warning
39713 | Santa Clara PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39714 | Santa Clara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21357FS-1d |  | 0.2 | Start No Earlier Than | Warning
39715 | Santa Clara PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39716 | Santa Clara PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21362 | 1 | Start No Earlier Than | Warning
39717 | Santa Clara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21361 |  | 0 | Start No Earlier Than | Warning
39718 | Santa Clara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39719 | Santa Clara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21365FS+19d | 0 | Finish No Earlier Than | Warning
39720 | Santa Clara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21364FS+19d | 21366 | 0 | Start No Earlier Than | Warning
39722 | Santa Clara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39723 | Santa Clara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21369 | 0 | Start No Earlier Than | Warning
39724 | Santa Clara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21368 | 21370FS-1d | 0 | Start No Earlier Than | Warning
39725 | Santa Clara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21369FS-1d |  | 0 | Finish No Earlier Than | Warning
39726 | Santa Clara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39727 | Santa Clara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39730 | Santa Clara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21376SS | 0 | Finish No Earlier Than | Warning
39731 | Santa Clara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21375SS |  | 0 | Finish No Earlier Than | Warning
39732 | Santa Clara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39733 | Santa Clara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39735 | Santa Clara PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21381SS | 0 | Finish No Earlier Than | Warning
39736 | Santa Clara PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21380SS | 21395SS | 0 | Start No Earlier Than | Warning
39738 | Santa Clara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39739 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39741 | Santa Clara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21387SS | 0 | Start No Earlier Than | Warning
39742 | Santa Clara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21386SS | 21388SS,21389 | 0 | Finish No Earlier Than | Warning
39744 | Santa Clara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21387,21388 |  | 0 | Finish No Earlier Than | Warning
39745 | Santa Clara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39747 | Santa Clara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21393SS | 0 | Finish No Earlier Than | Warning
39748 | Santa Clara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21392SS |  | 0 | Finish No Earlier Than | Warning
39749 | Santa Clara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39750 | Santa Clara PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21381SS |  | 0 | Finish No Earlier Than | Warning
39752 | Santa Clara PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21398SS | 0 | Finish No Earlier Than | Warning
39753 | Santa Clara PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21397SS |  | 0 | Finish No Earlier Than | Warning
39755 | Santa Clara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21401SS+18d | 0 | Start No Earlier Than | Warning
39756 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21400SS+18d |  | 0 | Finish No Earlier Than | Warning
39758 | Santa Clara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21404SS | 0 | Start No Earlier Than | Warning
39759 | Santa Clara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21403SS |  | 0 | Finish No Earlier Than | Warning
39760 | Santa Clara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21406 | 0 | Start No Earlier Than | Warning
39761 | Santa Clara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21405 |  | 0 | Finish No Earlier Than | Warning
39762 | Santa Clara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39764 | Santa Clara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21410SS | 0 | Start No Earlier Than | Warning
39765 | Santa Clara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21409SS | 21411SS | 0 | Finish No Earlier Than | Warning
39766 | Santa Clara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21410SS | 21412SS | 0 | Finish No Earlier Than | Warning
39767 | Santa Clara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21411SS | 21413SS | 0 | Finish No Earlier Than | Warning
39768 | Santa Clara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21412SS | 21414SS | 0 | Finish No Earlier Than | Warning
39769 | Santa Clara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21413SS | 21415SS | 0 | Finish No Earlier Than | Warning
39770 | Santa Clara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21414SS | 21416SS | 0 | Finish No Earlier Than | Warning
39771 | Santa Clara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21415SS | 21417SS | 0 | Finish No Earlier Than | Warning
39772 | Santa Clara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21416SS | 21418SS | 0 | Finish No Earlier Than | Warning
39773 | Santa Clara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21417SS | 21419SS | 0 | Finish No Earlier Than | Warning
39774 | Santa Clara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21418SS |  | 0 | Finish No Earlier Than | Warning
39775 | Santa Clara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39776 | Santa Clara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39778 | Santa Clara PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21424SS,21428 | 0 | Start No Earlier Than | Warning
39779 | Santa Clara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21423SS |  | 0 | Start No Earlier Than | Warning
39780 | Santa Clara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39781 | Santa Clara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21434 | 0 | Start No Earlier Than | Warning
39782 | Santa Clara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21435 | 0 | Start No Earlier Than | Warning
39783 | Santa Clara PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21423 |  | 0 | Start No Earlier Than | Warning
39784 | Santa Clara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39785 | Santa Clara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21431SS,21439SS+20d | 0 | Start No Earlier Than | Warning
39786 | Santa Clara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21430SS | 21432SS,21440SS+20d | 0 | Finish No Earlier Than | Warning
39787 | Santa Clara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21431SS | 21441SS+20d | 0 | Finish No Earlier Than | Warning
39788 | Santa Clara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39789 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21426 | 21435SS | 0 | Start No Earlier Than | Warning
39790 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21427,21434SS |  | 0 | Finish No Earlier Than | Warning
39791 | Santa Clara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21444FS+12d | 0 | Start No Earlier Than | Warning
39792 | Santa Clara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21438SS | 0 | Start No Earlier Than | Warning
39793 | Santa Clara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21437SS |  | 0 | Start No Earlier Than | Warning
39797 | Santa Clara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21444SS+44d | 0 | Start No Earlier Than | Warning
39798 | Santa Clara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39803 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39804 | Santa Cruz PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39805 | Santa Cruz PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39806 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
39807 | Santa Cruz PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39808 | Santa Cruz PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39809 | Santa Cruz PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39810 | Santa Cruz PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39811 | Santa Cruz PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39812 | Santa Cruz PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39813 | Santa Cruz PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39814 | Santa Cruz PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39815 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39816 | Santa Cruz PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39817 | Santa Cruz PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39818 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39819 | Santa Cruz PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39820 | Santa Cruz PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39821 | Santa Cruz PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39822 | Santa Cruz PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39823 | Santa Cruz PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39824 | Santa Cruz PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39825 | Santa Cruz PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39826 | Santa Cruz PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39827 | Santa Cruz PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39828 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21474SS | 0 | Start No Earlier Than | Warning
39829 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21473SS |  | 0 | Finish No Earlier Than | Warning
39830 | Santa Cruz PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21476SS | 0 | Start No Earlier Than | Warning
39831 | Santa Cruz PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21475SS |  | 0 | Start No Earlier Than | Warning
39832 | Santa Cruz PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39833 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21479SS | 0 | Finish No Earlier Than | Warning
39834 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21478SS |  | 0 | Finish No Earlier Than | Warning
39835 | Santa Cruz PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39836 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21482SS | 0 | Finish No Earlier Than | Warning
39838 | Santa Cruz PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39839 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21485SS | 0 | Finish No Earlier Than | Warning
39840 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21484SS |  | 0 | Start No Earlier Than | Warning
39841 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21487SS | 0 | Start No Earlier Than | Warning
39842 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21486SS |  | 0 | Start No Earlier Than | Warning
39843 | Santa Cruz PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39844 | Santa Cruz PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39847 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39848 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39849 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39850 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21496FS+10d | 0 | Start No Earlier Than | Warning
39851 | Santa Cruz PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21495FS+10d |  | 0 | Start No Earlier Than | Warning
39853 | Santa Cruz PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21500FS-1d | 1 | Start No Earlier Than | Warning
39854 | Santa Cruz PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39855 | Santa Cruz PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21498FS-1d |  | 0.2 | Start No Earlier Than | Warning
39856 | Santa Cruz PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39857 | Santa Cruz PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21503 | 1 | Start No Earlier Than | Warning
39858 | Santa Cruz PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21502 |  | 0 | Start No Earlier Than | Warning
39859 | Santa Cruz PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39860 | Santa Cruz PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21506FS+19d | 0 | Finish No Earlier Than | Warning
39861 | Santa Cruz PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21505FS+19d | 21507 | 0 | Start No Earlier Than | Warning
39863 | Santa Cruz PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39864 | Santa Cruz PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21510 | 0 | Start No Earlier Than | Warning
39865 | Santa Cruz PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21509 | 21511FS-1d | 0 | Start No Earlier Than | Warning
39866 | Santa Cruz PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21510FS-1d |  | 0 | Finish No Earlier Than | Warning
39867 | Santa Cruz PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39868 | Santa Cruz PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39871 | Santa Cruz PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21517SS | 0 | Start No Earlier Than | Warning
39872 | Santa Cruz PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21516SS | 21518SS | 0 | Finish No Earlier Than | Warning
39873 | Santa Cruz PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21517SS | 21519SS | 0 | Finish No Earlier Than | Warning
39874 | Santa Cruz PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21518SS | 21520SS | 0 | Finish No Earlier Than | Warning
39875 | Santa Cruz PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21519SS | 21521SS | 0 | Finish No Earlier Than | Warning
39876 | Santa Cruz PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21520SS | 21522SS | 0 | Finish No Earlier Than | Warning
39877 | Santa Cruz PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21521SS | 21523SS | 0 | Finish No Earlier Than | Warning
39878 | Santa Cruz PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21522SS | 21524SS | 0 | Finish No Earlier Than | Warning
39879 | Santa Cruz PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21523SS | 21525SS | 0 | Finish No Earlier Than | Warning
39880 | Santa Cruz PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21524SS | 21526SS | 0 | Finish No Earlier Than | Warning
39881 | Santa Cruz PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21525SS |  | 0 | Finish No Earlier Than | Warning
39882 | Santa Cruz PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
39883 | Santa Cruz PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
39885 | Santa Cruz PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21531SS,21535 | 0 | Start No Earlier Than | Warning
39886 | Santa Cruz PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21530SS |  | 0 | Start No Earlier Than | Warning
39887 | Santa Cruz PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
39888 | Santa Cruz PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21541 | 0 | Start No Earlier Than | Warning
39889 | Santa Cruz PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21542 | 0 | Start No Earlier Than | Warning
39890 | Santa Cruz PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21530 |  | 0 | Start No Earlier Than | Warning
39891 | Santa Cruz PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
39892 | Santa Cruz PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21538SS,21546SS+20d | 0 | Start No Earlier Than | Warning
39893 | Santa Cruz PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21537SS | 21539SS,21547SS+20d | 0 | Finish No Earlier Than | Warning
39894 | Santa Cruz PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21538SS | 21548SS+20d | 0 | Finish No Earlier Than | Warning
39895 | Santa Cruz PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
39896 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21533 | 21542SS | 0 | Start No Earlier Than | Warning
39897 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21534,21541SS |  | 0 | Finish No Earlier Than | Warning
39898 | Santa Cruz PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21551FS+12d | 0 | Start No Earlier Than | Warning
39899 | Santa Cruz PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21545SS | 0 | Start No Earlier Than | Warning
39900 | Santa Cruz PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21544SS |  | 0 | Start No Earlier Than | Warning
39904 | Santa Cruz PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21551SS+44d | 0 | Start No Earlier Than | Warning
39905 | Santa Cruz PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
39910 | Shasta PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39911 | Shasta PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39912 | Shasta PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
39913 | Shasta PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
39914 | Shasta PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
39915 | Shasta PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
39916 | Shasta PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
39917 | Shasta PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
39918 | Shasta PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
39919 | Shasta PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
39920 | Shasta PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
39921 | Shasta PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
39922 | Shasta PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
39923 | Shasta PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
39924 | Shasta PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39925 | Shasta PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
39926 | Shasta PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39927 | Shasta PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39928 | Shasta PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39929 | Shasta PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39930 | Shasta PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39931 | Shasta PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39932 | Shasta PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39933 | Shasta PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39934 | Shasta PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
39935 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21581SS | 0 | Start No Earlier Than | Warning
39936 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21580SS |  | 0 | Finish No Earlier Than | Warning
39937 | Shasta PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21583SS | 0 | Start No Earlier Than | Warning
39938 | Shasta PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21582SS |  | 0 | Start No Earlier Than | Warning
39939 | Shasta PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
39940 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21586SS | 0 | Finish No Earlier Than | Warning
39941 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21585SS |  | 0 | Finish No Earlier Than | Warning
39942 | Shasta PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
39943 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21589SS | 0 | Finish No Earlier Than | Warning
39945 | Shasta PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
39946 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21592SS | 0 | Finish No Earlier Than | Warning
39947 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21591SS |  | 0 | Start No Earlier Than | Warning
39948 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21594SS | 0 | Start No Earlier Than | Warning
39949 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21593SS |  | 0 | Start No Earlier Than | Warning
39950 | Shasta PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
39951 | Shasta PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
39954 | Shasta PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
39955 | Shasta PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
39956 | Shasta PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
39957 | Shasta PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21603FS+10d | 0 | Start No Earlier Than | Warning
39958 | Shasta PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21602FS+10d |  | 0 | Start No Earlier Than | Warning
39960 | Shasta PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21607FS-1d | 1 | Start No Earlier Than | Warning
39961 | Shasta PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
39962 | Shasta PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21605FS-1d |  | 0.2 | Start No Earlier Than | Warning
39963 | Shasta PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
39964 | Shasta PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21610 | 1 | Start No Earlier Than | Warning
39965 | Shasta PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21609 |  | 0.2 | Start No Earlier Than | Warning
39966 | Shasta PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39967 | Shasta PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM | 22 | 0d |  | 21613FS+19d | 1 | Finish No Earlier Than | Warning
39968 | Shasta PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21612FS+19d | 21614 | 0 | Start No Earlier Than | Warning
39970 | Shasta PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
39971 | Shasta PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21617 | 0 | Start No Earlier Than | Warning
39972 | Shasta PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21616 | 21618FS-1d | 0 | Start No Earlier Than | Warning
39973 | Shasta PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21617FS-1d |  | 0 | Finish No Earlier Than | Warning
39974 | Shasta PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
39975 | Shasta PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
39978 | Shasta PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21624SS | 0 | Finish No Earlier Than | Warning
39979 | Shasta PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21623SS |  | 0 | Finish No Earlier Than | Warning
39980 | Shasta PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39981 | Shasta PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
39983 | Shasta PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21629SS | 0 | Finish No Earlier Than | Warning
39984 | Shasta PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21628SS | 21643SS | 0 | Start No Earlier Than | Warning
39986 | Shasta PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
39987 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
39989 | Shasta PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21635SS | 0 | Start No Earlier Than | Warning
39990 | Shasta PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21634SS | 21636SS,21637 | 0 | Finish No Earlier Than | Warning
39992 | Shasta PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21635,21636 |  | 0 | Finish No Earlier Than | Warning
39993 | Shasta PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
39995 | Shasta PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21641SS | 0 | Finish No Earlier Than | Warning
39996 | Shasta PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21640SS |  | 0 | Finish No Earlier Than | Warning
39997 | Shasta PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
39998 | Shasta PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21629SS |  | 0 | Finish No Earlier Than | Warning
40000 | Shasta PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21646SS | 0 | Finish No Earlier Than | Warning
40001 | Shasta PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21645SS |  | 0 | Finish No Earlier Than | Warning
40003 | Shasta PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21649SS+18d | 0 | Start No Earlier Than | Warning
40004 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21648SS+18d |  | 0 | Finish No Earlier Than | Warning
40006 | Shasta PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21652SS | 0 | Start No Earlier Than | Warning
40007 | Shasta PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21651SS |  | 0 | Finish No Earlier Than | Warning
40008 | Shasta PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21654 | 0 | Start No Earlier Than | Warning
40009 | Shasta PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21653 |  | 0 | Finish No Earlier Than | Warning
40010 | Shasta PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40012 | Shasta PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21658SS | 0 | Start No Earlier Than | Warning
40013 | Shasta PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21657SS | 21659SS | 0 | Finish No Earlier Than | Warning
40014 | Shasta PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21658SS | 21660SS | 0 | Finish No Earlier Than | Warning
40015 | Shasta PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21659SS | 21661SS | 0 | Finish No Earlier Than | Warning
40016 | Shasta PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21660SS | 21662SS | 0 | Finish No Earlier Than | Warning
40017 | Shasta PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21661SS | 21663SS | 0 | Finish No Earlier Than | Warning
40018 | Shasta PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21662SS | 21664SS | 0 | Finish No Earlier Than | Warning
40019 | Shasta PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21663SS | 21665SS | 0 | Finish No Earlier Than | Warning
40020 | Shasta PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21664SS | 21666SS | 0 | Finish No Earlier Than | Warning
40021 | Shasta PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21665SS | 21667SS | 0 | Finish No Earlier Than | Warning
40022 | Shasta PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21666SS |  | 0 | Finish No Earlier Than | Warning
40023 | Shasta PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40024 | Shasta PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40026 | Shasta PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21672SS,21676 | 0 | Start No Earlier Than | Warning
40027 | Shasta PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21671SS |  | 0 | Start No Earlier Than | Warning
40028 | Shasta PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40029 | Shasta PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21682 | 0 | Start No Earlier Than | Warning
40030 | Shasta PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21683 | 0 | Start No Earlier Than | Warning
40031 | Shasta PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21671 |  | 0 | Start No Earlier Than | Warning
40032 | Shasta PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40033 | Shasta PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21679SS,21687SS+20d | 0 | Start No Earlier Than | Warning
40034 | Shasta PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21678SS | 21680SS,21688SS+20d | 0 | Finish No Earlier Than | Warning
40035 | Shasta PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21679SS | 21689SS+20d | 0 | Finish No Earlier Than | Warning
40036 | Shasta PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40037 | Shasta PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21674 | 21683SS | 0 | Start No Earlier Than | Warning
40038 | Shasta PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21675,21682SS |  | 0 | Finish No Earlier Than | Warning
40039 | Shasta PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21692FS+12d | 0 | Start No Earlier Than | Warning
40040 | Shasta PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21686SS | 0 | Start No Earlier Than | Warning
40041 | Shasta PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21685SS |  | 0 | Start No Earlier Than | Warning
40045 | Shasta PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21692SS+44d | 0 | Start No Earlier Than | Warning
40046 | Shasta PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40051 | Sierra PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40052 | Sierra PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40053 | Sierra PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40054 | Sierra PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40055 | Sierra PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40056 | Sierra PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40057 | Sierra PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40058 | Sierra PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40059 | Sierra PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40060 | Sierra PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40061 | Sierra PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40062 | Sierra PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40063 | Sierra PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40064 | Sierra PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40065 | Sierra PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40066 | Sierra PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40067 | Sierra PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40068 | Sierra PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40069 | Sierra PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40070 | Sierra PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40071 | Sierra PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40072 | Sierra PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40073 | Sierra PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40074 | Sierra PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40075 | Sierra PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
40076 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21722SS | 0 | Start No Earlier Than | Warning
40077 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21721SS |  | 0 | Finish No Earlier Than | Warning
40078 | Sierra PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21724SS | 0 | Start No Earlier Than | Warning
40079 | Sierra PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21723SS |  | 0 | Start No Earlier Than | Warning
40080 | Sierra PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40081 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21727SS | 0 | Finish No Earlier Than | Warning
40082 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21726SS |  | 0 | Finish No Earlier Than | Warning
40083 | Sierra PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40084 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21730SS | 0 | Finish No Earlier Than | Warning
40086 | Sierra PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40087 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21733SS | 0 | Finish No Earlier Than | Warning
40088 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21732SS |  | 0 | Start No Earlier Than | Warning
40089 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21735SS | 0 | Start No Earlier Than | Warning
40090 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21734SS |  | 0 | Start No Earlier Than | Warning
40091 | Sierra PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40092 | Sierra PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40095 | Sierra PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40096 | Sierra PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40097 | Sierra PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40098 | Sierra PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21744FS+10d | 0 | Start No Earlier Than | Warning
40099 | Sierra PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21743FS+10d |  | 0 | Start No Earlier Than | Warning
40101 | Sierra PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21748FS-1d | 1 | Start No Earlier Than | Warning
40102 | Sierra PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40103 | Sierra PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21746FS-1d |  | 0.2 | Start No Earlier Than | Warning
40104 | Sierra PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40105 | Sierra PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21751 | 1 | Start No Earlier Than | Warning
40106 | Sierra PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21750 |  | 0 | Start No Earlier Than | Warning
40107 | Sierra PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40108 | Sierra PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21754FS+19d | 0 | Finish No Earlier Than | Warning
40109 | Sierra PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21753FS+19d | 21755 | 0 | Start No Earlier Than | Warning
40111 | Sierra PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40112 | Sierra PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21758 | 0 | Start No Earlier Than | Warning
40113 | Sierra PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21757 | 21759FS-1d | 0 | Start No Earlier Than | Warning
40114 | Sierra PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21758FS-1d |  | 0 | Finish No Earlier Than | Warning
40115 | Sierra PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40116 | Sierra PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40119 | Sierra PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21765SS | 0 | Finish No Earlier Than | Warning
40120 | Sierra PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21764SS |  | 0 | Finish No Earlier Than | Warning
40121 | Sierra PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40122 | Sierra PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40124 | Sierra PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21770SS | 0 | Finish No Earlier Than | Warning
40125 | Sierra PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21769SS | 21784SS | 0 | Start No Earlier Than | Warning
40127 | Sierra PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40128 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40130 | Sierra PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21776SS | 0 | Start No Earlier Than | Warning
40131 | Sierra PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21775SS | 21777SS,21778 | 0 | Finish No Earlier Than | Warning
40133 | Sierra PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21776,21777 |  | 0 | Finish No Earlier Than | Warning
40134 | Sierra PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40136 | Sierra PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21782SS | 0 | Finish No Earlier Than | Warning
40137 | Sierra PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21781SS |  | 0 | Finish No Earlier Than | Warning
40138 | Sierra PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40139 | Sierra PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21770SS |  | 0 | Finish No Earlier Than | Warning
40141 | Sierra PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21787SS | 0 | Finish No Earlier Than | Warning
40142 | Sierra PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21786SS |  | 0 | Finish No Earlier Than | Warning
40144 | Sierra PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 18.8d |  | 21790SS+18d | 0 | Start No Earlier Than | Warning
40145 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21789SS+18d |  | 0.2 | Finish No Earlier Than | Warning
40147 | Sierra PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21793SS | 0 | Start No Earlier Than | Warning
40148 | Sierra PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21792SS |  | 0 | Finish No Earlier Than | Warning
40149 | Sierra PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 3.4d |  | 21795 | 0 | Start No Earlier Than | Warning
40150 | Sierra PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21794 |  | 0.2 | Finish No Earlier Than | Warning
40151 | Sierra PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40153 | Sierra PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21799SS | 0 | Start No Earlier Than | Warning
40154 | Sierra PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21798SS | 21800SS | 0 | Finish No Earlier Than | Warning
40155 | Sierra PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21799SS | 21801SS | 0 | Finish No Earlier Than | Warning
40156 | Sierra PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21800SS | 21802SS | 0 | Finish No Earlier Than | Warning
40157 | Sierra PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21801SS | 21803SS | 0 | Finish No Earlier Than | Warning
40158 | Sierra PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21802SS | 21804SS | 0 | Finish No Earlier Than | Warning
40159 | Sierra PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21803SS | 21805SS | 0 | Finish No Earlier Than | Warning
40160 | Sierra PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21804SS | 21806SS | 0 | Finish No Earlier Than | Warning
40161 | Sierra PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21805SS | 21807SS | 0 | Finish No Earlier Than | Warning
40162 | Sierra PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21806SS | 21808SS | 0 | Finish No Earlier Than | Warning
40163 | Sierra PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21807SS |  | 0 | Finish No Earlier Than | Warning
40164 | Sierra PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40165 | Sierra PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40167 | Sierra PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21813SS,21817 | 0 | Start No Earlier Than | Warning
40168 | Sierra PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21812SS |  | 0 | Start No Earlier Than | Warning
40169 | Sierra PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40170 | Sierra PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21823 | 0 | Start No Earlier Than | Warning
40171 | Sierra PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21824 | 0 | Start No Earlier Than | Warning
40172 | Sierra PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21812 |  | 0 | Start No Earlier Than | Warning
40173 | Sierra PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40174 | Sierra PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21820SS,21828SS+20d | 0 | Start No Earlier Than | Warning
40175 | Sierra PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21819SS | 21821SS,21829SS+20d | 0 | Finish No Earlier Than | Warning
40176 | Sierra PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21820SS | 21830SS+20d | 0 | Finish No Earlier Than | Warning
40177 | Sierra PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40178 | Sierra PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21815 | 21824SS | 0 | Start No Earlier Than | Warning
40179 | Sierra PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21816,21823SS |  | 0 | Finish No Earlier Than | Warning
40180 | Sierra PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21833FS+12d | 0 | Start No Earlier Than | Warning
40181 | Sierra PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21827SS | 0 | Start No Earlier Than | Warning
40182 | Sierra PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21826SS |  | 0 | Start No Earlier Than | Warning
40186 | Sierra PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21833SS+44d | 0 | Start No Earlier Than | Warning
40187 | Sierra PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40192 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40193 | Siskiyou PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40194 | Siskiyou PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40195 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40196 | Siskiyou PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40197 | Siskiyou PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40198 | Siskiyou PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40199 | Siskiyou PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40200 | Siskiyou PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40201 | Siskiyou PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40202 | Siskiyou PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40203 | Siskiyou PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40204 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40205 | Siskiyou PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40206 | Siskiyou PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40207 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40208 | Siskiyou PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40209 | Siskiyou PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40210 | Siskiyou PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40211 | Siskiyou PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40212 | Siskiyou PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40213 | Siskiyou PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40214 | Siskiyou PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40215 | Siskiyou PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40216 | Siskiyou PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
40217 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 21863SS | 0 | Start No Earlier Than | Warning
40218 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 21862SS |  | 0 | Finish No Earlier Than | Warning
40219 | Siskiyou PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 21865SS | 0 | Start No Earlier Than | Warning
40220 | Siskiyou PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 21864SS |  | 0 | Start No Earlier Than | Warning
40221 | Siskiyou PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40222 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 21868SS | 0 | Finish No Earlier Than | Warning
40223 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 21867SS |  | 0 | Finish No Earlier Than | Warning
40224 | Siskiyou PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40225 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 21871SS | 0 | Finish No Earlier Than | Warning
40227 | Siskiyou PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40228 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 21874SS | 0 | Finish No Earlier Than | Warning
40229 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 21873SS |  | 0 | Start No Earlier Than | Warning
40230 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 21876SS | 0 | Start No Earlier Than | Warning
40231 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 21875SS |  | 0 | Start No Earlier Than | Warning
40232 | Siskiyou PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40233 | Siskiyou PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40236 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40237 | Siskiyou PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40238 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40239 | Siskiyou PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 21885FS+10d | 0 | Start No Earlier Than | Warning
40240 | Siskiyou PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 21884FS+10d |  | 0 | Start No Earlier Than | Warning
40242 | Siskiyou PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 21889FS-1d | 1 | Start No Earlier Than | Warning
40243 | Siskiyou PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40244 | Siskiyou PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 21887FS-1d |  | 0.2 | Start No Earlier Than | Warning
40245 | Siskiyou PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40246 | Siskiyou PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 21892 | 1 | Start No Earlier Than | Warning
40247 | Siskiyou PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21891 |  | 0 | Start No Earlier Than | Warning
40248 | Siskiyou PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40249 | Siskiyou PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 21895FS+19d | 0 | Finish No Earlier Than | Warning
40250 | Siskiyou PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 21894FS+19d | 21896 | 0 | Start No Earlier Than | Warning
40252 | Siskiyou PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40253 | Siskiyou PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 21899 | 0 | Start No Earlier Than | Warning
40254 | Siskiyou PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 21898 | 21900FS-1d | 0 | Start No Earlier Than | Warning
40255 | Siskiyou PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 21899FS-1d |  | 0 | Finish No Earlier Than | Warning
40256 | Siskiyou PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40257 | Siskiyou PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40260 | Siskiyou PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21906SS | 0 | Finish No Earlier Than | Warning
40261 | Siskiyou PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21905SS |  | 0 | Finish No Earlier Than | Warning
40262 | Siskiyou PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40263 | Siskiyou PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40265 | Siskiyou PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21911SS | 0 | Finish No Earlier Than | Warning
40266 | Siskiyou PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21910SS | 21925SS | 0 | Start No Earlier Than | Warning
40268 | Siskiyou PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40269 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40271 | Siskiyou PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 21917SS | 0 | Start No Earlier Than | Warning
40272 | Siskiyou PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21916SS | 21918SS,21919 | 0 | Finish No Earlier Than | Warning
40274 | Siskiyou PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21917,21918 |  | 0 | Finish No Earlier Than | Warning
40275 | Siskiyou PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40277 | Siskiyou PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21923SS | 0 | Finish No Earlier Than | Warning
40278 | Siskiyou PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 21922SS |  | 0 | Finish No Earlier Than | Warning
40279 | Siskiyou PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40280 | Siskiyou PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21911SS |  | 0 | Finish No Earlier Than | Warning
40282 | Siskiyou PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 21928SS | 0 | Finish No Earlier Than | Warning
40283 | Siskiyou PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 21927SS |  | 0 | Finish No Earlier Than | Warning
40285 | Siskiyou PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 21931SS+18d | 0 | Start No Earlier Than | Warning
40286 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 21930SS+18d |  | 0 | Finish No Earlier Than | Warning
40288 | Siskiyou PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 21934SS | 0 | Start No Earlier Than | Warning
40289 | Siskiyou PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 21933SS |  | 0 | Finish No Earlier Than | Warning
40290 | Siskiyou PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21936 | 0 | Start No Earlier Than | Warning
40291 | Siskiyou PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 21935 |  | 0 | Finish No Earlier Than | Warning
40292 | Siskiyou PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40294 | Siskiyou PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 21940SS | 0 | Start No Earlier Than | Warning
40295 | Siskiyou PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21939SS | 21941SS | 0 | Finish No Earlier Than | Warning
40296 | Siskiyou PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21940SS | 21942SS | 0 | Finish No Earlier Than | Warning
40297 | Siskiyou PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21941SS | 21943SS | 0 | Finish No Earlier Than | Warning
40298 | Siskiyou PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21942SS | 21944SS | 0 | Finish No Earlier Than | Warning
40299 | Siskiyou PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21943SS | 21945SS | 0 | Finish No Earlier Than | Warning
40300 | Siskiyou PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21944SS | 21946SS | 0 | Finish No Earlier Than | Warning
40301 | Siskiyou PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21945SS | 21947SS | 0 | Finish No Earlier Than | Warning
40302 | Siskiyou PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21946SS | 21948SS | 0 | Finish No Earlier Than | Warning
40303 | Siskiyou PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21947SS | 21949SS | 0 | Finish No Earlier Than | Warning
40304 | Siskiyou PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 21948SS |  | 0 | Finish No Earlier Than | Warning
40305 | Siskiyou PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40306 | Siskiyou PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40308 | Siskiyou PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 21954SS,21958 | 0 | Start No Earlier Than | Warning
40309 | Siskiyou PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 21953SS |  | 0 | Start No Earlier Than | Warning
40310 | Siskiyou PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40311 | Siskiyou PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21964 | 0 | Start No Earlier Than | Warning
40312 | Siskiyou PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 21965 | 0 | Start No Earlier Than | Warning
40313 | Siskiyou PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 21953 |  | 0 | Start No Earlier Than | Warning
40314 | Siskiyou PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40315 | Siskiyou PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 21961SS,21969SS+20d | 0 | Start No Earlier Than | Warning
40316 | Siskiyou PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21960SS | 21962SS,21970SS+20d | 0 | Finish No Earlier Than | Warning
40317 | Siskiyou PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 21961SS | 21971SS+20d | 0 | Finish No Earlier Than | Warning
40318 | Siskiyou PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40319 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21956 | 21965SS | 0 | Start No Earlier Than | Warning
40320 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 21957,21964SS |  | 0 | Finish No Earlier Than | Warning
40321 | Siskiyou PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 21974FS+12d | 0 | Start No Earlier Than | Warning
40322 | Siskiyou PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 21968SS | 0 | Start No Earlier Than | Warning
40323 | Siskiyou PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 21967SS |  | 0 | Start No Earlier Than | Warning
40327 | Siskiyou PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 21974SS+44d | 0 | Start No Earlier Than | Warning
40328 | Siskiyou PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40333 | Solano PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40334 | Solano PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40335 | Solano PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40336 | Solano PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40337 | Solano PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40338 | Solano PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40339 | Solano PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40340 | Solano PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40341 | Solano PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40342 | Solano PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40343 | Solano PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40344 | Solano PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40345 | Solano PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40346 | Solano PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40347 | Solano PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40348 | Solano PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40349 | Solano PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40350 | Solano PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40351 | Solano PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40352 | Solano PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40353 | Solano PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40354 | Solano PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40355 | Solano PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40356 | Solano PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40357 | Solano PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.2 | Start No Earlier Than | Warning
40358 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22004SS | 0 | Start No Earlier Than | Warning
40359 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22003SS |  | 0 | Finish No Earlier Than | Warning
40360 | Solano PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22006SS | 0 | Start No Earlier Than | Warning
40361 | Solano PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22005SS |  | 0 | Start No Earlier Than | Warning
40362 | Solano PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40363 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22009SS | 0 | Finish No Earlier Than | Warning
40364 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22008SS |  | 0 | Finish No Earlier Than | Warning
40365 | Solano PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40366 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22012SS | 0 | Finish No Earlier Than | Warning
40368 | Solano PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40369 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22015SS | 0 | Finish No Earlier Than | Warning
40370 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22014SS |  | 0 | Start No Earlier Than | Warning
40371 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22017SS | 0 | Start No Earlier Than | Warning
40372 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22016SS |  | 0 | Start No Earlier Than | Warning
40373 | Solano PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40374 | Solano PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40377 | Solano PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40378 | Solano PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40379 | Solano PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40380 | Solano PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22026FS+10d | 0 | Start No Earlier Than | Warning
40381 | Solano PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22025FS+10d |  | 0 | Start No Earlier Than | Warning
40383 | Solano PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22030FS-1d | 1 | Start No Earlier Than | Warning
40384 | Solano PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40385 | Solano PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22028FS-1d |  | 0.2 | Start No Earlier Than | Warning
40386 | Solano PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40387 | Solano PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22033 | 1 | Start No Earlier Than | Warning
40388 | Solano PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22032 |  | 0.2 | Start No Earlier Than | Warning
40389 | Solano PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40390 | Solano PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22036FS+19d | 0 | Finish No Earlier Than | Warning
40391 | Solano PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22035FS+19d | 22037 | 0 | Start No Earlier Than | Warning
40393 | Solano PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40394 | Solano PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22040 | 0 | Start No Earlier Than | Warning
40395 | Solano PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22039 | 22041FS-1d | 0 | Start No Earlier Than | Warning
40396 | Solano PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22040FS-1d |  | 0 | Finish No Earlier Than | Warning
40397 | Solano PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40398 | Solano PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40401 | Solano PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22047SS | 0 | Finish No Earlier Than | Warning
40402 | Solano PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22046SS |  | 0 | Finish No Earlier Than | Warning
40403 | Solano PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40404 | Solano PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40406 | Solano PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22052SS | 0 | Finish No Earlier Than | Warning
40407 | Solano PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22051SS | 22066SS | 0 | Start No Earlier Than | Warning
40409 | Solano PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40410 | Solano PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40412 | Solano PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22058SS | 0 | Start No Earlier Than | Warning
40413 | Solano PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22057SS | 22059SS,22060 | 0 | Finish No Earlier Than | Warning
40415 | Solano PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22058,22059 |  | 0 | Finish No Earlier Than | Warning
40416 | Solano PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40418 | Solano PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22064SS | 0 | Finish No Earlier Than | Warning
40419 | Solano PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22063SS |  | 0 | Finish No Earlier Than | Warning
40420 | Solano PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40421 | Solano PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22052SS |  | 0 | Finish No Earlier Than | Warning
40423 | Solano PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22069SS | 0 | Finish No Earlier Than | Warning
40424 | Solano PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22068SS |  | 0 | Finish No Earlier Than | Warning
40426 | Solano PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22072SS+18d | 0 | Start No Earlier Than | Warning
40427 | Solano PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22071SS+18d |  | 0 | Finish No Earlier Than | Warning
40429 | Solano PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22075SS | 0 | Start No Earlier Than | Warning
40430 | Solano PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22074SS |  | 0 | Finish No Earlier Than | Warning
40431 | Solano PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22077 | 0 | Start No Earlier Than | Warning
40432 | Solano PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22076 |  | 0 | Finish No Earlier Than | Warning
40433 | Solano PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40435 | Solano PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22081SS | 0 | Start No Earlier Than | Warning
40436 | Solano PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22080SS | 22082SS | 0 | Finish No Earlier Than | Warning
40437 | Solano PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22081SS | 22083SS | 0 | Finish No Earlier Than | Warning
40438 | Solano PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22082SS | 22084SS | 0 | Finish No Earlier Than | Warning
40439 | Solano PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22083SS | 22085SS | 0 | Finish No Earlier Than | Warning
40440 | Solano PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22084SS | 22086SS | 0 | Finish No Earlier Than | Warning
40441 | Solano PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22085SS | 22087SS | 0 | Finish No Earlier Than | Warning
40442 | Solano PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22086SS | 22088SS | 0 | Finish No Earlier Than | Warning
40443 | Solano PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22087SS | 22089SS | 0 | Finish No Earlier Than | Warning
40444 | Solano PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22088SS | 22090SS | 0 | Finish No Earlier Than | Warning
40445 | Solano PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22089SS |  | 0 | Finish No Earlier Than | Warning
40446 | Solano PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40447 | Solano PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40449 | Solano PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22095SS,22099 | 0.2 | Start No Earlier Than | Warning
40450 | Solano PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22094SS |  | 0 | Start No Earlier Than | Warning
40451 | Solano PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40452 | Solano PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22105 | 0 | Start No Earlier Than | Warning
40453 | Solano PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22106 | 0 | Start No Earlier Than | Warning
40454 | Solano PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22094 |  | 0 | Start No Earlier Than | Warning
40455 | Solano PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40456 | Solano PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22102SS,22110SS+20d | 0 | Start No Earlier Than | Warning
40457 | Solano PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22101SS | 22103SS,22111SS+20d | 0 | Finish No Earlier Than | Warning
40458 | Solano PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22102SS | 22112SS+20d | 0 | Finish No Earlier Than | Warning
40459 | Solano PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40460 | Solano PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22097 | 22106SS | 0 | Start No Earlier Than | Warning
40461 | Solano PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22098,22105SS |  | 0 | Finish No Earlier Than | Warning
40462 | Solano PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22115FS+12d | 0 | Start No Earlier Than | Warning
40463 | Solano PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22109SS | 0 | Start No Earlier Than | Warning
40464 | Solano PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22108SS |  | 0 | Start No Earlier Than | Warning
40468 | Solano PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22115SS+44d | 0 | Start No Earlier Than | Warning
40469 | Solano PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40474 | Sonoma PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40475 | Sonoma PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40476 | Sonoma PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40477 | Sonoma PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40478 | Sonoma PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40479 | Sonoma PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40480 | Sonoma PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40481 | Sonoma PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40482 | Sonoma PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40483 | Sonoma PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40484 | Sonoma PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40485 | Sonoma PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40486 | Sonoma PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40487 | Sonoma PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40488 | Sonoma PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40489 | Sonoma PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40490 | Sonoma PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40491 | Sonoma PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40492 | Sonoma PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40493 | Sonoma PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40494 | Sonoma PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40495 | Sonoma PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40496 | Sonoma PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40497 | Sonoma PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40498 | Sonoma PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
40499 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22145SS | 0 | Start No Earlier Than | Warning
40500 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22144SS |  | 0 | Finish No Earlier Than | Warning
40501 | Sonoma PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22147SS | 0 | Start No Earlier Than | Warning
40502 | Sonoma PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22146SS |  | 0 | Start No Earlier Than | Warning
40503 | Sonoma PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40504 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22150SS | 0 | Finish No Earlier Than | Warning
40505 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22149SS |  | 0 | Finish No Earlier Than | Warning
40506 | Sonoma PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40507 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22153SS | 0 | Finish No Earlier Than | Warning
40509 | Sonoma PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40510 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22156SS | 0 | Finish No Earlier Than | Warning
40511 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22155SS |  | 0 | Start No Earlier Than | Warning
40512 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22158SS | 0 | Start No Earlier Than | Warning
40513 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22157SS |  | 0 | Start No Earlier Than | Warning
40514 | Sonoma PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40515 | Sonoma PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40518 | Sonoma PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40519 | Sonoma PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40520 | Sonoma PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40521 | Sonoma PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22167FS+10d | 0 | Start No Earlier Than | Warning
40522 | Sonoma PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22166FS+10d |  | 0 | Start No Earlier Than | Warning
40524 | Sonoma PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22171FS-1d | 1 | Start No Earlier Than | Warning
40525 | Sonoma PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40526 | Sonoma PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22169FS-1d |  | 0.2 | Start No Earlier Than | Warning
40527 | Sonoma PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40528 | Sonoma PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 466d |  | 22174 | 0 | Start No Earlier Than | Warning
40529 | Sonoma PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22173 |  | 0 | Start No Earlier Than | Warning
40530 | Sonoma PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40531 | Sonoma PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22177FS+19d | 0 | Finish No Earlier Than | Warning
40532 | Sonoma PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22176FS+19d | 22178 | 0 | Start No Earlier Than | Warning
40534 | Sonoma PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40535 | Sonoma PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22181 | 0 | Start No Earlier Than | Warning
40536 | Sonoma PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22180 | 22182FS-1d | 0 | Start No Earlier Than | Warning
40537 | Sonoma PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22181FS-1d |  | 0 | Finish No Earlier Than | Warning
40538 | Sonoma PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40539 | Sonoma PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40542 | Sonoma PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22188SS | 0 | Finish No Earlier Than | Warning
40543 | Sonoma PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22187SS |  | 0 | Finish No Earlier Than | Warning
40544 | Sonoma PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40545 | Sonoma PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40547 | Sonoma PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22193SS | 0 | Finish No Earlier Than | Warning
40548 | Sonoma PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22192SS | 22207SS | 0 | Start No Earlier Than | Warning
40550 | Sonoma PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40551 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40553 | Sonoma PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22199SS | 0 | Start No Earlier Than | Warning
40554 | Sonoma PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22198SS | 22200SS,22201 | 0 | Finish No Earlier Than | Warning
40556 | Sonoma PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22199,22200 |  | 0 | Finish No Earlier Than | Warning
40557 | Sonoma PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40559 | Sonoma PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22205SS | 0 | Finish No Earlier Than | Warning
40560 | Sonoma PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22204SS |  | 0 | Finish No Earlier Than | Warning
40561 | Sonoma PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40562 | Sonoma PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22193SS |  | 0 | Finish No Earlier Than | Warning
40564 | Sonoma PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22210SS | 0 | Finish No Earlier Than | Warning
40565 | Sonoma PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22209SS |  | 0 | Finish No Earlier Than | Warning
40567 | Sonoma PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22213SS+18d | 0 | Start No Earlier Than | Warning
40568 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22212SS+18d |  | 0 | Finish No Earlier Than | Warning
40570 | Sonoma PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22216SS | 0 | Start No Earlier Than | Warning
40571 | Sonoma PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22215SS |  | 0 | Finish No Earlier Than | Warning
40572 | Sonoma PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22218 | 0 | Start No Earlier Than | Warning
40573 | Sonoma PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22217 |  | 0 | Finish No Earlier Than | Warning
40574 | Sonoma PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40576 | Sonoma PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22222SS | 0 | Start No Earlier Than | Warning
40577 | Sonoma PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22221SS | 22223SS | 0 | Finish No Earlier Than | Warning
40578 | Sonoma PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22222SS | 22224SS | 0 | Finish No Earlier Than | Warning
40579 | Sonoma PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22223SS | 22225SS | 0 | Finish No Earlier Than | Warning
40580 | Sonoma PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22224SS | 22226SS | 0 | Finish No Earlier Than | Warning
40581 | Sonoma PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22225SS | 22227SS | 0 | Finish No Earlier Than | Warning
40582 | Sonoma PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22226SS | 22228SS | 0 | Finish No Earlier Than | Warning
40583 | Sonoma PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22227SS | 22229SS | 0 | Finish No Earlier Than | Warning
40584 | Sonoma PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22228SS | 22230SS | 0 | Finish No Earlier Than | Warning
40585 | Sonoma PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22229SS | 22231SS | 0 | Finish No Earlier Than | Warning
40586 | Sonoma PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22230SS |  | 0 | Finish No Earlier Than | Warning
40587 | Sonoma PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40588 | Sonoma PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40590 | Sonoma PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22236SS,22240 | 0 | Start No Earlier Than | Warning
40591 | Sonoma PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22235SS |  | 0 | Start No Earlier Than | Warning
40592 | Sonoma PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40593 | Sonoma PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22246 | 0 | Start No Earlier Than | Warning
40594 | Sonoma PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22247 | 0 | Start No Earlier Than | Warning
40595 | Sonoma PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22235 |  | 0 | Start No Earlier Than | Warning
40596 | Sonoma PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40597 | Sonoma PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22243SS,22251SS+20d | 0 | Start No Earlier Than | Warning
40598 | Sonoma PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22242SS | 22244SS,22252SS+20d | 0 | Finish No Earlier Than | Warning
40599 | Sonoma PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22243SS | 22253SS+20d | 0 | Finish No Earlier Than | Warning
40600 | Sonoma PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40601 | Sonoma PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22238 | 22247SS | 0 | Start No Earlier Than | Warning
40602 | Sonoma PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22239,22246SS |  | 0 | Finish No Earlier Than | Warning
40603 | Sonoma PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22256FS+12d | 0 | Start No Earlier Than | Warning
40604 | Sonoma PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22250SS | 0 | Start No Earlier Than | Warning
40605 | Sonoma PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22249SS |  | 0 | Start No Earlier Than | Warning
40609 | Sonoma PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22256SS+44d | 0 | Start No Earlier Than | Warning
40610 | Sonoma PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40615 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40616 | Stanislaus PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40617 | Stanislaus PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40618 | Stanislaus PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
40619 | Stanislaus PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40620 | Stanislaus PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40621 | Stanislaus PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40622 | Stanislaus PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40623 | Stanislaus PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40624 | Stanislaus PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40625 | Stanislaus PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40626 | Stanislaus PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40627 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40628 | Stanislaus PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40629 | Stanislaus PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40630 | Stanislaus PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40631 | Stanislaus PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40632 | Stanislaus PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40633 | Stanislaus PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40634 | Stanislaus PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40635 | Stanislaus PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40636 | Stanislaus PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40637 | Stanislaus PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40638 | Stanislaus PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40639 | Stanislaus PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0.1 | Start No Earlier Than | Warning
40640 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22286SS | 0 | Start No Earlier Than | Warning
40641 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22285SS |  | 0 | Finish No Earlier Than | Warning
40642 | Stanislaus PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22288SS | 0 | Start No Earlier Than | Warning
40643 | Stanislaus PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22287SS |  | 0 | Start No Earlier Than | Warning
40644 | Stanislaus PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40645 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22291SS | 0 | Finish No Earlier Than | Warning
40646 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22290SS |  | 0 | Finish No Earlier Than | Warning
40647 | Stanislaus PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40648 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22294SS | 0 | Finish No Earlier Than | Warning
40650 | Stanislaus PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40651 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22297SS | 0 | Finish No Earlier Than | Warning
40652 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22296SS |  | 0 | Start No Earlier Than | Warning
40653 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22299SS | 0 | Start No Earlier Than | Warning
40654 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22298SS |  | 0 | Start No Earlier Than | Warning
40655 | Stanislaus PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40656 | Stanislaus PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40659 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40660 | Stanislaus PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40661 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40662 | Stanislaus PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22308FS+10d | 0 | Start No Earlier Than | Warning
40663 | Stanislaus PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22307FS+10d |  | 0 | Start No Earlier Than | Warning
40665 | Stanislaus PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22312FS-1d | 1 | Start No Earlier Than | Warning
40666 | Stanislaus PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40667 | Stanislaus PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22310FS-1d |  | 0.4 | Start No Earlier Than | Warning
40668 | Stanislaus PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40669 | Stanislaus PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22315 | 1 | Start No Earlier Than | Warning
40670 | Stanislaus PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22314 |  | 0.2 | Start No Earlier Than | Warning
40671 | Stanislaus PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40672 | Stanislaus PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22318FS+19d | 0.2 | Finish No Earlier Than | Warning
40673 | Stanislaus PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22317FS+19d | 22319 | 0 | Start No Earlier Than | Warning
40675 | Stanislaus PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40676 | Stanislaus PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22322 | 0 | Start No Earlier Than | Warning
40677 | Stanislaus PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22321 | 22323FS-1d | 0 | Start No Earlier Than | Warning
40678 | Stanislaus PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22322FS-1d |  | 0 | Finish No Earlier Than | Warning
40679 | Stanislaus PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40680 | Stanislaus PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40683 | Stanislaus PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22329SS | 0 | Finish No Earlier Than | Warning
40684 | Stanislaus PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22328SS |  | 0 | Finish No Earlier Than | Warning
40685 | Stanislaus PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40686 | Stanislaus PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40688 | Stanislaus PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22334SS | 0 | Finish No Earlier Than | Warning
40689 | Stanislaus PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22333SS | 22348SS | 0 | Start No Earlier Than | Warning
40691 | Stanislaus PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40692 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40694 | Stanislaus PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22340SS | 0 | Start No Earlier Than | Warning
40695 | Stanislaus PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22339SS | 22341SS,22342 | 0 | Finish No Earlier Than | Warning
40697 | Stanislaus PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22340,22341 |  | 0 | Finish No Earlier Than | Warning
40698 | Stanislaus PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40700 | Stanislaus PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22346SS | 0 | Finish No Earlier Than | Warning
40701 | Stanislaus PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22345SS |  | 0 | Finish No Earlier Than | Warning
40702 | Stanislaus PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40703 | Stanislaus PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22334SS |  | 0 | Finish No Earlier Than | Warning
40705 | Stanislaus PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22351SS | 0 | Finish No Earlier Than | Warning
40706 | Stanislaus PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22350SS |  | 0 | Finish No Earlier Than | Warning
40708 | Stanislaus PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22354SS+18d | 0 | Start No Earlier Than | Warning
40709 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22353SS+18d |  | 0 | Finish No Earlier Than | Warning
40711 | Stanislaus PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22357SS | 0 | Start No Earlier Than | Warning
40712 | Stanislaus PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22356SS |  | 0 | Finish No Earlier Than | Warning
40713 | Stanislaus PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22359 | 0 | Start No Earlier Than | Warning
40714 | Stanislaus PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22358 |  | 0 | Finish No Earlier Than | Warning
40715 | Stanislaus PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40717 | Stanislaus PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22363SS | 0 | Start No Earlier Than | Warning
40718 | Stanislaus PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22362SS | 22364SS | 0 | Finish No Earlier Than | Warning
40719 | Stanislaus PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22363SS | 22365SS | 0 | Finish No Earlier Than | Warning
40720 | Stanislaus PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22364SS | 22366SS | 0 | Finish No Earlier Than | Warning
40721 | Stanislaus PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22365SS | 22367SS | 0 | Finish No Earlier Than | Warning
40722 | Stanislaus PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22366SS | 22368SS | 0 | Finish No Earlier Than | Warning
40723 | Stanislaus PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22367SS | 22369SS | 0 | Finish No Earlier Than | Warning
40724 | Stanislaus PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22368SS | 22370SS | 0 | Finish No Earlier Than | Warning
40725 | Stanislaus PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22369SS | 22371SS | 0 | Finish No Earlier Than | Warning
40726 | Stanislaus PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22370SS | 22372SS | 0 | Finish No Earlier Than | Warning
40727 | Stanislaus PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22371SS |  | 0 | Finish No Earlier Than | Warning
40728 | Stanislaus PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40729 | Stanislaus PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40731 | Stanislaus PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22377SS,22381 | 0.2 | Start No Earlier Than | Warning
40732 | Stanislaus PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22376SS |  | 0 | Start No Earlier Than | Warning
40733 | Stanislaus PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40734 | Stanislaus PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22387 | 0 | Start No Earlier Than | Warning
40735 | Stanislaus PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22388 | 0 | Start No Earlier Than | Warning
40736 | Stanislaus PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22376 |  | 0 | Start No Earlier Than | Warning
40737 | Stanislaus PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40738 | Stanislaus PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22384SS,22392SS+20d | 0 | Start No Earlier Than | Warning
40739 | Stanislaus PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22383SS | 22385SS,22393SS+20d | 0 | Finish No Earlier Than | Warning
40740 | Stanislaus PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22384SS | 22394SS+20d | 0 | Finish No Earlier Than | Warning
40741 | Stanislaus PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40742 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22379 | 22388SS | 0 | Start No Earlier Than | Warning
40743 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22380,22387SS |  | 0 | Finish No Earlier Than | Warning
40744 | Stanislaus PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22397FS+12d | 0 | Start No Earlier Than | Warning
40745 | Stanislaus PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22391SS | 0 | Start No Earlier Than | Warning
40746 | Stanislaus PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22390SS |  | 0 | Start No Earlier Than | Warning
40750 | Stanislaus PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22397SS+44d | 0 | Start No Earlier Than | Warning
40751 | Stanislaus PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40756 | Sutter PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40757 | Sutter PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40758 | Sutter PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40759 | Sutter PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40760 | Sutter PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40761 | Sutter PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40762 | Sutter PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40763 | Sutter PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40764 | Sutter PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40765 | Sutter PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40766 | Sutter PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40767 | Sutter PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40768 | Sutter PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40769 | Sutter PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40770 | Sutter PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40771 | Sutter PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40772 | Sutter PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40773 | Sutter PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40774 | Sutter PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40775 | Sutter PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40776 | Sutter PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40777 | Sutter PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40778 | Sutter PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40779 | Sutter PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40780 | Sutter PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
40781 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22427SS | 0 | Start No Earlier Than | Warning
40782 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22426SS |  | 0 | Finish No Earlier Than | Warning
40783 | Sutter PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22429SS | 0 | Start No Earlier Than | Warning
40784 | Sutter PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22428SS |  | 0 | Start No Earlier Than | Warning
40785 | Sutter PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40786 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22432SS | 0 | Finish No Earlier Than | Warning
40787 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22431SS |  | 0 | Finish No Earlier Than | Warning
40788 | Sutter PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40789 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22435SS | 0 | Finish No Earlier Than | Warning
40791 | Sutter PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40792 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22438SS | 0 | Finish No Earlier Than | Warning
40793 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22437SS |  | 0 | Start No Earlier Than | Warning
40794 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22440SS | 0 | Start No Earlier Than | Warning
40795 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22439SS |  | 0 | Start No Earlier Than | Warning
40796 | Sutter PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40797 | Sutter PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40800 | Sutter PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40801 | Sutter PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40802 | Sutter PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40803 | Sutter PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22449FS+10d | 0 | Start No Earlier Than | Warning
40804 | Sutter PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22448FS+10d |  | 0 | Start No Earlier Than | Warning
40806 | Sutter PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22453FS-1d | 1 | Start No Earlier Than | Warning
40807 | Sutter PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40808 | Sutter PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22451FS-1d |  | 0.2 | Start No Earlier Than | Warning
40809 | Sutter PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40810 | Sutter PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22456 | 1 | Start No Earlier Than | Warning
40811 | Sutter PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22455 |  | 0 | Start No Earlier Than | Warning
40812 | Sutter PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40813 | Sutter PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 0d |  | 22459FS+19d | 1 | Finish No Earlier Than | Warning
40814 | Sutter PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22458FS+19d | 22460 | 0 | Start No Earlier Than | Warning
40816 | Sutter PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40817 | Sutter PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22463 | 0 | Start No Earlier Than | Warning
40818 | Sutter PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22462 | 22464FS-1d | 0 | Start No Earlier Than | Warning
40819 | Sutter PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22463FS-1d |  | 0 | Finish No Earlier Than | Warning
40820 | Sutter PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40821 | Sutter PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40824 | Sutter PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22470SS | 0 | Finish No Earlier Than | Warning
40825 | Sutter PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22469SS |  | 0 | Finish No Earlier Than | Warning
40826 | Sutter PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40827 | Sutter PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
40829 | Sutter PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22475SS | 0 | Finish No Earlier Than | Warning
40830 | Sutter PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22474SS | 22489SS | 0 | Start No Earlier Than | Warning
40832 | Sutter PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
40833 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
40835 | Sutter PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22481SS | 0 | Start No Earlier Than | Warning
40836 | Sutter PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22480SS | 22482SS,22483 | 0 | Finish No Earlier Than | Warning
40838 | Sutter PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22481,22482 |  | 0 | Finish No Earlier Than | Warning
40839 | Sutter PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40841 | Sutter PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22487SS | 0 | Finish No Earlier Than | Warning
40842 | Sutter PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22486SS |  | 0 | Finish No Earlier Than | Warning
40843 | Sutter PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
40844 | Sutter PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22475SS |  | 0 | Finish No Earlier Than | Warning
40846 | Sutter PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22492SS | 0 | Finish No Earlier Than | Warning
40847 | Sutter PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22491SS |  | 0 | Finish No Earlier Than | Warning
40849 | Sutter PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22495SS+18d | 0 | Start No Earlier Than | Warning
40850 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22494SS+18d |  | 0 | Finish No Earlier Than | Warning
40852 | Sutter PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22498SS | 0 | Start No Earlier Than | Warning
40853 | Sutter PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22497SS |  | 0 | Finish No Earlier Than | Warning
40854 | Sutter PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22500 | 0 | Start No Earlier Than | Warning
40855 | Sutter PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22499 |  | 0 | Finish No Earlier Than | Warning
40856 | Sutter PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
40858 | Sutter PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22504SS | 0 | Start No Earlier Than | Warning
40859 | Sutter PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22503SS | 22505SS | 0 | Finish No Earlier Than | Warning
40860 | Sutter PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22504SS | 22506SS | 0 | Finish No Earlier Than | Warning
40861 | Sutter PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22505SS | 22507SS | 0 | Finish No Earlier Than | Warning
40862 | Sutter PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22506SS | 22508SS | 0 | Finish No Earlier Than | Warning
40863 | Sutter PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22507SS | 22509SS | 0 | Finish No Earlier Than | Warning
40864 | Sutter PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22508SS | 22510SS | 0 | Finish No Earlier Than | Warning
40865 | Sutter PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22509SS | 22511SS | 0 | Finish No Earlier Than | Warning
40866 | Sutter PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22510SS | 22512SS | 0 | Finish No Earlier Than | Warning
40867 | Sutter PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22511SS | 22513SS | 0 | Finish No Earlier Than | Warning
40868 | Sutter PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22512SS |  | 0 | Finish No Earlier Than | Warning
40869 | Sutter PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40870 | Sutter PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40872 | Sutter PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22518SS,22522 | 0 | Start No Earlier Than | Warning
40873 | Sutter PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22517SS |  | 0 | Start No Earlier Than | Warning
40874 | Sutter PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40875 | Sutter PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22528 | 0 | Start No Earlier Than | Warning
40876 | Sutter PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22529 | 0 | Start No Earlier Than | Warning
40877 | Sutter PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22517 |  | 0 | Start No Earlier Than | Warning
40878 | Sutter PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40879 | Sutter PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22525SS,22533SS+20d | 0 | Start No Earlier Than | Warning
40880 | Sutter PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22524SS | 22526SS,22534SS+20d | 0 | Finish No Earlier Than | Warning
40881 | Sutter PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22525SS | 22535SS+20d | 0 | Finish No Earlier Than | Warning
40882 | Sutter PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40883 | Sutter PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22520 | 22529SS | 0 | Start No Earlier Than | Warning
40884 | Sutter PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22521,22528SS |  | 0 | Finish No Earlier Than | Warning
40885 | Sutter PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22538FS+12d | 0 | Start No Earlier Than | Warning
40886 | Sutter PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22532SS | 0 | Start No Earlier Than | Warning
40887 | Sutter PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22531SS |  | 0 | Start No Earlier Than | Warning
40891 | Sutter PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22538SS+44d | 0 | Start No Earlier Than | Warning
40892 | Sutter PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
40897 | Tehama PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40898 | Tehama PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40899 | Tehama PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
40900 | Tehama PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
40901 | Tehama PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
40902 | Tehama PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
40903 | Tehama PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
40904 | Tehama PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
40905 | Tehama PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
40906 | Tehama PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
40907 | Tehama PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
40908 | Tehama PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
40909 | Tehama PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
40910 | Tehama PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
40911 | Tehama PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40912 | Tehama PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
40913 | Tehama PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40914 | Tehama PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40915 | Tehama PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40916 | Tehama PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40917 | Tehama PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40918 | Tehama PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40919 | Tehama PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40920 | Tehama PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40921 | Tehama PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
40922 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22568SS | 0 | Start No Earlier Than | Warning
40923 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22567SS |  | 0 | Finish No Earlier Than | Warning
40924 | Tehama PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22570SS | 0 | Start No Earlier Than | Warning
40925 | Tehama PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22569SS |  | 0 | Start No Earlier Than | Warning
40926 | Tehama PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
40927 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22573SS | 0 | Finish No Earlier Than | Warning
40928 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22572SS |  | 0 | Finish No Earlier Than | Warning
40929 | Tehama PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
40930 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22576SS | 0 | Finish No Earlier Than | Warning
40932 | Tehama PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
40933 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22579SS | 0 | Finish No Earlier Than | Warning
40934 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22578SS |  | 0 | Start No Earlier Than | Warning
40935 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22581SS | 0 | Start No Earlier Than | Warning
40936 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22580SS |  | 0 | Start No Earlier Than | Warning
40937 | Tehama PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
40938 | Tehama PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
40941 | Tehama PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
40942 | Tehama PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
40943 | Tehama PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
40944 | Tehama PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22590FS+10d | 0 | Start No Earlier Than | Warning
40945 | Tehama PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22589FS+10d |  | 0 | Start No Earlier Than | Warning
40947 | Tehama PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22594FS-1d | 1 | Start No Earlier Than | Warning
40948 | Tehama PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
40949 | Tehama PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22592FS-1d |  | 0.2 | Start No Earlier Than | Warning
40950 | Tehama PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
40951 | Tehama PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22597 | 1 | Start No Earlier Than | Warning
40952 | Tehama PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22596 |  | 0 | Start No Earlier Than | Warning
40953 | Tehama PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40954 | Tehama PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22600FS+19d | 0 | Finish No Earlier Than | Warning
40955 | Tehama PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22599FS+19d | 22601 | 0 | Start No Earlier Than | Warning
40957 | Tehama PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
40958 | Tehama PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22604 | 0 | Start No Earlier Than | Warning
40959 | Tehama PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22603 | 22605FS-1d | 0 | Start No Earlier Than | Warning
40960 | Tehama PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22604FS-1d |  | 0 | Finish No Earlier Than | Warning
40961 | Tehama PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
40962 | Tehama PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
40965 | Tehama PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22611SS | 0 | Start No Earlier Than | Warning
40966 | Tehama PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22610SS | 22612SS | 0 | Finish No Earlier Than | Warning
40967 | Tehama PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22611SS | 22613SS | 0 | Finish No Earlier Than | Warning
40968 | Tehama PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22612SS | 22614SS | 0 | Finish No Earlier Than | Warning
40969 | Tehama PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22613SS | 22615SS | 0 | Finish No Earlier Than | Warning
40970 | Tehama PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22614SS | 22616SS | 0 | Finish No Earlier Than | Warning
40971 | Tehama PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22615SS | 22617SS | 0 | Finish No Earlier Than | Warning
40972 | Tehama PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22616SS | 22618SS | 0 | Finish No Earlier Than | Warning
40973 | Tehama PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22617SS | 22619SS | 0 | Finish No Earlier Than | Warning
40974 | Tehama PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22618SS | 22620SS | 0 | Finish No Earlier Than | Warning
40975 | Tehama PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22619SS |  | 0 | Finish No Earlier Than | Warning
40976 | Tehama PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
40977 | Tehama PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
40979 | Tehama PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22625SS,22629 | 0 | Start No Earlier Than | Warning
40980 | Tehama PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22624SS |  | 0 | Start No Earlier Than | Warning
40981 | Tehama PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
40982 | Tehama PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22635 | 0 | Start No Earlier Than | Warning
40983 | Tehama PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22636 | 0 | Start No Earlier Than | Warning
40984 | Tehama PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22624 |  | 0 | Start No Earlier Than | Warning
40985 | Tehama PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
40986 | Tehama PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22632SS,22640SS+20d | 0 | Start No Earlier Than | Warning
40987 | Tehama PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22631SS | 22633SS,22641SS+20d | 0 | Finish No Earlier Than | Warning
40988 | Tehama PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22632SS | 22642SS+20d | 0 | Finish No Earlier Than | Warning
40989 | Tehama PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
40990 | Tehama PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22627 | 22636SS | 0 | Start No Earlier Than | Warning
40991 | Tehama PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22628,22635SS |  | 0 | Finish No Earlier Than | Warning
40992 | Tehama PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22645FS+12d | 0 | Start No Earlier Than | Warning
40993 | Tehama PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22639SS | 0 | Start No Earlier Than | Warning
40994 | Tehama PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22638SS |  | 0 | Start No Earlier Than | Warning
40998 | Tehama PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22645SS+44d | 0 | Start No Earlier Than | Warning
40999 | Tehama PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41004 | Trinity PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41005 | Trinity PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41006 | Trinity PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41007 | Trinity PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41008 | Trinity PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41009 | Trinity PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41010 | Trinity PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41011 | Trinity PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41012 | Trinity PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41013 | Trinity PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41014 | Trinity PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41015 | Trinity PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41016 | Trinity PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41017 | Trinity PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41018 | Trinity PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41019 | Trinity PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41020 | Trinity PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41021 | Trinity PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41022 | Trinity PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41023 | Trinity PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41024 | Trinity PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41025 | Trinity PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41026 | Trinity PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41027 | Trinity PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41028 | Trinity PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41029 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22675SS | 0 | Start No Earlier Than | Warning
41030 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22674SS |  | 0 | Finish No Earlier Than | Warning
41031 | Trinity PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22677SS | 0 | Start No Earlier Than | Warning
41032 | Trinity PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22676SS |  | 0 | Start No Earlier Than | Warning
41033 | Trinity PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
41034 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22680SS | 0 | Finish No Earlier Than | Warning
41035 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22679SS |  | 0 | Finish No Earlier Than | Warning
41036 | Trinity PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
41037 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22683SS | 0 | Finish No Earlier Than | Warning
41039 | Trinity PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
41040 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22686SS | 0 | Finish No Earlier Than | Warning
41041 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22685SS |  | 0 | Start No Earlier Than | Warning
41042 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22688SS | 0 | Start No Earlier Than | Warning
41043 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22687SS |  | 0 | Start No Earlier Than | Warning
41044 | Trinity PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41045 | Trinity PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
41048 | Trinity PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41049 | Trinity PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41050 | Trinity PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
41051 | Trinity PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22697FS+10d | 0 | Start No Earlier Than | Warning
41052 | Trinity PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22696FS+10d |  | 0 | Start No Earlier Than | Warning
41054 | Trinity PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22701FS-1d | 1 | Start No Earlier Than | Warning
41055 | Trinity PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41056 | Trinity PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22699FS-1d |  | 0.2 | Start No Earlier Than | Warning
41057 | Trinity PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41058 | Trinity PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22704 | 1 | Start No Earlier Than | Warning
41059 | Trinity PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22703 |  | 0 | Start No Earlier Than | Warning
41060 | Trinity PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41061 | Trinity PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22707FS+19d | 0 | Finish No Earlier Than | Warning
41062 | Trinity PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22706FS+19d | 22708 | 0 | Start No Earlier Than | Warning
41064 | Trinity PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41065 | Trinity PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22711 | 0 | Start No Earlier Than | Warning
41066 | Trinity PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22710 | 22712FS-1d | 0 | Start No Earlier Than | Warning
41067 | Trinity PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22711FS-1d |  | 0 | Finish No Earlier Than | Warning
41068 | Trinity PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41069 | Trinity PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41072 | Trinity PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22718SS | 0 | Start No Earlier Than | Warning
41073 | Trinity PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22717SS | 22719SS | 0 | Finish No Earlier Than | Warning
41074 | Trinity PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22718SS | 22720SS | 0 | Finish No Earlier Than | Warning
41075 | Trinity PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22719SS | 22721SS | 0 | Finish No Earlier Than | Warning
41076 | Trinity PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22720SS | 22722SS | 0 | Finish No Earlier Than | Warning
41077 | Trinity PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22721SS | 22723SS | 0 | Finish No Earlier Than | Warning
41078 | Trinity PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22722SS | 22724SS | 0 | Finish No Earlier Than | Warning
41079 | Trinity PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22723SS | 22725SS | 0 | Finish No Earlier Than | Warning
41080 | Trinity PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22724SS | 22726SS | 0 | Finish No Earlier Than | Warning
41081 | Trinity PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22725SS | 22727SS | 0 | Finish No Earlier Than | Warning
41082 | Trinity PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22726SS |  | 0 | Finish No Earlier Than | Warning
41083 | Trinity PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
41084 | Trinity PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
41086 | Trinity PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22732SS,22736 | 0 | Start No Earlier Than | Warning
41087 | Trinity PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22731SS |  | 0 | Start No Earlier Than | Warning
41088 | Trinity PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41089 | Trinity PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22742 | 0 | Start No Earlier Than | Warning
41090 | Trinity PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22743 | 0 | Start No Earlier Than | Warning
41091 | Trinity PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22731 |  | 0 | Start No Earlier Than | Warning
41092 | Trinity PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41093 | Trinity PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22739SS,22747SS+20d | 0 | Start No Earlier Than | Warning
41094 | Trinity PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22738SS | 22740SS,22748SS+20d | 0 | Finish No Earlier Than | Warning
41095 | Trinity PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22739SS | 22749SS+20d | 0 | Finish No Earlier Than | Warning
41096 | Trinity PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41097 | Trinity PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22734 | 22743SS | 0 | Start No Earlier Than | Warning
41098 | Trinity PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22735,22742SS |  | 0 | Finish No Earlier Than | Warning
41099 | Trinity PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22752FS+12d | 0 | Start No Earlier Than | Warning
41100 | Trinity PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22746SS | 0 | Start No Earlier Than | Warning
41101 | Trinity PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22745SS |  | 0 | Start No Earlier Than | Warning
41105 | Trinity PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22752SS+44d | 0 | Start No Earlier Than | Warning
41106 | Trinity PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41111 | Tulare PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41112 | Tulare PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41113 | Tulare PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41114 | Tulare PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41115 | Tulare PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41116 | Tulare PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41117 | Tulare PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41118 | Tulare PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41119 | Tulare PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41120 | Tulare PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41121 | Tulare PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41122 | Tulare PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41123 | Tulare PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41124 | Tulare PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41125 | Tulare PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41126 | Tulare PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41127 | Tulare PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41128 | Tulare PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41129 | Tulare PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41130 | Tulare PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41131 | Tulare PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41132 | Tulare PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41133 | Tulare PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41134 | Tulare PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41135 | Tulare PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41136 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22782SS | 0 | Start No Earlier Than | Warning
41137 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22781SS |  | 0 | Finish No Earlier Than | Warning
41138 | Tulare PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22784SS | 0 | Start No Earlier Than | Warning
41139 | Tulare PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22783SS |  | 0 | Start No Earlier Than | Warning
41140 | Tulare PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
41141 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 22787SS | 0 | Finish No Earlier Than | Warning
41142 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 22786SS |  | 0 | Finish No Earlier Than | Warning
41143 | Tulare PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
41144 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 22790SS | 0 | Finish No Earlier Than | Warning
41146 | Tulare PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
41147 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 22793SS | 0 | Finish No Earlier Than | Warning
41148 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 22792SS |  | 0 | Start No Earlier Than | Warning
41149 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 22795SS | 0 | Start No Earlier Than | Warning
41150 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 22794SS |  | 0 | Start No Earlier Than | Warning
41151 | Tulare PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41152 | Tulare PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
41155 | Tulare PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41156 | Tulare PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41157 | Tulare PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
41158 | Tulare PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 22804FS+10d | 0 | Start No Earlier Than | Warning
41159 | Tulare PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 22803FS+10d |  | 0 | Start No Earlier Than | Warning
41161 | Tulare PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22808FS-1d | 1 | Start No Earlier Than | Warning
41162 | Tulare PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41163 | Tulare PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 22806FS-1d |  | 0.2 | Start No Earlier Than | Warning
41164 | Tulare PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41165 | Tulare PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22811 | 1 | Start No Earlier Than | Warning
41166 | Tulare PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22810 |  | 0 | Start No Earlier Than | Warning
41167 | Tulare PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41168 | Tulare PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22814FS+19d | 0 | Finish No Earlier Than | Warning
41169 | Tulare PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22813FS+19d | 22815 | 0 | Start No Earlier Than | Warning
41171 | Tulare PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41172 | Tulare PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22818 | 0 | Start No Earlier Than | Warning
41173 | Tulare PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22817 | 22819FS-1d | 0 | Start No Earlier Than | Warning
41174 | Tulare PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22818FS-1d |  | 0 | Finish No Earlier Than | Warning
41175 | Tulare PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41176 | Tulare PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41179 | Tulare PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22825SS | 0 | Finish No Earlier Than | Warning
41180 | Tulare PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22824SS |  | 0 | Finish No Earlier Than | Warning
41181 | Tulare PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41182 | Tulare PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
41184 | Tulare PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22830SS | 0 | Finish No Earlier Than | Warning
41185 | Tulare PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22829SS | 22844SS | 0 | Start No Earlier Than | Warning
41187 | Tulare PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
41188 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
41190 | Tulare PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 22836SS | 0 | Start No Earlier Than | Warning
41191 | Tulare PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22835SS | 22837SS,22838 | 0 | Finish No Earlier Than | Warning
41193 | Tulare PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22836,22837 |  | 0 | Finish No Earlier Than | Warning
41194 | Tulare PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41196 | Tulare PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22842SS | 0 | Finish No Earlier Than | Warning
41197 | Tulare PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 22841SS |  | 0 | Finish No Earlier Than | Warning
41198 | Tulare PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41199 | Tulare PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22830SS |  | 0 | Finish No Earlier Than | Warning
41201 | Tulare PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 22847SS | 0 | Finish No Earlier Than | Warning
41202 | Tulare PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22846SS |  | 0 | Finish No Earlier Than | Warning
41204 | Tulare PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 22850SS+18d | 0 | Start No Earlier Than | Warning
41205 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 22849SS+18d |  | 0 | Finish No Earlier Than | Warning
41207 | Tulare PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 22853SS | 0 | Start No Earlier Than | Warning
41208 | Tulare PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 22852SS |  | 0 | Finish No Earlier Than | Warning
41209 | Tulare PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22855 | 0 | Start No Earlier Than | Warning
41210 | Tulare PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 22854 |  | 0 | Finish No Earlier Than | Warning
41211 | Tulare PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41213 | Tulare PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22859SS | 0 | Start No Earlier Than | Warning
41214 | Tulare PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22858SS | 22860SS | 0 | Finish No Earlier Than | Warning
41215 | Tulare PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22859SS | 22861SS | 0 | Finish No Earlier Than | Warning
41216 | Tulare PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22860SS | 22862SS | 0 | Finish No Earlier Than | Warning
41217 | Tulare PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22861SS | 22863SS | 0 | Finish No Earlier Than | Warning
41218 | Tulare PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22862SS | 22864SS | 0 | Finish No Earlier Than | Warning
41219 | Tulare PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22863SS | 22865SS | 0 | Finish No Earlier Than | Warning
41220 | Tulare PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22864SS | 22866SS | 0 | Finish No Earlier Than | Warning
41221 | Tulare PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22865SS | 22867SS | 0 | Finish No Earlier Than | Warning
41222 | Tulare PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22866SS | 22868SS | 0 | Finish No Earlier Than | Warning
41223 | Tulare PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22867SS |  | 0 | Finish No Earlier Than | Warning
41224 | Tulare PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
41225 | Tulare PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
41227 | Tulare PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22873SS,22877 | 0 | Start No Earlier Than | Warning
41228 | Tulare PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22872SS |  | 0 | Start No Earlier Than | Warning
41229 | Tulare PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41230 | Tulare PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22883 | 0 | Start No Earlier Than | Warning
41231 | Tulare PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 22884 | 0 | Start No Earlier Than | Warning
41232 | Tulare PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22872 |  | 0 | Start No Earlier Than | Warning
41233 | Tulare PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41234 | Tulare PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 22880SS,22888SS+20d | 0 | Start No Earlier Than | Warning
41235 | Tulare PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22879SS | 22881SS,22889SS+20d | 0 | Finish No Earlier Than | Warning
41236 | Tulare PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 22880SS | 22890SS+20d | 0 | Finish No Earlier Than | Warning
41237 | Tulare PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41238 | Tulare PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22875 | 22884SS | 0 | Start No Earlier Than | Warning
41239 | Tulare PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 22876,22883SS |  | 0 | Finish No Earlier Than | Warning
41240 | Tulare PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 22893FS+12d | 0 | Start No Earlier Than | Warning
41241 | Tulare PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22887SS | 0 | Start No Earlier Than | Warning
41242 | Tulare PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22886SS |  | 0 | Start No Earlier Than | Warning
41246 | Tulare PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 22893SS+44d | 0 | Start No Earlier Than | Warning
41247 | Tulare PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41252 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41253 | Tuolumne PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41254 | Tuolumne PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41255 | Tuolumne PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
41256 | Tuolumne PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41257 | Tuolumne PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41258 | Tuolumne PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41259 | Tuolumne PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41260 | Tuolumne PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41261 | Tuolumne PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41262 | Tuolumne PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41263 | Tuolumne PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41264 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41265 | Tuolumne PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41266 | Tuolumne PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41267 | Tuolumne PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41268 | Tuolumne PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41269 | Tuolumne PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41270 | Tuolumne PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41271 | Tuolumne PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41272 | Tuolumne PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41273 | Tuolumne PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41274 | Tuolumne PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41275 | Tuolumne PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41276 | Tuolumne PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41277 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 22923SS | 0 | Start No Earlier Than | Warning
41278 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 22922SS |  | 0 | Finish No Earlier Than | Warning
41279 | Tuolumne PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 22925SS | 0 | Start No Earlier Than | Warning
41280 | Tuolumne PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 22924SS |  | 0 | Start No Earlier Than | Warning
41281 | Tuolumne PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 22928SS,22927SS | 0 | Finish No Earlier Than | Warning
41284 | Tuolumne PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
41285 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 22931SS | 0 | Start No Earlier Than | Warning
41287 | Tuolumne PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
41288 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 22934SS | 0 | Start No Earlier Than | Warning
41289 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 22933SS |  | 0 | Start No Earlier Than | Warning
41290 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 22936SS | 0 | Start No Earlier Than | Warning
41292 | Tuolumne PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
41293 | Tuolumne PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
41296 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41297 | Tuolumne PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41298 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
41299 | Tuolumne PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
41301 | Tuolumne PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 22948FS-1d | 1 | Start No Earlier Than | Warning
41302 | Tuolumne PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41303 | Tuolumne PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 22946FS-1d |  | 0 | Start No Earlier Than | Warning
41304 | Tuolumne PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41305 | Tuolumne PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 22951 | 1 | Start No Earlier Than | Warning
41306 | Tuolumne PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 22950 |  | 0 | Start No Earlier Than | Warning
41307 | Tuolumne PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41308 | Tuolumne PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 22954FS+19d | 0 | Finish No Earlier Than | Warning
41309 | Tuolumne PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 22953FS+19d | 22955 | 0 | Start No Earlier Than | Warning
41311 | Tuolumne PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41312 | Tuolumne PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 22958 | 0 | Start No Earlier Than | Warning
41313 | Tuolumne PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 22957 | 22959FS-1d | 0 | Start No Earlier Than | Warning
41314 | Tuolumne PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 22958FS-1d |  | 0 | Finish No Earlier Than | Warning
41315 | Tuolumne PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41316 | Tuolumne PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41319 | Tuolumne PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 22965SS | 0 | Start No Earlier Than | Warning
41320 | Tuolumne PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22964SS | 22966SS | 0 | Finish No Earlier Than | Warning
41321 | Tuolumne PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22965SS | 22967SS | 0 | Finish No Earlier Than | Warning
41322 | Tuolumne PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22966SS | 22968SS | 0 | Finish No Earlier Than | Warning
41323 | Tuolumne PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22967SS | 22969SS | 0 | Finish No Earlier Than | Warning
41324 | Tuolumne PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22968SS | 22970SS | 0 | Finish No Earlier Than | Warning
41325 | Tuolumne PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22969SS | 22971SS | 0 | Finish No Earlier Than | Warning
41326 | Tuolumne PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22970SS | 22972SS | 0 | Finish No Earlier Than | Warning
41327 | Tuolumne PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22971SS | 22973SS | 0 | Finish No Earlier Than | Warning
41328 | Tuolumne PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22972SS | 22974SS | 0 | Finish No Earlier Than | Warning
41329 | Tuolumne PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 22973SS |  | 0 | Finish No Earlier Than | Warning
41330 | Tuolumne PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
41331 | Tuolumne PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
41333 | Tuolumne PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 22979SS,22983 | 0 | Start No Earlier Than | Warning
41334 | Tuolumne PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 22978SS |  | 0 | Start No Earlier Than | Warning
41335 | Tuolumne PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41336 | Tuolumne PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 22989 | 0 | Start No Earlier Than | Warning
41337 | Tuolumne PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 22990 | 0 | Start No Earlier Than | Warning
41338 | Tuolumne PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 22978 |  | 0 | Start No Earlier Than | Warning
41339 | Tuolumne PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41340 | Tuolumne PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 22986SS,22994SS+20d | 0 | Start No Earlier Than | Warning
41343 | Tuolumne PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41344 | Tuolumne PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 22981 | 22990SS | 0 | Start No Earlier Than | Warning
41346 | Tuolumne PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 22999FS+12d | 0 | Start No Earlier Than | Warning
41347 | Tuolumne PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 22993SS | 0 | Start No Earlier Than | Warning
41348 | Tuolumne PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 22992SS |  | 0 | Start No Earlier Than | Warning
41352 | Tuolumne PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 22999SS+44d | 0 | Start No Earlier Than | Warning
41353 | Tuolumne PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41358 | Ventura PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41359 | Ventura PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41360 | Ventura PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41361 | Ventura PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41362 | Ventura PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41363 | Ventura PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41364 | Ventura PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41365 | Ventura PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41366 | Ventura PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41367 | Ventura PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41368 | Ventura PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41369 | Ventura PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41370 | Ventura PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41371 | Ventura PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41372 | Ventura PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41373 | Ventura PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41374 | Ventura PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41375 | Ventura PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41376 | Ventura PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41377 | Ventura PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41378 | Ventura PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41379 | Ventura PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41380 | Ventura PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41381 | Ventura PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41382 | Ventura PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41383 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23029SS | 0 | Start No Earlier Than | Warning
41384 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23028SS |  | 0 | Finish No Earlier Than | Warning
41385 | Ventura PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23031SS | 0 | Start No Earlier Than | Warning
41386 | Ventura PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23030SS |  | 0 | Start No Earlier Than | Warning
41387 | Ventura PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23034SS,23033SS | 0 | Finish No Earlier Than | Warning
41390 | Ventura PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
41391 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23037SS | 0 | Start No Earlier Than | Warning
41393 | Ventura PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
41394 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23040SS | 0 | Start No Earlier Than | Warning
41395 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 32 | 311d | 23039SS |  | 0 | Start No Earlier Than | Warning
41396 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23042SS | 0 | Start No Earlier Than | Warning
41398 | Ventura PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
41399 | Ventura PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
41402 | Ventura PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41403 | Ventura PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41404 | Ventura PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM | 42 | 279d |  |  | 0 | Start No Earlier Than | Warning
41405 | Ventura PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
41407 | Ventura PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23054FS-1d | 1 | Start No Earlier Than | Warning
41408 | Ventura PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41409 | Ventura PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 252 | 277d | 23052FS-1d |  | 0.2 | Start No Earlier Than | Warning
41410 | Ventura PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41411 | Ventura PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23057 | 1 | Start No Earlier Than | Warning
41412 | Ventura PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23056 |  | 0 | Start No Earlier Than | Warning
41413 | Ventura PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41414 | Ventura PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23060FS+19d | 0 | Finish No Earlier Than | Warning
41415 | Ventura PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23059FS+19d | 23061 | 0 | Start No Earlier Than | Warning
41417 | Ventura PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41418 | Ventura PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23064 | 0 | Start No Earlier Than | Warning
41419 | Ventura PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23063 | 23065FS-1d | 0 | Start No Earlier Than | Warning
41420 | Ventura PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23064FS-1d |  | 0 | Finish No Earlier Than | Warning
41421 | Ventura PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41422 | Ventura PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41425 | Ventura PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23071SS | 0 | Finish No Earlier Than | Warning
41426 | Ventura PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23070SS |  | 0 | Finish No Earlier Than | Warning
41427 | Ventura PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41428 | Ventura PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
41430 | Ventura PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23076SS | 0 | Finish No Earlier Than | Warning
41431 | Ventura PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23075SS | 23090SS | 0 | Start No Earlier Than | Warning
41433 | Ventura PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
41434 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
41436 | Ventura PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 23082SS | 0 | Start No Earlier Than | Warning
41437 | Ventura PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23081SS | 23083SS,23084 | 0 | Finish No Earlier Than | Warning
41439 | Ventura PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23082,23083 |  | 0 | Finish No Earlier Than | Warning
41440 | Ventura PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41442 | Ventura PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23088SS | 0 | Finish No Earlier Than | Warning
41443 | Ventura PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23087SS |  | 0 | Finish No Earlier Than | Warning
41444 | Ventura PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41445 | Ventura PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23076SS |  | 0 | Finish No Earlier Than | Warning
41447 | Ventura PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23093SS | 0 | Finish No Earlier Than | Warning
41448 | Ventura PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23092SS |  | 0 | Finish No Earlier Than | Warning
41450 | Ventura PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 23096SS+18d | 0 | Start No Earlier Than | Warning
41451 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 23095SS+18d |  | 0 | Finish No Earlier Than | Warning
41453 | Ventura PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 23099SS | 0 | Start No Earlier Than | Warning
41454 | Ventura PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 23098SS |  | 0 | Finish No Earlier Than | Warning
41455 | Ventura PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23101 | 0 | Start No Earlier Than | Warning
41456 | Ventura PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23100 |  | 0 | Finish No Earlier Than | Warning
41457 | Ventura PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41459 | Ventura PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23105SS | 0 | Start No Earlier Than | Warning
41460 | Ventura PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23104SS | 23106SS | 0 | Finish No Earlier Than | Warning
41461 | Ventura PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23105SS | 23107SS | 0 | Finish No Earlier Than | Warning
41462 | Ventura PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23106SS | 23108SS | 0 | Finish No Earlier Than | Warning
41463 | Ventura PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23107SS | 23109SS | 0 | Finish No Earlier Than | Warning
41464 | Ventura PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23108SS | 23110SS | 0 | Finish No Earlier Than | Warning
41465 | Ventura PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23109SS | 23111SS | 0 | Finish No Earlier Than | Warning
41466 | Ventura PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23110SS | 23112SS | 0 | Finish No Earlier Than | Warning
41467 | Ventura PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23111SS | 23113SS | 0 | Finish No Earlier Than | Warning
41468 | Ventura PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23112SS | 23114SS | 0 | Finish No Earlier Than | Warning
41469 | Ventura PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23113SS |  | 0 | Finish No Earlier Than | Warning
41470 | Ventura PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
41471 | Ventura PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
41473 | Ventura PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 23119SS,23123 | 0 | Start No Earlier Than | Warning
41474 | Ventura PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23118SS |  | 0 | Start No Earlier Than | Warning
41475 | Ventura PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41476 | Ventura PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 23129 | 0 | Start No Earlier Than | Warning
41477 | Ventura PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 273d |  | 23130 | 0 | Start No Earlier Than | Warning
41478 | Ventura PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 23118 |  | 0 | Start No Earlier Than | Warning
41479 | Ventura PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41480 | Ventura PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23126SS,23134SS+20d | 0 | Start No Earlier Than | Warning
41483 | Ventura PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41484 | Ventura PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 89 | 273d | 23121 | 23130SS | 0 | Start No Earlier Than | Warning
41486 | Ventura PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 279d |  | 23139FS+12d | 0 | Start No Earlier Than | Warning
41487 | Ventura PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23133SS | 0 | Start No Earlier Than | Warning
41488 | Ventura PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23132SS |  | 0 | Start No Earlier Than | Warning
41492 | Ventura PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 279d |  | 23139SS+44d | 0 | Start No Earlier Than | Warning
41493 | Ventura PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41498 | Yolo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41499 | Yolo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41500 | Yolo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41501 | Yolo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41502 | Yolo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41503 | Yolo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41504 | Yolo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41505 | Yolo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41506 | Yolo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41507 | Yolo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41508 | Yolo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41509 | Yolo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41510 | Yolo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41511 | Yolo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41512 | Yolo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41513 | Yolo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41514 | Yolo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41515 | Yolo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41516 | Yolo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41517 | Yolo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41518 | Yolo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41519 | Yolo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41520 | Yolo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41521 | Yolo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41522 | Yolo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41523 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23169SS | 0 | Start No Earlier Than | Warning
41524 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23168SS |  | 0 | Finish No Earlier Than | Warning
41525 | Yolo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23171SS | 0 | Start No Earlier Than | Warning
41526 | Yolo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23170SS |  | 0 | Start No Earlier Than | Warning
41527 | Yolo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
41528 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23174SS | 0 | Finish No Earlier Than | Warning
41529 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23173SS |  | 0 | Finish No Earlier Than | Warning
41530 | Yolo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
41531 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23177SS | 0 | Finish No Earlier Than | Warning
41533 | Yolo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
41534 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23180SS | 0 | Finish No Earlier Than | Warning
41535 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23179SS |  | 0 | Start No Earlier Than | Warning
41536 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 23182SS | 0 | Start No Earlier Than | Warning
41537 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23181SS |  | 0 | Start No Earlier Than | Warning
41538 | Yolo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41539 | Yolo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
41542 | Yolo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41543 | Yolo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41544 | Yolo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
41545 | Yolo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 23191FS+10d | 0 | Start No Earlier Than | Warning
41546 | Yolo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 23190FS+10d |  | 0 | Start No Earlier Than | Warning
41548 | Yolo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23195FS-1d | 1 | Start No Earlier Than | Warning
41549 | Yolo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41550 | Yolo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 23193FS-1d |  | 0.2 | Start No Earlier Than | Warning
41551 | Yolo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41552 | Yolo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23198 | 1 | Start No Earlier Than | Warning
41553 | Yolo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23197 |  | 0.2 | Start No Earlier Than | Warning
41554 | Yolo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41555 | Yolo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23201FS+19d | 0 | Finish No Earlier Than | Warning
41556 | Yolo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23200FS+19d | 23202 | 0 | Start No Earlier Than | Warning
41558 | Yolo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41559 | Yolo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23205 | 0 | Start No Earlier Than | Warning
41560 | Yolo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23204 | 23206FS-1d | 0 | Start No Earlier Than | Warning
41561 | Yolo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23205FS-1d |  | 0 | Finish No Earlier Than | Warning
41562 | Yolo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41563 | Yolo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41566 | Yolo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23212SS | 0 | Start No Earlier Than | Warning
41567 | Yolo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23211SS | 23213SS | 0 | Finish No Earlier Than | Warning
41568 | Yolo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23212SS | 23214SS | 0 | Finish No Earlier Than | Warning
41569 | Yolo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23213SS | 23215SS | 0 | Finish No Earlier Than | Warning
41570 | Yolo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23214SS | 23216SS | 0 | Finish No Earlier Than | Warning
41571 | Yolo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23215SS | 23217SS | 0 | Finish No Earlier Than | Warning
41572 | Yolo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23216SS | 23218SS | 0 | Finish No Earlier Than | Warning
41573 | Yolo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23217SS | 23219SS | 0 | Finish No Earlier Than | Warning
41574 | Yolo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23218SS | 23220SS | 0 | Finish No Earlier Than | Warning
41575 | Yolo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23219SS | 23221SS | 0 | Finish No Earlier Than | Warning
41576 | Yolo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23220SS |  | 0 | Finish No Earlier Than | Warning
41577 | Yolo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
41578 | Yolo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
41580 | Yolo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 23226SS,23230 | 0 | Start No Earlier Than | Warning
41581 | Yolo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23225SS |  | 0 | Start No Earlier Than | Warning
41582 | Yolo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41583 | Yolo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23236 | 0 | Start No Earlier Than | Warning
41584 | Yolo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23237 | 0 | Start No Earlier Than | Warning
41585 | Yolo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 23225 |  | 0 | Start No Earlier Than | Warning
41586 | Yolo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41587 | Yolo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 23233SS,23241SS+20d | 0 | Start No Earlier Than | Warning
41588 | Yolo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23232SS | 23234SS,23242SS+20d | 0 | Finish No Earlier Than | Warning
41589 | Yolo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23233SS | 23243SS+20d | 0 | Finish No Earlier Than | Warning
41590 | Yolo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41591 | Yolo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23228 | 23237SS | 0 | Start No Earlier Than | Warning
41592 | Yolo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23229,23236SS |  | 0 | Finish No Earlier Than | Warning
41593 | Yolo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 23246FS+12d | 0 | Start No Earlier Than | Warning
41594 | Yolo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23240SS | 0 | Start No Earlier Than | Warning
41595 | Yolo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23239SS |  | 0 | Start No Earlier Than | Warning
41599 | Yolo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 23246SS+44d | 0 | Start No Earlier Than | Warning
41600 | Yolo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41605 | Yuba PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41606 | Yuba PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41607 | Yuba PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41608 | Yuba PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41609 | Yuba PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41610 | Yuba PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41611 | Yuba PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41612 | Yuba PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41613 | Yuba PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
41614 | Yuba PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41615 | Yuba PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41616 | Yuba PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41617 | Yuba PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41618 | Yuba PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41619 | Yuba PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41620 | Yuba PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41621 | Yuba PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41622 | Yuba PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM | 16 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41623 | Yuba PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41624 | Yuba PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41625 | Yuba PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41626 | Yuba PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41627 | Yuba PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41628 | Yuba PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41629 | Yuba PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
41630 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 414d |  | 23276SS | 0 | Start No Earlier Than | Warning
41631 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d | 23275SS |  | 0 | Finish No Earlier Than | Warning
41632 | Yuba PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 23278SS | 0 | Start No Earlier Than | Warning
41633 | Yuba PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 23277SS |  | 0 | Start No Earlier Than | Warning
41634 | Yuba PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
41635 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23281SS | 0 | Finish No Earlier Than | Warning
41636 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23280SS |  | 0 | Finish No Earlier Than | Warning
41637 | Yuba PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
41638 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23284SS | 0 | Finish No Earlier Than | Warning
41640 | Yuba PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
41641 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23287SS | 0 | Finish No Earlier Than | Warning
41642 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23286SS |  | 0 | Start No Earlier Than | Warning
41643 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 246d |  | 23289SS | 0 | Start No Earlier Than | Warning
41644 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23288SS |  | 0 | Start No Earlier Than | Warning
41645 | Yuba PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41646 | Yuba PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
41649 | Yuba PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41650 | Yuba PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
41651 | Yuba PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
41652 | Yuba PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 12 | 195d |  | 23298FS+10d | 0 | Start No Earlier Than | Warning
41653 | Yuba PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d | 23297FS+10d |  | 0 | Start No Earlier Than | Warning
41655 | Yuba PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23302FS-1d | 1 | Start No Earlier Than | Warning
41656 | Yuba PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41657 | Yuba PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 296 | 233d | 23300FS-1d |  | 0.2 | Start No Earlier Than | Warning
41658 | Yuba PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM | 20 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41659 | Yuba PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23305 | 1 | Start No Earlier Than | Warning
41660 | Yuba PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23304 |  | 0 | Start No Earlier Than | Warning
41661 | Yuba PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM | 76 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41662 | Yuba PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 405d |  | 23308FS+19d | 0.2 | Finish No Earlier Than | Warning
41663 | Yuba PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 405d | 23307FS+19d | 23309 | 0 | Start No Earlier Than | Warning
41665 | Yuba PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41666 | Yuba PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 363d |  | 23312 | 0 | Start No Earlier Than | Warning
41667 | Yuba PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23311 | 23313FS-1d | 0 | Start No Earlier Than | Warning
41668 | Yuba PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23312FS-1d |  | 0 | Finish No Earlier Than | Warning
41669 | Yuba PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
41670 | Yuba PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41673 | Yuba PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23319SS | 0 | Finish No Earlier Than | Warning
41674 | Yuba PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23318SS |  | 0 | Finish No Earlier Than | Warning
41675 | Yuba PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41676 | Yuba PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d |  |  | 0 | Start No Earlier Than | Warning
41678 | Yuba PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23324SS | 0 | Finish No Earlier Than | Warning
41679 | Yuba PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23323SS | 23338SS | 0 | Start No Earlier Than | Warning
41681 | Yuba PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
41682 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d |  |  | 0 | Start No Earlier Than | Warning
41684 | Yuba PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 345d |  | 23330SS | 0 | Start No Earlier Than | Warning
41685 | Yuba PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23329SS | 23331SS,23332 | 0 | Finish No Earlier Than | Warning
41687 | Yuba PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23330,23331 |  | 0 | Finish No Earlier Than | Warning
41688 | Yuba PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41690 | Yuba PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23336SS | 0 | Finish No Earlier Than | Warning
41691 | Yuba PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 84 | 424d | 23335SS |  | 0 | Finish No Earlier Than | Warning
41692 | Yuba PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d |  |  | 0 | Start No Earlier Than | Warning
41693 | Yuba PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 0d | 23324SS |  | 1 | Finish No Earlier Than | Warning
41695 | Yuba PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM | 22 | 486d |  | 23341SS | 0 | Finish No Earlier Than | Warning
41696 | Yuba PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 42 | 466d | 23340SS |  | 0 | Finish No Earlier Than | Warning
41698 | Yuba PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 373d |  | 23344SS+18d | 0 | Start No Earlier Than | Warning
41699 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 94 | 373d | 23343SS+18d |  | 0 | Finish No Earlier Than | Warning
41701 | Yuba PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 43 | 362d |  | 23347SS | 0 | Start No Earlier Than | Warning
41702 | Yuba PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 362d | 23346SS |  | 0 | Finish No Earlier Than | Warning
41703 | Yuba PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23349 | 0 | Start No Earlier Than | Warning
41704 | Yuba PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23348 |  | 0 | Finish No Earlier Than | Warning
41705 | Yuba PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41707 | Yuba PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23353SS | 0 | Start No Earlier Than | Warning
41708 | Yuba PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23352SS | 23354SS | 0 | Finish No Earlier Than | Warning
41709 | Yuba PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23353SS | 23355SS | 0 | Finish No Earlier Than | Warning
41710 | Yuba PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23354SS | 23356SS | 0 | Finish No Earlier Than | Warning
41711 | Yuba PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23355SS | 23357SS | 0 | Finish No Earlier Than | Warning
41712 | Yuba PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23356SS | 23358SS | 0 | Finish No Earlier Than | Warning
41713 | Yuba PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23357SS | 23359SS | 0 | Finish No Earlier Than | Warning
41714 | Yuba PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23358SS | 23360SS | 0 | Finish No Earlier Than | Warning
41715 | Yuba PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23359SS | 23361SS | 0 | Finish No Earlier Than | Warning
41716 | Yuba PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23360SS | 23362SS | 0 | Finish No Earlier Than | Warning
41717 | Yuba PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23361SS |  | 0 | Finish No Earlier Than | Warning
41718 | Yuba PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
41719 | Yuba PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Start No Earlier Than | Warning
41721 | Yuba PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 195d |  | 23367SS,23371 | 0 | Start No Earlier Than | Warning
41722 | Yuba PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d | 23366SS |  | 0 | Start No Earlier Than | Warning
41723 | Yuba PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
41724 | Yuba PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23377 | 0 | Start No Earlier Than | Warning
41725 | Yuba PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 234d |  | 23378 | 0 | Start No Earlier Than | Warning
41726 | Yuba PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 189 | 195d | 23366 |  | 0 | Start No Earlier Than | Warning
41727 | Yuba PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41728 | Yuba PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 240d |  | 23374SS,23382SS+20d | 0 | Start No Earlier Than | Warning
41729 | Yuba PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23373SS | 23375SS,23383SS+20d | 0 | Finish No Earlier Than | Warning
41730 | Yuba PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d | 23374SS | 23384SS+20d | 0 | Finish No Earlier Than | Warning
41731 | Yuba PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
41732 | Yuba PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23369 | 23378SS | 0 | Start No Earlier Than | Warning
41733 | Yuba PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 128 | 234d | 23370,23377SS |  | 0 | Finish No Earlier Than | Warning
41734 | Yuba PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 240d |  | 23387FS+12d | 0 | Start No Earlier Than | Warning
41735 | Yuba PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  | 23381SS | 0 | Start No Earlier Than | Warning
41736 | Yuba PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d | 23380SS |  | 0 | Start No Earlier Than | Warning
41740 | Yuba PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 240d |  | 23387SS+44d | 0 | Start No Earlier Than | Warning
41741 | Yuba PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
41746 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
41747 | CCLD CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
41748 | CCLD CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41749 | CCLD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41750 | CCLD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
41751 | CCLD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41752 | CCLD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41753 | CCLD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41754 | CCLD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41755 | CCLD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41756 | CCLD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41757 | CCLD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41758 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
41759 | CCLD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41760 | CCLD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41761 | CCLD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41762 | CCLD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41763 | CCLD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
41764 | CCLD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41765 | CCLD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41766 | CCLD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41767 | CCLD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41768 | CCLD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41769 | CCLD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41770 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41774 | CCLD CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41775 | CCLD CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41776 | CCLD CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41777 | CCLD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
41778 | CCLD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
41779 | CCLD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
41780 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23427SS | 0 | Finish No Earlier Than | Warning
41781 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23426SS |  | 0 | Finish No Earlier Than | Warning
41782 | CCLD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41783 | CCLD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41784 | CCLD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23431SS | 0 | Finish No Earlier Than | Warning
41787 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23434SS | 0 | Start No Earlier Than | Warning
41789 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23436SS | 0 | Start No Earlier Than | Warning
41791 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23438SS | 0 | Start No Earlier Than | Warning
41793 | CCLD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
41794 | CCLD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
41797 | CCLD CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41799 | CCLD CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41800 | CCLD CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41801 | CCLD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41802 | CCLD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 23449 | 1 | Finish No Earlier Than | Warning
41804 | CCLD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 0d | 23449FS-1d |  | 1 | Start No Earlier Than | Warning
41805 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41806 | CCLD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23453FS-1d | 1 | Finish No Earlier Than | Warning
41807 | CCLD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23452FS-1d | 23454 | 0 | Finish No Earlier Than | Warning
41808 | CCLD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23453 |  | 0 | Finish No Earlier Than | Warning
41809 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41810 | CCLD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23457 | 0 | Start No Earlier Than | Warning
41811 | CCLD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23456 | 23458 | 0 | Finish No Earlier Than | Warning
41812 | CCLD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23457 |  | 0 | Finish No Earlier Than | Warning
41813 | CCLD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41814 | CCLD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23461 | 0 | Finish No Earlier Than | Warning
41815 | CCLD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23460 | 23463FS-1d | 0 | Finish No Earlier Than | Warning
41816 | CCLD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41817 | CCLD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23461FS-1d |  | 0 | Finish No Earlier Than | Warning
41818 | CCLD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
41819 | CCLD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
41820 | CCLD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41821 | CCLD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41823 | CCLD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23470SS,23473 | 1 | Start No Earlier Than | Warning
41829 | CCLD CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41831 | CCLD CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 23478 | 1 | Finish No Earlier Than | Warning
41832 | CCLD CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 23477 | 23480 | 1 | Finish No Earlier Than | Warning
41834 | CCLD CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d | 23478 | 23481FS+1d | 0.6 | Finish No Earlier Than | Warning
41835 | CCLD CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 373d | 23480FS+1d |  | 0 | Start No Earlier Than | Warning
41837 | CCLD CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM | 35 | 0d |  | 23484 | 1 | Finish No Earlier Than | Warning
41838 | CCLD CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23483 | 23485FF | 0 | Start No Earlier Than | Warning
41839 | CCLD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23484FF | 23486 | 0 | Finish No Earlier Than | Warning
41840 | CCLD CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23485 |  | 0 | Finish No Earlier Than | Warning
41841 | CCLD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
41843 | CCLD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23490SS | 0 | Start No Earlier Than | Warning
41844 | CCLD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23489SS | 23491SS | 0 | Finish No Earlier Than | Warning
41845 | CCLD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23490SS | 23492SS | 0 | Finish No Earlier Than | Warning
41846 | CCLD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23491SS | 23493SS | 0 | Finish No Earlier Than | Warning
41847 | CCLD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23492SS | 23494SS | 0 | Finish No Earlier Than | Warning
41848 | CCLD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23493SS | 23495SS | 0 | Finish No Earlier Than | Warning
41849 | CCLD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23494SS | 23496SS | 0 | Finish No Earlier Than | Warning
41850 | CCLD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23495SS | 23497SS | 0 | Finish No Earlier Than | Warning
41851 | CCLD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23496SS | 23498SS | 0 | Finish No Earlier Than | Warning
41852 | CCLD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23497SS | 23499SS | 0 | Finish No Earlier Than | Warning
41853 | CCLD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23498SS |  | 0 | Finish No Earlier Than | Warning
41854 | CCLD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
41855 | CCLD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
41857 | CCLD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
41858 | CCLD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 23510 | 0 | Finish No Earlier Than | Warning
41859 | CCLD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
41860 | CCLD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41861 | CCLD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
41862 | CCLD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23518 | 0 | Finish No Earlier Than | Warning
41863 | CCLD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23519 | 0 | Finish No Earlier Than | Warning
41864 | CCLD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 23504 |  | 0 | Start No Earlier Than | Warning
41865 | CCLD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
41866 | CCLD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23513SS,23521SS+20d | 0 | Start No Earlier Than | Warning
41871 | CCLD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
41872 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23508 |  | 0 | Start No Earlier Than | Warning
41873 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23509 |  | 0 | Start No Earlier Than | Warning
41874 | CCLD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23528FS+13d | 0 | Finish No Earlier Than | Warning
41880 | CCLD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23528SS+40d | 0 | Start No Earlier Than | Warning
41881 | CCLD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
41886 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
41887 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41888 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41889 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
41890 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41891 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41892 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41893 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41894 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41895 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41896 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
41897 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
41898 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
41899 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
41900 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
41901 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
41902 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
41903 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
41904 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
41905 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
41906 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
41907 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
41908 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41909 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
41913 | CFSD_Adoptions CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41914 | CFSD_Adoptions CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41915 | CFSD_Adoptions CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM | 37 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41916 | CFSD_Adoptions CDSS - Establish method for keeping interim processes and release notes current (if applicable) | May 30, 2025 8:00 AM | September 15, 2026 12:00 AM | 325 | 269d |  |  | 0 | Finish No Earlier Than | Warning
41917 | CFSD_Adoptions CDSS - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 12:00 AM | 54 | 258d |  |  | 0 | Finish No Earlier Than | Warning
41918 | CFSD_Adoptions CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0.2 | Finish No Earlier Than | Warning
41919 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23566SS | 0 | Finish No Earlier Than | Warning
41920 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23565SS |  | 0 | Finish No Earlier Than | Warning
41921 | CFSD_Adoptions CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41922 | CFSD_Adoptions CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41923 | CFSD_Adoptions CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  |  | 0 | Finish No Earlier Than | Warning
41924 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM | 21 | 364d |  | 23571SS | 0 | Finish No Earlier Than | Warning
41925 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 32 | 353d | 23570SS |  | 0 | Finish No Earlier Than | Warning
41926 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM | 21 | 300d |  | 23573SS | 0 | Finish No Earlier Than | Warning
41927 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d | 23572SS |  | 0 | Finish No Earlier Than | Warning
41928 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM | 20 | 279d |  | 23575SS | 0 | Finish No Earlier Than | Warning
41929 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d | 23574SS |  | 0 | Finish No Earlier Than | Warning
41930 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 12:00 AM | 20 | 258d |  | 23577SS | 0 | Finish No Earlier Than | Warning
41931 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 23576SS |  | 0 | Finish No Earlier Than | Warning
41932 | CFSD_Adoptions CDSS - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
41933 | CFSD_Adoptions CDSS - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM | 4 | 246d |  |  | 0 | Finish No Earlier Than | Warning
41935 | CFSD_Adoptions CDSS - Review and customize Organization Communication Plan template | February 3, 2025 8:00 AM | April 30, 2025 5:00 PM | 61 | 0d |  | 23583SS+40d | 1 | Finish No Earlier Than | Warning
41936 | CFSD_Adoptions CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41938 | CFSD_Adoptions CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41939 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41940 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41941 | CFSD_Adoptions CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 23588 | 1 | Finish No Earlier Than | Warning
41942 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 23587 |  | 1 | Finish No Earlier Than | Warning
41943 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41944 | CFSD_Adoptions CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23591FS-1d | 1 | Finish No Earlier Than | Warning
41945 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23590FS-1d | 23592 | 0.2 | Finish No Earlier Than | Warning
41946 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23591 |  | 0 | Finish No Earlier Than | Warning
41947 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41948 | CFSD_Adoptions CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 0d |  | 23595 | 1 | Start No Earlier Than | Warning
41949 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23594 | 23596 | 0 | Finish No Earlier Than | Warning
41950 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23595 |  | 0 | Finish No Earlier Than | Warning
41951 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41952 | CFSD_Adoptions CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23599 | 0 | Finish No Earlier Than | Warning
41953 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23598 | 23601FS-1d | 0 | Finish No Earlier Than | Warning
41954 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
41955 | CFSD_Adoptions CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23599FS-1d |  | 0 | Finish No Earlier Than | Warning
41956 | CFSD_Adoptions CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
41957 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
41958 | CFSD_Adoptions CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
41959 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
41963 | CFSD_Adoptions CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d | 23608SS |  | 1 | Finish No Earlier Than | Warning
41964 | CFSD_Adoptions CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 0d |  |  | 1 | Start No Earlier Than | Warning
41965 | CFSD_Adoptions CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 86 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41967 | CFSD_Adoptions CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41968 | CFSD_Adoptions CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
41969 | CFSD_Adoptions CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23616SS,23619 | 1 | Start No Earlier Than | Warning
41976 | CFSD_Adoptions CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23623FS+1d,23625SS | 0 | Finish No Earlier Than | Warning
41979 | CFSD_Adoptions CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 23622SS | 23626 | 1 | Finish No Earlier Than | Warning
41980 | CFSD_Adoptions CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23625 | 23627SS,23628 | 0 | Finish No Earlier Than | Warning
41981 | CFSD_Adoptions CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23626SS | 23628 | 0 | Finish No Earlier Than | Warning
41982 | CFSD_Adoptions CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23626,23627 |  | 0 | Finish No Earlier Than | Warning
41983 | CFSD_Adoptions CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
41985 | CFSD_Adoptions CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 0d |  | 23632SS | 1 | Finish No Earlier Than | Warning
41986 | CFSD_Adoptions CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 0d | 23631SS |  | 1 | Finish No Earlier Than | Warning
41987 | CFSD_Adoptions CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM | 273 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41988 | CFSD_Adoptions CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
41990 | CFSD_Adoptions CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 23637 | 1 | Finish No Earlier Than | Warning
41991 | CFSD_Adoptions CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 23636 | 23639 | 1 | Finish No Earlier Than | Warning
41993 | CFSD_Adoptions CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 0d | 23637 | 23640FS+1d | 1 | Finish No Earlier Than | Warning
41994 | CFSD_Adoptions CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 0d | 23639FS+1d |  | 1 | Start No Earlier Than | Warning
41996 | CFSD_Adoptions CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM | 35 | 0d |  | 23643 | 1 | Finish No Earlier Than | Warning
41997 | CFSD_Adoptions CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 23642 | 23644FF | 1 | Start No Earlier Than | Warning
41998 | CFSD_Adoptions CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 23643FF | 23645 | 1 | Finish No Earlier Than | Warning
41999 | CFSD_Adoptions CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 0d | 23644 |  | 1 | Finish No Earlier Than | Warning
42000 | CFSD_Adoptions CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
42002 | CFSD_Adoptions CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23649SS | 0 | Start No Earlier Than | Warning
42003 | CFSD_Adoptions CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23648SS | 23650SS | 0 | Finish No Earlier Than | Warning
42004 | CFSD_Adoptions CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23649SS | 23651SS | 0 | Finish No Earlier Than | Warning
42005 | CFSD_Adoptions CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23650SS | 23652SS | 0 | Finish No Earlier Than | Warning
42006 | CFSD_Adoptions CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23651SS | 23653SS | 0 | Finish No Earlier Than | Warning
42007 | CFSD_Adoptions CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23652SS | 23654SS | 0 | Finish No Earlier Than | Warning
42008 | CFSD_Adoptions CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23653SS | 23655SS | 0 | Finish No Earlier Than | Warning
42009 | CFSD_Adoptions CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23654SS | 23656SS | 0 | Finish No Earlier Than | Warning
42010 | CFSD_Adoptions CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23655SS | 23657SS | 0 | Finish No Earlier Than | Warning
42011 | CFSD_Adoptions CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23656SS | 23658SS | 0 | Finish No Earlier Than | Warning
42012 | CFSD_Adoptions CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23657SS |  | 0 | Finish No Earlier Than | Warning
42013 | CFSD_Adoptions CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 12:00 AM | 38 | 324d |  |  | 0 | Finish No Earlier Than | Warning
42014 | CFSD_Adoptions CDSS - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 12:00 AM | 28 | 315d |  |  | 0 | Finish No Earlier Than | Warning
42016 | CFSD_Adoptions CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42017 | CFSD_Adoptions CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 23669 | 0.2 | Finish No Earlier Than | Warning
42018 | CFSD_Adoptions CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42019 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42020 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42021 | CFSD_Adoptions CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 236d |  | 23677 | 0 | Finish No Earlier Than | Warning
42022 | CFSD_Adoptions CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 236d |  | 23678 | 0 | Finish No Earlier Than | Warning
42023 | CFSD_Adoptions CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 23663 |  | 0 | Start No Earlier Than | Warning
42024 | CFSD_Adoptions CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42025 | CFSD_Adoptions CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d |  | 23672SS,23680SS+21d | 0 | Finish No Earlier Than | Warning
42026 | CFSD_Adoptions CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23671SS | 23673SS,23681SS+21d | 0 | Finish No Earlier Than | Warning
42027 | CFSD_Adoptions CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23672SS | 23674SS,23682SS+21d | 0 | Finish No Earlier Than | Warning
42028 | CFSD_Adoptions CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23673SS | 23675SS,23683SS+21d | 0 | Finish No Earlier Than | Warning
42029 | CFSD_Adoptions CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 53 | 310d | 23674SS | 23684SS+21d | 0 | Finish No Earlier Than | Warning
42030 | CFSD_Adoptions CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42031 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 23667 |  | 0 | Start No Earlier Than | Warning
42032 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 23668 |  | 0 | Start No Earlier Than | Warning
42033 | CFSD_Adoptions CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 242d |  | 23687FS+12d | 0 | Finish No Earlier Than | Warning
42039 | CFSD_Adoptions CDSS - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 12:00 AM | 92 | 251d |  | 23687SS+40d | 0 | Finish No Earlier Than | Warning
42040 | CFSD_Adoptions CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42041 | CFSD_Adoptions CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 12:00 AM | 58 | 241d | 23679FS+12d,23685SS+40d |  | 0 | Finish No Earlier Than | Warning
42045 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42046 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42047 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42048 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42049 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42050 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42051 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42052 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42053 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42054 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42055 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42056 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42057 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42058 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42059 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
42060 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
42061 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
42062 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42063 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
42064 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42065 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42066 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42067 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42068 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42072 | CFSD_CSQMB CDSS - Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM | 27 | 0d |  |  | 1 | Start No Earlier Than | Warning
42073 | CFSD_CSQMB CDSS - Schedule Organization Assessment spreadsheet review meeting | September 3, 2024 8:00 AM | January 31, 2025 5:00 PM | 103 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42074 | CFSD_CSQMB CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | September 3, 2024 8:00 AM | February 28, 2025 5:00 PM | 122 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42075 | CFSD_CSQMB CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42076 | CFSD_CSQMB CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42077 | CFSD_CSQMB CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42078 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23725SS | 0 | Finish No Earlier Than | Warning
42079 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23724SS |  | 0 | Finish No Earlier Than | Warning
42080 | CFSD_CSQMB CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42081 | CFSD_CSQMB CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42082 | CFSD_CSQMB CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23729SS | 0 | Finish No Earlier Than | Warning
42085 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23732SS | 0 | Start No Earlier Than | Warning
42087 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23734SS | 0 | Start No Earlier Than | Warning
42089 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23736SS | 0 | Start No Earlier Than | Warning
42091 | CFSD_CSQMB CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42092 | CFSD_CSQMB CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42095 | CFSD_CSQMB CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42097 | CFSD_CSQMB CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42098 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42099 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42100 | CFSD_CSQMB CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 23747 | 1 | Finish No Earlier Than | Warning
42101 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 23746 | 23748FS-1d | 1 | Finish No Earlier Than | Warning
42102 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 23747FS-1d |  | 0.4 | Start No Earlier Than | Warning
42103 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42104 | CFSD_CSQMB CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23751FS-1d | 1 | Finish No Earlier Than | Warning
42105 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23750FS-1d | 23752 | 0.2 | Finish No Earlier Than | Warning
42106 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23751 |  | 0 | Finish No Earlier Than | Warning
42107 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42108 | CFSD_CSQMB CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23755 | 0 | Start No Earlier Than | Warning
42109 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23754 | 23756 | 0 | Finish No Earlier Than | Warning
42110 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23755 |  | 0 | Finish No Earlier Than | Warning
42111 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42112 | CFSD_CSQMB CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23759 | 0 | Finish No Earlier Than | Warning
42113 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23758 | 23761FS-1d | 0 | Finish No Earlier Than | Warning
42114 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42115 | CFSD_CSQMB CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23759FS-1d |  | 0 | Finish No Earlier Than | Warning
42116 | CFSD_CSQMB CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42117 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42118 | CFSD_CSQMB CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42119 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42123 | CFSD_CSQMB CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d | 23768SS |  | 1 | Finish No Earlier Than | Warning
42124 | CFSD_CSQMB CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42125 | CFSD_CSQMB CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42127 | CFSD_CSQMB CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42128 | CFSD_CSQMB CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42129 | CFSD_CSQMB CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 298d |  | 23776SS,23779 | 0.4 | Start No Earlier Than | Warning
42136 | CFSD_CSQMB CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23783FS+1d,23785SS | 0 | Finish No Earlier Than | Warning
42139 | CFSD_CSQMB CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 23782SS | 23786 | 1 | Finish No Earlier Than | Warning
42140 | CFSD_CSQMB CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23785 | 23787SS,23788 | 0 | Finish No Earlier Than | Warning
42141 | CFSD_CSQMB CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23786SS | 23788 | 0 | Finish No Earlier Than | Warning
42142 | CFSD_CSQMB CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23786,23787 |  | 0 | Finish No Earlier Than | Warning
42143 | CFSD_CSQMB CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
42144 | CFSD_CSQMB CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42146 | CFSD_CSQMB CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 23793 | 1 | Finish No Earlier Than | Warning
42147 | CFSD_CSQMB CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 23792 |  | 1 | Finish No Earlier Than | Warning
42149 | CFSD_CSQMB CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23796SS | 0 | Start No Earlier Than | Warning
42150 | CFSD_CSQMB CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23795SS | 23797SS | 0 | Finish No Earlier Than | Warning
42151 | CFSD_CSQMB CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23796SS | 23798SS | 0 | Finish No Earlier Than | Warning
42152 | CFSD_CSQMB CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23797SS | 23799SS | 0 | Finish No Earlier Than | Warning
42153 | CFSD_CSQMB CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23798SS | 23800SS | 0 | Finish No Earlier Than | Warning
42154 | CFSD_CSQMB CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23799SS | 23801SS | 0 | Finish No Earlier Than | Warning
42155 | CFSD_CSQMB CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23800SS | 23802SS | 0 | Finish No Earlier Than | Warning
42156 | CFSD_CSQMB CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23801SS | 23803SS | 0 | Finish No Earlier Than | Warning
42157 | CFSD_CSQMB CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23802SS | 23804SS | 0 | Finish No Earlier Than | Warning
42158 | CFSD_CSQMB CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23803SS | 23805SS | 0 | Finish No Earlier Than | Warning
42159 | CFSD_CSQMB CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23804SS |  | 0 | Finish No Earlier Than | Warning
42160 | CFSD_CSQMB CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42161 | CFSD_CSQMB CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42163 | CFSD_CSQMB CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42164 | CFSD_CSQMB CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 23816 | 0 | Finish No Earlier Than | Warning
42165 | CFSD_CSQMB CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42166 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42167 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42168 | CFSD_CSQMB CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23824 | 0 | Finish No Earlier Than | Warning
42169 | CFSD_CSQMB CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23825 | 0 | Finish No Earlier Than | Warning
42170 | CFSD_CSQMB CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 23810 |  | 0 | Start No Earlier Than | Warning
42171 | CFSD_CSQMB CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42172 | CFSD_CSQMB CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23819SS,23827SS+20d | 0 | Start No Earlier Than | Warning
42177 | CFSD_CSQMB CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42178 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23814 |  | 0 | Start No Earlier Than | Warning
42179 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23815 |  | 0 | Start No Earlier Than | Warning
42180 | CFSD_CSQMB CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23834FS+13d | 0 | Finish No Earlier Than | Warning
42186 | CFSD_CSQMB CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23834SS+40d | 0 | Start No Earlier Than | Warning
42187 | CFSD_CSQMB CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42192 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 23 | 0d |  |  | 1 | Start No Earlier Than | Warning
42193 | CFSD_Permanency CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42194 | CFSD_Permanency CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42195 | CFSD_Permanency CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42196 | CFSD_Permanency CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42197 | CFSD_Permanency CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42198 | CFSD_Permanency CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42199 | CFSD_Permanency CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42200 | CFSD_Permanency CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42201 | CFSD_Permanency CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42202 | CFSD_Permanency CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42203 | CFSD_Permanency CDSS - Monthly Readiness Meetings | September 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42204 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42205 | CFSD_Permanency CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42206 | CFSD_Permanency CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42207 | CFSD_Permanency CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
42208 | CFSD_Permanency CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
42209 | CFSD_Permanency CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
42210 | CFSD_Permanency CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42211 | CFSD_Permanency CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
42212 | CFSD_Permanency CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42213 | CFSD_Permanency CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42214 | CFSD_Permanency CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42215 | CFSD_Permanency CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42216 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42220 | CFSD_Permanency CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42222 | CFSD_Permanency CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM | 37 | 0d |  |  | 1 | Start No Earlier Than | Warning
42223 | CFSD_Permanency CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42224 | CFSD_Permanency CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42225 | CFSD_Permanency CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42226 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 23873SS | 0 | Finish No Earlier Than | Warning
42227 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 23872SS |  | 0 | Finish No Earlier Than | Warning
42228 | CFSD_Permanency CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42229 | CFSD_Permanency CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42230 | CFSD_Permanency CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 23877SS | 0 | Finish No Earlier Than | Warning
42233 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 23880SS | 0 | Start No Earlier Than | Warning
42235 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 23882SS | 0 | Start No Earlier Than | Warning
42237 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 23884SS | 0 | Start No Earlier Than | Warning
42239 | CFSD_Permanency CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42240 | CFSD_Permanency CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42243 | CFSD_Permanency CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42245 | CFSD_Permanency CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42246 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42247 | CFSD_Permanency CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 23894 | 1 | Finish No Earlier Than | Warning
42248 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 23893 | 23895FS-1d | 1 | Finish No Earlier Than | Warning
42249 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 23894FS-1d |  | 0.8 | Start No Earlier Than | Warning
42250 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42251 | CFSD_Permanency CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operationa | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 23898FS-1d | 1 | Finish No Earlier Than | Warning
42252 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 23897FS-1d | 23899 | 0.2 | Finish No Earlier Than | Warning
42253 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 23898 |  | 0 | Finish No Earlier Than | Warning
42254 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42255 | CFSD_Permanency CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 23902 | 0 | Start No Earlier Than | Warning
42256 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 23901 | 23903 | 0 | Finish No Earlier Than | Warning
42257 | CFSD_Permanency CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 23902 |  | 0 | Finish No Earlier Than | Warning
42258 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42259 | CFSD_Permanency CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures an | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 23906 | 0 | Finish No Earlier Than | Warning
42260 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 23905 | 23908FS-1d | 0 | Finish No Earlier Than | Warning
42261 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42262 | CFSD_Permanency CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 23906FS-1d |  | 0 | Finish No Earlier Than | Warning
42263 | CFSD_Permanency CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42264 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42265 | CFSD_Permanency CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42266 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42269 | CFSD_Permanency CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 23916SS | 1 | Finish No Earlier Than | Warning
42270 | CFSD_Permanency CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 23915SS |  | 0.2 | Finish No Earlier Than | Warning
42271 | CFSD_Permanency CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42272 | CFSD_Permanency CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 86 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42274 | CFSD_Permanency CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42275 | CFSD_Permanency CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42276 | CFSD_Permanency CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 23923SS,23926 | 1 | Start No Earlier Than | Warning
42283 | CFSD_Permanency CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 23930FS+1d,23932SS | 0 | Finish No Earlier Than | Warning
42286 | CFSD_Permanency CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 23929SS | 23933 | 1 | Finish No Earlier Than | Warning
42287 | CFSD_Permanency CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23932 | 23934SS,23935 | 0 | Finish No Earlier Than | Warning
42288 | CFSD_Permanency CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23933SS | 23935 | 0 | Finish No Earlier Than | Warning
42289 | CFSD_Permanency CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 23933,23934 |  | 0 | Finish No Earlier Than | Warning
42290 | CFSD_Permanency CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
42291 | CFSD_Permanency CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | July 31, 2025 5:00 PM | 64 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42293 | CFSD_Permanency CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 23940 | 1 | Finish No Earlier Than | Warning
42294 | CFSD_Permanency CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 23939 |  | 1 | Finish No Earlier Than | Warning
42296 | CFSD_Permanency CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 23943SS | 0 | Start No Earlier Than | Warning
42297 | CFSD_Permanency CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23942SS | 23944SS | 0 | Finish No Earlier Than | Warning
42298 | CFSD_Permanency CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23943SS | 23945SS | 0 | Finish No Earlier Than | Warning
42299 | CFSD_Permanency CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23944SS | 23946SS | 0 | Finish No Earlier Than | Warning
42300 | CFSD_Permanency CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23945SS | 23947SS | 0 | Finish No Earlier Than | Warning
42301 | CFSD_Permanency CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23946SS | 23948SS | 0 | Finish No Earlier Than | Warning
42302 | CFSD_Permanency CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23947SS | 23949SS | 0 | Finish No Earlier Than | Warning
42303 | CFSD_Permanency CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alt | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23948SS | 23950SS | 0 | Finish No Earlier Than | Warning
42304 | CFSD_Permanency CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23949SS | 23951SS | 0 | Finish No Earlier Than | Warning
42305 | CFSD_Permanency CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23950SS | 23952SS | 0 | Finish No Earlier Than | Warning
42306 | CFSD_Permanency CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 23951SS |  | 0 | Finish No Earlier Than | Warning
42307 | CFSD_Permanency CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42308 | CFSD_Permanency CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42310 | CFSD_Permanency CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42311 | CFSD_Permanency CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 23963 | 0 | Finish No Earlier Than | Warning
42312 | CFSD_Permanency CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42313 | CFSD_Permanency CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42314 | CFSD_Permanency CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42315 | CFSD_Permanency CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23971 | 0 | Finish No Earlier Than | Warning
42316 | CFSD_Permanency CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 23972 | 0 | Finish No Earlier Than | Warning
42317 | CFSD_Permanency CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 23957 |  | 0 | Start No Earlier Than | Warning
42318 | CFSD_Permanency CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42319 | CFSD_Permanency CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 23966SS,23974SS+20d | 0 | Start No Earlier Than | Warning
42324 | CFSD_Permanency CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42325 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23961 |  | 0 | Start No Earlier Than | Warning
42326 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 23962 |  | 0 | Start No Earlier Than | Warning
42327 | CFSD_Permanency CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 23981FS+13d | 0 | Finish No Earlier Than | Warning
42333 | CFSD_Permanency CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 23981SS+40d | 0 | Start No Earlier Than | Warning
42334 | CFSD_Permanency CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42339 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42340 | CFSD_System of Care CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42341 | CFSD_System of Care CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42342 | CFSD_System of Care CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42343 | CFSD_System of Care CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42344 | CFSD_System of Care CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42345 | CFSD_System of Care CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42346 | CFSD_System of Care CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42347 | CFSD_System of Care CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42348 | CFSD_System of Care CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42349 | CFSD_System of Care CDSS - Monthly Readiness Meetings | September 1, 2025 8:00 AM | September 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42350 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42351 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42352 | CFSD_System of Care CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42353 | CFSD_System of Care CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
42354 | CFSD_System of Care CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
42355 | CFSD_System of Care CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
42356 | CFSD_System of Care CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42357 | CFSD_System of Care CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
42358 | CFSD_System of Care CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42359 | CFSD_System of Care CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42360 | CFSD_System of Care CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42361 | CFSD_System of Care CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42362 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42366 | CFSD_System of Care CDSS - Attend Kickoff Meeting | August 1, 2024 8:00 AM | September 30, 2024 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42367 | CFSD_System of Care CDSS - Schedule Organization Assessment spreadsheet review meeting | September 3, 2024 8:00 AM | October 31, 2024 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42369 | CFSD_System of Care CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42370 | CFSD_System of Care CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42371 | CFSD_System of Care CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42372 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24019SS | 0 | Finish No Earlier Than | Warning
42373 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24018SS |  | 0 | Finish No Earlier Than | Warning
42374 | CFSD_System of Care CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42375 | CFSD_System of Care CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42376 | CFSD_System of Care CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24023SS | 0 | Finish No Earlier Than | Warning
42379 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24026SS | 0 | Start No Earlier Than | Warning
42381 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24028SS | 0 | Start No Earlier Than | Warning
42383 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24030SS | 0 | Start No Earlier Than | Warning
42385 | CFSD_System of Care CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42386 | CFSD_System of Care CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42388 | CFSD_System of Care CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | June 2, 2025 5:00 PM | 64 | 0d |  | 24036SS+40d | 1 | Finish No Earlier Than | Warning
42391 | CFSD_System of Care CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42392 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Intake | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42393 | CFSD_System of Care CDSS - Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 30, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42394 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42395 | CFSD_System of Care CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 24042 | 1 | Finish No Earlier Than | Warning
42396 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 24041 | 24043FS-1d | 1 | Finish No Earlier Than | Warning
42397 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24042FS-1d |  | 0 | Start No Earlier Than | Warning
42398 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42399 | CFSD_System of Care CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operat | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 24046FS-1d | 1 | Finish No Earlier Than | Warning
42400 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24045FS-1d | 24047 | 0.2 | Finish No Earlier Than | Warning
42401 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24046 |  | 0 | Finish No Earlier Than | Warning
42402 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42403 | CFSD_System of Care CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24050 | 0 | Start No Earlier Than | Warning
42404 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24049 | 24051 | 0 | Finish No Earlier Than | Warning
42405 | CFSD_System of Care CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24050 |  | 0 | Finish No Earlier Than | Warning
42406 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42407 | CFSD_System of Care CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedure | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24054 | 0 | Finish No Earlier Than | Warning
42408 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24053 | 24056FS-1d | 0 | Finish No Earlier Than | Warning
42409 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42410 | CFSD_System of Care CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24054FS-1d |  | 0 | Finish No Earlier Than | Warning
42411 | CFSD_System of Care CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42412 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42413 | CFSD_System of Care CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42414 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42417 | CFSD_System of Care CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 24064SS | 1 | Finish No Earlier Than | Warning
42418 | CFSD_System of Care CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d | 24063SS |  | 1 | Finish No Earlier Than | Warning
42419 | CFSD_System of Care CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42420 | CFSD_System of Care CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 86 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42422 | CFSD_System of Care CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42423 | CFSD_System of Care CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42424 | CFSD_System of Care CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 24071SS,24074 | 1 | Start No Earlier Than | Warning
42431 | CFSD_System of Care CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24078FS+1d,24080SS | 0 | Finish No Earlier Than | Warning
42434 | CFSD_System of Care CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 24077SS | 24081 | 1 | Finish No Earlier Than | Warning
42435 | CFSD_System of Care CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24080 | 24082SS,24083 | 0 | Finish No Earlier Than | Warning
42436 | CFSD_System of Care CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24081SS | 24083 | 0 | Finish No Earlier Than | Warning
42437 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24081,24082 |  | 0 | Finish No Earlier Than | Warning
42438 | CFSD_System of Care CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
42440 | CFSD_System of Care CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24087SS | 0 | Finish No Earlier Than | Warning
42441 | CFSD_System of Care CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d | 24086SS |  | 0 | Finish No Earlier Than | Warning
42442 | CFSD_System of Care CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM | 273 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42443 | CFSD_System of Care CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42445 | CFSD_System of Care CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 24092 | 1 | Finish No Earlier Than | Warning
42446 | CFSD_System of Care CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 24091 | 24094 | 1 | Finish No Earlier Than | Warning
42448 | CFSD_System of Care CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d | 24092 | 24095FS+1d | 0 | Finish No Earlier Than | Warning
42449 | CFSD_System of Care CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 373d | 24094FS+1d |  | 0 | Start No Earlier Than | Warning
42451 | CFSD_System of Care CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM | 35 | 0d |  | 24098 | 1 | Finish No Earlier Than | Warning
42452 | CFSD_System of Care CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24097 | 24099FF | 0 | Start No Earlier Than | Warning
42453 | CFSD_System of Care CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24098FF | 24100 | 0 | Finish No Earlier Than | Warning
42454 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24099 |  | 0 | Finish No Earlier Than | Warning
42455 | CFSD_System of Care CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
42457 | CFSD_System of Care CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24104SS | 0 | Start No Earlier Than | Warning
42458 | CFSD_System of Care CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24103SS | 24105SS | 0 | Finish No Earlier Than | Warning
42459 | CFSD_System of Care CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24104SS | 24106SS | 0 | Finish No Earlier Than | Warning
42460 | CFSD_System of Care CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24105SS | 24107SS | 0 | Finish No Earlier Than | Warning
42461 | CFSD_System of Care CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24106SS | 24108SS | 0 | Finish No Earlier Than | Warning
42462 | CFSD_System of Care CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24107SS | 24109SS | 0 | Finish No Earlier Than | Warning
42463 | CFSD_System of Care CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24108SS | 24110SS | 0 | Finish No Earlier Than | Warning
42464 | CFSD_System of Care CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24109SS | 24111SS | 0 | Finish No Earlier Than | Warning
42465 | CFSD_System of Care CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24110SS | 24112SS | 0 | Finish No Earlier Than | Warning
42466 | CFSD_System of Care CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24111SS | 24113SS | 0 | Finish No Earlier Than | Warning
42467 | CFSD_System of Care CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24112SS |  | 0 | Finish No Earlier Than | Warning
42468 | CFSD_System of Care CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42469 | CFSD_System of Care CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42471 | CFSD_System of Care CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42472 | CFSD_System of Care CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 24124 | 0 | Finish No Earlier Than | Warning
42473 | CFSD_System of Care CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42474 | CFSD_System of Care CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42475 | CFSD_System of Care CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42476 | CFSD_System of Care CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24132 | 0 | Finish No Earlier Than | Warning
42477 | CFSD_System of Care CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24133 | 0 | Finish No Earlier Than | Warning
42478 | CFSD_System of Care CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 24118 |  | 0 | Start No Earlier Than | Warning
42479 | CFSD_System of Care CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42480 | CFSD_System of Care CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24127SS,24135SS+20d | 0 | Start No Earlier Than | Warning
42485 | CFSD_System of Care CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42486 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24122 |  | 0 | Start No Earlier Than | Warning
42487 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24123 |  | 0 | Start No Earlier Than | Warning
42488 | CFSD_System of Care CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24142FS+13d | 0 | Finish No Earlier Than | Warning
42494 | CFSD_System of Care CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24142SS+40d | 0 | Start No Earlier Than | Warning
42495 | CFSD_System of Care CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42500 | FAD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42501 | FAD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42502 | FAD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42503 | FAD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42504 | FAD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42505 | FAD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42506 | FAD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42507 | FAD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42508 | FAD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42509 | FAD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42510 | FAD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42511 | FAD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42512 | FAD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
42513 | FAD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
42514 | FAD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
42515 | FAD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42516 | FAD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
42517 | FAD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42518 | FAD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42519 | FAD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42520 | FAD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42521 | FAD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42523 | FAD CDSS - Conduct Discovery Conversations | September 3, 2024 8:00 AM | September 30, 2024 5:00 PM | 20 | 0d |  |  | 1 | Start No Earlier Than | Warning
42525 | FAD CDSS - Attend Kickoff Meeting | September 25, 2024 8:00 AM | December 31, 2024 5:00 PM | 66 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42526 | FAD CDSS - Schedule Organization Assessment spreadsheet review meeting | December 16, 2024 8:00 AM | December 31, 2024 5:00 PM | 11 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42527 | FAD CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42528 | FAD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42529 | FAD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42530 | FAD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42531 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24178SS | 0 | Finish No Earlier Than | Warning
42532 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24177SS |  | 0 | Finish No Earlier Than | Warning
42533 | FAD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42534 | FAD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42535 | FAD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24182SS | 0 | Finish No Earlier Than | Warning
42538 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24185SS | 0 | Start No Earlier Than | Warning
42540 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24187SS | 0 | Start No Earlier Than | Warning
42542 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24189SS | 0 | Start No Earlier Than | Warning
42544 | FAD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42545 | FAD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42547 | FAD CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | September 2, 2025 5:00 PM | 128 | 0d |  | 24195SS+40d | 1 | Finish No Earlier Than | Warning
42550 | FAD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42551 | FAD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 24198 | 1 | Finish No Earlier Than | Warning
42552 | FAD CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 24197 | 24199FS-1d | 1 | Finish No Earlier Than | Warning
42553 | FAD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 0d | 24198FS-1d |  | 1 | Start No Earlier Than | Warning
42554 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42555 | FAD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 24202FS-1d | 1 | Finish No Earlier Than | Warning
42556 | FAD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24201FS-1d | 24203 | 0.2 | Finish No Earlier Than | Warning
42557 | FAD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24202 |  | 0 | Finish No Earlier Than | Warning
42558 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42559 | FAD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24206 | 0 | Start No Earlier Than | Warning
42560 | FAD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24205 | 24207 | 0 | Finish No Earlier Than | Warning
42561 | FAD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24206 |  | 0 | Finish No Earlier Than | Warning
42562 | FAD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42563 | FAD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24210 | 0 | Finish No Earlier Than | Warning
42564 | FAD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24209 | 24212FS-1d | 0 | Finish No Earlier Than | Warning
42565 | FAD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42566 | FAD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24210FS-1d |  | 0 | Finish No Earlier Than | Warning
42567 | FAD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42568 | FAD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42569 | FAD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42570 | FAD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42573 | FAD CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | July 21, 2025 5:00 PM | 337 | 0d |  | 24220SS | 1 | Finish No Earlier Than | Warning
42574 | FAD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 24219SS |  | 0.2 | Finish No Earlier Than | Warning
42575 | FAD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42576 | FAD CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 86 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42578 | FAD CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42579 | FAD CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42580 | FAD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 298d |  | 24227SS,24230 | 0.2 | Start No Earlier Than | Warning
42587 | FAD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24234FS+1d,24236SS | 0 | Finish No Earlier Than | Warning
42590 | FAD CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 24233SS | 24237 | 1 | Finish No Earlier Than | Warning
42591 | FAD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24236 | 24238SS,24239 | 0 | Finish No Earlier Than | Warning
42592 | FAD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24237SS | 24239 | 0 | Finish No Earlier Than | Warning
42593 | FAD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24237,24238 |  | 0 | Finish No Earlier Than | Warning
42594 | FAD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
42595 | FAD CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42597 | FAD CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 24244 | 1 | Finish No Earlier Than | Warning
42598 | FAD CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 24243 |  | 1 | Finish No Earlier Than | Warning
42600 | FAD CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM | 35 | 0d |  | 24247 | 1 | Finish No Earlier Than | Warning
42601 | FAD CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24246 | 24248FF | 1 | Start No Earlier Than | Warning
42602 | FAD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24247FF | 24249 | 1 | Finish No Earlier Than | Warning
42603 | FAD CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 0d | 24248 |  | 1 | Finish No Earlier Than | Warning
42604 | FAD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
42606 | FAD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24253SS | 0 | Start No Earlier Than | Warning
42607 | FAD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24252SS | 24254SS | 0 | Finish No Earlier Than | Warning
42608 | FAD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24253SS | 24255SS | 0 | Finish No Earlier Than | Warning
42609 | FAD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24254SS | 24256SS | 0 | Finish No Earlier Than | Warning
42610 | FAD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24255SS | 24257SS | 0 | Finish No Earlier Than | Warning
42611 | FAD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24256SS | 24258SS | 0 | Finish No Earlier Than | Warning
42612 | FAD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24257SS | 24259SS | 0 | Finish No Earlier Than | Warning
42613 | FAD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24258SS | 24260SS | 0 | Finish No Earlier Than | Warning
42614 | FAD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24259SS | 24261SS | 0 | Finish No Earlier Than | Warning
42615 | FAD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24260SS | 24262SS | 0 | Finish No Earlier Than | Warning
42616 | FAD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24261SS |  | 0 | Finish No Earlier Than | Warning
42617 | FAD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42618 | FAD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42620 | FAD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42621 | FAD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 24273 | 0 | Finish No Earlier Than | Warning
42622 | FAD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42623 | FAD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42624 | FAD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42625 | FAD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24281 | 0 | Finish No Earlier Than | Warning
42626 | FAD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24282 | 0 | Finish No Earlier Than | Warning
42627 | FAD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 24267 |  | 0 | Start No Earlier Than | Warning
42628 | FAD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42629 | FAD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24276SS,24284SS+20d | 0 | Start No Earlier Than | Warning
42634 | FAD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42635 | FAD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24271 |  | 0 | Start No Earlier Than | Warning
42636 | FAD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24272 |  | 0 | Start No Earlier Than | Warning
42637 | FAD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24291FS+13d | 0 | Finish No Earlier Than | Warning
42643 | FAD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24291SS+40d | 0 | Start No Earlier Than | Warning
42644 | FAD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42649 | OOE CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42650 | OOE CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42651 | OOE CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42652 | OOE CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42653 | OOE CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42654 | OOE CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42655 | OOE CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42656 | OOE CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42657 | OOE CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42658 | OOE CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42659 | OOE CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42660 | OOE CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 20 | 425d |  |  | 0 | Start No Earlier Than | Warning
42661 | OOE CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 19 | 406d |  |  | 0 | Start No Earlier Than | Warning
42662 | OOE CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
42663 | OOE CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42664 | OOE CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 343d |  |  | 0 | Start No Earlier Than | Warning
42665 | OOE CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42666 | OOE CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42667 | OOE CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42668 | OOE CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42669 | OOE CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42673 | OOE CDSS - Attend Kickoff Meeting | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42674 | OOE CDSS - Schedule Organization Assessment spreadsheet review meeting | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42675 | OOE CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42676 | OOE CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42677 | OOE CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42678 | OOE CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42679 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24326SS | 0 | Finish No Earlier Than | Warning
42680 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24325SS |  | 0 | Finish No Earlier Than | Warning
42681 | OOE CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42682 | OOE CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42683 | OOE CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24330SS | 0 | Finish No Earlier Than | Warning
42686 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24333SS | 0 | Start No Earlier Than | Warning
42688 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24335SS | 0 | Start No Earlier Than | Warning
42690 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24337SS | 0 | Start No Earlier Than | Warning
42692 | OOE CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42693 | OOE CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42697 | OOE CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | June 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 360 | 233d | 24341SS+21d |  | 0.4 | Start No Earlier Than | Warning
42698 | OOE CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42699 | OOE CDSS - Participate in OCM led Process Information Session for Intake | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42700 | OOE CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42701 | OOE CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 24348 | 1 | Finish No Earlier Than | Warning
42702 | OOE CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 24347 | 24349FS-1d | 1 | Finish No Earlier Than | Warning
42703 | OOE CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24348FS-1d |  | 0 | Start No Earlier Than | Warning
42704 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42705 | OOE CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 24352FS-1d | 1 | Finish No Earlier Than | Warning
42706 | OOE CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24351FS-1d | 24353 | 0 | Finish No Earlier Than | Warning
42707 | OOE CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24352 |  | 0 | Finish No Earlier Than | Warning
42708 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42709 | OOE CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24356 | 0 | Start No Earlier Than | Warning
42710 | OOE CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24355 | 24357 | 0 | Finish No Earlier Than | Warning
42711 | OOE CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24356 |  | 0 | Finish No Earlier Than | Warning
42712 | OOE CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42713 | OOE CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24360 | 0 | Finish No Earlier Than | Warning
42714 | OOE CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24359 | 24362FS-1d | 0 | Finish No Earlier Than | Warning
42715 | OOE CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42716 | OOE CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24360FS-1d |  | 0 | Finish No Earlier Than | Warning
42717 | OOE CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42718 | OOE CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42719 | OOE CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42720 | OOE CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42722 | OOE CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42723 | OOE CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 24370SS,24373 | 1 | Start No Earlier Than | Warning
42730 | OOE CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24377SS | 0 | Start No Earlier Than | Warning
42731 | OOE CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24376SS | 24378SS | 0 | Finish No Earlier Than | Warning
42732 | OOE CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24377SS | 24379SS | 0 | Finish No Earlier Than | Warning
42733 | OOE CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24378SS | 24380SS | 0 | Finish No Earlier Than | Warning
42734 | OOE CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24379SS | 24381SS | 0 | Finish No Earlier Than | Warning
42735 | OOE CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24380SS | 24382SS | 0 | Finish No Earlier Than | Warning
42736 | OOE CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24381SS | 24383SS | 0 | Finish No Earlier Than | Warning
42737 | OOE CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24382SS | 24384SS | 0 | Finish No Earlier Than | Warning
42738 | OOE CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24383SS | 24385SS | 0 | Finish No Earlier Than | Warning
42739 | OOE CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24384SS | 24386SS | 0 | Finish No Earlier Than | Warning
42740 | OOE CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24385SS |  | 0 | Finish No Earlier Than | Warning
42741 | OOE CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42742 | OOE CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42744 | OOE CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42745 | OOE CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 24397 | 0 | Finish No Earlier Than | Warning
42746 | OOE CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42747 | OOE CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42748 | OOE CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42749 | OOE CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24405 | 0 | Finish No Earlier Than | Warning
42750 | OOE CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24406 | 0 | Finish No Earlier Than | Warning
42751 | OOE CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 24391 |  | 0 | Start No Earlier Than | Warning
42752 | OOE CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42753 | OOE CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24400SS,24408SS+20d | 0 | Start No Earlier Than | Warning
42758 | OOE CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42759 | OOE CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24395 |  | 0 | Start No Earlier Than | Warning
42760 | OOE CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24396 |  | 0 | Start No Earlier Than | Warning
42761 | OOE CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24415FS+13d | 0 | Finish No Earlier Than | Warning
42767 | OOE CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24415SS+40d | 0 | Start No Earlier Than | Warning
42768 | OOE CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42773 | RADD CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42774 | RADD CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42775 | RADD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42776 | RADD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42777 | RADD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42778 | RADD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42779 | RADD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42780 | RADD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42781 | RADD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42782 | RADD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42783 | RADD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42784 | RADD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42785 | RADD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42786 | RADD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42787 | RADD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
42788 | RADD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
42789 | RADD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
42790 | RADD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42791 | RADD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
42792 | RADD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42793 | RADD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42794 | RADD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42795 | RADD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42796 | RADD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42800 | RADD CDSS - Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM | 27 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42803 | RADD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42804 | RADD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42805 | RADD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42806 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24453SS | 0 | Finish No Earlier Than | Warning
42807 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24452SS |  | 0 | Finish No Earlier Than | Warning
42808 | RADD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42809 | RADD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42810 | RADD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24457SS | 0 | Finish No Earlier Than | Warning
42813 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24460SS | 0 | Start No Earlier Than | Warning
42815 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24462SS | 0 | Start No Earlier Than | Warning
42817 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24464SS | 0 | Start No Earlier Than | Warning
42819 | RADD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42820 | RADD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42825 | RADD CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42826 | RADD CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42827 | RADD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42828 | RADD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 24475 | 1 | Finish No Earlier Than | Warning
42829 | RADD CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 24474 | 24476FS-1d | 1 | Finish No Earlier Than | Warning
42830 | RADD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d | 24475FS-1d |  | 0 | Start No Earlier Than | Warning
42831 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42832 | RADD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 24479FS-1d | 1 | Finish No Earlier Than | Warning
42833 | RADD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24478FS-1d | 24480 | 0.2 | Finish No Earlier Than | Warning
42834 | RADD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24479 |  | 0 | Finish No Earlier Than | Warning
42835 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42836 | RADD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24483 | 0 | Start No Earlier Than | Warning
42837 | RADD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24482 | 24484 | 0 | Finish No Earlier Than | Warning
42838 | RADD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24483 |  | 0 | Finish No Earlier Than | Warning
42839 | RADD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42840 | RADD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24487 | 0 | Finish No Earlier Than | Warning
42841 | RADD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24486 | 24489FS-1d | 0 | Finish No Earlier Than | Warning
42842 | RADD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42843 | RADD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24487FS-1d |  | 0 | Finish No Earlier Than | Warning
42844 | RADD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42845 | RADD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42846 | RADD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42847 | RADD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42850 | RADD CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d |  | 24497SS | 0.6 | Finish No Earlier Than | Warning
42851 | RADD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 405d | 24496SS |  | 0.6 | Finish No Earlier Than | Warning
42852 | RADD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42853 | RADD CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 86 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42855 | RADD CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42856 | RADD CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42857 | RADD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 24504SS,24507 | 1 | Start No Earlier Than | Warning
42864 | RADD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24511FS+1d,24513SS | 0.6 | Finish No Earlier Than | Warning
42867 | RADD CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 24510SS | 24514 | 1 | Finish No Earlier Than | Warning
42868 | RADD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24513 | 24515SS,24516 | 0 | Finish No Earlier Than | Warning
42869 | RADD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24514SS | 24516 | 0 | Finish No Earlier Than | Warning
42870 | RADD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24514,24515 |  | 0 | Finish No Earlier Than | Warning
42871 | RADD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
42873 | RADD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24520SS | 0 | Start No Earlier Than | Warning
42874 | RADD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24519SS | 24521SS | 0 | Finish No Earlier Than | Warning
42875 | RADD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24520SS | 24522SS | 0 | Finish No Earlier Than | Warning
42876 | RADD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24521SS | 24523SS | 0 | Finish No Earlier Than | Warning
42877 | RADD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24522SS | 24524SS | 0 | Finish No Earlier Than | Warning
42878 | RADD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24523SS | 24525SS | 0 | Finish No Earlier Than | Warning
42879 | RADD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24524SS | 24526SS | 0 | Finish No Earlier Than | Warning
42880 | RADD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24525SS | 24527SS | 0 | Finish No Earlier Than | Warning
42881 | RADD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24526SS | 24528SS | 0 | Finish No Earlier Than | Warning
42882 | RADD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24527SS | 24529SS | 0 | Finish No Earlier Than | Warning
42883 | RADD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24528SS |  | 0 | Finish No Earlier Than | Warning
42884 | RADD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
42885 | RADD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
42887 | RADD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
42888 | RADD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 24540 | 0 | Finish No Earlier Than | Warning
42889 | RADD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
42890 | RADD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42891 | RADD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
42892 | RADD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24548 | 0 | Finish No Earlier Than | Warning
42893 | RADD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24549 | 0 | Finish No Earlier Than | Warning
42894 | RADD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 24534 |  | 0 | Start No Earlier Than | Warning
42895 | RADD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
42896 | RADD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24543SS,24551SS+20d | 0 | Start No Earlier Than | Warning
42901 | RADD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
42902 | RADD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24538 |  | 0 | Start No Earlier Than | Warning
42903 | RADD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24539 |  | 0 | Start No Earlier Than | Warning
42904 | RADD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24558FS+13d | 0 | Finish No Earlier Than | Warning
42910 | RADD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24558SS+40d | 0 | Start No Earlier Than | Warning
42911 | RADD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
42916 | SPEI CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42917 | SPEI CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42918 | SPEI CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
42919 | SPEI CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42920 | SPEI CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42921 | SPEI CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42922 | SPEI CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42923 | SPEI CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42924 | SPEI CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
42925 | SPEI CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
42926 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
42927 | SPEI CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
42928 | SPEI CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
42929 | SPEI CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
42930 | SPEI CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
42931 | SPEI CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM | 22 | 384d |  |  | 0 | Start No Earlier Than | Warning
42932 | SPEI CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
42933 | SPEI CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
42934 | SPEI CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
42935 | SPEI CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
42936 | SPEI CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 21 | 278d |  |  | 0 | Start No Earlier Than | Warning
42937 | SPEI CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
42938 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
42942 | SPEI CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 27, 2024 5:00 PM | 63 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42943 | SPEI CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42944 | SPEI CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM | 65 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42945 | SPEI CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM | 75 | 307d |  |  | 0 | Start No Earlier Than | Warning
42946 | SPEI CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM | 54 | 296d |  |  | 0 | Start No Earlier Than | Warning
42947 | SPEI CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM | 62 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42948 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM | 20 | 424d |  | 24595SS | 0 | Finish No Earlier Than | Warning
42949 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 29 | 415d | 24594SS |  | 0 | Finish No Earlier Than | Warning
42950 | SPEI CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42951 | SPEI CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42952 | SPEI CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM | 65 | 342d |  | 24599SS | 0 | Finish No Earlier Than | Warning
42955 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 20 | 332d |  | 24602SS | 0 | Start No Earlier Than | Warning
42957 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 311d |  | 24604SS | 0 | Start No Earlier Than | Warning
42959 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 289d |  | 24606SS | 0 | Start No Earlier Than | Warning
42961 | SPEI CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM | 22 | 296d |  |  | 0 | Start No Earlier Than | Warning
42962 | SPEI CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 5 | 284d |  |  | 0 | Start No Earlier Than | Warning
42963 | SPEI CDSS - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM | 44 | 234d |  |  | 0 | Start No Earlier Than | Warning
42966 | SPEI CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM | 21 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42968 | SPEI CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42969 | SPEI CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM | 43 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42970 | SPEI CDSS - Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 30, 2025 5:00 PM | 40 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42971 | SPEI CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42972 | SPEI CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  | 24619 | 1 | Finish No Earlier Than | Warning
42973 | SPEI CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d | 24618 | 24620FS-1d | 1 | Finish No Earlier Than | Warning
42975 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42976 | SPEI CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  | 24623FS-1d | 1 | Finish No Earlier Than | Warning
42977 | SPEI CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d | 24622FS-1d | 24624 | 0.2 | Finish No Earlier Than | Warning
42978 | SPEI CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d | 24623 |  | 0 | Finish No Earlier Than | Warning
42979 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42980 | SPEI CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 405d |  | 24627 | 0 | Start No Earlier Than | Warning
42981 | SPEI CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 405d | 24626 | 24628 | 0 | Finish No Earlier Than | Warning
42982 | SPEI CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d | 24627 |  | 0 | Finish No Earlier Than | Warning
42983 | SPEI CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42984 | SPEI CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 364d |  | 24631 | 0 | Finish No Earlier Than | Warning
42985 | SPEI CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 363d | 24630 | 24633FS-1d | 0 | Finish No Earlier Than | Warning
42986 | SPEI CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Finish No Earlier Than | Warning
42987 | SPEI CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 43 | 363d | 24631FS-1d |  | 0 | Finish No Earlier Than | Warning
42988 | SPEI CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM | 39 | 446d |  |  | 0 | Finish No Earlier Than | Warning
42989 | SPEI CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Finish No Earlier Than | Warning
42990 | SPEI CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM | 43 | 364d |  |  | 0 | Finish No Earlier Than | Warning
42991 | SPEI CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
42994 | SPEI CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d |  | 24641SS | 1 | Finish No Earlier Than | Warning
42995 | SPEI CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 490 | 0d | 24640SS |  | 1 | Finish No Earlier Than | Warning
42996 | SPEI CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM | 49 | 357d |  |  | 0 | Start No Earlier Than | Warning
42997 | SPEI CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
42999 | SPEI CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 108 | 0d |  |  | 1 | Finish No Earlier Than | Warning
43000 | SPEI CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43001 | SPEI CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  | 24648SS,24651 | 1 | Start No Earlier Than | Warning
43008 | SPEI CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM | 58 | 373d |  | 24655FS+1d,24657SS | 0 | Finish No Earlier Than | Warning
43011 | SPEI CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 0d | 24654SS | 24658 | 1 | Finish No Earlier Than | Warning
43012 | SPEI CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24657 | 24659SS,24660 | 0 | Finish No Earlier Than | Warning
43013 | SPEI CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24658SS | 24660 | 0 | Finish No Earlier Than | Warning
43014 | SPEI CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24658,24659 |  | 0 | Finish No Earlier Than | Warning
43015 | SPEI CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Start No Earlier Than | Warning
43017 | SPEI CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 0d |  | 24664SS | 1 | Finish No Earlier Than | Warning
43018 | SPEI CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 0d | 24663SS |  | 1 | Finish No Earlier Than | Warning
43019 | SPEI CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM | 273 | 0d |  |  | 1 | Finish No Earlier Than | Warning
43020 | SPEI CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
43022 | SPEI CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM | 64 | 0d |  | 24669 | 1 | Finish No Earlier Than | Warning
43023 | SPEI CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 28 | 0d | 24668 | 24671 | 1 | Finish No Earlier Than | Warning
43025 | SPEI CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 0d | 24669 | 24672FS+1d | 1 | Finish No Earlier Than | Warning
43026 | SPEI CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 111 | 0d | 24671FS+1d |  | 1 | Start No Earlier Than | Warning
43028 | SPEI CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM | 35 | 0d |  | 24675 | 1 | Finish No Earlier Than | Warning
43029 | SPEI CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24674 | 24676FF | 1 | Start No Earlier Than | Warning
43030 | SPEI CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24675FF | 24677 | 1 | Finish No Earlier Than | Warning
43031 | SPEI CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 0d | 24676 |  | 1 | Finish No Earlier Than | Warning
43032 | SPEI CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
43034 | SPEI CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24681SS | 0 | Start No Earlier Than | Warning
43035 | SPEI CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24680SS | 24682SS | 0 | Finish No Earlier Than | Warning
43036 | SPEI CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24681SS | 24683SS | 0 | Finish No Earlier Than | Warning
43037 | SPEI CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24682SS | 24684SS | 0 | Finish No Earlier Than | Warning
43038 | SPEI CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24683SS | 24685SS | 0 | Finish No Earlier Than | Warning
43039 | SPEI CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24684SS | 24686SS | 0 | Finish No Earlier Than | Warning
43040 | SPEI CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24685SS | 24687SS | 0 | Finish No Earlier Than | Warning
43041 | SPEI CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24686SS | 24688SS | 0 | Finish No Earlier Than | Warning
43042 | SPEI CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24687SS | 24689SS | 0 | Finish No Earlier Than | Warning
43043 | SPEI CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24688SS | 24690SS | 0 | Finish No Earlier Than | Warning
43044 | SPEI CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24689SS |  | 0 | Finish No Earlier Than | Warning
43045 | SPEI CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM | 19 | 343d |  |  | 0 | Start No Earlier Than | Warning
43046 | SPEI CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM | 29 | 333d |  |  | 0 | Start No Earlier Than | Warning
43048 | SPEI CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Finish No Earlier Than | Warning
43049 | SPEI CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM | 123 | 196d |  | 24701 | 0 | Finish No Earlier Than | Warning
43050 | SPEI CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM | 187 | 322d |  |  | 0 | Finish No Earlier Than | Warning
43051 | SPEI CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43052 | SPEI CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43053 | SPEI CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24709 | 0 | Finish No Earlier Than | Warning
43054 | SPEI CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM | 62 | 275d |  | 24710 | 0 | Finish No Earlier Than | Warning
43055 | SPEI CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d | 24695 |  | 0 | Start No Earlier Than | Warning
43056 | SPEI CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM | 19 | 358d |  |  | 0 | Finish No Earlier Than | Warning
43057 | SPEI CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 30 | 299d |  | 24704SS,24712SS+20d | 0 | Start No Earlier Than | Warning
43062 | SPEI CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Finish No Earlier Than | Warning
43063 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24699 |  | 0 | Start No Earlier Than | Warning
43064 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 89 | 274d | 24700 |  | 0 | Start No Earlier Than | Warning
43065 | SPEI CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM | 50 | 279d |  | 24719FS+13d | 0 | Finish No Earlier Than | Warning
43071 | SPEI CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 44 | 283d |  | 24719SS+40d | 0 | Start No Earlier Than | Warning
43072 | SPEI CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM | 33 | 300d |  |  | 0 | Finish No Earlier Than | Warning
43079 | Karuk TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43080 | Karuk TR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43081 | Karuk TR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43082 | Karuk TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
43083 | Karuk TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
43084 | Karuk TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
43085 | Karuk TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
43086 | Karuk TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
43087 | Karuk TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
43088 | Karuk TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
43089 | Karuk TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
43090 | Karuk TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43091 | Karuk TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
43092 | Karuk TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 22 | 278d |  |  | 0 | Start No Earlier Than | Warning
43093 | Karuk TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
43094 | Karuk TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
43095 | Karuk TR - Attend Executive Briefing Meeting | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
43096 | Karuk TR - Schedule Kickoff Meeting | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43097 | Karuk TR - Attend Kickoff Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  | 24743FS-1d | 1 | Finish No Earlier Than | Warning
43099 | Karuk TR - Confirm Tribal Implementation Team | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43100 | Karuk TR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43101 | Karuk TR - IL to demonstrate how to access Imp Portal throughÂ cwds.ca.gov | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43102 | Karuk TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
43103 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM | 21 | 423d |  |  | 0 | Start No Earlier Than | Warning
43104 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d |  |  | 0 | Start No Earlier Than | Warning
43105 | Karuk TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 24751SS | 0 | Start No Earlier Than | Warning
43106 | Karuk TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 24750SS |  | 0 | Start No Earlier Than | Warning
43107 | Karuk TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM | 65 | 341d |  |  | 0 | Start No Earlier Than | Warning
43108 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
43109 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d |  |  | 0 | Start No Earlier Than | Warning
43110 | Karuk TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
43111 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
43112 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d |  |  | 0 | Start No Earlier Than | Warning
43113 | Karuk TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
43114 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM | 22 | 277d |  |  | 0 | Start No Earlier Than | Warning
43115 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d |  |  | 0 | Start No Earlier Than | Warning
43116 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  | 24762SS | 0 | Start No Earlier Than | Warning
43117 | Karuk TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d | 24761SS | 24763SS | 0 | Finish No Earlier Than | Warning
43118 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 24762SS |  | 0 | Finish No Earlier Than | Warning
43119 | Karuk TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
43122 | Karuk TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43123 | Karuk TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
43124 | Karuk TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
43125 | Karuk TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM | 40 | 217d |  |  | 0 | Start No Earlier Than | Warning
43126 | Karuk TR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
43128 | Karuk TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.2 | Start No Earlier Than | Warning
43130 | Karuk TR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43131 | Karuk TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43132 | Karuk TR - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
43133 | Karuk TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d |  |  | 0 | Start No Earlier Than | Warning
43134 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43135 | Karuk TR - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
43136 | Karuk TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | Start No Earlier Than | Warning
43137 | Karuk TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d |  |  | 0 | Start No Earlier Than | Warning
43138 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43139 | Karuk TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | Start No Earlier Than | Warning
43140 | Karuk TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
43141 | Karuk TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43142 | Karuk TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43143 | Karuk TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
43144 | Karuk TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43145 | Karuk TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
43146 | Karuk TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d |  |  | 0 | Start No Earlier Than | Warning
43147 | Karuk TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
43150 | Karuk TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d |  | 24796SS,24797 | 0 | Start No Earlier Than | Warning
43154 | Karuk TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24800 | 0 | Start No Earlier Than | Warning
43157 | Karuk TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d |  |  | 0 | Start No Earlier Than | Warning
43158 | Karuk TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  | 24804SS | 0 | Start No Earlier Than | Warning
43160 | Karuk TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | Finish No Earlier Than | Warning
43161 | Karuk TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
43163 | Karuk TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24809SS | 0 | Start No Earlier Than | Warning
43165 | Karuk TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 274 | 362d |  |  | 0 | Start No Earlier Than | Warning
43167 | Karuk TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24813 | 0 | Start No Earlier Than | Warning
43168 | Karuk TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24812 |  | 0 | Start No Earlier Than | Warning
43170 | Karuk TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 345d |  | 24816 | 0 | Start No Earlier Than | Warning
43172 | Karuk TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24816SS | 24818 | 0 | Start No Earlier Than | Warning
43173 | Karuk TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24816,24817 |  | 0 | Start No Earlier Than | Warning
43174 | Karuk TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
43176 | Karuk TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24822SS | 0 | Start No Earlier Than | Warning
43177 | Karuk TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24821SS | 24823SS | 0 | Start No Earlier Than | Warning
43178 | Karuk TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24822SS | 24824SS | 0 | Start No Earlier Than | Warning
43179 | Karuk TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24823SS | 24825SS | 0 | Start No Earlier Than | Warning
43180 | Karuk TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24824SS | 24826SS | 0 | Start No Earlier Than | Warning
43181 | Karuk TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24825SS | 24827SS | 0 | Start No Earlier Than | Warning
43182 | Karuk TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24826SS | 24828SS | 0 | Start No Earlier Than | Warning
43183 | Karuk TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24827SS | 24829SS | 0 | Start No Earlier Than | Warning
43184 | Karuk TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24828SS | 24830SS | 0 | Start No Earlier Than | Warning
43185 | Karuk TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24829SS | 24831SS | 0 | Start No Earlier Than | Warning
43186 | Karuk TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24830SS |  | 0 | Start No Earlier Than | Warning
43187 | Karuk TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
43188 | Karuk TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Finish No Earlier Than | Warning
43190 | Karuk TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
43191 | Karuk TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
43192 | Karuk TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
43193 | Karuk TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
43194 | Karuk TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
43195 | Karuk TR - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d |  |  | 0 | Start No Earlier Than | Warning
43196 | Karuk TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
43197 | Karuk TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d |  | 24843SS | 0 | Start No Earlier Than | Warning
43202 | Karuk TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d |  | 24848SS | 0 | Start No Earlier Than | Warning
43203 | Karuk TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 24847SS |  | 0 | Start No Earlier Than | Warning
43204 | Karuk TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 311d |  |  | 0 | Start No Earlier Than | Warning
43205 | Karuk TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43206 | Karuk TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43207 | Karuk TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
43208 | Karuk TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 24854SS | 0 | Start No Earlier Than | Warning
43213 | Karuk TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  |  | 0 | Start No Earlier Than | Warning
43214 | Karuk TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
43215 | Karuk TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d |  |  | 0 | Start No Earlier Than | Warning
43219 | Yurok TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43220 | Yurok TR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43221 | Yurok TR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43222 | Yurok TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 23 | 485d |  |  | 0 | Start No Earlier Than | Warning
43223 | Yurok TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 19 | 466d |  |  | 0 | Start No Earlier Than | Warning
43224 | Yurok TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22 | 445d |  |  | 0 | Start No Earlier Than | Warning
43225 | Yurok TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM | 21 | 424d |  |  | 0 | Start No Earlier Than | Warning
43226 | Yurok TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20 | 405d |  |  | 0 | Start No Earlier Than | Warning
43227 | Yurok TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM | 22 | 385d |  |  | 0 | Start No Earlier Than | Warning
43228 | Yurok TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
43229 | Yurok TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 21 | 342d |  |  | 0 | Start No Earlier Than | Warning
43230 | Yurok TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43231 | Yurok TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
43232 | Yurok TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 22 | 278d |  |  | 0 | Start No Earlier Than | Warning
43233 | Yurok TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  |  | 0 | Start No Earlier Than | Warning
43234 | Yurok TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 22 | 235d |  |  | 0 | Start No Earlier Than | Warning
43235 | Yurok TR - Attend Executive Briefing Meeting | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 19 | 0d |  |  | 1 | Start No Earlier Than | Warning
43236 | Yurok TR - Schedule Kickoff Meeting | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43237 | Yurok TR - Attend Kickoff Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d |  | 24883FS-1d | 1 | Finish No Earlier Than | Warning
43239 | Yurok TR - Confirm Tribal Implementation Team | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 21 | 0d |  |  | 1 | Start No Earlier Than | Warning
43240 | Yurok TR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43241 | Yurok TR - IL to demonstrate how to access Imp Portal throughÂ cwds.ca.gov | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43242 | Yurok TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 63 | 445d |  |  | 0 | Start No Earlier Than | Warning
43243 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM | 21 | 423d |  |  | 0 | Start No Earlier Than | Warning
43244 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 30 | 414d |  |  | 0 | Start No Earlier Than | Warning
43245 | Yurok TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  | 24891SS | 0 | Start No Earlier Than | Warning
43246 | Yurok TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d | 24890SS |  | 0 | Start No Earlier Than | Warning
43247 | Yurok TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM | 65 | 341d |  |  | 0 | Start No Earlier Than | Warning
43248 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 22 | 363d |  |  | 0 | Start No Earlier Than | Warning
43249 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 33 | 352d |  |  | 0 | Start No Earlier Than | Warning
43250 | Yurok TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM | 75 | 268d |  |  | 0 | Start No Earlier Than | Warning
43251 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22 | 299d |  |  | 0 | Start No Earlier Than | Warning
43252 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 33 | 288d |  |  | 0 | Start No Earlier Than | Warning
43253 | Yurok TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM | 55 | 257d |  |  | 0 | Start No Earlier Than | Warning
43254 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM | 22 | 277d |  |  | 0 | Start No Earlier Than | Warning
43255 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 31 | 268d |  |  | 0 | Start No Earlier Than | Warning
43256 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d |  | 24902SS | 0 | Start No Earlier Than | Warning
43257 | Yurok TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 21 | 257d | 24901SS | 24903SS | 0 | Finish No Earlier Than | Warning
43258 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 32 | 246d | 24902SS |  | 0 | Finish No Earlier Than | Warning
43259 | Yurok TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM | 5 | 245d |  |  | 0 | Start No Earlier Than | Warning
43262 | Yurok TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43263 | Yurok TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 | 342d |  |  | 0 | Start No Earlier Than | Warning
43264 | Yurok TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 43 | 278d |  |  | 0 | Start No Earlier Than | Warning
43265 | Yurok TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM | 40 | 217d |  |  | 0 | Start No Earlier Than | Warning
43266 | Yurok TR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 40 | 195d |  |  | 0 | Start No Earlier Than | Warning
43268 | Yurok TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 381 | 233d |  |  | 0.2 | Start No Earlier Than | Warning
43270 | Yurok TR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 22 | 0d |  |  | 1 | Start No Earlier Than | Warning
43271 | Yurok TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43272 | Yurok TR - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 42 | 0d |  |  | 1 | Finish No Earlier Than | Warning
43273 | Yurok TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 63 | 466d |  |  | 0 | Start No Earlier Than | Warning
43274 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43275 | Yurok TR - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 44 | 0d |  |  | 1 | Start No Earlier Than | Warning
43276 | Yurok TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | Start No Earlier Than | Warning
43277 | Yurok TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 80 | 405d |  |  | 0 | Start No Earlier Than | Warning
43278 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43279 | Yurok TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 44 | 485d |  |  | 0 | Start No Earlier Than | Warning
43280 | Yurok TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
43281 | Yurok TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43282 | Yurok TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 28 | 357d |  |  | 0 | Start No Earlier Than | Warning
43283 | Yurok TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 40 | 445d |  |  | 0 | Start No Earlier Than | Warning
43284 | Yurok TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 40 | 405d |  |  | 0 | Start No Earlier Than | Warning
43285 | Yurok TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM | 6 | 357d |  |  | 0 | Start No Earlier Than | Warning
43286 | Yurok TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 44 | 362d |  |  | 0 | Start No Earlier Than | Warning
43287 | Yurok TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 76 | 309d |  |  | 0 | Start No Earlier Than | Warning
43290 | Yurok TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 490 | 356d |  | 24936SS,24937 | 0 | Start No Earlier Than | Warning
43294 | Yurok TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24940 | 0 | Start No Earlier Than | Warning
43297 | Yurok TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 508d |  |  | 0 | Start No Earlier Than | Warning
43298 | Yurok TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d |  | 24944SS | 0 | Start No Earlier Than | Warning
43300 | Yurok TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM | 17 | 346d |  |  | 0 | Finish No Earlier Than | Warning
43301 | Yurok TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
43303 | Yurok TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 251 | 424d |  | 24949SS | 0 | Start No Earlier Than | Warning
43305 | Yurok TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 274 | 362d |  |  | 0 | Start No Earlier Than | Warning
43307 | Yurok TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 59 | 373d |  | 24953 | 0 | Start No Earlier Than | Warning
43308 | Yurok TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 112 | 373d | 24952 |  | 0 | Start No Earlier Than | Warning
43310 | Yurok TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 36 | 345d |  | 24956 | 0 | Start No Earlier Than | Warning
43312 | Yurok TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24956SS | 24958 | 0 | Start No Earlier Than | Warning
43313 | Yurok TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17 | 345d | 24956,24957 |  | 0 | Start No Earlier Than | Warning
43314 | Yurok TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Start No Earlier Than | Warning
43316 | Yurok TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d |  | 24962SS | 0 | Start No Earlier Than | Warning
43317 | Yurok TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24961SS | 24963SS | 0 | Start No Earlier Than | Warning
43318 | Yurok TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24962SS | 24964SS | 0 | Start No Earlier Than | Warning
43319 | Yurok TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24963SS | 24965SS | 0 | Start No Earlier Than | Warning
43320 | Yurok TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24964SS | 24966SS | 0 | Start No Earlier Than | Warning
43321 | Yurok TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24965SS | 24967SS | 0 | Start No Earlier Than | Warning
43322 | Yurok TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24966SS | 24968SS | 0 | Start No Earlier Than | Warning
43323 | Yurok TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24967SS | 24969SS | 0 | Start No Earlier Than | Warning
43324 | Yurok TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24968SS | 24970SS | 0 | Start No Earlier Than | Warning
43325 | Yurok TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24969SS | 24971SS | 0 | Start No Earlier Than | Warning
43326 | Yurok TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 83 | 362d | 24970SS |  | 0 | Start No Earlier Than | Warning
43327 | Yurok TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM | 39 | 323d |  |  | 0 | Start No Earlier Than | Warning
43328 | Yurok TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM | 29 | 314d |  |  | 0 | Finish No Earlier Than | Warning
43330 | Yurok TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 188 | 384d |  |  | 0.2 | Start No Earlier Than | Warning
43331 | Yurok TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 124 | 384d |  |  | 0 | Start No Earlier Than | Warning
43332 | Yurok TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM | 188 | 320d |  |  | 0 | Start No Earlier Than | Warning
43333 | Yurok TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
43334 | Yurok TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 63 | 362d |  |  | 0 | Start No Earlier Than | Warning
43335 | Yurok TR - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 189 | 196d |  |  | 0 | Start No Earlier Than | Warning
43336 | Yurok TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 20 | 357d |  |  | 0 | Start No Earlier Than | Warning
43337 | Yurok TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 54 | 309d |  | 24983SS | 0 | Start No Earlier Than | Warning
43342 | Yurok TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d |  | 24988SS | 0 | Start No Earlier Than | Warning
43343 | Yurok TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 128 | 235d | 24987SS |  | 0 | Start No Earlier Than | Warning
43344 | Yurok TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM | 51 | 311d |  |  | 0 | Start No Earlier Than | Warning
43345 | Yurok TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43346 | Yurok TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22 | 321d |  |  | 0 | Start No Earlier Than | Warning
43347 | Yurok TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM | 88 | 255d |  |  | 0 | Start No Earlier Than | Warning
43348 | Yurok TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 103 | 240d |  | 24994SS | 0 | Start No Earlier Than | Warning
43353 | Yurok TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM | 93 | 250d |  |  | 0 | Start No Earlier Than | Warning
43354 | Yurok TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM | 34 | 299d |  |  | 0 | Start No Earlier Than | Warning
43355 | Yurok TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 59 | 240d |  |  | 0 | Start No Earlier Than | Warning

## Baseline_Late
UID | Task Name | Start | Finish | Duration | Total Slack | Predecessors | Successors | Percent Complete | Baseline_Finish | Variance_Days | Severity
1 | CARES V1 | April 1, 2021 8:00 AM | October 11, 2027 5:00 PM | 1638 | 0 |  |  | 0.65 | April 19, 2027 5:00 PM | 175 | Critical
11270 | M10: Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d |  |  | 1 | April 11, 2025 5:00 PM | 119 | Critical
11287 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 608SS | 378SS | 1 | April 11, 2025 5:00 PM | 119 | Critical
11288 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 377SS | 380 | 1 | April 11, 2025 5:00 PM | 119 | Critical
6482 | Design Cycle 2 | September 2, 2024 8:00 AM | December 2, 2024 5:00 PM | 63 | 0d |  |  | 1 | September 27, 2024 5:00 PM | 66 | Critical
6484 | Case Management Group 1 Design Cycle 2 - Conduct Pre-build Prototype Demo | September 11, 2024 8:00 AM | October 31, 2024 5:00 PM | 37 | 0d | 577 | 579SS+7d | 1 | September 19, 2024 5:00 PM | 42 | Critical
6485 | Case Management Group 1 Design Cycle 2 - Review & implement Pre-build Prototype Demo Observations | September 20, 2024 8:00 AM | December 2, 2024 5:00 PM | 49 | 0d | 578SS+7d | 4381SS+29d,4405SS+40d,4417FS+1d,4428FS+1d,581FS-1d | 1 | September 27, 2024 5:00 PM | 66 | Critical
11361 | M10: Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 198 | 0d | 608SS | 631 | 1 | April 10, 2025 5:00 PM | 120 | Critical
252 | Case Management: Design | July 17, 2024 8:00 AM | August 8, 2025 5:00 PM | 268 | 0d |  |  | 1 | May 30, 2025 5:00 PM | 70 | Critical
471 | Milestone 13: Adoption (CARESV1-531) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d |  |  | 1 | May 30, 2025 5:00 PM | 70 | Critical
472 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 608SS | 690SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
473 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 689SS | 691SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
474 | M13: B3 07.02 Find Potential Adoptive Matches and Make Placement (CARESV1-9) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 690SS | 692SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
475 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 691SS | 693SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
476 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 692SS | 694SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
477 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 693SS | 709,1407SS-417d | 1 | May 30, 2025 5:00 PM | 70 | Critical
478 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d |  |  | 1 | May 30, 2025 5:00 PM | 70 | Critical
479 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 678,608SS | 697SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
480 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 696SS | 698SS | 1 | May 30, 2025 5:00 PM | 70 | Critical
481 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 697SS | 699FF,715 | 1 | May 30, 2025 5:00 PM | 70 | Critical
266 | Case Management Design Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 0 | 0d | 698FF | 4506FS+18d | 1 | May 30, 2025 5:00 PM | 70 | Critical
2824 | Case Management - User Feedback Session 1 (6.1, 7, 9, 10, 10.1, 11, 13) | October 6, 2025 8:00 AM | October 29, 2025 5:00 PM | 18 | 23.08d |  |  | 0 | September 23, 2025 5:00 PM | 36 | Critical
2825 | Case Management User Feedback Session 1 - Conduct and Gather User Feedback | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 | 23.08d | 715SS+39d | 720,4475 | 0 | August 11, 2025 5:00 PM | 67 | Critical
2826 | Case Management User Feedback Session 1 - Capture and Document in JIRA | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 2 | 23.08d | 719 | 724,721,4475 | 0 | August 25, 2025 5:00 PM | 57 | Critical
11205 | Case Management User Feedback Session 1 - Complete Build / SIT | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 1 | 23.08d | 720 | 722FS-5d,4475 | 0 | September 9, 2025 5:00 PM | 43 | Critical
11207 | Case Management User Feedback Session 1 - State QA | October 16, 2025 8:00 AM | October 29, 2025 5:00 PM | 10 | 23.08d | 721FS-5d | 724,4475 | 0 | September 23, 2025 5:00 PM | 36 | Critical
843 | Courts: Design | July 1, 2024 8:00 AM | June 27, 2025 5:00 PM | 250 | 0d |  |  | 1 | March 28, 2025 5:00 PM | 91 | Critical
850 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | July 22, 2024 8:00 AM | June 27, 2025 5:00 PM | 236 | 0d |  |  | 1 | March 28, 2025 5:00 PM | 91 | Critical
851 | M16: B1 09.11 Generate Notices (CARESV1-67) | July 22, 2024 8:00 AM | June 27, 2025 5:00 PM | 234 | 0d | 806FF,849FS-10d | 853SS,867,871,876 | 1 | March 28, 2025 5:00 PM | 91 | Critical
966 | Resource Family Approval | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | December 30, 2025 5:00 PM | 24 | Critical
967 | Resource Family Approval: Holistic Design Milestones | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | December 30, 2025 5:00 PM | 24 | Critical
968 | Group 1 Resource Family Approval (Milestones 26, 27, 28) | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM | 652 | 430d |  |  | 0.77 | December 30, 2025 5:00 PM | 24 | Critical
2656 | Resource Family Approval: Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 254 | 0d |  |  | 1 | May 2, 2025 5:00 PM | 154 | Critical
2657 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 254 | 0d |  |  | 1 | March 28, 2025 5:00 PM | 189 | Critical
2663 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 151 | 0d | 996SS+103d | 998SS | 1 | March 28, 2025 5:00 PM | 189 | Critical
2664 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 151 | 0d | 997SS | 1011 | 1 | March 28, 2025 5:00 PM | 189 | Critical
2688 | Milestone 28: Legal Action (CARESV1-504) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d |  |  | 0 | November 28, 2025 5:00 PM | 28 | Critical
2689 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1011SS+38d | 1025SS,4661FS-19d | 0 | November 28, 2025 5:00 PM | 28 | Critical
2690 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1024SS | 1026SS,4661FS-19d | 0 | November 28, 2025 5:00 PM | 28 | Critical
2691 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | -32d | 1025SS | 4661FS-19d | 0 | November 28, 2025 5:00 PM | 28 | Critical
2701 | Resource Family: SIT | October 6, 2025 8:00 AM | December 26, 2025 5:00 PM | 57 | -13d |  |  | 0 | November 28, 2025 5:00 PM | 28 | Critical
2715 | Milestone 28: Legal Action (CARESV1-504) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d |  |  | 0 | November 28, 2025 5:00 PM | 28 | Critical
2716 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1029SS+38d | 1043SS,1060 | 0 | November 28, 2025 5:00 PM | 28 | Critical
2717 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1042SS | 1044SS | 0 | November 28, 2025 5:00 PM | 28 | Critical
2718 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 40d | 1043SS | 4665FF | 0 | November 28, 2025 5:00 PM | 28 | Critical
2719 | Resource Family Approval: State QA | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM | 37 | 430d |  |  | 0.18 | December 30, 2025 5:00 PM | 24 | Critical
2697 | Milestone 28: Legal Action (CARESV1-504) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 171d |  |  | 0 | December 30, 2025 5:00 PM | 24 | Critical
2698 | M28: B1: RFA Legal actions (CARESV1-17) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 171d | 1042 | 1061SS,1062SS | 0 | December 30, 2025 5:00 PM | 24 | Critical
2699 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 171d | 1060SS | 1062SS | 0 | December 30, 2025 5:00 PM | 24 | Critical
2700 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 171d | 1060SS,1061SS | 1080SS,5503 | 0 | December 30, 2025 5:00 PM | 24 | Critical
2767 | Resource Family Approval: Joint Review | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM | 37 | 430d |  |  | 0 | December 30, 2025 5:00 PM | 24 | Critical
2798 | Milestone 28: Legal Action (CARESV1-504) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d |  |  | 0 | December 30, 2025 5:00 PM | 24 | Critical
2800 | M28: B1: RFA Legal actions (CARESV1-17) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1062SS | 1081SS | 0 | December 30, 2025 5:00 PM | 24 | Critical
2801 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1080SS | 1082SS | 0 | December 30, 2025 5:00 PM | 24 | Critical
2802 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 430d | 1081SS | 1083FF | 0 | December 30, 2025 5:00 PM | 24 | Critical
10457 | Milestone 28: Legal Action (CARESV1-504) Complete | January 23, 2026 5:00 PM | January 23, 2026 5:00 PM | 0 | 430d | 1082FF |  | 0 | December 30, 2025 5:00 PM | 24 | Critical
1176 | Financial Management | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | December 30, 2025 5:00 PM | 52 | Critical
1190 | Financial Management: Holistic Design Milestones | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | December 30, 2025 5:00 PM | 52 | Critical
4899 | Group 1 Financial Management (Milestones 23/23.1, 24) | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM | 537 | 411d |  |  | 0.8 | December 30, 2025 5:00 PM | 52 | Critical
1225 | Financial Management: Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d |  |  | 1 | July 11, 2025 5:00 PM | 84 | Critical
1226 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d |  |  | 1 | July 11, 2025 5:00 PM | 84 | Critical
1227 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1130,1092SS | 1134SS,1135SS,1136SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
1229 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1133SS,1134SS | 1136SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
1230 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1133SS,1135SS | 1144FS+57d,1432SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
1231 | Milestone 24: Track Assistance Costs (CARESV1-506) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d |  |  | 1 | July 11, 2025 5:00 PM | 84 | Critical
1232 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1092SS | 1139SS,1140SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
1233 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1138SS | 1140SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
1234 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1138SS,1139SS | 1141FF,1149 | 1 | July 11, 2025 5:00 PM | 84 | Critical
2851 | Financial Management Design Milestone Completion | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 0d | 1140FF | 1144 | 1 | July 11, 2025 5:00 PM | 84 | Critical
1235 | Financial Management: Build | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM | 75 | -50d |  |  | 0 | December 30, 2025 5:00 PM | 24 | Critical
1236 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d |  |  | 0 | November 28, 2025 5:00 PM | 56 | Critical
1237 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1136FS+57d,1141 | 1145SS,1146SS,1147SS,1366SS | 0 | November 28, 2025 5:00 PM | 56 | Critical
1238 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS | 1146SS | 0 | November 28, 2025 5:00 PM | 56 | Critical
1239 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS,1145SS | 1147SS,4685FS-19d | 0 | November 28, 2025 5:00 PM | 56 | Critical
1240 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -50d | 1144SS,1146SS | 1154SS,4685FS-19d | 0 | November 28, 2025 5:00 PM | 56 | Critical
1245 | Financial Management: SIT | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM | 75 | -16d |  |  | 0 | November 28, 2025 5:00 PM | 56 | Critical
1246 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d |  |  | 0 | November 28, 2025 5:00 PM | 56 | Critical
1247 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1147SS | 1155SS,1156SS,1157SS,4689 | 0 | November 28, 2025 5:00 PM | 56 | Critical
1248 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1154SS | 1156SS,4689 | 0 | November 28, 2025 5:00 PM | 56 | Critical
1249 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | -44d | 1154SS,1155SS | 1157SS,4689 | 0 | November 28, 2025 5:00 PM | 56 | Critical
1250 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 18 | 0d | 1154SS,1156SS | 1164,4684FF | 0 | November 28, 2025 5:00 PM | 56 | Critical
1255 | Financial Management: State QA | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0.14 | December 30, 2025 5:00 PM | 52 | Critical
1256 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0.25 | December 30, 2025 5:00 PM | 52 | Critical
1257 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 0d | 1157 | 1165SS,1166SS,1167SS,1357SS | 0 | December 30, 2025 5:00 PM | 52 | Critical
1258 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1164SS | 1166SS | 0 | December 30, 2025 5:00 PM | 52 | Critical
1260 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 0d | 1164SS,1166SS | 1176SS,5511,4690SS-36d | 0 | December 30, 2025 5:00 PM | 52 | Critical
1265 | Financial Management: Joint Review | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM | 56 | 411d |  |  | 0 | December 30, 2025 5:00 PM | 52 | Critical
1266 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d |  |  | 0 | December 30, 2025 5:00 PM | 52 | Critical
1268 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1167SS | 1177SS,1178SS,1179SS | 0 | December 30, 2025 5:00 PM | 52 | Critical
1269 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS | 1178SS | 0 | December 30, 2025 5:00 PM | 52 | Critical
1270 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS,1177SS | 1179SS | 0 | December 30, 2025 5:00 PM | 52 | Critical
1271 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 19 | 411d | 1176SS,1178SS | 1180FF | 0 | December 30, 2025 5:00 PM | 52 | Critical
10458 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) Complete | February 20, 2026 5:00 PM | February 20, 2026 5:00 PM | 0 | 411d | 1179FF,1173FF |  | 0 | December 30, 2025 5:00 PM | 52 | Critical
7532 | Eligibility | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | December 30, 2025 5:00 PM | 27 | Critical
7533 | Eligibility: Holistic Design Milestones | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | December 30, 2025 5:00 PM | 27 | Critical
7534 | Group 1 Eligibility (Milestone 21) | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM | 692 | 429d |  |  | 0.87 | December 30, 2025 5:00 PM | 27 | Critical
7623 | Eligibility: Joint Review | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d |  |  | 0 | December 30, 2025 5:00 PM | 27 | Critical
7624 | Milestone 21: Eligibility Programs (CARESV1-511) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d |  |  | 0 | December 30, 2025 5:00 PM | 27 | Critical
7638 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1249 |  | 0 | December 29, 2025 5:00 PM | 28 | Critical
7625 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1249 | 1254SS,1255SS,1256SS | 0 | December 30, 2025 5:00 PM | 27 | Critical
7626 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS | 1255SS | 0 | December 30, 2025 5:00 PM | 27 | Critical
7627 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS,1254SS | 1256SS | 0 | December 30, 2025 5:00 PM | 27 | Critical
7628 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 19 | 429d | 1253SS,1255SS | 1257FF | 0 | December 30, 2025 5:00 PM | 27 | Critical
10460 | Milestone 21: Eligibility Programs (CARESV1-511) Complete | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 429d | 1256FF |  | 0 | December 30, 2025 5:00 PM | 27 | Critical
6335 | Shared Services | November 3, 2022 8:00 AM | March 2, 2026 3:00 PM | 829.75 | 405.25d |  |  | 0.93 | December 30, 2025 5:00 PM | 61 | Critical
6340 | Shared Services - Design Cycle 1 | July 15, 2024 8:00 AM | June 13, 2025 5:00 PM | 231 | 0d |  |  | 1 | April 4, 2025 5:00 PM | 70 | Critical
6341 | Shared Services - Design Cycle 1 - Prepare Design | July 15, 2024 8:00 AM | May 30, 2025 5:00 PM | 221 | 0d | 1261SS | 1294SS+10d | 1 | March 21, 2025 5:00 PM | 70 | Critical
6342 | Shared Services - Design Cycle 1 - Review Design | July 29, 2024 8:00 AM | June 6, 2025 5:00 PM | 216 | 0d | 1293SS+10d | 1295SS+5d | 1 | March 28, 2025 5:00 PM | 70 | Critical
6343 | Shared Services - Design Cycle 1 - Revise and Finalize Design | August 5, 2024 8:00 AM | June 13, 2025 5:00 PM | 216 | 0d | 1294SS+5d | 1297SS+63d | 1 | April 4, 2025 5:00 PM | 70 | Critical
11203 | Shared Services Milestones | August 14, 2023 8:00 AM | March 2, 2026 3:00 PM | 637.75 | 405.25d |  |  | 0.89 | December 30, 2025 5:00 PM | 61 | Critical
11111 | Shared Services - Deletion (M11) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 608SS | 1328 | 1 | May 30, 2025 5:00 PM | 70 | Critical
11126 | Shared Services - MDM (Master Data Management) (M26) - Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 254 | 0d | 934SS | 1344 | 1 | March 28, 2025 5:00 PM | 189 | Critical
11128 | Shared Services - Notifications (reminders, alerts) (M15) | August 14, 2023 8:00 AM | October 3, 2025 5:00 PM | 538 | 505d |  |  | 0.92 | February 28, 2025 5:00 PM | 217 | Critical
11130 | Shared Services - Notifications (reminders, alerts) (M15) - Build / SIT | October 7, 2024 8:00 AM | August 8, 2025 5:00 PM | 210 | 0d | 433SS,1347 | 1349 | 1 | January 28, 2025 5:00 PM | 192 | Critical
11373 | Shared Services - Notifications (reminders, alerts) (M15) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 39 | 505d | 439SS,1348 |  | 0 | February 28, 2025 5:00 PM | 217 | Critical
11132 | Shared Services - Person Profile (M13) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 608SS | 1352 | 1 | May 30, 2025 5:00 PM | 70 | Critical
11134 | Shared Services - Product Metrics (M23) | December 4, 2024 8:00 AM | February 4, 2026 1:48 PM | 292.6 | 422.4d |  |  | 0.83 | December 30, 2025 5:00 PM | 35 | Critical
11135 | Shared Services - Product Metrics (M23) - Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1092SS | 1356 | 1 | July 11, 2025 5:00 PM | 84 | Critical
11375 | Shared Services - Product Metrics (M23) - State QA | December 1, 2025 8:00 AM | February 4, 2026 1:48 PM | 19 | 422.4d | 1164SS,1356FS-127d |  | 0.6 | December 30, 2025 5:00 PM | 35 | Critical
11143 | Shared Services - Search (M23) | December 4, 2024 8:00 AM | March 2, 2026 3:00 PM | 309.75 | 405.25d |  |  | 0.84 | December 30, 2025 5:00 PM | 61 | Critical
11144 | Shared Services - Search (M23) - Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 210 | 0d | 1092SS | 1366 | 1 | July 11, 2025 5:00 PM | 84 | Critical
11145 | Shared Services - Search (M23) - Build / SIT | December 29, 2025 8:00 AM | February 23, 2026 5:00 PM | 38 | 0d | 1144SS,1365 | 1367 | 0 | November 28, 2025 5:00 PM | 87 | Critical
11377 | Shared Services - Search (M23) - State QA | December 1, 2025 8:00 AM | March 2, 2026 3:00 PM | 19 | 405.25d | 1366 |  | 0.75 | December 30, 2025 5:00 PM | 61 | Critical
11147 | Shared Services - Worker Mgmt./ Hierarchy (M26) - Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 254 | 448d | 934SS | 1370 | 0.94 | March 28, 2025 5:00 PM | 189 | Critical
11150 | Shared Services - Workload View (M13) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 200 | 0d | 608SS | 1374 | 1 | May 30, 2025 5:00 PM | 70 | Critical
4289 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM | 366 | 448d |  |  | 0.73 | November 28, 2025 5:00 PM | 28 | Critical
4291 | Milestone (LIS/FAS data) 26.1 - Design | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 151 | -7d |  | 1427 | 0.86 | March 7, 2025 5:00 PM | 210 | Critical
4292 | Milestone (LIS/FAS data) 26.1 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | -7d | 1426 | 1428,4644 | 0 | November 7, 2025 5:00 PM | 21 | Critical
4293 | Milestone (LIS/FAS data) 26.1 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1427 | 1429FF | 0.08 | November 28, 2025 5:00 PM | 28 | Critical
11590 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1428FF |  | 0 | November 28, 2025 5:00 PM | 28 | Critical
4294 | Milestone CECRIS 23.2 (CARESV1-45376) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM | 366 | 448d |  |  | 0.79 | October 31, 2025 5:00 PM | 56 | Critical
4296 | Milestone CECRIS 23.2 - Design | March 10, 2025 8:00 AM | October 3, 2025 5:00 PM | 146 | 0d | 1136SS,1431 | 1433 | 1 | June 27, 2025 5:00 PM | 98 | Critical
4297 | Milestone CECRIS 23.2 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 | 446d | 1432 | 1434,523FF+21d | 0 | October 31, 2025 5:00 PM | 28 | Critical
4298 | Milestone CECRIS 23.2 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 | 448d | 1433 | 1435 | 0 | October 31, 2025 5:00 PM | 56 | Critical
11591 | Milestone CECRIS 23.2 (CARESV1-45376) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 | 448d | 1434 |  | 0 | October 31, 2025 5:00 PM | 56 | Critical
6814 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) | April 24, 2023 8:00 AM | October 3, 2025 5:00 PM | 616 | 505d |  |  | 0.97 | July 11, 2025 5:00 PM | 84 | Critical
6470 | M10.1: State QA | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d |  |  | 0.96 | July 11, 2025 5:00 PM | 84 | Critical
6471 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 0d | 1461SS | 1464SS,1467SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
6472 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1463SS | 1465SS | 0.96 | July 11, 2025 5:00 PM | 84 | Critical
6473 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1464SS | 1469FF | 0.92 | July 11, 2025 5:00 PM | 84 | Critical
6477 | M10.1: Joint Review | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d |  |  | 0.84 | July 11, 2025 5:00 PM | 84 | Critical
6478 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 0d | 1463SS | 1468SS | 1 | July 11, 2025 5:00 PM | 84 | Critical
6479 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1467SS | 1469SS | 0.92 | July 11, 2025 5:00 PM | 84 | Critical
6480 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 189 | 505d | 1468SS,1465FF | 1470 | 0.59 | July 11, 2025 5:00 PM | 84 | Critical
11592 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 0 | 505d | 1469 |  | 0 | July 11, 2025 5:00 PM | 84 | Critical
2861 | EUST - 2 | October 4, 2024 8:00 AM | June 10, 2025 5:00 PM | 169 | 0d |  |  | 1 | May 5, 2025 5:00 PM | 36 | Critical
4842 | EUST 2 - Identification and validation of scenarios | October 22, 2024 8:00 AM | February 28, 2025 5:00 PM | 87 | 0d |  |  | 1 | December 30, 2024 5:00 PM | 60 | Critical
43567 | EUST 3 - Preparation | October 28, 2024 8:00 AM | February 26, 2026 5:00 PM | 332 | 407d? |  |  | 0.29 | March 18, 2025 5:00 PM | 345 | Critical
43568 | EUST 3 - Scenario Writing | May 19, 2025 8:00 AM | December 26, 2025 5:00 PM | 154 | 448d? |  |  | 0.6 | December 30, 2024 5:00 PM | 361 | Critical
43717 | EUST 3 - Deployment to CARES EUST V1 | January 6, 2026 8:00 AM | January 27, 2026 5:00 PM | 15 | 428d |  |  | 0 | March 18, 2025 5:00 PM | 315 | Critical
3120 | Document Migration | January 30, 2024 8:00 AM | June 25, 2025 5:00 PM | 354 | 0d |  |  | 1 | December 5, 2024 5:00 PM | 202 | Critical
3121 | Document Ingestion | January 30, 2024 8:00 AM | September 27, 2024 5:00 PM | 170 | 0d |  |  | 1 | September 6, 2024 5:00 PM | 21 | Critical
3124 | Document Ingestion - DC QA | August 26, 2024 8:00 AM | September 27, 2024 5:00 PM | 25 | 0d | 2130 | 2132 | 1 | July 26, 2024 5:00 PM | 63 | Critical
3131 | Data Conversion LOE (CARESV1-13763) | June 20, 2022 8:00 AM | December 9, 2026 3:24 PM | 1120.8 | 210.2d |  |  | 0.9 | August 27, 2026 5:00 PM | 103 | Critical
3155 | Generating document linking metadata - Build Document Ingestion and Linking Reports | June 26, 2025 8:00 AM | July 2, 2025 5:00 PM | 5 | 0d | 2142 | 2198FS-24d | 1 | September 19, 2024 5:00 PM | 286 | Critical
5573 | Trigger analysis for data conversion - Analysis for DC Cycle5 scope objects | January 6, 2025 8:00 AM | July 10, 2025 9:07 AM | 42 | 0d | 2167FS-24d | 2363 | 1 | March 6, 2025 5:00 PM | 125 | Critical
5575 | Legacy User loads | January 1, 2024 8:00 AM | September 5, 2025 5:00 PM | 423 | 0d |  |  | 1 | February 28, 2025 5:00 PM | 189 | Critical
5579 | Legacy User loads - Build revision with the Legacy vs CARES Persona finalized mapping | July 14, 2025 8:00 AM | September 5, 2025 5:00 PM | 39 | 0d | 2203FS+135d | 2205SS-150d,2212SS+8d | 1 | February 28, 2025 5:00 PM | 189 | Critical
3190 | Structured Data Conversion Activities | June 20, 2022 8:00 AM | May 8, 2026 3:24 PM | 973.8 | 13.2d |  |  | 0.92 | December 30, 2025 5:00 PM | 128 | Critical
3263 | Data Conversion - Milestone 18 (CARESV1-13748) | October 15, 2024 8:00 AM | January 22, 2026 3:00 PM | 316.75 | 87.25d |  |  | 0.81 | December 30, 2025 5:00 PM | 22 | Critical
3266 | Data Conversion - Milestone 18 - Build and SIT | April 2, 2025 8:00 AM | January 22, 2026 3:00 PM | 189 | 87.25d | 876SS,2295FS-29d | 2379 | 0.66 | December 30, 2025 5:00 PM | 22 | Critical
3287 | Data Conversion - Milestone 26 (CARESV1-13757) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM | 401.8 | 13.2d |  |  | 0.75 | December 29, 2025 5:00 PM | 129 | Critical
3290 | Data Conversion - Milestone 26 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 105 | 13.2d | 1011SS,2315 | 2379 | 0.49 | December 29, 2025 5:00 PM | 129 | Critical
3291 | Data Conversion - Milestone 27 (CARESV1-13758) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM | 401.8 | 13.2d |  |  | 0.75 | December 29, 2025 5:00 PM | 129 | Critical
3294 | Data Conversion - Milestone 27 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 105 | 13.2d | 1019SS,2319 | 2379 | 0.49 | December 29, 2025 5:00 PM | 129 | Critical
3295 | Data Conversion - Milestone 28 (CARESV1-13759) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM | 401.8 | 13.2d |  |  | 0.75 | December 29, 2025 5:00 PM | 129 | Critical
3298 | Data Conversion - Milestone 28 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 105 | 13.2d | 1019SS,2323 | 2379 | 0.49 | December 29, 2025 5:00 PM | 129 | Critical
3311 | Conversion Cycles | April 3, 2023 8:00 AM | December 9, 2026 3:24 PM | 925.8 | 210.2d |  |  | 0.67 | August 27, 2026 5:00 PM | 103 | Critical
5620 | Cycle 5 (Court II, Case Management II) | March 24, 2025 8:00 AM | September 12, 2025 9:07 AM | 120.14 | 0d |  |  | 1 | August 8, 2025 5:00 PM | 34 | Critical
5625 | Conversion Cycle 5 - Micro Conversion Execution | July 10, 2025 9:07 AM | September 12, 2025 9:07 AM | 45 | 0d | 2185,2192,2198,2362 | 2364FS-55d | 1 | July 22, 2025 5:00 PM | 51 | Critical
5626 | Conversion Cycle 5 - SIT | June 25, 2025 9:07 AM | July 9, 2025 9:07 AM | 9 | 0d | 2363FS-55d | 2365 | 1 | May 30, 2025 5:00 PM | 39 | Critical
5627 | Conversion Cycle 5 - QA | July 9, 2025 9:07 AM | July 22, 2025 9:07 AM | 9 | 0d | 2364 | 2366 | 1 | June 27, 2025 5:00 PM | 24 | Critical
5640 | Full Mock Cycle 1 | May 8, 2026 3:24 PM | June 29, 2026 3:24 PM | 35 | 13.2d |  |  | 0 | March 3, 2026 5:00 PM | 117 | Critical
5641 | Conversion Full Mock Cycle 1 - ETL & SIT | May 8, 2026 3:24 PM | June 8, 2026 3:24 PM | 20 | 13.2d | 2264,2268,2272,2276,2280,2284,2288,2292,2296,2300,2304,2308,2316,2320,2324,2248,2252 | 2380 | 0 | February 9, 2026 5:00 PM | 118 | Critical
5642 | Conversion Full Mock Cycle 1 - QA | June 8, 2026 3:24 PM | June 15, 2026 3:24 PM | 5 | 13.2d | 2379 | 2381 | 0 | February 17, 2026 5:00 PM | 117 | Critical
5643 | Conversion Full Mock Cycle 1 - County Testing | June 15, 2026 3:24 PM | June 22, 2026 3:24 PM | 5 | 13.2d | 2380 | 2382 | 0 | February 24, 2026 5:00 PM | 117 | Critical
5644 | Conversion Full Mock Cycle 1 - Review & Closure | June 22, 2026 3:24 PM | June 29, 2026 3:24 PM | 5 | 13.2d | 2381 | 2384 | 0 | March 3, 2026 5:00 PM | 117 | Critical
5645 | Full Mock Cycle 2 | June 29, 2026 3:24 PM | August 18, 2026 3:24 PM | 35 | 13.2d |  |  | 0 | May 4, 2026 5:00 PM | 105 | Critical
5646 | Conversion Full Mock Cycle 2 - ETL & SIT | June 29, 2026 3:24 PM | July 28, 2026 3:24 PM | 20 | 13.2d | 2382 | 2385 | 0 | April 13, 2026 5:00 PM | 105 | Critical
5647 | Conversion Full Mock Cycle 2 - QA | July 28, 2026 3:24 PM | August 4, 2026 3:24 PM | 5 | 13.2d | 2384 | 2386 | 0 | April 20, 2026 5:00 PM | 105 | Critical
5648 | Conversion Full Mock Cycle 2 - County Testing | August 4, 2026 3:24 PM | August 11, 2026 3:24 PM | 5 | 13.2d | 2385 | 2387 | 0 | April 27, 2026 5:00 PM | 105 | Critical
5649 | Conversion Full Mock Cycle 2 - Review & Closure | August 11, 2026 3:24 PM | August 18, 2026 3:24 PM | 5 | 13.2d | 2386 | 2389 | 0 | May 4, 2026 5:00 PM | 105 | Critical
5650 | Full Mock Cycle 3 | August 18, 2026 3:24 PM | October 7, 2026 3:24 PM | 35 | 13.2d |  |  | 0 | June 29, 2026 5:00 PM | 99 | Critical
5651 | Conversion Full Mock Cycle 3 - ETL & SIT | August 18, 2026 3:24 PM | September 16, 2026 3:24 PM | 20 | 13.2d | 2219,2387 | 2390 | 0 | June 8, 2026 5:00 PM | 99 | Critical
5652 | Conversion Full Mock Cycle 3 - QA | September 16, 2026 3:24 PM | September 23, 2026 3:24 PM | 5 | 13.2d | 2389 | 2391 | 0 | June 15, 2026 5:00 PM | 99 | Critical
5653 | Conversion Full Mock Cycle 3 - County Testing | September 23, 2026 3:24 PM | September 30, 2026 3:24 PM | 5 | 13.2d | 2390 | 2392 | 0 | June 22, 2026 5:00 PM | 99 | Critical
5654 | Conversion Full Mock Cycle 3 - Review & Closure | September 30, 2026 3:24 PM | October 7, 2026 3:24 PM | 5 | 13.2d | 2391 | 5630,2394FS-1d | 0 | June 29, 2026 5:00 PM | 99 | Critical
11580 | Final Conversion | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM | 43 | 210.2d |  |  | 0 | August 27, 2026 5:00 PM | 103 | Critical
11581 | Final Structured Data Conversion | October 6, 2026 3:24 PM | November 3, 2026 3:24 PM | 20 | 210.2d | 2392FS-1d | 2395FS-13d | 0 | July 27, 2026 5:00 PM | 98 | Critical
11582 | Final Conversion - Link Documents to Structured Data | October 15, 2026 3:24 PM | December 9, 2026 3:24 PM | 36 | 210.2d | 2394FS-13d | 2396FS-43d | 0 | August 27, 2026 5:00 PM | 103 | Critical
11583 | Final Conversion - Run Micro Conversion (Structured Data and Documents) | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM | 43 | 210.2d | 2395FS-43d |  | 0 | August 27, 2026 5:00 PM | 103 | Critical
6943 | County Transition | May 1, 2023 8:00 AM | November 24, 2026 5:00 PM | 897 | 219d |  |  | 0.46 | May 26, 2026 5:00 PM | 182 | Critical
11548 | County - External Systems | July 9, 2025 8:00 AM | November 24, 2026 5:00 PM | 348 | 219d |  |  | 0 | May 26, 2026 5:00 PM | 182 | Critical
11549 | County - External Systems - Identify | July 9, 2025 8:00 AM | February 11, 2026 5:00 PM | 150 | 219d | 1049SS-100d | 2431 | 0 | August 8, 2025 5:00 PM | 187 | Critical
11550 | County - External Systems - Prioritize | February 12, 2026 8:00 AM | October 14, 2026 5:00 PM | 170 | 219d | 2430 | 2432FS-170d | 0 | April 15, 2026 5:00 PM | 182 | Critical
11559 | Monitor Progress for Prioritized External Systems | February 12, 2026 8:00 AM | November 24, 2026 5:00 PM | 198 | 219d | 2431FS-170d |  | 0 | May 26, 2026 5:00 PM | 182 | Critical
3619 | Testing - ADA (CARESV1-5420) | April 4, 2022 8:00 AM | January 30, 2026 5:00 PM | 960 | 425d |  |  | 0.34 | January 5, 2026 5:00 PM | 25 | Critical
3621 | Perform ADA Validation (CARESV1-5421) | January 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 269 | 425d |  |  | 0.33 | January 5, 2026 5:00 PM | 25 | Critical
3622 | M1: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2627FS+420d | 2630SS,2631SS,2632SS,2633SS,2634SS,2638SS,2645SS,2649SS,2651SS | 1 | May 31, 2022 5:00 PM | 1025 | Critical
3623 | M2: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | July 15, 2022 5:00 PM | 980 | Critical
3624 | M3: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | August 12, 2022 5:00 PM | 952 | Critical
3625 | M4: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | September 9, 2022 5:00 PM | 924 | Critical
3626 | M5: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | October 7, 2022 5:00 PM | 896 | Critical
3627 | M6: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS | 2635FS-40d,2636FS-40d,2637FS-40d,2639FS-40d,2640FS-40d,2641FS-40d,2642FS-40d,2643FS-40d,2644FS-40d,2646FS-40d,2647FS-40d,2648FS-40d,2650FS-40d,2652FS-40d,2653FS-40d,2654FS-40d,2655FS-40d,2656FS-40d,2657FS-40d,2658FS-40d,2659FS-40d,2660FS-40d,2661FS-40d... | 1 | November 4, 2022 5:00 PM | 868 | Critical
3628 | M6.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | December 2, 2022 5:00 PM | 1155 | Critical
3629 | M7: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | December 30, 2022 5:00 PM | 1127 | Critical
3630 | M7.1 ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | January 27, 2023 5:00 PM | 1099 | Critical
3631 | M8: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | February 24, 2023 5:00 PM | 756 | Critical
3632 | M9: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | March 24, 2023 5:00 PM | 1043 | Critical
3633 | M10: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | April 21, 2023 5:00 PM | 1015 | Critical
3634 | M10.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | May 19, 2023 5:00 PM | 987 | Critical
3635 | M11: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | June 16, 2023 5:00 PM | 959 | Critical
3636 | M13: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | July 14, 2023 5:00 PM | 931 | Critical
3637 | M14: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | August 11, 2023 5:00 PM | 903 | Critical
3638 | M15: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | September 8, 2023 5:00 PM | 560 | Critical
3640 | M16: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | November 3, 2023 5:00 PM | 819 | Critical
3641 | M17: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | December 1, 2023 5:00 PM | 791 | Critical
3642 | M18: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | December 29, 2023 5:00 PM | 763 | Critical
3643 | M19: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | January 26, 2024 5:00 PM | 420 | Critical
3644 | M21: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | February 26, 2024 5:00 PM | 704 | Critical
3645 | M20: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 53 | 0d | 2629SS |  | 1 | March 25, 2024 5:00 PM | 361 | Critical
3646 | M20.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | April 23, 2024 5:00 PM | 647 | Critical
3647 | M23: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | May 21, 2024 5:00 PM | 619 | Critical
3648 | M23.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | June 19, 2024 5:00 PM | 590 | Critical
3649 | M23.2: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | July 18, 2024 5:00 PM | 561 | Critical
3650 | M24: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | August 15, 2024 5:00 PM | 533 | Critical
3651 | M26: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | September 12, 2024 5:00 PM | 505 | Critical
3652 | M26.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | October 10, 2024 5:00 PM | 477 | Critical
3653 | M27: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | November 7, 2024 5:00 PM | 449 | Critical
3654 | M28: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | December 10, 2024 5:00 PM | 416 | Critical
3655 | M29: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | January 9, 2025 5:00 PM | 386 | Critical
5536 | M30: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | January 28, 2025 5:00 PM | 367 | Critical
5537 | M31: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | February 24, 2025 5:00 PM | 340 | Critical
5538 | M32: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 42 | 425d | 2634FS-40d |  | 0 | March 21, 2025 5:00 PM | 315 | Critical
3658 | M1: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d |  | 2668SS,2676SS,2704FS+4d,2744SS,2745SS,2746SS,2747SS,2748SS,2752SS,2780FS+4d,2743SS | 1 | May 31, 2022 5:00 PM | 969 | Critical
3659 | M2: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS | 2674SS+8d,2678SS+4d,2685SS+4d,2686SS+4d,2750SS+8d,2754SS+4d,2760SS+4d,2761SS+4d,2762SS+4d,2669SS | 1 | July 15, 2022 5:00 PM | 924 | Critical
3660 | M3: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2668SS | 2670SS | 1 | August 12, 2022 5:00 PM | 896 | Critical
3661 | M4: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2669SS | 2671SS | 1 | September 9, 2022 5:00 PM | 868 | Critical
3662 | M5: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2670SS | 2672SS | 1 | October 7, 2022 5:00 PM | 840 | Critical
3663 | M6: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2671SS | 2673,2749 | 1 | November 4, 2022 5:00 PM | 819 | Critical
3664 | M6.1: Create Automation scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 425d | 2672 | 2688SS-10d,2710FS+6d,2711FS+6d,2712FS+6d,2714FS+6d,2715FS+6d,2716FS+6d,2717FS+6d,2718FS+6d,2719FS+6d,2721FS+6d,2722FS+6d,2723FS+6d,2725FS+6d,2727FS+6d,2728FS+6d,2729FS+6d,2730FS+6d,2731FS+6d,2732FS+6d,2733FS+6d,2734FS+6d,2735FS+6d,2736FS+6d,2737FS+6d,2... | 0 | December 2, 2022 5:00 PM | 1117 | Critical
3665 | M7: Create Automation scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 59 | 452d | 2668SS+8d | 2675SS-92d,2751SS-92d | 0.1 | December 30, 2022 5:00 PM | 1085 | Critical
3666 | M7.1 Create Automation scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d | 2677SS-20d,2679SS-20d,2682SS-20d,2753SS-20d,2755SS-20d,2758SS-20d | 0.83 | January 27, 2023 5:00 PM | 1008 | Critical
3667 | M8: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS | 2683SS,2687SS,2689SS,2759SS,2763SS,2765SS | 1 | February 24, 2023 5:00 PM | 707 | Critical
3668 | M9: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | March 24, 2023 5:00 PM | 1005 | Critical
3669 | M10: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d | 2680SS-23d,2681SS-23d,2756SS-23d,2757SS-23d | 0.23 | April 21, 2023 5:00 PM | 977 | Critical
3670 | M10.1: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | May 19, 2023 5:00 PM | 949 | Critical
3671 | M11: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | June 16, 2023 5:00 PM | 921 | Critical
3672 | M13: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | July 14, 2023 5:00 PM | 893 | Critical
3673 | M14: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 173 | 450d | 2675SS-20d |  | 0.68 | August 11, 2023 5:00 PM | 865 | Critical
3674 | M15: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS | 2684FS+154d | 1 | September 8, 2023 5:00 PM | 511 | Critical
3676 | M16: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2683FS+154d | 2690SS+3d,2766SS+3d | 0.23 | November 3, 2023 5:00 PM | 781 | Critical
3677 | M17: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | December 1, 2023 5:00 PM | 753 | Critical
3678 | M18: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | December 29, 2023 5:00 PM | 725 | Critical
3679 | M19: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2676SS |  | 1 | January 18, 2024 5:00 PM | 379 | Critical
3680 | M21: Create Automation scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 49 | 450d | 2673SS-10d |  | 0 | April 14, 2025 5:00 PM | 253 | Critical
3682 | M20.1: Create Automation scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 68 | 450d | 2684SS+3d | 2691SS-7d,2692SS-7d,2693SS-7d,2699SS-7d,2700SS-7d,2701SS-7d,2767SS-7d,2768SS-7d,2769SS-7d,2775SS-7d,2776SS-7d,2777SS-7d | 0.19 | June 28, 2024 5:00 PM | 543 | Critical
3683 | M23: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | December 13, 2024 5:00 PM | 375 | Critical
3685 | M23.2: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2694SS-33d,2695SS-33d,2696SS-33d,2697SS-33d,2698SS-33d,2770SS-33d,2771SS-33d,2772SS-33d,2773SS-33d,2774SS-33d | 0.27 | August 22, 2025 5:00 PM | 123 | Critical
3688 | M26.1: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | September 16, 2024 5:00 PM | 463 | Critical
3689 | M27: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | April 8, 2025 5:00 PM | 259 | Critical
3693 | M31: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d | 2702SS-1d,2778SS-1d | 0.27 | April 8, 2025 5:00 PM | 259 | Critical
3694 | M32: Create Automation scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | April 8, 2025 5:00 PM | 234 | Critical
3705 | M1: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2667FS+4d | 2705SS,2706SS,2707SS,2708SS,2709SS+5d | 1 | May 31, 2022 5:00 PM | 1004 | Critical
3706 | M2: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS | 2713SS+5d,2789SS+5d | 1 | July 15, 2022 5:00 PM | 959 | Critical
3707 | M3: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | August 12, 2022 5:00 PM | 931 | Critical
3708 | M4: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | September 9, 2022 5:00 PM | 903 | Critical
3709 | M5: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2704SS |  | 1 | October 7, 2022 5:00 PM | 875 | Critical
3710 | M6: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2704SS+5d | 2720SS | 1 | November 4, 2022 5:00 PM | 861 | Critical
3711 | M6.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 2, 2022 5:00 PM | 1155 | Critical
3712 | M7: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 30, 2022 5:00 PM | 1127 | Critical
3713 | M7.1 Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | January 27, 2023 5:00 PM | 1099 | Critical
3714 | M8: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2705SS+5d |  | 1 | February 24, 2023 5:00 PM | 749 | Critical
3715 | M9: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | March 24, 2023 5:00 PM | 1043 | Critical
3716 | M10: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | April 21, 2023 5:00 PM | 1015 | Critical
3717 | M10.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | May 19, 2023 5:00 PM | 987 | Critical
3718 | M11: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | June 16, 2023 5:00 PM | 959 | Critical
3719 | M13: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | July 14, 2023 5:00 PM | 931 | Critical
3720 | M14: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | August 11, 2023 5:00 PM | 903 | Critical
3721 | M15: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2709SS | 2724SS,2726SS | 1 | September 8, 2023 5:00 PM | 553 | Critical
3723 | M16: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | November 3, 2023 5:00 PM | 819 | Critical
3724 | M17: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 1, 2023 5:00 PM | 791 | Critical
3725 | M18: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 29, 2023 5:00 PM | 763 | Critical
3726 | M19: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 25 | 0d | 2720SS |  | 1 | February 23, 2024 5:00 PM | 385 | Critical
3727 | M21: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | May 19, 2025 5:00 PM | 256 | Critical
3729 | M20.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 31, 2024 5:00 PM | 395 | Critical
3730 | M23: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | March 18, 2025 5:00 PM | 318 | Critical
3732 | M23.2: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 31, 2025 5:00 PM | 30 | Critical
3735 | M26.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 17, 2024 5:00 PM | 409 | Critical
3736 | M27: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | June 30, 2025 5:00 PM | 214 | Critical
5480 | M1: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | April 13, 2023 5:00 PM | 652 | Critical
5481 | M2: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | June 8, 2023 5:00 PM | 596 | Critical
5482 | M3: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | August 3, 2023 5:00 PM | 540 | Critical
5483 | M4: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | January 25, 2024 5:00 PM | 365 | Critical
5484 | M5: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 37 | 0d | 2667SS |  | 1 | April 4, 2024 5:00 PM | 295 | Critical
5485 | M6: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS |  | 1 | June 28, 2024 5:00 PM | 217 | Critical
5655 | M6.1: Create Performance Testing scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 44 | 450d | 2672 |  | 0 | January 31, 2025 5:00 PM | 326 | Critical
5486 | M7.1 Create Performance Testing scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 118 | 485d | 2674SS-92d |  | 0.83 | June 28, 2024 5:00 PM | 490 | Critical
5487 | M8: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 | 0d | 2667SS |  | 1 | May 17, 2024 5:00 PM | 259 | Critical
5489 | M10: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | March 28, 2025 5:00 PM | 270 | Critical
5491 | M11: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 94 | 450d | 2678SS-23d |  | 0.41 | March 28, 2025 5:00 PM | 270 | Critical
5497 | M17: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | June 30, 2025 5:00 PM | 176 | Critical
5498 | M18: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 71 | 450d | 2668SS+4d |  | 0.23 | January 31, 2025 5:00 PM | 326 | Critical
5509 | M24: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | September 7, 2023 5:00 PM | 838 | Critical
5510 | M26: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | October 11, 2023 5:00 PM | 804 | Critical
5511 | M26.1: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | November 16, 2023 5:00 PM | 768 | Critical
5512 | M27: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | May 9, 2024 5:00 PM | 593 | Critical
5513 | M28: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 108 | 450d | 2693SS-33d |  | 0.49 | July 1, 2024 5:00 PM | 540 | Critical
5514 | M29: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | November 21, 2024 5:00 PM | 397 | Critical
5657 | M30: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 75 | 450d | 2690SS-7d |  | 0.27 | June 30, 2025 5:00 PM | 176 | Critical
5515 | M32: Create Performance Testing scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 59 | 467d | 2701SS-1d |  | 0.36 | December 31, 2024 5:00 PM | 332 | Critical
5516 | M1: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 20 | 0d | 2667FS+4d | 2781SS,2782SS,2783SS,2784SS,2785SS+5d | 1 | October 11, 2024 5:00 PM | 140 | Critical
5526 | M9: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | December 31, 2025 5:00 PM | 30 | Critical
5527 | M10: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 19 | 425d | 2673FS+6d |  | 0 | June 30, 2025 5:00 PM | 214 | Critical
3821 | Security | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM | 921 | 423d |  |  | 0.98 | April 1, 2025 4:12 PM | 308 | Critical
3822 | Information Security (CARESV1-12620) | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM | 921 | 0d |  |  | 1 | December 31, 2024 5:00 PM | 399 | Critical
3823 | County IAM Integration | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM | 921 | 0d |  |  | 1 | October 7, 2024 5:00 PM | 484 | Critical
3824 | Security - Privileged Access Management (PAM) | November 4, 2024 8:00 AM | April 18, 2025 5:00 PM | 112 | 0d | 2869FS-4d | 1855,2880SS-37d | 1 | December 31, 2024 5:00 PM | 108 | Critical
3828 | DevSecOps (CARESV1-14453) | April 8, 2024 8:00 AM | December 19, 2025 5:00 PM | 430 | 452d |  |  | 0.85 | April 1, 2025 4:12 PM | 262 | Critical
3833 | Okta FedRAMP Transition | February 3, 2025 8:00 AM | September 22, 2025 5:00 PM | 161 | 0d | 2902 |  | 1 | April 1, 2025 4:12 PM | 174 | Critical
6134 | CWDS Staff Newsletter, Volume 1 Issue 1 | June 17, 2024 8:00 AM | August 30, 2024 5:00 PM | 54 | 0d |  | 3018FS+10d | 1 | June 30, 2024 5:00 PM | 61 | Critical
6135 | CWDS Staff Newsletter, Volume 1 Issue 2 | September 16, 2024 8:00 AM | November 27, 2024 5:00 PM | 52 | 0d | 3017FS+10d | 3019FS+10d | 1 | September 27, 2024 5:00 PM | 61 | Critical
6136 | CWDS Staff Newsletter, Volume 1 Issue 3 | December 16, 2024 8:00 AM | March 14, 2025 5:00 PM | 61 | 0d | 3018FS+10d | 3020 | 1 | December 31, 2024 5:00 PM | 73 | Critical
6137 | CWDS Staff Newsletter, Volume 1 Issue 4 | March 17, 2025 8:00 AM | June 30, 2025 5:00 PM | 74 | 0d | 3019 | 3021FS-1d | 1 | March 28, 2025 5:00 PM | 94 | Critical
6486 | CARES V1 - Implementation | June 1, 2022 8:00 AM | June 7, 2027 5:00 PM | 1256 | 88d |  |  | 0.8 | April 19, 2027 5:00 PM | 49 | Critical
7639 | Implementation | June 1, 2022 8:00 AM | June 7, 2027 5:00 PM | 1256 | 88d |  |  | 0.91 | April 19, 2027 5:00 PM | 49 | Critical
11018 | Create Outline with Updated Content Based on Gaps | November 7, 2024 8:00 AM | December 6, 2024 5:00 PM | 19 | 0d | 3303 | 3305 | 1 | November 1, 2024 5:00 PM | 35 | Critical
11002 | Review outline of recommended updates on content with State Implementation Leadership Team | December 9, 2024 8:00 AM | December 13, 2024 5:00 PM | 5 | 0d | 3304 | 3306 | 1 | November 8, 2024 5:00 PM | 35 | Critical
11003 | Draft Updated Content Based on Outline | December 16, 2024 8:00 AM | December 27, 2024 5:00 PM | 9 | 0d | 3305 | 3307 | 1 | November 18, 2024 5:00 PM | 39 | Critical
11004 | Edit / Validate all Updates IL | December 30, 2024 8:00 AM | January 8, 2025 5:00 PM | 7 | 0d | 3306 | 3308 | 1 | December 4, 2024 5:00 PM | 35 | Critical
11005 | Review Updated MIP with IDO and Michelle | January 9, 2025 8:00 AM | January 16, 2025 5:00 PM | 6 | 0d | 3307 | 3309 | 1 | December 18, 2024 5:00 PM | 29 | Critical
11006 | Review updated MIP with State Implementation Lead | January 17, 2025 8:00 AM | January 22, 2025 5:00 PM | 3 | 0d | 3308 | 3310 | 1 | December 18, 2024 5:00 PM | 35 | Critical
11007 | Incorporate feedback/comments from State Imp Lead | January 23, 2025 8:00 AM | January 27, 2025 5:00 PM | 3 | 0d | 3309 | 3311 | 1 | December 18, 2024 5:00 PM | 40 | Critical
11008 | Review updated MIP with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 28, 2025 8:00 AM | February 4, 2025 5:00 PM | 6 | 0d | 3310 | 3312 | 1 | January 14, 2025 5:00 PM | 21 | Critical
11073 | Develop Pilot Plan - Version 2 | January 2, 2024 8:00 AM | July 19, 2024 5:00 PM | 139 | 0d |  |  | 1 | June 28, 2024 5:00 PM | 21 | Critical
11075 | Conduct RACI, ELT, and BOD Pilot Review Processes | April 26, 2024 8:00 AM | June 28, 2024 5:00 PM | 45 | 0d | 3431SS+80d | 3433FS+1d | 1 | May 29, 2024 5:00 PM | 30 | Critical
11077 | Final Pilot Plan Version 2 Approved | July 19, 2024 5:00 PM | July 19, 2024 5:00 PM | 0 | 0d | 3433FS+5d | 3436FS+115d | 1 | June 28, 2024 5:00 PM | 21 | Critical
8124 | Phase 1: Engage Orgs in Planning and Preparation Activities | November 7, 2022 8:00 AM | September 22, 2026 5:00 PM | 970 | 8d |  |  | 0.91 | February 27, 2025 5:00 PM | 572 | Critical
8150 | Establish Org Implementation Teams | August 1, 2023 8:00 AM | June 30, 2025 5:00 PM | 480 | 0d |  |  | 1 | January 16, 2025 5:00 PM | 165 | Critical
8155 | Kickoff Meetings with Org Implementation Teams | September 11, 2023 8:00 AM | June 30, 2025 5:00 PM | 452 | 0d |  |  | 1 | January 16, 2025 5:00 PM | 165 | Critical
8156 | Schedule Kickoff Meetings | September 11, 2023 8:00 AM | April 30, 2025 5:00 PM | 410 | 0d |  |  | 1 | December 30, 2024 5:00 PM | 121 | Critical
8159 | Schedule Kickoff Meetings - Counties' Probation Depts | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d | 3492FS+20d | 3497 | 1 | September 24, 2024 5:00 PM | 218 | Critical
8161 | Conduct Kickoff Meetings | September 25, 2023 8:00 AM | June 30, 2025 5:00 PM | 442 | 0d |  |  | 1 | January 16, 2025 5:00 PM | 165 | Critical
8164 | Conduct Kickoff Meetings - Counties' Probation Depts (Wave I) | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 21 | 0d | 3493 | 3498,3563SS+12d | 1 | October 24, 2024 5:00 PM | 218 | Critical
8165 | Conduct Kickoff Meetings - Tribes | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 19 | 0d | 3494FS+22d | 3561 | 1 | January 16, 2025 5:00 PM | 43 | Critical
8178 | Initiate CDSS Engagement | October 2, 2023 8:00 AM | April 30, 2025 5:00 PM | 395 | 0d |  |  | 1 | January 6, 2025 5:00 PM | 114 | Critical
8179 | CFSD | October 30, 2023 8:00 AM | January 31, 2025 5:00 PM | 314 | 0d |  |  | 1 | October 30, 2024 5:00 PM | 93 | Critical
8181 | Schedule Kickoff Meeting with CFSD Implementation Team | July 15, 2024 8:00 AM | August 23, 2024 5:00 PM | 30 | 0d | 3514FS+101d | 3516FS+14d | 1 | July 26, 2024 5:00 PM | 28 | Critical
8182 | Conduct Kickoff Meeting with CFSD Implementation Team | September 13, 2024 8:00 AM | November 4, 2024 5:00 PM | 37 | 0d | 3515FS+14d,3511 | 3517SS+3d | 1 | August 30, 2024 5:00 PM | 66 | Critical
8183 | Schedule Organization Assessment | September 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 47 | 0d | 3516SS+3d | 3518SS+17d | 1 | October 10, 2024 5:00 PM | 43 | Critical
8184 | CFSD - Conduct Organization Assessment | October 11, 2024 8:00 AM | January 31, 2025 5:00 PM | 75 | 0d | 3517SS+17d | 3886 | 1 | October 30, 2024 5:00 PM | 93 | Critical
8186 | Establish CCLD Implementation Team | April 2, 2024 8:00 AM | August 20, 2024 5:00 PM | 99 | 0d | 3514FS+29d | 3521SS+34d | 1 | June 28, 2024 5:00 PM | 53 | Critical
8192 | Establish RADD Implementation Team | October 2, 2023 8:00 AM | September 5, 2024 5:00 PM | 234 | 0d |  |  | 1 | June 28, 2024 5:00 PM | 69 | Critical
8204 | Conduct Org Assessments | June 29, 2023 8:00 AM | July 15, 2025 5:00 PM | 512 | 0d |  |  | 1 | February 27, 2025 5:00 PM | 138 | Critical
8212 | Schedule Org Assessments - Tribes | March 3, 2025 8:00 AM | March 13, 2025 5:00 PM | 9 | 0d | 3499,3535,3560 | 3562FS+20d | 1 | January 30, 2025 5:00 PM | 42 | Critical
8213 | Conduct Org Assessments - Tribes | April 14, 2025 8:00 AM | May 8, 2025 5:00 PM | 19 | 0d | 3561FS+20d,3524 | 3872 | 1 | February 27, 2025 5:00 PM | 70 | Critical
8214 | Prepare for Org Readiness Meetings | December 4, 2023 8:00 AM | September 22, 2026 5:00 PM | 704 | 8d |  |  | 0.66 | November 21, 2024 5:00 PM | 670 | Critical
8266 | Conduct Org Readiness Meetings | January 2, 2024 8:00 AM | January 23, 2026 5:00 PM | 518 | 175d |  |  | 0.87 | January 22, 2025 5:00 PM | 366 | Critical
8376 | Phase 2: Readiness and Cutover | October 6, 2025 8:00 AM | December 16, 2026 5:00 PM | 300 | -50d |  |  | 0.01 | October 23, 2026 5:00 PM | 54 | Critical
8378 | CARES V1 Train the Trainer | August 7, 2026 8:00 AM | September 18, 2026 5:00 PM | 30 | -50d | 5617SS,3872 | 3874 | 0 | July 30, 2026 5:00 PM | 50 | Critical
8379 | CARES V1 End-User Training | September 21, 2026 8:00 AM | December 16, 2026 5:00 PM | 60 | -50d | 3873 | 3886 | 0 | October 23, 2026 5:00 PM | 54 | Critical
8380 | CARES V1 Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 29 | -38d | 5626SS | 3886 | 0 | October 9, 2026 5:00 PM | 52 | Critical
8381 | Phase 3: Go-Live and Support Phase | January 9, 2025 8:00 AM | June 7, 2027 5:00 PM | 603 | 88d |  |  | 0.51 | April 19, 2027 5:00 PM | 49 | Critical
8390 | CARES V1 Go-Live and Support | December 17, 2026 8:00 AM | January 15, 2027 5:00 PM | 20 | -50d | 3874,3875,5629,3885,3528,3381,3386,3429,3496,3518,3522,3544,3549,3552,3701,3870,3449,3498,3564,3881 | 3887,3889SS | 0 | November 24, 2026 5:00 PM | 52 | Critical
8391 | SPR 6 - Complete the CWS-CARES V1 Implementation | January 15, 2027 5:00 PM | January 15, 2027 5:00 PM | 0 | -50d | 3886 | 3893 | 0 | November 24, 2026 5:00 PM | 52 | Critical
8392 | Knowledge Transfer Plan | December 17, 2026 8:00 AM | June 7, 2027 5:00 PM | 117 | 88d |  |  | 0 | April 19, 2027 5:00 PM | 49 | Critical
8393 | Create Knowledge Transfer Plan | December 17, 2026 8:00 AM | February 23, 2027 5:00 PM | 45 | 88d | 3886SS | 3890 | 0 | January 4, 2027 5:00 PM | 50 | Critical
8394 | Review and Incorporate Feedback to Knowledge Transfer Plan | February 24, 2027 8:00 AM | April 7, 2027 5:00 PM | 30 | 88d | 3889 | 3891 | 0 | February 17, 2027 5:00 PM | 49 | Critical
8395 | Complete Knowledge Transfer Plan | April 7, 2027 5:00 PM | April 7, 2027 5:00 PM | 0 | 88d | 3890 | 3892 | 0 | February 17, 2027 5:00 PM | 49 | Critical
8396 | Execute Knowledge Transfer Plan | April 8, 2027 8:00 AM | June 7, 2027 5:00 PM | 42 | 88d | 3891 | 3893 | 0 | April 19, 2027 5:00 PM | 49 | Critical
8397 | Complete Execution of Knowledge Transfer Plan | June 7, 2027 5:00 PM | June 7, 2027 5:00 PM | 0 | 88d | 3892,3887 |  | 0 | April 19, 2027 5:00 PM | 49 | Critical
8402 | RFA Release Support | October 3, 2022 8:00 AM | July 22, 2025 5:00 PM | 701 | 0d |  |  | 1 | July 12, 2024 5:00 PM | 375 | Critical
8587 | Development Training Materials | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM | 842 | 334d |  |  | 0.78 | March 27, 2026 5:00 PM | 76 | Critical
8588 | Participate in Inception Meetings | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM | 842 | 334d |  |  | 0.78 | March 27, 2026 5:00 PM | 76 | Critical
11506 | Person(s) | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4307 | 4312SS | 0.78 | July 26, 2024 5:00 PM | 595 | Critical
11505 | Contact Log and Tribal Inquiries | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4311SS | 4313SS | 0.78 | July 26, 2024 5:00 PM | 595 | Critical
11503 | Task | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4312SS | 4314SS | 0.78 | July 26, 2024 5:00 PM | 595 | Critical
11502 | Documents | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 396d | 4313SS | 4315SS | 0.78 | July 26, 2024 5:00 PM | 595 | Critical
11501 | Case Management Engagement: Family Transfer Request | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 480 | 376d | 4314SS | 4925 | 0.78 | July 26, 2024 5:00 PM | 595 | Critical
10500 | Process Areas | May 28, 2024 8:00 AM | May 14, 2026 5:00 PM | 494 | 353d |  |  | 0.73 | February 27, 2026 5:00 PM | 76 | Critical
10501 | Case Management | May 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 418 | 429d |  |  | 0.85 | December 8, 2025 5:00 PM | 49 | Critical
10503 | Group 1 Placement (Milestones 1, 2, 6, 8, 15, 19, 20) | May 28, 2024 8:00 AM | April 3, 2025 5:00 PM | 214 | 0d |  |  | 1 | March 4, 2025 5:00 PM | 30 | Critical
10535 | Placement: Training | May 28, 2024 8:00 AM | April 3, 2025 5:00 PM | 214 | 0d |  |  | 1 | March 4, 2025 5:00 PM | 30 | Critical
11088 | End-To-End Business Scenarios - (MS 1,2,6,8) | May 28, 2024 8:00 AM | August 23, 2024 5:00 PM | 63 | 0d |  |  | 1 | July 12, 2024 5:00 PM | 42 | Critical
10537 | Review End-To-End Business Scenarios with VPODs | July 18, 2024 8:00 AM | August 16, 2024 5:00 PM | 22 | 0d | 4371FS+12d | 4373FF+5d | 1 | July 5, 2024 5:00 PM | 42 | Critical
10538 | Incorporate VPODs Feedback | July 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 25 | 0d | 4372FF+5d | 4374FF | 1 | July 5, 2024 5:00 PM | 49 | Critical
10539 | Finalize End-To-End Business Scenarios | July 25, 2024 8:00 AM | August 23, 2024 5:00 PM | 22 | 0d | 4373FF | 4538,4385 | 1 | July 12, 2024 5:00 PM | 42 | Critical
11089 | End-To-End Business Scenarios - (MS 15, 19) | May 28, 2024 8:00 AM | September 20, 2024 5:00 PM | 83 | 0d |  |  | 1 | August 9, 2024 5:00 PM | 42 | Critical
11090 | Develop End-To-End Business Scenarios | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 58 | 0d | 5379SS+10d | 4381,4377FS+5d | 1 | July 26, 2024 5:00 PM | 21 | Critical
11091 | Review End-To-End Business Scenarios with VPODs | August 26, 2024 8:00 AM | September 6, 2024 5:00 PM | 10 | 0d | 4376FS+5d | 4378FF+5d | 1 | August 2, 2024 5:00 PM | 35 | Critical
11092 | Incorporate VPODs Feedback | September 2, 2024 8:00 AM | September 13, 2024 5:00 PM | 10 | 0d | 4377FF+5d | 4379 | 1 | August 2, 2024 5:00 PM | 42 | Critical
11093 | MS 15, 19, 20 - Finalize End-To-End Business Scenarios | September 16, 2024 8:00 AM | September 20, 2024 5:00 PM | 5 | 0d | 4378 | 4538,4385 | 1 | August 9, 2024 5:00 PM | 42 | Critical
10540 | Milestone 06 - Case Management Engagement | October 31, 2024 8:00 AM | April 3, 2025 5:00 PM | 103 | 0d |  |  | 1 | February 10, 2025 5:00 PM | 52 | Critical
10542 | Review Training Curriculum with TAW & VPOD | December 3, 2024 8:00 AM | December 31, 2024 5:00 PM | 20 | 0d | 4382 | 4384 | 1 | November 25, 2024 5:00 PM | 36 | Critical
10543 | Incorporate Feedback from VPOD & TAW | January 2, 2025 8:00 AM | January 8, 2025 5:00 PM | 5 | 0d | 4383 | 4386 | 1 | December 4, 2024 5:00 PM | 35 | Critical
10550 | Milestone 08 - Placement | October 31, 2024 8:00 AM | April 3, 2025 5:00 PM | 103 | 0d |  |  | 1 | February 19, 2025 5:00 PM | 43 | Critical
10564 | Milestone 15 - Court Hearing Framework | November 18, 2024 8:00 AM | April 3, 2025 5:00 PM | 92 | 0d |  |  | 1 | March 4, 2025 5:00 PM | 30 | Critical
10570 | Review Training Curriculum with TAW & VPOD | December 18, 2024 8:00 AM | January 9, 2025 5:00 PM | 15 | 0d | 4406 | 4408 | 1 | December 11, 2024 5:00 PM | 29 | Critical
10571 | Incorporate Feedback from VPOD & TAW | January 10, 2025 8:00 AM | January 16, 2025 5:00 PM | 5 | 0d | 4407 | 4411 | 1 | December 18, 2024 5:00 PM | 29 | Critical
10578 | Milestone 19 - Request Determination | December 4, 2024 8:00 AM | April 3, 2025 5:00 PM | 82 | 0d |  |  | 1 | March 3, 2025 5:00 PM | 31 | Critical
10584 | Review Training Curriculum with TAW & VPOD | January 3, 2025 8:00 AM | January 24, 2025 5:00 PM | 15 | 0d | 4418 | 4420 | 1 | December 26, 2024 5:00 PM | 29 | Critical
10585 | Incorporate Feedback from VPOD & TAW | January 27, 2025 8:00 AM | January 31, 2025 5:00 PM | 5 | 0d | 4419 | 4422 | 1 | January 3, 2025 5:00 PM | 28 | Critical
10592 | Milestone 20/20.1 - Redetermine Eligibility | December 4, 2024 8:00 AM | April 3, 2025 5:00 PM | 82 | 0d |  |  | 1 | February 26, 2025 5:00 PM | 36 | Critical
10597 | MS20/20.1 - Develop Training Curriculum Map | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 10 | 0d | 579FS+1d | 4429 | 1 | November 25, 2024 5:00 PM | 22 | Critical
10598 | Review Training Curriculum with TAW & VPOD | January 3, 2025 8:00 AM | January 24, 2025 5:00 PM | 15 | 0d | 4429 | 4431 | 1 | December 11, 2024 5:00 PM | 44 | Critical
10599 | Incorporate Feedback from VPOD & TAW | January 27, 2025 8:00 AM | January 31, 2025 5:00 PM | 5 | 0d | 4430 | 4433 | 1 | December 18, 2024 5:00 PM | 44 | Critical
10606 | Group 2 On-Going Case Work (Milestones 6.1, 7) | June 17, 2024 8:00 AM | January 26, 2026 5:00 PM | 404 | 429d |  |  | 0.82 | December 5, 2025 5:00 PM | 52 | Critical
10623 | Incorporate VPODs Feedback | July 29, 2024 8:00 AM | August 2, 2024 5:00 PM | 5 | 0d | 4441 | 4443FF | 1 | July 8, 2024 5:00 PM | 25 | Critical
10624 | Finalize End-To-End Business Scenarios | July 30, 2024 8:00 AM | August 2, 2024 5:00 PM | 4 | 0d | 4442FF | 4538 | 1 | July 12, 2024 5:00 PM | 21 | Critical
11095 | MS 6.1 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 601,4385 | 4451FF,4460 | 1 | May 27, 2025 5:00 PM | 71 | Critical
11096 | MS 6.1 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 50 | 0d | 4450FF | 4452FF,4454SS+1d | 1 | June 10, 2025 5:00 PM | 57 | Critical
11097 | MS 6.1 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 45 | 0d | 4451FF | 4453FF | 1 | June 17, 2025 5:00 PM | 50 | Critical
11098 | MS 6.1 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 35 | 0d | 4452FF | 4463 | 1 | June 24, 2025 5:00 PM | 43 | Critical
11100 | MS 6.1 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | September 8, 2025 8:00 AM | October 6, 2025 5:00 PM | 21 | 0d | 4450,748SS,749SS,750SS,751SS,752SS,753SS,4459FS+2d | 4461FS+4d | 1 | July 29, 2025 5:00 PM | 69 | Critical
11101 | BD 3 - MS 6.1 - Review Training Content with VPOD & TAW (Build Drop Update) | October 13, 2025 8:00 AM | October 20, 2025 5:00 PM | 6 | 76d | 4460FS+4d | 4462 | 0 | August 4, 2025 5:00 PM | 77 | Critical
11102 | BD 3 - MS 6.1 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | October 21, 2025 8:00 AM | November 3, 2025 5:00 PM | 10 | 76d | 4461 | 4463 | 0 | August 11, 2025 5:00 PM | 84 | Critical
10625 | Milestone 07/7.1 - Case Plan | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.76 | December 5, 2025 5:00 PM | 52 | Critical
10626 | MS 07/7.1 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 601,4385 | 4466FF | 1 | May 27, 2025 5:00 PM | 71 | Critical
10627 | MS 07/7.1 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 50 | 0d | 4465FF | 4467FF,4469SS+1d | 1 | June 10, 2025 5:00 PM | 57 | Critical
10628 | MS 07/7.1 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 45 | 0d | 4466FF | 4468FF | 1 | June 17, 2025 5:00 PM | 50 | Critical
10629 | MS 07/7.1 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 35 | 0d | 4467FF | 4478 | 1 | June 24, 2025 5:00 PM | 43 | Critical
10631 | BD 3 - MS 7/7.1 - Develop Training Content On-Demand Programs and Lessons (Build Drop Update) | November 3, 2025 8:00 AM | December 22, 2025 5:00 PM | 34 | 21.08d | 748SS,749SS,750SS,751SS,752SS,753SS,4474,719,720,721,722 | 4476,4490SS | 0 | July 29, 2025 5:00 PM | 146 | Critical
10632 | BD 3 - MS 7/7.1 - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 8 | 26d | 4475 | 4477 | 0 | August 4, 2025 5:00 PM | 154 | Critical
10633 | BD 3 - MS 7/7.1 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 9 | 26d | 4476 | 4478 | 0 | August 11, 2025 5:00 PM | 158 | Critical
10634 | MS 07/7.1 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4477,4468,4469FS-76d | 4538,5611,5612,4782,4783,4904 | 0 | December 5, 2025 5:00 PM | 52 | Critical
10635 | Milestone 09 - Case Management - Engagement and Services | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.82 | December 5, 2025 5:00 PM | 52 | Critical
10640 | MS 09 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 601 | 4481FF,4490 | 1 | May 27, 2025 5:00 PM | 71 | Critical
10641 | MS 09 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 50 | 0d | 4480FF | 4482FF | 1 | June 10, 2025 5:00 PM | 57 | Critical
10642 | MS 09 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 45 | 0d | 4481FF | 4483FF | 1 | June 17, 2025 5:00 PM | 50 | Critical
10643 | MS 09 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 35 | 0d | 4482FF | 4493 | 1 | June 24, 2025 5:00 PM | 43 | Critical
10644 | MS 09 - Validate and Provide Feedback on Critical Scenarios for the EUST | April 29, 2025 8:00 AM | October 27, 2025 5:00 PM | 127 | 81d | 349FS+330d | 4493 | 0.91 | January 3, 2024 5:00 PM | 663 | Critical
10645 | BD 3 - MS 9 - Develop Training Content - On Demand Programs and Lessons (Build Drop Update) | November 3, 2025 8:00 AM | December 22, 2025 5:00 PM | 34 | 26d | 4480,351,352,353,354,355,4475SS | 4491 | 0.62 | November 14, 2025 5:00 PM | 38 | Critical
10646 | BD 3 - MS 9 - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 8 | 26d | 4490 | 4492 | 0 | November 20, 2025 5:00 PM | 46 | Critical
10647 | BD 3 - MS 9 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 9 | 26d | 4491 | 4493 | 0 | November 28, 2025 5:00 PM | 49 | Critical
10648 | MS 09 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4492,4483,4484 | 4538,5611,5612,4784,4785,4904 | 0 | December 5, 2025 5:00 PM | 52 | Critical
10649 | Group 3 Finish a Case (Milestones 10, 11, 13) | August 12, 2024 8:00 AM | January 26, 2026 5:00 PM | 365 | 410d |  |  | 0.78 | December 8, 2025 5:00 PM | 49 | Critical
10675 | BD 4 - MS 10 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4496,699FS+18d,4504,631FF,632FF | 4507SS,4512,4508SS | 1 | July 14, 2025 5:00 PM | 88 | Critical
10676 | BD 4- MS 10 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4506SS |  | 1 | July 28, 2025 5:00 PM | 74 | Critical
10677 | BD 4 - MS 10 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4506SS | 4509 | 1 | August 4, 2025 5:00 PM | 67 | Critical
10678 | BD 4 - MS 10: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 53d | 4508 | 4515,4511,4512 | 0 | August 11, 2025 5:00 PM | 67 | Critical
10689 | BD 4- MS 11 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 715FS-21d,716FS-21d,717FS-21d,743FS-21d,744FS-21d,745FS-21d | 4518FF,4523 | 1 | July 14, 2025 5:00 PM | 88 | Critical
10690 | BD 4 - MS 11 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4517FF | 4519FF | 1 | July 28, 2025 5:00 PM | 74 | Critical
10691 | BD 4 - MS 11 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4518FF | 4520 | 1 | August 4, 2025 5:00 PM | 67 | Critical
10692 | BD 4 - MS 11: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 53d | 4519 | 4526,4521,4523 | 0 | August 11, 2025 5:00 PM | 67 | Critical
10698 | Milestone 13 - Adoption | June 3, 2025 8:00 AM | January 26, 2026 5:00 PM | 163 | 410d |  |  | 0.71 | December 8, 2025 5:00 PM | 49 | Critical
10703 | BD 4 - MS 13 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 709FS-21d,710FS-21d,711FF+5d,712FF+5d,713FF+5d,737FF+5d,738FF+5d,739FF+5d,740FF+5d,741FF+5d | 4529FF,4534 | 1 | July 14, 2025 5:00 PM | 88 | Critical
10704 | BD 4 - MS 13 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4528FF | 4530FF | 1 | July 28, 2025 5:00 PM | 74 | Critical
10705 | BD 4 - MS 13 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 26 | 0d | 4529FF | 4531 | 1 | August 4, 2025 5:00 PM | 67 | Critical
10706 | BD 4 - MS 13: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 5 | 26d | 4530 | 4537,4532FS+15d,4534FS+15d | 0 | August 11, 2025 5:00 PM | 67 | Critical
10708 | BD 4 -MS 13 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | November 10, 2025 8:00 AM | December 22, 2025 5:00 PM | 29 | 26d | 4528,755SS,756SS,757SS,758SS,759SS,4531FS+15d,590,591,592,593,594,595 | 4535 | 0 | November 14, 2025 5:00 PM | 38 | Critical
10709 | BD 4 - MS 13 - Review Training Content with VPOD & TAW ( Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 8 | 26d | 4534 | 4536 | 0 | November 21, 2025 5:00 PM | 45 | Critical
10710 | BD 4 - MS 13 - Incorporate Feedback from VPOD & TAW (Buiild Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 9 | 26d | 4535 | 4537 | 0 | December 1, 2025 5:00 PM | 46 | Critical
10711 | MS 13 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4536,4531,4533 | 4538,5611,5612,4790,4791,4904 | 0 | December 8, 2025 5:00 PM | 49 | Critical
10712 | Case Management Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4374,4389,4401,4414,4425,4436,4443,4478,4493,4499,4515,4526,4537,5382,5388,5394,5400,5406,5419,5425,5433,5440,5448,5413,4379,4463 | 4925 | 0 | December 8, 2025 5:00 PM | 49 | Critical
10713 | Courts | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | January 2, 2026 5:00 PM | 24 | Critical
10715 | Group 1 Courts Processing (Milestones 14, 16, 17, 18) | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | January 2, 2026 5:00 PM | 24 | Critical
10741 | Courts Processing: Training | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM | 395 | 429d |  |  | 0.85 | January 2, 2026 5:00 PM | 24 | Critical
10747 | MS 14 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 4542,864 | 4548FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10748 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4547FF | 4549FF | 1 | July 9, 2025 5:00 PM | 28 | Critical
10749 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 25 | 0d | 4548FF | 4550FF | 1 | July 16, 2025 5:00 PM | 21 | Critical
10751 | MS 14 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 19, 2025 8:00 AM | November 14, 2025 5:00 PM | 126 | 476d | 409FS+289d |  | 0.81 | March 22, 2024 5:00 PM | 602 | Critical
10761 | MS 16 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 864 | 4563FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10762 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4562FF | 4564FF | 1 | July 9, 2025 5:00 PM | 28 | Critical
10763 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 25 | 0d | 4563FF | 4565FF | 1 | July 16, 2025 5:00 PM | 21 | Critical
10770 | Milestone 17 - Status Review | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM | 207 | 429d |  |  | 0.77 | December 29, 2025 5:00 PM | 28 | Critical
10775 | MS 17 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 864 | 4578FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10776 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4577FF | 4579FF | 1 | July 9, 2025 5:00 PM | 28 | Critical
10777 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 25 | 0d | 4578FF | 4580FF | 1 | July 16, 2025 5:00 PM | 21 | Critical
10781 | BD 3 - MS 17: - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 8 | 26d | 4587 | 4589 | 0 | December 12, 2025 5:00 PM | 24 | Critical
10782 | BD 3 - MS 17: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 9 | 26d | 4588 | 4590 | 0 | December 19, 2025 5:00 PM | 28 | Critical
10783 | MS 17 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4589,4580,4581 | 4606,5611,5612,4796,4797,4904 | 0 | December 29, 2025 5:00 PM | 28 | Critical
10789 | MS 18 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 864 | 4593FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10790 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4592FF | 4594FF | 1 | July 9, 2025 5:00 PM | 28 | Critical
10791 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 25 | 0d | 4593FF | 4595FF | 1 | July 16, 2025 5:00 PM | 21 | Critical
10798 | Courts Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4560,4575,4590,4605 | 4925 | 0 | January 2, 2026 5:00 PM | 24 | Critical
10799 | Eligibility | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | December 5, 2025 5:00 PM | 52 | Critical
10801 | Group 1 Eligibility (Milestones 21) | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | December 5, 2025 5:00 PM | 52 | Critical
10809 | Eligibility: Training | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM | 370 | 409d |  |  | 0.88 | December 5, 2025 5:00 PM | 52 | Critical
10814 | Milestone 21 - Eligibility Programs | February 3, 2025 8:00 AM | January 26, 2026 5:00 PM | 246 | 26d |  |  | 0.88 | December 5, 2025 5:00 PM | 52 | Critical
10815 | MS 21 - Develop Training Curriculum | February 3, 2025 8:00 AM | August 6, 2025 5:00 PM | 129 | 0d | 4613FS+89d | 4616FF,4617FF,4621FS+2d | 1 | March 7, 2025 5:00 PM | 152 | Critical
10816 | Review Training Curriculum with VPODs | April 3, 2025 8:00 AM | August 6, 2025 5:00 PM | 88 | 0d | 4615FF,4616FF | 4618FF | 1 | March 21, 2025 5:00 PM | 138 | Critical
10817 | Incorporate VPODs Feedback | April 10, 2025 8:00 AM | August 6, 2025 5:00 PM | 83 | 0d | 4617FF | 4619FF | 1 | March 28, 2025 5:00 PM | 131 | Critical
10818 | MS 21 - Finalize Training Curriculum | April 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 73 | 0d | 4618FF | 4629 | 1 | April 7, 2025 5:00 PM | 121 | Critical
10821 | BD 3 - MS 21: - Review Training Content with VPOD& TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 8 | 26d | 4626 | 4628 | 0 | November 17, 2025 5:00 PM | 49 | Critical
10822 | BD 3 - MS 21: - Incorporate Feedback from VPOD& TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 9 | 26d | 4627 | 4629 | 0 | November 24, 2025 5:00 PM | 53 | Critical
10823 | MS 21 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 5 | 26d | 4628,4619,4620FS-3d | 4630,5611,5612,4800,4801,4904 | 0 | December 5, 2025 5:00 PM | 52 | Critical
10824 | Eligibility Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 0 | 409d | 4629 | 4925 | 0 | December 5, 2025 5:00 PM | 52 | Critical
10825 | Resource Family Approval | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM | 423 | 351d |  |  | 0.35 | December 30, 2025 5:00 PM | 111 | Critical
10827 | Group 1 Resource Family Approval (Milestones 26/26.1, 27, 28) | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM | 423 | -32d |  |  | 0.35 | December 30, 2025 5:00 PM | 111 | Critical
10852 | Milestone 26/26.1 - Maintain Resource Family Home | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM | 203 | -13d |  |  | 0.33 | December 26, 2025 5:00 PM | 87 | Critical
10853 | BD 5 - MS 26/26.1: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4634,1008,1011FS-19d,1029FS-19d | 4640SS | 0 | September 10, 2025 5:00 PM | 96 | Critical
10854 | BD 5 - MS 26/26.1: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4639SS | 4641FF | 0 | September 24, 2025 5:00 PM | 82 | Critical
10855 | BD 5 - MS 26/26.1: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4640FF | 4642FS-5d,4644FS-5d | 0 | October 1, 2025 5:00 PM | 75 | Critical
10856 | BD 5 - MS 26/26.1: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | 48d | 4641FS-5d | 4648 | 0 | October 8, 2025 5:00 PM | 68 | Critical
10858 | BD 5 - MS 26/26.1: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4644FS+12d | 4646 | 0 | November 26, 2025 5:00 PM | 79 | Critical
10859 | BD 5 - MS 26/26.1: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4645 | 4647 | 0 | December 11, 2025 5:00 PM | 81 | Critical
10860 | BD 5 - MS 26/26.1: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4646 | 4648 | 0 | December 18, 2025 5:00 PM | 88 | Critical
10861 | MS 26/26.1 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4647,4642,4643 | 4671,5611,5612,4806,4807 | 0 | December 26, 2025 5:00 PM | 87 | Critical
10862 | Milestone 27 - Complaints | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM | 203 | -13d |  |  | 0.33 | December 30, 2025 5:00 PM | 83 | Critical
10867 | BD 5 - MS 27: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 1008,1019SS+19d,1020SS | 4651SS | 0 | September 10, 2025 5:00 PM | 96 | Critical
10868 | BD 5 - MS 27: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4650SS | 4652SS | 0 | September 24, 2025 5:00 PM | 82 | Critical
10869 | BD 5 - MS 27: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4651SS | 4653FS-5d,4655FS-5d | 0 | October 1, 2025 5:00 PM | 75 | Critical
10870 | BD 5- MS 27: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | 48d | 4652FS-5d | 4659 | 0 | October 8, 2025 5:00 PM | 68 | Critical
10872 | BD 5 - MS 27: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4655FS+12d | 4657 | 0 | December 1, 2025 5:00 PM | 74 | Critical
10873 | BD 5 - MS 27: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4656 | 4658 | 0 | December 15, 2025 5:00 PM | 77 | Critical
10874 | BD 5 - MS 27: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4657 | 4659 | 0 | December 22, 2025 5:00 PM | 84 | Critical
10875 | MS 27 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4658,4653,4654 | 4671,5611,5612,4808,4809 | 0 | December 30, 2025 5:00 PM | 83 | Critical
10876 | Milestone 28 - Legal Action | June 2, 2025 8:00 AM | April 20, 2026 5:00 PM | 222 | -32d |  |  | 0.31 | December 30, 2025 5:00 PM | 111 | Critical
10881 | BD 5 - MS 28: - Discovery and Develop Training Curriculum (Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 1024FS-19d,1025FS-19d,1026FS-19d | 4662SS | 0 | September 10, 2025 5:00 PM | 125 | Critical
10882 | BD 5 - MS 28: - Review Training Curriculum with VPODs(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 4661SS | 4663SS | 0 | September 24, 2025 5:00 PM | 111 | Critical
10883 | BD 5 - MS 28: - Incorporate VPODs Feedback(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 30 | -32d | 4662SS | 4664FS-5d,4666FS-5d | 0 | October 1, 2025 5:00 PM | 104 | Critical
10884 | BD 5 - MS 28: Finalize Training Curriculum (Build Drop Update) | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 5 | 29d | 4663FS-5d | 4670 | 0 | October 8, 2025 5:00 PM | 97 | Critical
10885 | MS 28 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | December 26, 2025 5:00 PM | 126 | 40d | 1044FF | 4670 | 0.7 | November 28, 2025 5:00 PM | 28 | Critical
10886 | BD 5 - MS 28: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 2, 2026 8:00 AM | March 13, 2026 5:00 PM | 29 | -32d | 4666FS+12d | 4668 | 0 | December 1, 2025 5:00 PM | 102 | Critical
10887 | BD 5 - MS 28: - Review Training Content with VPOD & TAW (Build Drop Update) | March 16, 2026 8:00 AM | March 27, 2026 5:00 PM | 10 | -32d | 4667 | 4669 | 0 | December 15, 2025 5:00 PM | 102 | Critical
10888 | BD 5 - MS 28: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 30, 2026 8:00 AM | April 13, 2026 5:00 PM | 10 | -32d | 4668 | 4670 | 0 | December 22, 2025 5:00 PM | 112 | Critical
10889 | MS 28 - Finalize Training Content | April 14, 2026 8:00 AM | April 20, 2026 5:00 PM | 5 | -32d | 4669,4664,4665 | 4671,5611,5612,4810,4811 | 0 | December 30, 2025 5:00 PM | 111 | Critical
10890 | Resource Family Approval Process Area Completed | April 20, 2026 5:00 PM | April 20, 2026 5:00 PM | 0 | 351d | 4648,4659,4670 | 4925 | 0 | December 30, 2025 5:00 PM | 111 | Critical
10891 | Financial Management | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM | 364 | 334d |  |  | 0.55 | February 3, 2026 5:00 PM | 100 | Critical
10893 | Group 1 Financial Management (Milestones 23/23.1, 24) | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM | 364 | 334d |  |  | 0.55 | February 3, 2026 5:00 PM | 100 | Critical
10912 | Milestone 23/23.1/23.2 - Track Administrative Costs | April 1, 2025 8:00 AM | May 14, 2026 5:00 PM | 283 | -50d |  |  | 0.51 | February 3, 2026 5:00 PM | 100 | Critical
10913 | MS 23/23.1/23.2 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 4675FS-24d,1008 | 4681FF | 1 | June 3, 2025 5:00 PM | 64 | Critical
10914 | Review Training Curriculum with VPODs | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 45 | 0d | 4680FF | 4682FF | 1 | June 17, 2025 5:00 PM | 50 | Critical
10915 | Incorporate VPODs Feedback | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4681FF | 4683FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10916 | MS 23/23.1/23.2 - Finalize Training Curriculum | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4682FF | 4693 | 1 | July 1, 2025 5:00 PM | 36 | Critical
10917 | MS 23/23.1/23.2 - Validate and Provide Feedback on Critical Scenarios for the EUST | November 28, 2025 8:00 AM | January 23, 2026 5:00 PM | 38 | 22d | 4675,1157FF,1242FF | 4693 | 0 | November 28, 2025 5:00 PM | 56 | Critical
10918 | BD 5- MS 23/23.1/23.2: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 27, 2026 8:00 AM | April 9, 2026 5:00 PM | 29 | -50d | 1167SS-36d,1249SS-36d,4689FS+12d | 4691 | 0 | January 5, 2026 5:00 PM | 94 | Critical
10919 | BD 5 - MS 23/23.1/23.2: - Review Training Content with VPOD & TAW (Build Drop Update) | April 10, 2026 8:00 AM | April 23, 2026 5:00 PM | 10 | -50d | 4690 | 4692 | 0 | January 20, 2026 5:00 PM | 93 | Critical
10920 | BD 5 - MS 23/23.1/23.2: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | April 24, 2026 8:00 AM | May 7, 2026 5:00 PM | 10 | -50d | 4691 | 4693 | 0 | January 27, 2026 5:00 PM | 100 | Critical
10921 | MS 23/23.1 - Finalize Training Content | May 8, 2026 8:00 AM | May 14, 2026 5:00 PM | 5 | -50d | 4692,4683,4684 | 4709,5611,5612,4802,4803 | 0 | February 3, 2026 5:00 PM | 100 | Critical
10922 | Milestone 24 - Track Assistance Costs | March 24, 2025 8:00 AM | March 23, 2026 5:00 PM | 251 | -13d |  |  | 0.53 | February 3, 2026 5:00 PM | 48 | Critical
10927 | MS 24 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 90 | 0d | 1008 | 4696FF | 1 | June 3, 2025 5:00 PM | 64 | Critical
10928 | Review Training Curriculum with VPODs | March 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 45 | 0d | 4695FF | 4697FF | 1 | June 17, 2025 5:00 PM | 50 | Critical
10929 | Incorporate VPODs Feedback | June 11, 2025 8:00 AM | August 6, 2025 5:00 PM | 40 | 0d | 4696FF | 4698FF | 1 | June 24, 2025 5:00 PM | 43 | Critical
10930 | MS 24 - Finalize Training Curriculum | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 30 | 0d | 4697FF | 4708 | 1 | July 1, 2025 5:00 PM | 36 | Critical
10932 | BD 5 - MS 24: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 1171SS-36d,4704FS+12d | 4706 | 0 | January 5, 2026 5:00 PM | 39 | Critical
10933 | BD 5 - MS 24: - Review Training Content with VPOD& TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4705 | 4707 | 0 | January 20, 2026 5:00 PM | 41 | Critical
10934 | BD 5 - MS 24: - Incorporate Feedback from VPOD& TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4706 | 4708 | 0 | January 27, 2026 5:00 PM | 48 | Critical
10935 | MS 24 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4707,4698,4699 | 4709,5611,5612,4804,4805 | 0 | February 3, 2026 5:00 PM | 48 | Critical
10936 | Financial Management Process Area Completed | May 14, 2026 5:00 PM | May 14, 2026 5:00 PM | 0 | 334d | 4693,4708 | 4925FS-1d | 0 | February 3, 2026 5:00 PM | 100 | Critical
10937 | Reports | October 31, 2025 8:00 AM | March 23, 2026 5:00 PM | 96 | 12d |  |  | 0 | February 27, 2026 5:00 PM | 24 | Critical
10939 | Group 1 Reports (Milestones 29, 30) | October 31, 2025 8:00 AM | March 23, 2026 5:00 PM | 96 | -13d |  |  | 0 | February 27, 2026 5:00 PM | 24 | Critical
10956 | BD 5 - MS 29,30 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4718 | 4720 | 0 | February 20, 2026 5:00 PM | 24 | Critical
10957 | MS 29, 30 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4719,4715 | 4721,5611,5612,4909 | 0 | February 27, 2026 5:00 PM | 24 | Critical
10958 | Reports Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 0 | 370d | 4720 | 4925,4812,4813 | 0 | February 27, 2026 5:00 PM | 24 | Critical
10959 | Admin Console | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM | 301 | 370d |  |  | 0.21 | January 21, 2026 5:00 PM | 61 | Critical
10961 | Group 1 Admin Console (Milestones 32 - Miscellaneous) | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM | 301 | -13d |  |  | 0.21 | January 21, 2026 5:00 PM | 61 | Critical
10971 | BD 5 - MS 32 - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4724,1278,1280FS-19d,1282FS-19d | 4729SS | 0 | September 22, 2025 5:00 PM | 84 | Critical
10972 | BD 5 - MS 32 - Review Training Curriculum with VPODs (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4728SS | 4730SS | 0 | October 6, 2025 5:00 PM | 70 | Critical
10973 | BD 5 - MS 32 - Incorporate VPODs Feedback (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 30 | -13d | 4729SS | 4731FS-5d | 0 | October 13, 2025 5:00 PM | 63 | Critical
10974 | MS 32 - Finalize Training Curriculum | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 5 | -13d | 4730FS-5d | 4736,4732SS | 0 | October 20, 2025 5:00 PM | 56 | Critical
10976 | BD 5 - MS 32 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Updates) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | -13d | 4732FS+12d | 4734 | 0 | December 22, 2025 5:00 PM | 53 | Critical
10977 | BD 5 - MS 32 - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 10 | -13d | 4733 | 4735 | 0 | January 6, 2026 5:00 PM | 55 | Critical
10978 | BE 5 - MS 32 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 10 | -13d | 4734 | 4736 | 0 | January 13, 2026 5:00 PM | 62 | Critical
10979 | MS 32 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 5 | -13d | 4735,4727,4731 | 4737,5611,5612,4814,4815 | 0 | January 21, 2026 5:00 PM | 61 | Critical
10980 | Admin Console Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 0 | 370d | 4736 | 4925 | 0 | January 21, 2026 5:00 PM | 61 | Critical
9646 | Develop Hardening Modules for MS 3,4,5 | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM | 548 | 334d |  |  | 0.64 | November 14, 2024 5:00 PM | 574 | Critical
9648 | Hardening M3 Screening | April 8, 2024 8:00 AM | February 7, 2025 5:00 PM | 212 | 0d |  |  | 1 | November 14, 2024 5:00 PM | 85 | Critical
9655 | Hardening M4 Investigations-Engagement | April 8, 2024 8:00 AM | February 7, 2025 5:00 PM | 212 | 0d |  |  | 1 | November 14, 2024 5:00 PM | 85 | Critical
9662 | Hardening M5 Investigations-Determination | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM | 548 | 334d |  |  | 0.26 | November 14, 2024 5:00 PM | 574 | Critical
9682 | Execute ILT Strategy | February 26, 2024 8:00 AM | July 18, 2025 5:00 PM | 352 | 0d |  |  | 1 | June 26, 2025 5:00 PM | 22 | Critical
9687 | Incorporate Review Feedback for ILT Training Materials - Cycle 2 | July 28, 2025 8:00 AM | August 22, 2025 5:00 PM | 20 | 0d | 4848 | 4850 | 1 | September 27, 2024 5:00 PM | 329 | Critical
9688 | Finalize ILT Training Materials - Cycle 2 | August 25, 2025 8:00 AM | September 10, 2025 5:00 PM | 12 | 0d | 4849 | 4851 | 1 | December 30, 2024 5:00 PM | 254 | Critical
9689 | Develop ILT Training Materials - Cycle 3 | September 11, 2025 8:00 AM | November 21, 2025 5:00 PM | 51 | 386d | 4850 | 4852 | 0.43 | August 28, 2025 5:00 PM | 85 | Critical
9697 | Develop Training Delivery Logistics | June 25, 2024 8:00 AM | August 20, 2025 5:00 PM | 291 | 0d |  |  | 1 | December 20, 2024 5:00 PM | 243 | Critical
9698 | Build Train-the-Trainer (T3) Curriculum | August 22, 2025 8:00 AM | September 25, 2025 5:00 PM | 24 | 0d | 4880 | 4882 | 1 | November 5, 2024 5:00 PM | 324 | Critical
9700 | Update CWS-CARES Glossary with Terms from Milestone 3,4,5,6,7,8,9,15,19,20, 21 | February 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 24 | 0d | 4884FS+112d | 4925,4923FS+175d | 1 | December 20, 2024 5:00 PM | 77 | Critical
9703 | Develop after-training evaluations | May 14, 2026 8:00 AM | June 11, 2026 5:00 PM | 20 | 334d | 4924,4104,4187,4247,4306,4310,4315,4341,4357,4365,4538,4545,4606,4630,4637,4671,4678,4709FS-1d,4721,4737,4738,4770,4922,4116,4127,4139,4150,4448,4754,4767,4777,4316,4317,4272,4852,4889 |  | 0 | March 27, 2026 5:00 PM | 76 | Critical
9729 | Review and Leverage existing CARES-Live OCM plan to develop the CWS-CARES OCM plan Version 1 & Version 2 | August 15, 2022 8:00 AM | May 20, 2025 5:00 PM | 692 | 0d |  |  | 1 | July 19, 2024 5:00 PM | 305 | Critical
9751 | CWS-CARES Organizational Change Management Plan Version 2 | February 26, 2024 8:00 AM | May 20, 2025 5:00 PM | 311 | 0d |  |  | 1 | July 19, 2024 5:00 PM | 305 | Critical
9761 | Develop draft of updated OCM Plan for State team review (CARES RACI) | April 29, 2024 8:00 AM | October 14, 2024 5:00 PM | 119 | 0d |  |  | 1 | July 19, 2024 5:00 PM | 87 | Critical
9767 | Review updated OCM Plan with PaaS SI Team, IV&V Team, Project Directors, and ELT | August 21, 2024 8:00 AM | September 3, 2024 5:00 PM | 10 | 0d | 5005 | 5007 | 1 | July 8, 2024 5:00 PM | 57 | Critical
9768 | Incorporate Feedback from PaaS SI Team, IV&V Team, Project Directors, and ELT | September 4, 2024 8:00 AM | September 10, 2024 5:00 PM | 5 | 0d | 5006 | 5008 | 1 | July 12, 2024 5:00 PM | 60 | Critical
9769 | State reviews updated OCM Plan with comments and provides signoff/approval | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5 | 0d | 5009 | 5621,5012FS+75d | 1 | July 19, 2024 5:00 PM | 87 | Critical
9871 | Discover Phase | September 1, 2022 8:00 AM | September 10, 2026 5:00 PM | 1008 | 32d |  |  | 0.92 | October 25, 2024 5:00 PM | 685 | Critical
9895 | OCM Visioning Session Follow-Up | August 11, 2023 8:00 AM | September 20, 2024 5:00 PM | 280 | 0d |  |  | 1 | August 6, 2024 5:00 PM | 45 | Critical
9904 | Visioning Session Follow-up Completed | September 20, 2024 5:00 PM | September 20, 2024 5:00 PM | 0 | 0d | 5096 | 5621 | 1 | August 6, 2024 5:00 PM | 45 | Critical
9958 | Define Phase | December 7, 2022 8:00 AM | October 23, 2026 5:00 PM | 974 | 239d |  |  | 0.76 | November 25, 2024 5:00 PM | 697 | Critical
9997 | OCM Advisory Workgroup Engagement | November 1, 2023 8:00 AM | October 23, 2026 5:00 PM | 747 | 239d |  |  | 0.64 | October 30, 2024 5:00 PM | 723 | Critical
10016 | Create Sandbox Strategy | October 3, 2023 8:00 AM | February 21, 2025 5:00 PM | 347 | 422d |  |  | 0.99 | July 16, 2024 5:00 PM | 220 | Critical
10041 | Develop Executive Summary slides for ELT and complete reviews with State Implementation Management Team | October 7, 2024 8:00 AM | October 18, 2024 5:00 PM | 10 | 0d | 5270FS+123d | 5272 | 1 | July 3, 2024 5:00 PM | 107 | Critical
10042 | Submit Sandbox Strategy to State Leadership: ELT | October 21, 2024 8:00 AM | October 29, 2024 5:00 PM | 7 | 0d | 5271 | 5273 | 1 | July 12, 2024 5:00 PM | 109 | Critical
10043 | Incorporate Feedback from ELT | October 30, 2024 8:00 AM | October 31, 2024 5:00 PM | 2 | 0d | 5272 | 5274 | 1 | July 16, 2024 5:00 PM | 107 | Critical
10044 | Sandbox Strategy Completed | October 31, 2024 5:00 PM | October 31, 2024 5:00 PM | 0 | 0d | 5273 | 5621,5275FS+49d | 1 | July 16, 2024 5:00 PM | 107 | Critical
10071 | Develop CWS-CARES 101: Intake video script and complete validation | March 3, 2025 8:00 AM | April 4, 2025 5:00 PM | 24 | 0d | 5299 | 5303 | 1 | October 15, 2024 5:00 PM | 171 | Critical
10075 | Develop and Complete Reviews of the 'Preparing for CARES Go-Live' video | April 27, 2026 8:00 AM | August 17, 2026 5:00 PM | 79 | -4d |  |  | 0 | July 24, 2026 5:00 PM | 24 | Critical
10076 | Develop and Launch the 'What Happens Next?' video | July 13, 2026 8:00 AM | November 2, 2026 5:00 PM | 80 | -4d |  |  | 0 | October 2, 2026 5:00 PM | 31 | Critical
10079 | To-Be Process Documentation - Deliverable Task 5.5 | February 27, 2023 8:00 AM | March 20, 2026 5:00 PM | 769 | 152d |  |  | 0.89 | January 29, 2026 5:00 PM | 50 | Critical
10091 | Review and Verify Investigations - Determination To-Be Processes with Service Managers | May 13, 2024 8:00 AM | March 20, 2026 5:00 PM | 466 | 152d |  |  | 0.86 | January 19, 2024 5:00 PM | 791 | Critical
10329 | Process Areas | May 13, 2024 8:00 AM | March 20, 2026 5:00 PM | 466 | 152d |  |  | 0.86 | January 29, 2026 5:00 PM | 50 | Critical
10297 | Milestone 06 - Case Management Engagement | May 13, 2024 8:00 AM | October 15, 2024 5:00 PM | 110 | 0d |  |  | 1 | August 9, 2024 5:00 PM | 67 | Critical
10299 | MS 06: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 10 | 0d | 5379FF+49d | 5381FF+5d | 1 | June 28, 2024 5:00 PM | 74 | Critical
10300 | MS 06: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 10 | 0d | 5380FF+5d | 5382FF | 1 | July 8, 2024 5:00 PM | 71 | Critical
10301 | MS 06: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5 | 0d | 5381FF | 5383,4538,5550 | 1 | July 12, 2024 5:00 PM | 67 | Critical
10302 | MS 06: Review, Validate and Update To-Be Business Flows/Processes | September 18, 2024 8:00 AM | October 15, 2024 5:00 PM | 20 | 0d | 5382 | 5613 | 1 | August 9, 2024 5:00 PM | 67 | Critical
10303 | Milestone 08 - Placement | May 13, 2024 8:00 AM | October 15, 2024 5:00 PM | 110 | 0d |  |  | 1 | August 9, 2024 5:00 PM | 67 | Critical
10305 | MS 08: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 10 | 0d | 5385FF+49d | 5387FF+5d | 1 | June 28, 2024 5:00 PM | 74 | Critical
10306 | MS 08: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 10 | 0d | 5386FF+5d | 5388FF | 1 | July 8, 2024 5:00 PM | 71 | Critical
10307 | MS 08: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5 | 0d | 5387FF | 5389,4538,5550 | 1 | July 12, 2024 5:00 PM | 67 | Critical
10308 | MS 08: Review, Validate and Update To-Be Business Flows/Processes | September 18, 2024 8:00 AM | October 15, 2024 5:00 PM | 20 | 0d | 5388 | 5613 | 1 | August 9, 2024 5:00 PM | 67 | Critical
10311 | MS 15: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 10 | 0d | 5391FF+27d | 5393FF+5d | 1 | August 16, 2024 5:00 PM | 25 | Critical
10312 | MS 15: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 10 | 0d | 5392FF+5d | 5394 | 1 | August 23, 2024 5:00 PM | 25 | Critical
10313 | MS 15: Finalize To-Be Business Flows/Processes | September 18, 2024 8:00 AM | September 24, 2024 5:00 PM | 5 | 0d | 5393 | 5395,4538,5550 | 1 | August 30, 2024 5:00 PM | 25 | Critical
10462 | Milestone 6.1 - Prevention Services | June 17, 2024 8:00 AM | October 14, 2024 5:00 PM | 85 | 0d |  |  | 1 | August 30, 2024 5:00 PM | 45 | Critical
10464 | MS 6.1: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 30, 2024 5:00 PM | 24 | 0d | 5410FS+39d | 5412FF+5d | 1 | July 8, 2024 5:00 PM | 84 | Critical
10465 | MS 6.1: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 7, 2024 5:00 PM | 10 | 0d | 5411FF+5d | 5413 | 1 | July 8, 2024 5:00 PM | 91 | Critical
10466 | MS 6.1: Finalize To-Be Business Flows/Processes | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5 | 0d | 5412 | 4538,5550,5414FF | 1 | July 12, 2024 5:00 PM | 94 | Critical
10467 | MS 6.1: Review, Validate and Update To-Be Business Flows/Processes | August 28, 2024 8:00 AM | October 14, 2024 5:00 PM | 20 | 0d | 2504,5413FF | 5526,5613 | 1 | August 30, 2024 5:00 PM | 45 | Critical
10332 | MS 07: Review To-Be Business Flows/Processes with VPODs | July 18, 2024 8:00 AM | August 2, 2024 5:00 PM | 12 | 0d | 5416FS+10d | 5418FF+8d | 1 | July 8, 2024 5:00 PM | 25 | Critical
10333 | MS 07: Incorporate VPODs Feedback | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 | 0d | 5417FF+8d | 5419 | 1 | July 8, 2024 5:00 PM | 37 | Critical
10334 | MS 07: Finalize To-Be Business Flows/Processes | August 15, 2024 8:00 AM | August 20, 2024 5:00 PM | 4 | 0d | 5418 | 4538,5550 | 1 | July 12, 2024 5:00 PM | 39 | Critical
10336 | Milestone 09 - Case Management - Engagement and Services | June 10, 2024 8:00 AM | October 14, 2024 5:00 PM | 90 | 0d |  |  | 1 | July 29, 2024 5:00 PM | 77 | Critical
10338 | MS 09: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 30, 2024 5:00 PM | 24 | 0d | 5422FS+39d | 5424FF+5d | 1 | July 8, 2024 5:00 PM | 84 | Critical
10339 | MS 09: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 7, 2024 5:00 PM | 10 | 0d | 5423FF+5d | 5425 | 1 | July 8, 2024 5:00 PM | 91 | Critical
10340 | MS 09: Finalize To-Be Business Flows/Processes | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5 | 0d | 5424 | 4538,5550,5426FF | 1 | July 12, 2024 5:00 PM | 94 | Critical
10341 | MS 09: Review, Validate and Update To-Be Business Flows/Processes | August 28, 2024 8:00 AM | October 14, 2024 5:00 PM | 20 | 0d | 355,5425FF | 5613 | 1 | July 29, 2024 5:00 PM | 77 | Critical
10356 | MS 13: Develop To-Be Business Flows/Processes | October 21, 2024 8:00 AM | November 25, 2024 5:00 PM | 25 | 0d | 5443FS+40d | 5449,4738FS+9mo,5445 | 1 | October 4, 2024 5:00 PM | 52 | Critical
10357 | MS 13: Review To-Be Business Flows/Processes with VPODs | December 10, 2024 8:00 AM | December 20, 2024 5:00 PM | 9 | 0d | 5445FF | 5447FF+5d | 1 | October 4, 2024 5:00 PM | 77 | Critical
10358 | MS 13: Incorporate VPODs Feedback | December 16, 2024 8:00 AM | December 30, 2024 5:00 PM | 10 | 0d | 5446FF+5d | 5448 | 1 | October 11, 2024 5:00 PM | 80 | Critical
10359 | MS13: Finalize To-Be Business Flows/Processes | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 5 | 0d | 5447 | 4538,5550FS+66d | 1 | October 18, 2024 5:00 PM | 81 | Critical
10362 | Milestone 14 - Warrants | June 28, 2024 8:00 AM | November 8, 2024 5:00 PM | 95 | 0d |  |  | 1 | September 11, 2024 5:00 PM | 58 | Critical
10364 | MS 14: Review To-Be Business Flows/Processes with VPODs | September 17, 2024 8:00 AM | September 30, 2024 5:00 PM | 10 | 0d | 5453FF+41d | 5455FF+5d | 1 | July 31, 2024 5:00 PM | 61 | Critical
10365 | MS 14: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 11, 2024 5:00 PM | 14 | 0d | 5454FF+5d | 5456FF | 1 | August 7, 2024 5:00 PM | 65 | Critical
10366 | MS 14: Finalize To-Be Business Flows/Processes | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5 | 0d | 5455FF | 5457 | 1 | August 14, 2024 5:00 PM | 58 | Critical
10367 | MS 14: Review, Validate and Update To-Be Business Flows/Processes | October 14, 2024 8:00 AM | November 8, 2024 5:00 PM | 20 | 0d | 5456,411 | 5526,5613 | 1 | September 11, 2024 5:00 PM | 58 | Critical
10395 | Eligibility | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM | 376 | 138d |  |  | 0.66 | January 24, 2025 5:00 PM | 368 | Critical
10394 | Group 1 Eligibility (Milestones 21) | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM | 376 | 138d |  |  | 0.66 | January 24, 2025 5:00 PM | 368 | Critical
10388 | Milestone 21 - Eligibility Programs | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM | 376 | 138d |  |  | 0.66 | January 24, 2025 5:00 PM | 368 | Critical
10393 | Review, Validate and Update To-Be Business Flows/Processes | December 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 20 | 138d | 5482,1249 | 5613 | 0 | January 24, 2025 5:00 PM | 368 | Critical
10415 | Resource Family Approval | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM | 389 | 171d |  |  | 0.73 | January 29, 2026 5:00 PM | 25 | Critical
10414 | Group 1 Resource Family Approval (Milestones 26, 27, 28) | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM | 389 | 171d |  |  | 0.73 | January 29, 2026 5:00 PM | 25 | Critical
10408 | Milestone 28 - Legal Action | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM | 389 | 171d |  |  | 0.73 | January 29, 2026 5:00 PM | 25 | Critical
10413 | Review, Validate and Update To-Be Business Flows/Processes | January 26, 2026 8:00 AM | February 23, 2026 5:00 PM | 20 | 171d | 5499,1062,5502 | 5526 | 0 | January 29, 2026 5:00 PM | 25 | Critical
10429 | Financial Management | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM | 353 | 101d |  |  | 0.7 | January 29, 2026 5:00 PM | 50 | Critical
10428 | Group 1 Financial Management (Milestones 23, 24) | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM | 353 | 101d |  |  | 0.7 | January 29, 2026 5:00 PM | 50 | Critical
10416 | Milestone 23 - Track Administrative Costs | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM | 353 | 101d |  |  | 0.7 | January 29, 2026 5:00 PM | 50 | Critical
10421 | Review, Validate and Update To-Be Business Flows/Processes | February 23, 2026 8:00 AM | March 20, 2026 5:00 PM | 20 | 101d | 5507,1167,1249,5510 | 5613 | 0 | January 29, 2026 5:00 PM | 50 | Critical
10100 | Deliverable Task 5.5 Completed | February 23, 2026 5:00 PM | February 23, 2026 5:00 PM | 0 | 171d | 5517,5525,5503,5420,5449,5457,5414,5491,5497 | 5630 | 0 | January 29, 2026 5:00 PM | 25 | Critical
10120 | Deliver Phase | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM | 920 | 239d |  |  | 0.7 | March 21, 2025 5:00 PM | 581 | Critical
10131 | Information Sessions | January 18, 2024 8:00 AM | February 27, 2026 5:00 PM | 531 | 405d |  |  | 0.7 | March 21, 2025 5:00 PM | 343 | Critical
10142 | Complete Reviews of Process Information Session 1: Intake Resources with the Service Managers and County Consultants and incorporate feedback | February 3, 2025 8:00 AM | March 10, 2025 5:00 PM | 25 | 0d | 5544SS+200d | 5546 | 1 | October 4, 2024 5:00 PM | 157 | Critical
10143 | Schedule Process Information Session 1: Intake Regional Sessions | March 11, 2025 8:00 AM | March 17, 2025 5:00 PM | 5 | 0d | 5545 | 5547 | 1 | October 11, 2024 5:00 PM | 157 | Critical
10144 | Conduct Dry Run for Process Information Session 1: Intake | March 18, 2025 8:00 AM | March 24, 2025 5:00 PM | 5 | 0d | 5546 | 5548FS+4d | 1 | October 18, 2024 5:00 PM | 157 | Critical
10145 | Complete Final Preparations for Process Information Session 1: Intake Regional Sessions | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 22 | 0d | 5547FS+4d | 5549 | 1 | January 23, 2025 5:00 PM | 97 | Critical
10146 | Develop Process Information Session 2: Case Management Resources (process flows, change impacts, draft worksheets, invitation communications) | April 15, 2025 8:00 AM | April 28, 2025 5:00 PM | 10 | 0d | 5382,5388,5394,5400,5406,5413,5419,5425,5440,5448FS+66d | 5551 | 1 | November 1, 2024 5:00 PM | 178 | Critical
10147 | Complete Reviews of Process Information Session 2: Case Management Resources with Implementation Leads, Training, and Implementation Management Team and incorporate feedback | April 29, 2025 8:00 AM | May 9, 2025 5:00 PM | 9 | 0d | 5550 | 5552FS+2d | 1 | November 15, 2024 5:00 PM | 175 | Critical
10148 | Complete Reviews of Process Information Session 2: Case Management Resources with the OCM Advisory Workgroup and incorporate feedback | May 14, 2025 8:00 AM | May 21, 2025 5:00 PM | 6 | 0d | 5551FS+2d | 5553FS+2d | 1 | November 27, 2024 5:00 PM | 175 | Critical
10149 | Complete Reviews of Process Information Session 2: Case Management Resources with the Service Managers and County Consultants and incorporate feedback | May 27, 2025 8:00 AM | June 9, 2025 5:00 PM | 10 | 0d | 5552FS+2d | 5554 | 1 | December 17, 2024 5:00 PM | 174 | Critical
10150 | Schedule Process Information Session 2: Case Management Regional Sessions | June 10, 2025 8:00 AM | June 16, 2025 5:00 PM | 5 | 0d | 5553 | 5555 | 1 | December 24, 2024 5:00 PM | 174 | Critical
10151 | Conduct Dry Run for Process Information Session 2: Case Management | June 17, 2025 8:00 AM | June 23, 2025 5:00 PM | 5 | 0d | 5554 | 5556FS+5d | 1 | January 2, 2025 5:00 PM | 172 | Critical
10152 | Deliver Process Information Session 2: Placement Regional Sessions - Part 1 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 22 | 0d | 5555FS+5d | 5557 | 1 | March 21, 2025 5:00 PM | 132 | Critical
12668 | Deliver Process Information Session 3: Ongoing Case Work and Finish a Case Regional Sessions - Part 1 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 21 | 0d | 5557 | 5559,5560SS | 1 | March 21, 2025 5:00 PM | 193 | Critical
12670 | Deliver Process Information Session 4: Court Processing Regional Sessions - Part 1 | November 3, 2025 8:00 AM | December 12, 2025 5:00 PM | 28 | 167d | 5559 | 5563,5565FS+13d | 0 | March 21, 2025 5:00 PM | 266 | Critical
12672 | Deliver Process Information Session 5: RFA/RM/FM/Admin Regional Sessions - Part 1 | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 29 | 167d | 5562FS+13d | 5566 | 0 | March 21, 2025 5:00 PM | 329 | Critical
10162 | Communications | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM | 920 | 239d |  |  | 0.69 | July 31, 2024 5:00 PM | 814 | Critical
10163 | Draft and distribute monthly communications products | July 3, 2023 8:00 AM | October 23, 2026 5:00 PM | 832 | 239d |  |  | 0.69 | July 31, 2024 5:00 PM | 814 | Critical
10982 | Content Integration - Pilot | May 1, 2026 8:00 AM | August 5, 2026 5:00 PM | 67 | -40d |  |  | 0 | June 19, 2026 5:00 PM | 47 | Critical
10983 | Integrate Final Product Updates into Online Training Content | May 15, 2026 8:00 AM | July 16, 2026 5:00 PM | 43 | -50d | 1856FF-5d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5616 | 0 | June 1, 2026 5:00 PM | 45 | Critical
10984 | Integrate Final Product Updates into ILT Content | May 15, 2026 8:00 AM | August 5, 2026 5:00 PM | 57 | -49d | 1856FF+8d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5617 | 0 | June 17, 2026 5:00 PM | 49 | Critical
10986 | Training, Pilot, and Production Execution | January 28, 2026 8:00 AM | December 15, 2026 5:00 PM | 222 | 68d |  |  | 0 | October 26, 2026 5:00 PM | 50 | Critical
10987 | Training Delivery | July 17, 2026 8:00 AM | December 14, 2026 5:00 PM | 103 | -50d |  |  | 0 | October 23, 2026 5:00 PM | 52 | Critical
10988 | Deliver Self Paced Online Training | July 17, 2026 8:00 AM | November 30, 2026 5:00 PM | 93 | -50d | 5611 | 5624SS+5d,5617SS+15d | 0 | July 14, 2026 5:00 PM | 139 | Critical
10989 | Deliver TTT Training | August 7, 2026 8:00 AM | September 17, 2026 5:00 PM | 29 | -50d | 5616SS+15d,5612 | 5624,5618,3873SS | 0 | July 30, 2026 5:00 PM | 49 | Critical
10990 | Deliver ILT | September 18, 2026 8:00 AM | December 14, 2026 5:00 PM | 59 | -32d | 5617,1904,1905,534,554,562 | 5620FF,5619FF | 0 | October 23, 2026 5:00 PM | 52 | Critical
10991 | Deliver Refresher Training | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -32d | 5618FF | 5620FS-40d | 0 | October 23, 2026 5:00 PM | 52 | Critical
10992 | Complete Final Sandbox Participation | October 15, 2026 8:00 AM | December 14, 2026 5:00 PM | 40 | -32d | 5618FF,5619FS-40d | 5630 | 0 | October 23, 2026 5:00 PM | 52 | Critical
10993 | Pilot Execution | January 28, 2026 8:00 AM | December 14, 2026 5:00 PM | 221 | -48d |  |  | 0 | October 23, 2026 5:00 PM | 52 | Critical
10995 | Conduct Pilot Users' Training | September 18, 2026 8:00 AM | October 15, 2026 5:00 PM | 20 | -49d | 5616SS+5d,5617 | 5626,5625SS+8d | 0 | August 27, 2026 5:00 PM | 49 | Critical
10996 | Pilot Readiness Review and Go-No-Go Decision | September 30, 2026 8:00 AM | October 13, 2026 5:00 PM | 10 | -47d | 2415,2416,2417FS+5d,2438,2440,2442,5624SS+8d | 5626 | 0 | August 27, 2026 5:00 PM | 47 | Critical
10997 | Conduct Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 29 | -49d | 5623,5625,5624 | 5627,5628,3875SS | 0 | October 9, 2026 5:00 PM | 52 | Critical
10998 | Pilot Remediation | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -48d | 5626 | 5629 | 0 | October 23, 2026 5:00 PM | 52 | Critical
10999 | Production Readiness Review and Go-No-Go Decision | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 10 | -49d | 5626,3049,2983,2152,1859 | 5629FS+1d,5630 | 0 | October 23, 2026 5:00 PM | 52 | Critical
11000 | Production Execution | December 15, 2026 5:00 PM | December 15, 2026 5:00 PM | 0 | -49d | 5627,5628FS+1d,5611,5612,5613,5361FS-43d | 5630,3886 | 0 | October 26, 2026 5:00 PM | 50 | Critical

## Low_Quality_Names
UID | Task Name | Start | Finish | Duration | Total Slack | Predecessors | Successors | Percent Complete | Severity
12725 | Smoke Test Initial Environment Build | December 20, 2024 8:00 AM | December 24, 2024 5:00 PM | 3 | 0d | 1543 | 1549 | 1 | Info
12746 | Communicate with County teams to test access to EUST 2 | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 5 | 0d | 1546FS+73d |  | 1 | Info
12751 | Smoke Test Deployment for User Feedback | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 5 | 0d | 1551 | 1553FS-2d | 1 | Info
12749 | Smoke Test Environment | March 3, 2025 8:00 AM | March 14, 2025 5:00 PM | 10 | 0d | 1554 |  | 1 | Info
12753 | Test interface integration with EUST environment - FCED/CalSAWS | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 5 | 0d | 1569,1570FS+56d |  | 1 | Info
12755 | Test interface integration with EUST environment - JNET/San Bern. | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 5 | 0d | 1569,1570FS+56d | 1581FS-1d | 1 | Info
43658 | Communicate with County teams to test access to EUST 3 | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM | 5 | 425d |  | 1725SS | 0 | Info
43688 | Smoke Test Initial Environment Build | February 5, 2026 8:00 AM | February 9, 2026 5:00 PM | 3 | 414d | 1753 | 1726 | 0 | Info
43692 | Smoke Test Environment | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 5 | 437d | 1756 |  | 0 | Info
43720 | Test interface integration with EUST environment - FCED/CalSAWS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43721 | Test interface integration with EUST environment - JNET/San Bern. | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43722 | Test interface integration with EUST environment - SDM/Evident Change | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43723 | Test interface integration with EUST environment - P-CIS/Opeeka | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43724 | Test interface integration with EUST environment - LIS/FAS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43725 | Test interface integration with EUST environment - CECRIS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 | 428d | 1784 |  | 0 | Info
43742 | Test interface integration with EUST environment - FCED/CalSAWS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
43743 | Test interface integration with EUST environment - JNET/San Bern. | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
43744 | Test interface integration with EUST environment - SDM/Evident Change | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
43745 | Test interface integration with EUST environment - P-CIS/Opeeka | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
43746 | Test interface integration with EUST environment - LIS/FAS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
43747 | Test interface integration with EUST environment - CECRIS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 43 | 382d | 1807SS |  | 0 | Info
3167 | Micro Conversion foundation framework - Unit Test | July 10, 2023 8:00 AM | October 27, 2023 5:00 PM | 80 | 0d | 2178 | 2180,2210SS | 1 | Info
3778 | Performance Test Plan | September 1, 2022 8:00 AM | March 1, 2023 5:00 PM | 130 | 0d |  |  | 1 | Info
13201 | Conversion ETL Development and Test | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 | 445d |  |  | 0.19 | Info
13783 | Test On-Demand Training Programs | November 26, 2025 8:00 AM | December 8, 2025 5:00 PM | 8 | 456d | 4894 | 4896 | 0 | Info
13789 | Test On-Demand Training Programs | February 25, 2026 8:00 AM | March 3, 2026 5:00 PM | 5 | 385d | 4900 | 4902 | 0 | Info
13772 | Test On-Demand Training Programs | February 4, 2026 8:00 AM | February 17, 2026 5:00 PM | 9 | 405d | 4905 | 4907 | 0 | Info
13777 | Test On-Demand Training Programs | April 1, 2026 8:00 AM | April 2, 2026 5:00 PM | 2 | 381d | 4910 | 4912 | 0 | Info
13778 | Test On-Demand Training Programs for Sandbox Envt | May 13, 2026 8:00 AM | May 27, 2026 5:00 PM | 10 | 335d | 4915 | 4917 | 0 | Info
24095 | Alameda CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5743SF+30d |  | 0 | Info
24096 | Alameda CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24113 | Alameda CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
24114 | Alameda CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24270 | Alpine CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 5918SF+30d |  | 0 | Info
24271 | Alpine CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24288 | Alpine CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
24289 | Alpine CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24445 | Amador CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6093SF+30d |  | 0 | Info
24446 | Amador CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24463 | Amador CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
24464 | Amador CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24773 | Contra Costa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6421SF+30d |  | 0 | Info
24774 | Contra Costa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24791 | Contra Costa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
24792 | Contra Costa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24947 | Del Norte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6595SF+30d |  | 0 | Info
24948 | Del Norte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
24965 | Del Norte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
24966 | Del Norte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25122 | El Dorado CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6770SF+30d |  | 0 | Info
25123 | El Dorado CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25140 | El Dorado CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
25141 | El Dorado CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25297 | Glenn CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 6945SF+30d |  | 0 | Info
25298 | Glenn CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25315 | Glenn CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
25316 | Glenn CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25472 | Humboldt CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7120SF+30d |  | 0 | Info
25473 | Humboldt CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25490 | Humboldt CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
25491 | Humboldt CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25647 | Imperial CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
25648 | Imperial CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25804 | Inyo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
25805 | Inyo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25961 | Kern CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7609SF+30d |  | 0 | Info
25962 | Kern CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
25979 | Kern CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
25980 | Kern CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26136 | Lake CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7784SF+30d |  | 0 | Info
26137 | Lake CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26154 | Lake CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
26155 | Lake CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26311 | Lassen CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 7959SF+30d |  | 0 | Info
26312 | Lassen CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26479 | Los Angeles CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8127SF+30d |  | 0 | Info
26480 | Los Angeles CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26497 | Los Angeles CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
26498 | Los Angeles CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26653 | Madera CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8301SF+30d |  | 0 | Info
26654 | Madera CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26671 | Madera CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
26672 | Madera CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26828 | Marin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8476SF+30d |  | 0 | Info
26829 | Marin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
26846 | Marin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
26847 | Marin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27003 | Mariposa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8651SF+30d |  | 0 | Info
27004 | Mariposa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27021 | Mariposa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
27022 | Mariposa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27178 | Mendocino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 8826SF+30d |  | 0 | Info
27179 | Mendocino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27196 | Mendocino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
27197 | Mendocino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27353 | Merced CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9001SF+30d |  | 0 | Info
27354 | Merced CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27371 | Merced CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
27372 | Merced CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27521 | Modoc CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d |  |  | 0 | Info
27522 | Modoc CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27684 | Mono CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9332SF+30d |  | 0 | Info
27685 | Mono CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27698 | Mono CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
27699 | Mono CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27855 | Monterey CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9503SF+30d |  | 0 | Info
27856 | Monterey CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
27873 | Monterey CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
27874 | Monterey CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28030 | Napa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9678SF+30d |  | 0 | Info
28031 | Napa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28048 | Napa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
28049 | Napa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28205 | Nevada CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 9853SF+30d |  | 0 | Info
28206 | Nevada CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28223 | Nevada CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
28224 | Nevada CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28380 | Orange CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10028SF+30d |  | 0 | Info
28381 | Orange CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28398 | Orange CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
28399 | Orange CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28555 | Placer CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10203SF+30d |  | 0 | Info
28556 | Placer CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28573 | Placer CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
28574 | Placer CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28730 | Plumas CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10378SF+30d |  | 0 | Info
28731 | Plumas CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28748 | Plumas CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
28749 | Plumas CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28905 | Sacramento CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10553SF+30d |  | 0 | Info
28906 | Sacramento CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
28923 | Sacramento CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
28924 | Sacramento CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29080 | San Benito CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 0d | 10728SF+30d |  | 1 | Info
29081 | San Benito CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29098 | San Benito CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
29099 | San Benito CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29255 | San Bernardino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 10903SF+30d |  | 0 | Info
29256 | San Bernardino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29273 | San Bernardino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
29274 | San Bernardino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29430 | San Francisco CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11078SF+30d |  | 0 | Info
29431 | San Francisco CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29448 | San Francisco CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
29449 | San Francisco CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29605 | San Joaquin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11253SF+30d |  | 0 | Info
29606 | San Joaquin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29623 | San Joaquin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.6 | Info
29624 | San Joaquin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29780 | San Luis Obispo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11428SF+30d |  | 0 | Info
29781 | San Luis Obispo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29798 | San Luis Obispo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
29799 | San Luis Obispo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29955 | Santa Barbara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11603SF+30d |  | 0 | Info
29956 | Santa Barbara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
29973 | Santa Barbara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
29974 | Santa Barbara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30130 | Santa Clara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11778SF+30d |  | 0 | Info
30131 | Santa Clara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30148 | Santa Clara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
30149 | Santa Clara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30305 | Santa Cruz CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 11953SF+30d |  | 0 | Info
30306 | Santa Cruz CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30323 | Santa Cruz CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
30324 | Santa Cruz CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30480 | Shasta CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12128SF+30d |  | 0 | Info
30481 | Shasta CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30498 | Shasta CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
30499 | Shasta CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30648 | Sierra CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12296SF+30d |  | 0 | Info
30649 | Sierra CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30661 | Sierra CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
30662 | Sierra CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30818 | Siskiyou CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12466SF+30d |  | 0 | Info
30819 | Siskiyou CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30836 | Siskiyou CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
30837 | Siskiyou CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
30993 | Solano CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12641SF+30d |  | 0.2 | Info
30994 | Solano CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31011 | Solano CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
31012 | Solano CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31168 | Sonoma CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12816SF+30d |  | 0 | Info
31169 | Sonoma CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31186 | Sonoma CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
31187 | Sonoma CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31343 | Stanislaus CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 12991SF+30d |  | 0 | Info
31344 | Stanislaus CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31361 | Stanislaus CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
31362 | Stanislaus CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31518 | Sutter CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13166SF+30d |  | 0 | Info
31519 | Sutter CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31536 | Sutter CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
31537 | Sutter CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31693 | Tehama CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13341SF+30d |  | 0 | Info
31694 | Tehama CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31711 | Tehama CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 0d |  |  | 1 | Info
31712 | Tehama CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31868 | Trinity CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13516SF+30d |  | 0 | Info
31869 | Trinity CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
31886 | Trinity CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
31887 | Trinity CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32043 | Tulare CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13691SF+30d |  | 0 | Info
32044 | Tulare CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32061 | Tulare CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
32062 | Tulare CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32218 | Yolo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 13866SF+30d |  | 0 | Info
32219 | Yolo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32236 | Yolo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
32237 | Yolo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32393 | Yuba CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14041SF+30d |  | 0 | Info
32394 | Yuba CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32411 | Yuba CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
32412 | Yuba CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32567 | Butte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14215SF+30d |  | 0 | Info
32568 | Butte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32585 | Butte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
32586 | Butte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32741 | Fresno CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14389SF+30d |  | 0 | Info
32742 | Fresno CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32759 | Fresno CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
32760 | Fresno CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32915 | San Diego CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14563SF+30d |  | 0 | Info
32916 | San Diego CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
32933 | San Diego CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
32934 | San Diego CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33089 | San Mateo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14737SF+30d |  | 0 | Info
33090 | San Mateo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33107 | San Mateo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
33108 | San Mateo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33263 | Tuolumne CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 14911SF+30d |  | 0 | Info
33264 | Tuolumne CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33281 | Tuolumne CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
33282 | Tuolumne CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33437 | Calaveras CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15085SF+30d |  | 0 | Info
33438 | Calaveras CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33455 | Calaveras CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0.2 | Info
33456 | Calaveras CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33611 | Kings CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15259SF+30d |  | 0 | Info
33612 | Kings CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33629 | Kings CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
33630 | Kings CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33785 | Riverside CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15433SF+30d |  | 0 | Info
33786 | Riverside CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33803 | Riverside CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
33804 | Riverside CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33959 | Ventura CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 210 | 298d | 15607SF+30d |  | 0 | Info
33960 | Ventura CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
33977 | Ventura CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 252 | 298d |  |  | 0 | Info
33978 | Ventura CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM | 141 | 299d |  |  | 0 | Info
34111 | Alameda PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15755SS | 15757 | 0 | Info
34113 | Alameda PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34128 | Alameda PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15774 | 0 | Info
34130 | Alameda PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34252 | Alpine PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 15896SS | 15898 | 0 | Info
34254 | Alpine PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34269 | Alpine PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 15915 | 0 | Info
34271 | Alpine PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34393 | Amador PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16037SS | 16039 | 0 | Info
34395 | Amador PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34410 | Amador PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16056 | 0 | Info
34412 | Amador PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34533 | Butte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16177SS | 16179 | 0 | Info
34535 | Butte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34550 | Butte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16196 | 0 | Info
34552 | Butte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34673 | Calaveras PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16317SS | 16319 | 0 | Info
34675 | Calaveras PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34690 | Calaveras PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16336 | 0 | Info
34692 | Calaveras PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34921 | Contra Costa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16565SS | 16567 | 0 | Info
34923 | Contra Costa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
34938 | Contra Costa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16584 | 0 | Info
34940 | Contra Costa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35062 | Del Norte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16706SS | 16708 | 0 | Info
35064 | Del Norte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35079 | Del Norte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16725 | 0 | Info
35081 | Del Norte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35203 | El Dorado PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 16847SS | 16849 | 0 | Info
35205 | El Dorado PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35220 | El Dorado PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 16866 | 0 | Info
35222 | El Dorado PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35560 | Humboldt PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17204SS | 17206 | 0 | Info
35562 | Humboldt PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35577 | Humboldt PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17223 | 0 | Info
35579 | Humboldt PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35701 | Imperial PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17345SS | 17347 | 0 | Info
35703 | Imperial PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35718 | Imperial PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17364 | 0 | Info
35720 | Imperial PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35842 | Inyo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17486SS | 17488 | 0 | Info
35844 | Inyo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35859 | Inyo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17505 | 0 | Info
35861 | Inyo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
35983 | Kern PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17627SS | 17629 | 0 | Info
35985 | Kern PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36000 | Kern PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17646 | 0 | Info
36002 | Kern PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36123 | Kings PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17767SS | 17769 | 0 | Info
36125 | Kings PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36140 | Kings PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17786 | 0 | Info
36142 | Kings PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36264 | Lake PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 17908SS | 17910 | 0 | Info
36266 | Lake PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36281 | Lake PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 17927 | 0 | Info
36283 | Lake PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36404 | Lassen PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18048SS | 18050 | 0 | Info
36406 | Lassen PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36421 | Lassen PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18067 | 0 | Info
36423 | Lassen PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36545 | Los Angeles PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18189SS | 18191 | 0 | Info
36547 | Los Angeles PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36562 | Los Angeles PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18208 | 0 | Info
36564 | Los Angeles PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36686 | Madera PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18330SS | 18332 | 0 | Info
36688 | Madera PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36703 | Madera PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18349 | 0 | Info
36705 | Madera PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36827 | Marin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18471SS | 18473 | 0 | Info
36829 | Marin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
36844 | Marin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18490 | 0 | Info
36846 | Marin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37075 | Mendocino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18719SS | 18721 | 0 | Info
37077 | Mendocino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37092 | Mendocino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18738 | 0 | Info
37094 | Mendocino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37216 | Merced PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 18860SS | 18862 | 0 | Info
37218 | Merced PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37233 | Merced PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 18879 | 0 | Info
37235 | Merced PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37357 | Modoc PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19001SS | 19003 | 0 | Info
37359 | Modoc PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37374 | Modoc PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19020 | 0 | Info
37376 | Modoc PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37712 | Napa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19356SS | 19358 | 0 | Info
37714 | Napa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37729 | Napa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19375 | 0 | Info
37731 | Napa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37852 | Nevada PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19496SS | 19498 | 0 | Info
37854 | Nevada PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37869 | Nevada PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19515 | 0 | Info
37871 | Nevada PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
37993 | Orange PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19637SS | 19639 | 0 | Info
37995 | Orange PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38010 | Orange PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19656 | 0 | Info
38012 | Orange PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38134 | Placer PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19778SS | 19780 | 0 | Info
38136 | Placer PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38151 | Placer PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19797 | 0 | Info
38153 | Placer PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38275 | Plumas PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 19919SS | 19921 | 0 | Info
38277 | Plumas PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38292 | Plumas PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 19938 | 0 | Info
38294 | Plumas PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38415 | Riverside PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20059SS | 20061 | 0 | Info
38417 | Riverside PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38432 | Riverside PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20078 | 0 | Info
38434 | Riverside PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38556 | Sacramento PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20200SS | 20202 | 0 | Info
38558 | Sacramento PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38573 | Sacramento PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20219 | 0 | Info
38575 | Sacramento PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38804 | San Bernardino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20448SS | 20450 | 0 | Info
38806 | San Bernardino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38821 | San Bernardino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20467 | 0 | Info
38823 | San Bernardino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38944 | San Diego PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20588SS | 20590 | 0 | Info
38946 | San Diego PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
38961 | San Diego PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20607 | 0 | Info
38963 | San Diego PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39192 | San Joaquin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20836SS | 20838 | 0 | Info
39194 | San Joaquin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39209 | San Joaquin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20855 | 0 | Info
39211 | San Joaquin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39330 | San Luis Obispo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 20974SS | 20976 | 0 | Info
39332 | San Luis Obispo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39344 | San Luis Obispo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 20990 | 0 | Info
39346 | San Luis Obispo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39467 | San Mateo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21111SS | 21113 | 0 | Info
39469 | San Mateo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39484 | San Mateo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21130 | 0 | Info
39486 | San Mateo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39605 | Santa Barbara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21249SS | 21251 | 0 | Info
39607 | Santa Barbara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39619 | Santa Barbara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21265 | 0 | Info
39621 | Santa Barbara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39743 | Santa Clara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21387SS | 21389 | 0 | Info
39745 | Santa Clara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39760 | Santa Clara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21406 | 0 | Info
39762 | Santa Clara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
39991 | Shasta PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21635SS | 21637 | 0 | Info
39993 | Shasta PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40008 | Shasta PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21654 | 0 | Info
40010 | Shasta PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40132 | Sierra PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21776SS | 21778 | 0 | Info
40134 | Sierra PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40149 | Sierra PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 3.4d |  | 21795 | 0 | Info
40151 | Sierra PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40273 | Siskiyou PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 21917SS | 21919 | 0 | Info
40275 | Siskiyou PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40290 | Siskiyou PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 21936 | 0 | Info
40292 | Siskiyou PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40414 | Solano PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22058SS | 22060 | 0 | Info
40416 | Solano PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40431 | Solano PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22077 | 0 | Info
40433 | Solano PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40555 | Sonoma PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22199SS | 22201 | 0 | Info
40557 | Sonoma PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40572 | Sonoma PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22218 | 0 | Info
40574 | Sonoma PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40696 | Stanislaus PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22340SS | 22342 | 0 | Info
40698 | Stanislaus PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40713 | Stanislaus PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22359 | 0 | Info
40715 | Stanislaus PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40837 | Sutter PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22481SS | 22483 | 0 | Info
40839 | Sutter PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
40854 | Sutter PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22500 | 0 | Info
40856 | Sutter PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41192 | Tulare PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 22836SS | 22838 | 0 | Info
41194 | Tulare PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41209 | Tulare PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 22855 | 0 | Info
41211 | Tulare PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41438 | Ventura PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23082SS | 23084 | 0 | Info
41440 | Ventura PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41455 | Ventura PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23101 | 0 | Info
41457 | Ventura PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41686 | Yuba PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d | 23330SS | 23332 | 0 | Info
41688 | Yuba PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41703 | Yuba PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 105 | 345d |  | 23349 | 0 | Info
41705 | Yuba PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41839 | CCLD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23484FF | 23486 | 0 | Info
41841 | CCLD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
41981 | CFSD_Adoptions CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23626SS | 23628 | 0 | Info
41983 | CFSD_Adoptions CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
41998 | CFSD_Adoptions CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 23643FF | 23645 | 1 | Info
42000 | CFSD_Adoptions CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
42141 | CFSD_CSQMB CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23786SS | 23788 | 0 | Info
42143 | CFSD_CSQMB CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
42288 | CFSD_Permanency CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 23933SS | 23935 | 0 | Info
42290 | CFSD_Permanency CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
42436 | CFSD_System of Care CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24081SS | 24083 | 0 | Info
42438 | CFSD_System of Care CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
42453 | CFSD_System of Care CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24098FF | 24100 | 0 | Info
42455 | CFSD_System of Care CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
42592 | FAD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24237SS | 24239 | 0 | Info
42594 | FAD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
42602 | FAD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24247FF | 24249 | 1 | Info
42604 | FAD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
42869 | RADD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24514SS | 24516 | 0 | Info
42871 | RADD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
43013 | SPEI CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24658SS | 24660 | 0 | Info
43015 | SPEI CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM | 146 | 293d |  |  | 0 | Info
43030 | SPEI CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 0d | 24675FF | 24677 | 1 | Info
43032 | SPEI CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
43159 | Karuk TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d | 24803SS |  | 0 | Info
43161 | Karuk TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
43172 | Karuk TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24816SS | 24818 | 0 | Info
43174 | Karuk TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
43299 | Yurok TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 362d | 24943SS |  | 0 | Info
43301 | Yurok TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info
43312 | Yurok TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 146 | 345d | 24956SS | 24958 | 0 | Info
43314 | Yurok TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM | 141 | 298d |  |  | 0 | Info